Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Combatting Illicit Economies Programme (CIEP)
Programme ID	CSSF-04-000004
Country and Region	Latin America: Colombia, Peru, Panama and Venezuela
IATI Unique ID
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office / (became Foreign, Commonwealth and Development Office (FCDO) midway through financial year)
Total Budget	ODA: £1.4m	Non-ODA: £0
Budget this FY	ODA: £1.4m	Non-ODA: £0
Spend this FY	ODA: £1.4m	Non-ODA: 0
Time Frame	Start Date: April 2020	End Date: March 2025

Outputs	Scale of Delivery
# of outputs harvested showing criminal justice stakeholders of CIEP have increased technical capabilities and knowledge to more effectively tackle organized crime and corruption.	2
# of outputs harvested showing criminal justice stakeholders of CIEP are more equipped to collaborate around transnational threats and illicit economies, including regionally / internationally.	1
# of outputs harvested showing non-state actors producing evidence and generating civil society capacity to highlight impact of SOC and its nexus with corruption/illicit economies	3
Overall Scale of Output Delivery	2

Outcome Assessment	The significant disruption and delays to delivery, recruitment and deployment of staff caused by the Covid-19 pandemic meant that the programme was unable to meet progress indicators for the outcomes and so need an amber rating. Nonetheless sufficient progress was made to suggest that the methodology, evidence base and approach of the programme is sound and will lead to Outcome delivery by programme end.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b	2018/19b	2019/20b	2020/21c
Programme Rating	2020/21 represented first year of programming				2	Amber
Risk Rating					Medium
Programme changes during this period		In its first year, programming was substantially impacted by the C19 pandemic which led to delays in delivery and a reduction in its planned budget. However, the programme adapted to the challenges of virtual delivery and used the year to undertake necessary analysis to further hone its focus to specific areas of illicit finance activity where the UK can best add value.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The Combatting Illicit Economies Programme (CIEP) seeks to tackle global illicit financial flow (IFFs) and money laundering dynamics, as they impact Latin America and generate instability, organized crime and corruption risks. The programme works regionally but with a particular focus on Colombia, Peru, Panama, and Venezuela (expanded to Brazil and Ecuador for FY21/22). The programme engages in a mixed delivery model, which encompasses work with Non-Governmental Organisations (NGOs), multilateral organisations and through deployed HMG advisors working with regional counterparts to build institutional capacity.

In financial year 20/21, the programme engaged in the following activity:

- Designing and developing new routes to rehabilitation for youth at risk of engaging in organized crime.
- Building the evidence base on the dynamics and possible approaches to tackling serious organized crime (SOC) and corruption dynamics in region.
- Supporting civil society organizations to improve their capacity to highlight organized crime and anti-corruption dynamics in region and to suggest governments may better respond.
- Technical capacity building of criminal justice counterparts in key thematic areas such as digital evidence and corporate corruption.
- Mentoring and providing assistance to regional organized crime and anti-corruption counterparts through UK advisers.

Key Results for FY 20/21:

1. Cooperation between Panamanian Prosecution Service and Financial Investigation Units enhanced through creation of new intelligence exchange processes.
2. Working with the Colombia state to pilot and test a new way of rehabilitating youth at danger of SOC recruitment that is now being extended to other cities.
3. Working with the Organisation for Economic Cooperation and Development (OECD) to reveal previously unknown details about the scale and scope of the illegal gold trade impacting particularly Venezuela, Colombia and Panama and identify pathways to international action to tackle the phenomenon.
Key Lessons

1. The narrowing of focus on tackling illicit financial flows rather than a broader range of SOC activity has strengthened the programme, made better use of HMG expertise and, ultimately, set the programme on a path to achieving greater impact than through a diffuse approach, and effectively tackling SOC in the region.
2. Co-funding of a UK financial crime expert with the US has been successful and is a model that allows greater cooperation and UK influence on tackling illicit financial follows. This model also maximises the value of respective expertise and resource and should be maintained and promoted.  More broadly, incorporating HMG diplomatically accredited advisors in the programme aids in alignment and cooperation with host and international partners.
3. In a regional, multi-stakeholder programme, communication cannot be limited to formal boards or decision-making. The programme has identified effective ways of ramping up regular informal communication with Heads of Missions, partners across government and other stakeholders in participating Posts to ensure alignment with strategic priorities, and strengthen strategic decision making

Key Recommendations for FY 21/22

1. Draw a clearer distinction between technical and strategic boards so that the programme team is more empowered to take technical decisions but senior leaders are more able to offer strategic direction and guidance. Continue to ensure regular communication amongst all HMG stakeholders to ensure alignment between the CSSF and Country Business Plans.
2. Assess the value for money of the in-house model of HMG advisers.
3. Maintain and publicise the benefits of the cooperation with the United States on illicit financial flows, particularly the co-funding of advisory roles.
4. Take early advantage of progress against the Covid-19 pandemic to use regional travel for activity monitoring and development and building relationships with key stakeholders.
5. Further hone the Outcome Harvesting model to ensure that there is an accessible and rigorous process for evaluating the influence and impact of a regional and diverse programme.