Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Partnering with the Caribbean on Serious and Organised Crime (SOC)
Programme ID	C-AMS-0005
Country and Region	Caribbean, Americas / Caribbean region: Antigua and Barbuda, Barbados, Dominica, Grenada, Guyana, Jamaica, St. Kitts and Nevis, St. Lucia, St. Vincent and the Grenadines, Trinidad and Tobago, Suriname. / (Some activity also delivers across the following British Overseas Territories: Anguilla, The Bahamas, Belize, British Virgin Islands, Cayman Islands, Dominican Republic, Haiti, Montserrat, Turks and Caicos Islands)
IATI Unique ID	CSSF-04-000001
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Department (FCDO), National Crime Agency (NCA), Home Office (HO) including Immigration Enforcement International (IEI), Crown Prosecution Service (CPS), ex-Department for International Development (DFID), Ministry of Justice (MoJ), Ministry of Defence (MoD), and the ACRO Criminal Records Office.
Total Budget	ODA Non ODA / 15/16 £5,550,000.00 £471,000.00 / 16/17 £4,510,000.00 £191,000.00 / 17/18 £4,043,000.00 £369,320.00 / 18/19 £3,901,179.00 £305,714.00 / 19/20 £3,297,262.00 £316,169.00 / 20/21 £1,993,719.00 £127,125.00 / Total £23,295,160.00 £1,780,328.00
Total Spend	ODA: £23,295,160.00	Non ODA: £1,780,328.00
Time Frame	Start Date: April 2015	End Date: March 2021

Outputs (for FY20/21)	Scale of Delivery
1.1 Delivery of prisoner (including gang members) rehabilitation programme in Jamaica	4
2.1 More tailored, structured support to key media professionals from regional and international experts	1
2.2 Increased support to key media organisations and institutions regionally	1
2.3 More opportunities to share experience, knowledge and contacts amongst key media professionals across the region	1
2.4 Improved ability to cooperate on regional security issues	2
3.1 Improved capacity of regional organisations to combat SOC threats	2
3.2 Targeted training on SOC and GC for the regions criminal justice practitioners increases expertise and regional responsiveness to SOC	4
3.3 UK expertise to police forces to support business change leading to effective implementation of technological change	1
3.4 Delivery of a criminal records module as part of the broader technological platform in the CARISECURE programme	3
3.5 UK bilateral support to police forces in the Eastern Caribbean to deliver additional expertise to strengthen forces ability to absorb the changes delivered by the CARISECURE programme	2
3.6 UK bilateral support to director of public prosecutions offices in the Eastern Caribbean to help deliver additional expertise to strengthen DPPs offices ability to absorb the changes delivered by the CARISECURE programme	1
3.7 Support to SOC MOUs in ODA and non-ODA countries in the Caribbean to help to deliver UK security priorities.	4
3.8 Work with international partner’s including the US to deliver aligned SOC priorities in the region	4
4.1 Design and deliver rapid COVID response support to the region	4
Final Overall Scale of Output Delivery	3

Outcome Assessment	The three year programme could not comprehensively deliver against outcomes due to the early closure of the programme at end of year one. Preparation for closure began at the beginning of Q4 including termination of activities and withdrawal from implementing partner agreements.
Final Overall Scale of Outcome Achievement:		1
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	C	B	C	B	B	A	B	3	1
Risk Rating	-	-		Medium		Medium		Medium
Note: an output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

 What support did the UK provide over the Programme Cycle?

- Mentoring of key domestic stakeholders tackling Serious and Organised Crime (SOC) by HMG-deployed expertise
- Provision of training to key defence and justice system domestic stakeholders engaged in tackling SOC, with a particular focus on homicides, drug trafficking, corruption, domestic/sexual violence, intelligence collection/handling.
- Development of legislation and policies for increased efficiency/effectiveness within regional criminal justice systems.
- Development of policies/protocols to promote increased efficiency/effectiveness within national and regional criminal justice systems.
- During the transition year, the Programme’s previous focus on deployed HMG expert mentoring and training design and delivery has continued but at a much smaller scale, with greater movement towards alternative delivery mechanisms including working with other international and multilateral partners such as USAID, OAS and implementing partners such as UNDP, UNLIREC and CARICOM IMPACS.

What Results Did the Programme Deliver?  Will they be sustained?

It has proved challenging to coherently demonstrate clear outcome-level deliverables for the period 2015-2020, due to projects being led by individual departments across a number of countries and lack of a clear strategy, overarching programme structure and corresponding monitoring, evaluation and learning (MEL) plan. However, the programme delivered value for money at the individual activity-level including:

- The digitalisation and integration of criminal records in Jamaica which has been expanded into the Eastern Caribbean (EC), demonstrating the value of this work. Funding secured to complete the delivery of this work, which will sit as part of a wider police platform that will functioning in 8 EC islands.
- The creation of the strong Director of Public Prosecutors (DPP) network between Caribbean and British Overseas Territories DPPs, to improve the capacity to prosecute trans-border crime by establishing a network of practitioners to share information and provide sustainable peer to peer learning, which is now self-managed by DPPs in the region.
- Comprehensive security sector reform support to Guyana, through a number of reports, UK driven international partner coordination meetings and securing previous and subsequent government buy in for the implementation of the recommendations. The High Commission in Guyana successfully transferred the work to IDB and the Government of Guyana, allowing the initial UK investment to continue delivering after our withdrawal.
- Increased capability of Jamaican authorities to develop rehabilitation plans for offenders through former DFID correctional support.
- Supported security and justice agencies in partner countries and at regional level to improve processes and capacities to better investigate, prosecute and mitigate impact of SOC.
- 200+ individuals trained across the Caribbean, increasing individual and institutional capability of defence forces and develop regional resilience and relationships.

The emphasis of work in 2015-20 was upon building the capacity of partner countries to tackle SOC. Evidence from previous annual reviews exists to show that new procedures, methods and legislation supported by the CSSF has been integrated into partner countries’ work and there are reasonable grounds to assume that changes and innovations will therefore be sustained without further UK assistance. Due to the delays in delivery caused by the COVID 19 pandemic and the closure of the revised programme due to the spending review it is difficult to measure or claim achievement of outcomes for which were expected to be reached over a three-year period. However, the programme delivered strongly on the activity level, particularly in its effective response to the COVID19 pandemic; pivoting funds and delivering rapid support both bilaterally and regionally through regional security institutions.

What lessons were learnt?

Insufficient investment was made in designing the programme, which took time to rectify. Once Governance structures were in place and the programme was supported by a full-time team and more robust analysis it began to deliver more consistent and sustained impact;

In a cross-HMG programme, it is preferable to identify tensions and trade-offs at the outset in order to establish a shared vision and expectations. Particularly in the area of SOC, where agencies and departments are specialised and some have operational independence, there were inevitable challenges around working across government in a diverse region. These were eventually resolved but would have been better discussed before the programme began.

Stronger SOC policy making brought greater coherence to the CSSF SOC programme. As the UK’s approach to tackling SOC overseas has become better resourced and coordinated so the programme was better able to add value to an integrated approach. However, the programme alone was unable to bring coherence to a field in which many HMG departments and agencies are active.

The FY20/21 programme demonstrated that regional delivery, while often complicated, is achievable and allows a flexible response to crisis. The programme underwent significant revision in its fifth year and has shown how similar such regional programmes might be set up elsewhere. The regional structure enabled the programme to offer flexible support to face the Covid-19 pandemic.

Regional, multi-pronged and multi-partner programmes such as this one require dedicated support to properly measure and demonstrate impact. The programme consistently struggled to adapt standard monitoring and evaluation tools to a necessarily broad and diverse set of actors. There was steady improvement but future programmes need dedicated support from the outset.

HMG should develop a stronger evidence base on the nexus between gender and SOC to ensure more strategic and systematic gender mainstreaming to future programmes. This is still an under-researched area, which creates challenges to properly integrate gender considerations into programming.