Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Philippines
Programme ID	CSSF-09-000007
Country and Region	Philippines, South East Asia
IATI Unique ID	CSSF-09-000007
HMG Partners / (Lead in bold)	FCDO
Total Budget	ODA: £2.75m	Non-ODA: £0
Budget this FY	ODA: £2.53m	Non-ODA: £0
Spend this FY	ODA: £2.75m	Non-ODA: £0
Time Frame	Start Date: April 2020	End Date: March 2025

Outputs	Scale of Delivery
1. Strengthen the democratic functions and governing capability of the Bangsamoro Autonomous Region of Muslim Mindanao (BARMM)	3
2. Public Awareness Campaigns and Community Engagement on the new Bangsamoro Autonomous Region (BAR)	4
3. Supporting women's political participation in post-conflict governance	4
4. COVID-19 Response	4
Overall Scale of Output Delivery	4

Outcome Assessment	The programme has made a promising start despite the difficult circumstances of the first year, and delivered strong results in both governance capacity building and political access and influence. However, the baseline analysis and RF should be strengthened to improve confidence in results.
Overall Outcome Progress Rating:		Green/Amber
Overall Risk Rating:		Medium-high

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A		N/A		N/A
Risk Rating					Medium-high
Programme changes during this period		First year of the programme.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The programme was designed to support the Bangsamoro peace process and establishment of the Bangsamoro Autonomous Region of Muslim Mindano (BARMM), thus addressing drivers of conflict in the southern Philippines and demonstrating the UK’s commitment to a stable and prosperous Indo-Pacific region. However, the onset of COVID-19 meant that the programme rapidly shifted some activity to mitigating the impact of the pandemic on the fragile situation in Mindanao through support to two UN agencies. In its first year, the CSSF Philippines programme funded six projects:
- Westminster Foundation for Democracy (WFD) – Capacity building for BARMM parliament and parties, including participation of women - £605,000
- The Asia Foundation – Building capacity of BARMM to outreach to citizens - £116,500
- Conciliation Resources – Community outreach and dialogue - £80,000
- Centre for Humanitarian Dialogue – Survey and report on public perceptions of BARMM - £100,000
- International Organisation for Migration – Direct support to BARMM agencies and local govt on COVID-19 - £999,500
- UNICEF – Supporting BARMM outreach and messaging on COVID-19 - £795,000

Key Results for FY 20/21:

- Despite the difficult circumstances, the first year of the programme has served as a successful ‘proof of concept’ for governance support to BARMM. UK support was instrumental in the delivery of the Bangsamoro Administrative and Civil Service Codes and the strengthening of the capacity of staff and parliamentarians.
- The programme also made a promising start in building BARMM comms capacity and community outreach.
- Progress towards institutionalisation of the Bangsamoro Women’s Caucus and the drafting of the BARMM Gender and Development Code are critical steps in ensuring women are represented equally in the new parliament.
- UK support to the BARMM COVID-19 response allowed the first delivery of vaccines to the area, as well as emergency hygiene and medical supplies. This support has also improved provincial and local government communications, improved health service provision at a critical time.

Key Lessons

- UK capacity building support on governance in Mindanao has been both effective and welcomed at all levels. The CSSF programme has demonstrated a clear UK USP amongst donors which can be built upon.
- Plans for the CSSF Philippines team to conduct in-depth conflict and gender analysis were unfortunately put on hold by the COVID-19 pandemic. Although the team and implementers did well on conflict and gender sensitivity of the programme, such analyses would have set a strong baseline against which to measure the success of the programme.
- There are a number of capable implementers operating in Mindanao with strong local links which the UK can rely on, although their choice of local partners should be scrutinised carefully. Hosting implementer forums is an effective method of cross-learning and improves the coherence of the programme.

Key Recommendations for FY 21/22

- On monitoring and evaluation, ensure that a standard CSSF-format results framework is in place from the outset, setting impact, outcomes, outputs and baseline, and including political access and influence (PAI) indicators where possible.
- Consider using a ‘capability tier’ system for measuring improvements in BARMM capability over time, with the intention of demonstrating what the government can now do that it could not before.
- Undertake a conflict and gender analysis for Mindanao, obtaining support from Joint Fund Unit (JFU) and Office of Stabilisation, Conflict and Mediation (OSCM) as required. In the interim, implementers have a significant amount of analysis which could be collated.
- In order to maximise VFM, the programme team should consider using a smaller number of implementers on larger, more sustainable projects. In addition, the balance of the programme should be carefully considered – in 20/21, only WFD delivered against Output 1 and 3, while three implementers delivered much smaller projects on Output 2.
- On the future of the programme, the decision was made to focus the programme on governance. Although we understand the need for COVID-19 emergency support and the decision to extend work to the normalisation strand in 21/22 was made as a result of a request from the Government of the Philippines, the programme team should carefully consider the type and balance or projects to ensure that, as a relatively small programme, it remains focused on a tight and achievable set of objectives. Implementer forums should be held on a regular basis to share best practice, especially on M&E and conflict and gender sensitivity, and to identify synergies between projects.