Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Physical Security and Attack Response programme (PSARP)
Programme ID	C-CTP-0009
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000015
HMG Partners / (Lead in bold)	Home Office (HO) Joint Overseas Protect & Prepare (JOPP), CONTEST Unit (CU), Foreign, Commonwealth and Development Office (FCDO), Cabinet Office (CO), Ministry of Defence (MoD)
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs / Note: a For comparison with the preceding year, equivalent score using FY 19/20 scale is provided in brackets.	Scale of Delivery
4.3.1.1. Protect awareness and capacity raised among national authorities and tourism.	3 (Aa)
4.3.1.2. HMG understanding of protect and prepare capabilities and level of vulnerabilities.	4 (A+a)
4.3.2.1. Improved strategic understanding of importance of cross-government coordination.	2 (Ba)
4.3.2.2. Improved host government capacity for effective crisis response operationally.	3 (Aa)
4.3.2.3. Local authorities’ capability to test and exercise CT crisis response improved.	2 (Ba)
Overall Scale of Output Delivery	3 (Aa)

Outcome Assessment	In FY 20/21, the PSARP performance held at a similar level to FY 19/20. Where the PSARP placed a subject matter expert (SME) the PSARP largely met intermediate outcome targets. Self-assessment using a “Weighted Scorecard” recorded positive improvements in protective security as well as attack response capabilities. Improved protective security and attack response intermediate outcome achievements were externally confirmed through a Monitoring, Evaluation, Learning and Technical Advisory Service (MELTAS) evaluation. Gains were more nuanced in other theatres, e.g., due to the complexities of working with devolved as well as central authorities and when engagement was more remote.
Overall Outcome Progress Rating:		Green (Aa)
Overall Risk Rating:		Medium-Low (programme delivery risk)

Summary of Programme Performance
Year	2016/17b	2017/18c		2018/19c		2019/20c		2020/21d
Programme Rating	B	B	B	B	B	B	B	3 (Aa)	Green (Aa)
Risk Rating	High	High		High		High		Medium-Low
Programme changes during this period		Weighted Scorecards were introduced and countries baselined. There were significant investments into impact studies and developing physical security and attack response products, including a self-assessment tool.
Note: b output scores; c output / outcome scores; d scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The programme advanced three main strands: (1) raising awareness of the threat from terrorism; (2) protective security training; and (3) crisis management training. The team also provided advice and support to draft physical security and attack response policies and aimed to embed training through work with national training institutes. This was in-person, remote, via train-the-trainer, mentoring and table-top exercises.

Key Lessons
- The delivery model needs diversification. Dependency on UK police/ex-police is not resilient because of competing demands and restricts creativity that comes from diverse inputs. The SME delivery model leans towards training delivery. Mentoring and obstacle removal relies on an in-country Protect and Prepare Coordinator. Longer-term institutional reform is left to FCDO. This system can be further optimised.
- The PSARP builds short-term competence in protective security and attack response, but not capability (which relies on budgets, staff retention etc.). Leveraging other institutional reform work may help support areas not covered like fundraising, human resource management etc.
- The credibility of British policing in a crisis is a unique selling point (USP), so keeping that British policing brand, even if some to most of the work is actually outsourced, keeps demand up.