Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Aviation Security Strategic Engagement and Training (ASSET) programme
Programme ID	C-CTP-0006
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000015
HMG Partners / (Lead in bold)	Department for Transport (DfT), Home Office (HO) CONTEST Unit (CU), Foreign, Commonwealth and Development Office (FCDO), Cabinet Office (CO), Ministry of Defence (MoD), HM Treasury (HMT)
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs / Note: a For comparison with the preceding year, equivalent score using FY 19/20 scale is provided in brackets.	Scale of Delivery
4.2.1.1. Increased capabilities in the use of security screening equipment and security procedures / management.	1 (Ca)
4.2.1.2. Improved host government capacity to deliver and operationalise effective training for aviation security personnel.	1 (Ca)
4.2.2.1. Capabilities of host states developed to implement comprehensive quality assurance processes for aviation security.	1 (Ca)
4.2.3.1. Constructive and regular strategic engagement with/by host state interlocutors to support enhancing and improving aviation security.	2 (Ca)
Overall Scale of Output Delivery	1 (Ca)

Outcome Assessment	In FY 20/21, ASSET performance significantly worsened due to external circumstances beyond HMG’s control, namely the coronavirus (C-19) pandemic impact on aviation sector. There was little on-the-ground work to improve national government capacities and capabilities, largely due to the grounding of flights and the inability of resource to transfer from the UK. Some virtual activities were utilised to encourage improved governance and procedures and threat understanding leading to a shared approach to counter terrorism (CT) risk mitigation across aviation security. Nonetheless, since UK exposure was so low the risk to British Nationals (BN)/UK interests was also lower.
Overall Outcome Progress Rating:		Red (Ca)
Overall Risk Rating:		High (C-19 and reputational, legal risks)

Summary of Programme Performance
Year	2016/17b	2017/18c		2018/19c		2019/20c		2020/21d
Programme Rating	B	B	N/A	B	N/A	B	B	1 (Ca)	Red (Ca)
Risk Rating	High	High		High		High		High
Programme changes during this period
Note: b output scores; c output / outcome scores; d scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

- The ASSET programme provides narrowly focussed support, assessing and assuring risk management of prohibited items, particularly explosives, interfering with aircraft flying directly to the UK. In FY 20/21 it focussed on 23 countries as agreed with the Aviation External Threats Group (AETG) as being highest risk.
- Aviation Security Liaison Officers (ASLOs) conducted assurance visits at international airports where direct flights operated to judge risk mitigation compliance in the immediate to short-term including the correct use of Explosive Trace Detection (ETD) machines.
- Aviation Security International Operations (ASIO) assessed long-term strategic trajectories based around DfT’s “Maturity Model” and delivered strategic engagement through senior-level meetings, workshops and presentations.

Key Results for FY 20/21:

There were no reports of explosives or other prohibited items detected or people arrested at international airports using capabilities delivered through the ASSET programme. Therefore, proximate results are listed below.

Demand for HMG aviation security support via the ASSET programme held, despite the C-19 pandemic, partly due to virtual global workshops and seminars to exchange best practices on topics such as Cyber and counter drone technology.

Despite aviation challenges, some refresher training to staff at airports resuming direct flights to the UK was delivered.

Aviation security training materials were produced, translated into five key languages and distributed to partners for use in their own programmes resulting in a more sustainable offer.

ASSET completed maintenance and repair visits to most of the airports where loaned explosive trace detection (ETD) machines are present.

In Q1 FY 20/21, DfT ASLOs demonstrated agility by using in-country networks to facilitate repatriation of BN at-scale at-pace, often using connections and informal exchanges to ensure the safe and timely departure from C-19 pandemic affected countries that had insufficient capability/capacity to protect BN.