Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Maritime Security Strategic Engagement and Training (MSSET) programme
Programme ID	C-CTP-0007
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000015
HMG Partners / (Lead in bold)	Department for Transport (DfT), Foreign, Commonwealth and Development Office (FCDO), Home Office (HO), CONTEST Unit (CU), Cabinet Office (CO), Ministry of Defence (MoD), HM Treasury (HMT)
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs / Note: a For comparison with the preceding year, equivalent score using FY 19/20 scale is provided in brackets.	Scale of Delivery
4.2.1.1. Capabilities of using screening equipment and security procedures / management.	1 (Ca)
4.2.1.2. Host government capacity to deliver training for maritime security personnel.	1 (Ca)
4.2.2.1. States capable of implementing quality assurance processes for maritime security.	1 (Ca)
4.2.3.1. Strategic engagement with/by states to support improving maritime security.	3 (Aa)
Overall Scale of Output Delivery	2 (Ba)

Outcome Assessment	In FY 20/21, MSSET performance more or less held compared to FY 19/20. Despite operating under half capacity due to HMG coronavirus (C-19) crisis response work, MSSET was on track. However there were some doubts about whether outcome targets would be fully met leading to an amber rating. Protection against attack and mitigation of its impact on maritime security was seriously reduced because of the C-19 pandemic. Exposure of British nationals (BN) also dropped because there were few cruises although risk remained towards BN crew and UK-interest cargo.
Overall Outcome Progress Rating:		Amber (Ba)
Overall Risk Rating:		High (if fail, then reputational, legal risks)

Summary of Programme Performance
Year	2016/17b	2017/18c		2018/19c		2019/20c		2020/21d
Programme Rating	B	B	B	B	N/A	B	B	2 (Ba)	Amber (Ba)
Risk Rating	High	High		High		High		High
Programme changes during this period		No change, port facility assessment (PFA)-based engagement to mitigate terrorism risk to BN tourists/contractors and ship-to-shore mitigations protecting BN crew and UK-needed cargo on UK Red Ensign/UK-registered vessels in high-risk countries set by JTAC.
Note: b output scores; c output / outcome scores; d scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

Deployment of two Maritime Security Liaison Officers (MaSLO) covering Africa and the programme remotely engaged with 12 priority countries regarding IMO ISPS codes affecting UK Red Ensign/UK-registered vessel, British National (BN) tourists on cruises, BN crew, BN contractors and UK-interest cargo.

Key Results for FY 20/21:

A selection of these is highlighted below:

- As a result of MASLO engagements, compliance with International Maritime Organisation (IMO) International Ship and Port Facility Security (ISPS) codes improved.
- Delivered risk management workshop in collaboration with US Coastguard that raised awareness of maritime security needs, and port facility management workshop on customs and immigration resulting in roll out to a further seven ports.
- Host counterparts self-initiated their own crisis response exercise and designated authorities began drafting their own national maritime security strategies. Host countries have asked HMG for support in establishment as a regional centre of excellence for maritime security.
- Conducted a virtual working group which further increased demand for HMG support, particularly in light of the 2022 FIFA World Cup.
- Developed and produced high- quality overseas training products including; threat and risk assessment systems; threat briefs; risk audits; and DfT’s International Maritime Security Operations Team (IMSOT) courses. Key partners have asked to use these materials in their training.