Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Cyber & Tech Security Programme 2020-21
Programme ID	C-CYB-0001
Country and Region	Global
IATI Unique ID	CSSF-14-000001
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) / Home Office / NCA / DCMS / NCSC / DIT / MoD / Cabinet Office
Total Budget	ODA: £12,000,000	Non-ODA: £500,000
Budget this FY	ODA: £12,000,000	Non-ODA: £500,000
Spend this FY	ODA: £4,373,377	Non-ODA: £500,000
Time Frame	Start Date: April 2020	End Date: March 2021

Outputs	Scale of Delivery
Projects	Amber
Commonwealth Cyber Awareness Campaign (Get Safe Online)	Amber
Africa Critical Information Infrastructure Training (Home Office)	Amber
Commonwealth CSIRT community (Torchlight)	Amber
Integrated Strategic Cyber Capacity Building (Home Office)	Amber
Scoping project to assess considerations for internationalising NCSC’s Automated Cyber Defence programme (Deloitte)	Green
Strategic Cyber Capacity Building (Global Cyber Security Capacity Centre)	Amber
Enhanced cyber attack detection and reporting for Africa and the Indo-Pacific (Shadowserver)	Green
Legislation reviews, enforcement training, outside Commonwealth (UNODC)	Amber
Legislation reviews, enforcement training in the Commonwealth (Commonwealth Secretariat)	Amber
Research, scoping and small projects (sub £500k)	Not assessed
Stakeholder mapping of international organisations in South Asia, Asia-Pacific, Africa and South America regions, and digital marketing (Eppix; Dartkite) / Final virtual meeting of the African Cyber Fellowship before transition to Commonwealth Secretariat (Protection Group International) / Regional Coordination Framework for Tackling Cybercrime in Africa (Interpol) / Update to website and creation of community platform (UN Internet Governance Forum) / National Cyber Security Strategy for Sierra Leone and Digital Rights review for the Pacific (Global Partners Governance) / Commonwealth Cyber and Tech scholarships (Chevening Secretariat) / Scoping project to review priorities for future projects on Human Rights in the Digital Age (RAND Europe) / Technical Cyber Security Training for officials in Somaliland’s Ministry of Information and Communication (Protection Group International) / Research on Social Media Disinformation in Taiwan (AI Labs)	Not assessed
Scoping report on International Data Transfers within the Commonwealth (Victoria University) / Cyber Threat Exercises on a range of themes with strategic partners (Royal United Services Institute) / Audience insight analysis on perceptions of the UK and how to influence (Alinea International)	Not assessed - contracts signed April, 2021.
Overall Scale of Output Delivery	Amber

Outcome Assessment	Not scored. Delivery has not yet progressed far enough to conduct an outcome assessment. However, evidence at this stage shows the programme is progressing in the right direction. Outcome-level evidence from 5 projects out of 15 demonstrates that approaches to support governments on better protecting critical national infrastructure (Outcome 1), and on improving cybersecurity attitudes among private citizens (Outcome 2), have generated expected results. No reportable progress has been made yet on raising cyber health of the private sector (Outcome 3).
Overall Outcome Progress Rating:		Not scored
Overall Risk Rating:		Medium/High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	N/A	N/A	Amber	Not Scored
Risk Rating	N/A	N/A		N/A		N/A		Medium/High
Programme changes during this period		N/A
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The programme delivered nineteen projects with a total value of £4,873,377. This provided national cyber authorities around the world with capacity building, legislative support, access to threat intelligence and an international peer community. It also generated essential research and scoping to inform future work. Delivery through the CSSF enabled the programme to be catalytic, take risks, and adapt interventions quickly during a challenging year.

Key Results for FY 20/21:
Foundations established for the new CSSF Cyber portfolio. The programme drew a large range of interventions, research and scoping together into a coherent package, providing a good foundation for delivery in FY21/22. Research reports examined: internationalising automated cyber defence (ACD); human rights in the digital age; cyber/digital stakeholder mapping in the Indo-Pacific, South Asia, Africa and South America, including multilateral fora; and social media disinformation in Taiwan.
- Governments increasingly protected critical national infrastructure from cyber attacks. Thirty countries signed up to the new Commonwealth Cyber Security Incident Response Team (CSIRT) community platform. Separately, thirty national CSIRTs in the Indo-Pacific and Africa began receiving free threat intelligence, and deployment of new honeypot network sensors helped to build UK resilience. Four countries completed the National Cyber Risk Assessment, and confirmed they would be running second iterations of the risk assessment process during 2021. A further sixteen countries participated in cyber threat exercises. Efforts generated positive knock-on effects: for example, support to a new National Cyber Strategy for Sierra Leone led to a review of national cybercrime legislation and a commitment to join the Budapest Convention.
- Cybersecurity attitudes improved among private citizens as a result of the programme. Individuals and small- and medium-sized enterprises across 22 Commonwealth countries in Africa, the Caribbean and the Pacific increased their awareness of online risks (41.5m ad impressions) and gained new cyber hygiene skills via Get Safe Online’s campaigns and Ambassador Scheme. Survey results indicate a significant improvement in cyber hygiene.
- Key partnerships secured. The programme successfully launched an active community of national cyber authorities across a diverse range of countries, and built important relationships with key partners such as the International Telecommunications Union (ITU). It also capitalised on windows of opportunity through a range of entry points for countries to engage. Within HMG, the programme drew partners with different agendas together to deliver on a common vision and strategy. It is well-positioned to deliver Integrated Review and National Security Council (NSC) ambitions.

Key Lessons
- The key decision to launch using a blend of existing and new programming was borne out, delivering a vital platform for the new portfolio and successes that are replicable and scalable. Providing technical support to understand, resolve and potentially defend against attacks in future remains an identified priority area to develop in order to match NSC intent on the ground.
- The programme was able to capitalise in part on the CSSF’s comparative advantages. However, it faced difficulties standing up new initiatives and some legacy efforts also proved resource-intensive to coordinate effectively, tilting the balance of effort towards these.
- The programme’s ‘Actor-Based Change’ approach proved invaluable for drawing partners together in support of a common vision and approach, but was significantly more labour-intensive to implement than traditional approaches to Monitoring, Evaluation and Learning (MEL). Supplementing internal resource with external support from GMEL provided an important partial mitigation but was insufficient to lead to mature day-to-day systems and processes. While delivery delays were a primary obstacle to the programme’s completing a full review this year, the fact that the portfolio’s MEL systems were not fully operational affected its potential to evolve.
Establishing an enduring platform for the portfolio through a one-year funding settlement proved a challenge. Staffing gaps, recruitment challenges and external factors this year created compounding issues that contributed to delays in delivery of new workstreams and limited the team’s ability to respond to the range of priorities of the new portfolio. The decision to prioritise coordination with departments and implementers paid off, but there is further potential here.
Adherence to ‘Agile’ principles and use of adaptive programming methods by both the core team and implementers resulted in rapid progress in some areas, even subject to these constraints. There is clear potential for overall performance to accelerate rapidly from here. However, the portfolio was unable to move beyond certain linear HMG processes and cultures, particularly on procurement. There is an ongoing risk that the cyber context outpaces the portfolio’s priorities.
While the first year has brought important lessons, they reflect a portfolio that has demonstrated that it is unafraid to stretch and which offers a model of experimentation and adaptation. These principles have enabled it to successfully make progress during an extremely challenging year.

Key Recommendations for FY 21/22
- Focus on getting all project delivery and systems running smoothly, and that the portfolio positions itself to complete a full Annual Review for FY21/22.
- Recruit a dedicated MEL advisor and procure dedicated MEL services from an external provider for FY22/23 onwards. There might be an opportunity and benefit in this new advisor and external provider also covering another CSSF Portfolio, such as the new State Threats Portfolio.
- Continue to prioritise filling all JFU-agreed roles in the team, to ensure and potentially accelerate delivery, and to support the MEL advisor and MEL services provider in ensuring that projects have agreed progress markers and that project implementers participate in harvesting outcomes.
- Focus on tightening up information and evidence collection pipelines to inform quarterly boards and other regular decision points.
Integrate an adaptive approach and ‘Agile’ principles further into systems, management and governance processes, to enable the programme to deliver at pace with global cyber dynamics, and to evolve with UK policy developments over the course of the next Spending Review period.