Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Lebanon: Community Stability Programme
Programme ID	C-MNA-0019
Country and Region	Lebanon, Middle East and North Africa
IATI Unique ID	CSSF-06-000020
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID) / Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £18.95	Non-ODA: £0
Budget this FY	ODA: £9.63m	Non-ODA: £0
Spend this FY	ODA: £9.55m	Non-ODA: £0
Time Frame	Start Date: April 2019	End Date: March 2022
Outputs			Scale of Delivery
Strengthened institutional capacity to inclusively identify, plan and deliver inclusive livelihoods			3
Increased community (including women) and local/sub-national government inclusive coordination on livelihoods			4
Strengthened institutional capacity to inclusively design, plan and deliver inclusive priority resource services			4
Increased community (including women) and local/sub-national government inclusive coordination on services			4
Strengthened institutional and community capacity (including women) to foster dialogue and address sources of tension and conflict			4
National, local, and social media engaged in defusing tensions			4
Overall Scale of Output Delivery			4

Outcome Assessment	In a year in which the drivers of conflict that the programme is designed to address have got worse across Lebanon, the Community Stability Programme has achieved impressive results in target communities. Targets have been met, or exceeded, for indicators designed to measure access to livelihood opportunities, access to inclusive services, and peacebuilding narratives.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	A	B	4	Green
Risk Rating	N/A	N/A		N/A		Medium		Medium-Low
Programme changes during this period		The programme has adapted frequently throughout the year due to the COVID-19 pandemic, Beirut port explosion and changes in ODA allocations.
Note: an output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The Community Stability Programme (CSP) aims to foster stability in the most conflict-vulnerable communities in Lebanon by addressing causes of tension and promoting peacebuilding amongst and between Lebanese, refugees, and local/sub-national and national authorities. It supports four complementary projects: the Lebanese Host Community Support Programme (LHSP), an innovative blend of CSSF and FCDO (ex-DFID) support to community-led stability projects built around a participatory process called Mechanisms for Stability and Local Development (MSLD); IJMAA, a local governance project addressing conflict around services as an entry point for wider community peacebuilding; a strategic communications project promoting local champions and emphasising pro-peace narratives; and support to a Tensions Monitoring System.

Key Results for FY 20/21:
The review year was an extremely challenging year for programme delivery due to the political and economic instability in Lebanon and the challenges posed by the COVID-19 pandemic. Despite these challenges, the programme has delivered the following key results:

23 communities prepared community development plans based on the MSLD process, strengthening trust in local municipalities, generating 3,187 worker days, benefitting 11,500 people through completed projects that improve access to services, and eight pilot municipality police units have begun implementing a capacity development plan, designed to boost community security.

Targets have been met, or exceeded, for indicators designed to measure the capacity of local governance bodies to deliver services; community perceptions of communication with local governance bodies, and the percentage of community representatives who report a positive interaction with a conflicting group or community (72% achieved, 40% target).

A social media campaign (#OneAct) highlighted the work of local peacebuilding champions across refugee/Lebanese/sectarian/political divides and reached 1.15m people. Regular perception surveys have shown that empathy towards refugees has increased over the course of the programme amongst the target group.

UK support for the Tensions Monitoring System has resulted in evidenced thematic briefings, including on conflict sensitivity best practice, feeding into international community decision-making and informing the way UN and NGO partners deliver.

Key Lessons
The context in which this programme operates, and critically the conflict drivers that the programme seeks to address, have significantly worsened since the programme was designed. As the needs have increased beyond the scale addressable by individual programmes by HMG or others, peacebuilding outputs and outcomes need to be integrated fully into development and, increasingly, humanitarian responses to the crisis – rather than standalone activities.

Key aspects of programme design that have worked well include strengthening subnational governance structures (e.g. municipalities), making these more inclusive, and providing medium-term flexibility.

“Strategic communications”, and media engagement on peacebuilding narratives is notoriously difficult to measure results and demonstrate change. Future UK communications efforts would benefit from being limited in target audience/geographical locations, responding to specific issues.

Key Recommendations for FY 21/22
Reconsider cuts to the programme (or find ways to integrate activities, lessons, and indicators into other HMG programmes). Despite the reduction in programmatic resources available to foster community stability in the coming year, HMG should not lose sight of the importance of addressing community level drivers of conflict in Lebanon, and the value for money that investment in conflict prevention provides compared to responding to the needs that emerge as a result of violent conflict. In particular, the UK should look to strengthen Lebanese host community resilience, and build host community-refugee tension reduction outputs into other programmes, especially those targeting refugee communities.

Better monitoring to improve results reporting. UNDP to provide more evidence on the links between livelihood interventions, economic benefits, and stability, given that economic drivers of tensions are likely to continue to deteriorate across Lebanon in the coming year.

Find ways to sustain results by, for example, focusing on sustainability of local governance initiatives. The CSSF should continue using its strong relationship with the UNDP LHSP team to test approaches to building sustainability of the project’s work at the local level.

Ensure lessons learnt strengthen conflict prevention elements of UK policy engagement.

UNDP should continue to mainstream gender throughout LHSP, moving beyond women’s inclusion in programme activities towards a more transformative approach to tackling gendered drivers of conflict and instability.