Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Morocco Programme
Programme ID	C-MNA-0003
Country and Region	Morocco, Middle East and North Africa
IATI Unique ID	CSSF-06-000007
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £21.9m	Non-ODA: £0
Budget this FY	ODA: £8.1m	Non-ODA: £0
Spend this FY	ODA: £6.86m	Non-ODA: £0
Time Frame	Start Date: April 2018	End Date: March 2021

Outputs	Scale of Delivery
Young women and men and Micro, Small and Medium Enterprises (MSMEs) are supported with education and / or economic opportunities.	3
Citizens, through their organisations, are supported to increase capability and motivation to hold public officials and service providers to account with non-violent, evidence-based strategies.	4
Selected national and regional institutions (government and parliament) are supported to increase service delivery capacity and responsiveness to citizens.	4
Overall Scale of Output Delivery	4

Outcome Assessment	FY 20/21 was a challenging year and COVID-19 and associated restrictions adversely affected delivery of all projects. The Programme was also affected by two rounds of ODA reprioritisation. However, most implementing partners were able to adapt their project strategies and delivery methods in line with the context, and the Programme’s Theory of Change remained relevant. Overall, the Programme performed well, with the exception of the International Finance Corporation (IFC ) Micro Small and Medium Enterprise (MSME) 2.0 project which reduced the progress rating.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	A	B	B	A	A	A	4	Amber
Risk Rating	Medium	High		High		Medium		Medium-Low
Programme changes during this period		After the early in-year ODA reprioritisation and multiple budget amendments, the final budget was £6.84m. Projects were adapted to respond to COVID-19 needs and delivery challenges, and in line with the reduced budget. In quarter four, as a result of ODA reprioritisation, decisions were taken to exit early from the IFC MSME 2.0 and United Nations Children's Fund (UNICEF) “Equipping young people with skills and opportunities for active economic and civic life” (FORSA) projects. The World Bank education project funding finished as planned and the Westminster Foundation for Democracy (WFD) project also came to an end as planned, after 10 years of engagement.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The UK provided support to strengthen relationships and trust between citizens and the state in Morocco through funding projects in the fields of inclusive governance, education and economic development. Governance work focused on participatory democracy, accountable and responsive governance, predominantly working with the Regional Council (RC) of Tangier Tetouan Al-Hoceima (TTA) and Parliament. Education and economic development focused on improving access to and quality of secondary education for marginalised young people, supporting the Government of Morocco’s education reforms and financial inclusion for MSMEs. Projects were adapted to address COVID-19, including through support to stakeholders to respond to the effects of the pandemic.

Key Results for FY 20/21:
- Stronger evidence of effective collaborations between civil society and the Moroccan state, including in relation to education delivery, inclusion of marginalised groups and addressing Violence against Women (through ARK project Daam support)
- Approval of a nationally recognised Technical and Vocational Education and Training (TVET) qualification for students at Second Chance Schools (SCS) and creation of an official network of SCS (through UNICEF FORSA support)
- Ministry of Education (MoE) commitment to a comprehensive review of the secondary education curriculum, which highlights CSSF’s potential to leverage others’ financing to take forward reform (through UNICEF FORSA support)
- 15,921 young people (10,395 m / 5526 f) supported with their education through skills development, school reintegration or Second Chance Schools (through UNICEF FORSA support)
- The Regional Council of Tangier Tetouan Al-Hoceima (TTA) became the first regional government in the Middle East and North Africa (MENA) region to join the Open Government Partnership (through TASHAROC support).
- Strengthening evidence of government at various levels being more responsive and taking into account citizens’ needs and priorities, for example on inclusive education and regional development (through ARK project Daam and TASHAROC support)
- Improved engagement with the Ministry of Education and some tangible steps forward in implementing education reform (through World Bank education project support)
- Successful capacity building interventions delivered for regional government, parliament and CSOs (through ARK project Daam, TASHAROC and WFD)
- Support to Parliament on business continuity planning, communications and increasing women’s participation (through WFD support)
- Enhanced partnership with the Government of Morocco (GoM), increasing the visibility of the UK as a development donor and supporting the wider bilateral relationship.

Key Lessons:
Effective partnerships rely on trusting relationships and good communication.
- Change in support of the Open Societies agenda takes time and annual funding allocations hinder longer-term change-oriented processes.
- Joint coordination and learning between policy and programme units remains vital.
- There is a continued and growing need for clear leadership from the top in encouraging cross-Embassy involvement and support of the programme to increase its effectiveness and ability to support UK influence and wider objectives in Morocco.
- The programme has been able to achieve catalytic effect through combining diplomatic and development efforts, particularly in the field of education. This success relied heavily on advisory support which is now at significant risk.
Key Recommendations for FY 21/22:
- Programme to clarify the UK’s risk appetite in Morocco and explore working on more sensitive areas, including human rights.
- Project Managers to make clear to all Implementing Partners (IPs) the nature of annual CSSF funding allocations and to ensure implications of this are well understood, including to any subcontractors.
- The programme should prioritise cross-Embassy donor coordination and showcase results of the programme and UK central contributions in high-level engagements to increase influence.
- Programme to review quarterly reporting to ensure strategic contributions are adequately reflected.
- Programme to consider how to use the Strategy Board more effectively for strategic discussions.
- Programme to restart monitoring visits and increase visibility through attendance at events.
- Programme to consider narrowing the focus of civil society work around specific themes.
- Programme Team to continue building knowledge of Memorandums of Understanding (MOUs) and grant agreements, including through continuing to lobby for vital support from the centre.
- Programme to ensure policy colleagues are regularly involved in meaningful discussions on risk.