Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Syria: Future Syria Programme
Programme ID	C-MNA-0005
Country and Region	Syria, Middle East and North Africa
IATI Unique ID	CSSF-06-000030
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £7.4m	Non-ODA: £0
Budget this FY	ODA: £4.9m	Non-ODA: £0
Spend this FY	ODA: £4.03m	Non-ODA: £0
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Scale of Delivery
CSSF support mechanisms to monitor and document Human Rights (HR)/International Humanitarian Law (IHL) crimes and abuses (including sexual and gender-based violence) and pass to higher authorities and other users.	3
Civil Society Organisations (CSOs) operate and increase their capacity and institutional strength.	4
Relationships built between Syrian/regional /international CSOs, activists and female networks.	4
Overall Scale of Output Delivery	4

Outcome Assessment	The Future Syria programme achieved the majority of intended outcomes and outputs. The key results below demonstrate impact far beyond the parameters of this programme and represent national level progress on improved accountability and strengthened civil society. These results are impressive in the face of significant challenges faced in the programme’s second year; which includes COVID-19, late contracting and programme start up, and some partners having to manage targeted disinformation campaigns. As with the previous Annual Review, there is clear evidence of the expert and helpful role played by the CSSF team in supporting Future Syria programme partners to manage these external risks and challenges; and mitigate and address internal weaknesses to ensure compliance and value for money (VFM). / A key reflection is the balance between the breadth of the programme and the resourcing, especially in managing risks and where a more streamline, simplified approach could reduce stretch. There also remains a need for a clear and realistic articulation of what this programme can achieve in the long-term, to better inform the programme’s monitoring and evaluation tools, and the simplicity and relevance of some outcome indicators – particularly under outcomes two and three.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	-	-	-	-	-	A	B	4	Amber
Risk Rating	-	-		-		High		Medium-High
Programme changes during this period		A significant increase in justice and civil society support and a downscaling of Track II governance work. The results framework, and in particular the indicators used at both output and outcome level, were revised to focus on impact, and where possible, integrate the recommendations from the previous annual review.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

- Syria CSSF delivered through five programme partnerships, focussed on three key sectors: justice, accountability, and civil society.
- There was a clear cross cutting focus on gender equality, and more specifically on preventing sexual violence and supporting the Women, Peace and Security agenda in Syria.

Key Results for FY 20/21:

- The evidence and analysis work of the Commission for International Justice and Accountability (CIJA) contributed to, and helped, secure the first war crimes conviction of a Syrian regime officer, and provided support to three new investigations being launched by relevant law enforcement authorities.
- Synergy and their partner Lawyers and Doctors for Human Rights (LDHR) completed medical expert reports of sexual violence and torture, shared with international mechanisms and justice actors, which have led to the first indictment of sexual violence as a crime against humanity.
- The details of additional missing persons have been added to the International Commission on Missing Persons (ICMP’s) database. 22 first responders were trained on safeguarding forensic evidence in mass graves.
- 85% of community members assessed under Search for Common Ground’s (SFCG) end of year assessment, reported more effective Civil Society Organisations (CSOs) interventions in their communities.
- 120 Syrian women from grassroots civil society organisations report an increased capacity to meaningfully participate in Syrian civil society.

Key Lessons

- There is a need to improve coordination between different partners working on the issue of the detained and the missing, to work towards one consolidated database of missing persons cases, and increase capacity to identify and restore family links. It is also important to expand data collection by downstream partners to more areas within Syria, and to countries hosting Syrian refugees.
- Within Syrian civil society, there is significant ongoing need for institutional capacity building, supported by financing for dedicated finance, HR, and reporting staff. This should be built into all actions that include downstream partners, regardless of whether the overall focus on the project is on civil society strengthening, or other sectors.
- Both the Women’s International League for Peace and Freedom (WILPF) and SFCG highlighted the importance of better integration of psycho-social support for participants in CSO collaboration and advocacy work. This needs to be better integrated and funded in future CSO strengthening work.
- It is worth noting that many of the key results achieved were the result of multi-year and forward leaning support from the UK early on in the conflict, which is now bringing significant impact.

Key Recommendations for FY 21/22

1. Improve visibility of the programme, via increased internal and external comms (where appropriate), including closer engagement with partners, to better understand how instrumental their work is to national and global accountability efforts and delivering UK policy objectives in Syria.
2. Consider internal resourcing and ability for CSSF and wider Syria team to provide increased support, such as conflict advisory support, M&E and Risk including safeguarding against Sexual Exploitation, Abuse and Harassment (SEAH).
3. Review the breadth of some of the most complex partnerships, in order to minimise risks and maximise CSSF programme team resources and programme impact.
4. Promote closer coordination amongst partners and convene an in-person partner meeting (delivered in January 2022 with great).