Annual Review (20/21 Ver.) - Summary Sheet
Programme Title	Tunisia Programme
Programme ID	C-MNA-0032
Country and Region	Tunisia, Middle East and North Africa
IATI Unique ID	CSSF-06-000028
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £52.7m	Non-ODA: £0.3m
Budget this FY	ODA: £15m	Non-ODA: £0
Spend this FY	ODA: £10.22m	Non-ODA: £0
Time Frame	Start Date: April 2018	End Date: March 2021

Outputs	Scale of Delivery
Output 1 Training and technical assistance are provided to private and public actors to modernise the financial sector, and enhance the country's financial resilience and to improve Small Medium Enterprises’ (SMEs’) responsiveness to COVID-19.	3
Output 2 Support provided to education system to increase employability of young Tunisians, taking into account the needs of the most marginalised.	4
Output 3 Support provided to strengthen state-citizen engagement, transparency and vulnerable communities.	4
Output 4 Training and technical assistance provided to strengthen security institutions towards crisis management	4
Output 5 Political Access and Influence (PAI) undertaken through Her Majesty’s Government (HMG) (including with and through implementing partners), delivering political engagement and lesson learning to evolve future programme adaptations.	4
Overall Scale of Output Delivery	4

Outcome Assessment	Delivering change in the Tunisian political context is very difficult and UK funding is limited. Programming has also been impacted by COVID-19 delaying the realisation of some outcomes making monitoring challenging. However, the Embassy was quick to pivot efforts to support the most vulnerable, while exploiting opportunities as they arose. / Efforts to support economic development are demonstrating impact, digitising and modernising systems with the UK enabling significant multilateral funds. / Support to education and English language teachers has had widespread effect and has been warmly received by Tunisian teachers and government. This visible UK flagship programming has delivered well. / Support to vulnerable groups and women was developed quickly and has opened opportunities for the future.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a & *		2017/18b & *				2018/19b		2019/20b		2020/21c
Programme Rating	A	A	B	B	B	A	A	A	A	A	4	Green
Risk Rating	Medium for both*		Medium (Security)		Medium (Economic & Governance)		Medium		Medium		Medium
Programme changes during this period			Following the COVID 19 pandemic, the planned and earlier approved programme was urgently repurposed to support the Government of Tunisia’s response to the pandemic, including support with the deployment of the COVID-19 vaccine. The revised programme continued to support the three outcomes in the Theory of Change, pivoting to include/emphasise supporting civil society resilience.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating * Two programmes merged to one FY18-19

What Support Did the UK Provide in FY 20/21?
The Tunisia CSSF Programme continues to deliver against HMG National Security Council (NSC) objectives. The programme is a key tool in tackling the long-term drivers of instability in Tunisia, directly contributing to the political and economic/prosperity objectives within the HMG Strategy as well as indirectly contributing to security and irregular migration objectives. The 20/21 programme comprised of 15 projects under five work stream areas: Macro-economic (4 projects); Private Sector Development (3 projects); Education (4 projects); Support to Vulnerable Groups (2 projects); Crisis Management Capability (2 projects)

Key Results for FY 20/21
- Initial steps taken towards digitising national and commercial financial activity.
- Accelerated digitalisation of government to people payments to help target those most vulnerable and affected by COVID-19.
- Provision of intensive care equipment (six intensive care ventilators, six monitors and two-syringe pump stations) to support effective response to COVID-19.
- Trained 5239 teachers on English language teaching, adapted to online delivery.
- Two second chance education centres opened, with a third centre to be opened in 21/22.
- Supported strategic communications from the Tunisian Government to its citizens on: COVID-19; entrepreneurship; reforms to local governance; investment promotion; crisis management.
- Support to mitigate the impact of COVID-19 on Tunisian SMEs and vulnerable groups.
- Enabled Government of Tunisia (GoT) security services to provide coaching, capacity building and support to other sections of the GoT security services.

Key Lessons
- The large variety of projects proved a significant administrative and governance burden. It is important to be modest in programming aspirations and not spread efforts too thinly.
- Positive lessons should be learned from the remote delivery of the education support, which extended the reach into remote regions and to those unable to attend training and led to significant cost savings.
- UK investment will not become comparable in size to other donors and therefore needs to be well directed. This year has proved the value of projects that enable wider large scale donor programming, where UK can have the most impact for relatively low investment.

Key Recommendations for FY 21/22
For HMG:
Given the evolving nature of the CSSF, HMG should consider developing a separate Tunisia or regional ODA funding stream to address education both as a fundamental conflict driver and as a key vehicle for UK influence at low cost in line with Global Partnership for Education (GPE) commitments.
For CSSF:
- Work with established partners and other donors to identify where CSSF investment can have most impact, using insights and lessons from 20/21 programming to identify ongoing and future opportunities.
- Contribute expertise to the United Nations Development Programme (UNDP), using lessons learned from the previous CSSF programme and wider UK interventions.
- Tunisia may provide an ideal opportunity to explore the relationship between education and peace and security in more detail with innovative and bold programming to support Open Societies through education.