Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Yemen Programme
Programme ID	C-MNA-0036
Country and Region	Yemen, Middle East and North Africa
IATI Unique ID	CSSF-06-000013
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £29.12m	Non-ODA: £1.6m
Budget this FY	ODA: £9.5m	Non-ODA: £0.5m
Spend this FY	ODA: £12.5m	Non-ODA: £0.53m
Time Frame	Start Date: April 2015	End Date: March 2022

Outputs	Scale of Delivery
UN has the capacity and tools to progress an inclusive peace process.	3
Platforms are created for marginalised and subnational groups to build consensus and participate in peace processes.	3
Key Yemeni financial institutions and international stakeholders have access to expertise and high-quality analysis that enhance their economic and humanitarian responses.	4
Communities and local authorities have access to resources that help address their stability needs.	3
Overall Scale of Output Delivery	3

Outcome Assessment	Regrettably, Yemen continues to suffer the severe consequences of conflict with little sign of the traction required to agree a viable political settlement, despite ongoing international effort. / Although COVID-19 and the FCO/Department for International Development (DFID) merger added to the delivery challenges, it is a credit to the collective effort of all concerned, both inside the programme partners, UK Government departments and others involved with the Yemen CSSF programme, that resulted in noteworthy progress in specific fields still being achieved in FY 2020/21.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	B	B	A	B	A	A	3	Amber
Risk Rating	High	High		High		High		High
Programme changes during this period		The main changes were because of COVID-19 and the reduction in UK Government funding to the Yemen Programme. CSSF resource was reprioritised to focus on the impact of COVID-19 by augmenting an existing Cash for Nutrition project. Funding was also secured at short notice for the UN-led process aimed at reducing the environmental threat from the SAFER floating oil storage vessel. The procurement freeze after the merger led to a delay in the development of the new Yemen Stabilisation Fund.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The Yemen Programme prioritised three areas:
- Make progress in national and sub-national level peace processes.
- Maintain the integrity of Yemen’s key financial institutions and formal economy, and curtail the war economy.
- Strengthen the basic human security and protection needs of Yemenis.

Key Results for FY 20/21:

- Rapidly responding to a major environmental threat: The CSSF programme was able to respond quickly to the emerging environmental threat presented by the decaying floating oil tanker SAFER, in turn catalysing other donors to make contributions.
- Adapting to COVID-19: To meet the needs of vulnerable women as a result of COVID, the CSSF team was able to quickly re-allocate funding to support a Cash for Nutrition project. Being able to make such adjustments successfully in-year was a significant achievement.
- Deploying UK expertise to support the peace process: The CSSF was able to fund and deploy technical advisers to support the UN and Yemeni institutions.

Key Lessons

- Realism of approach: The scale and severity of the conflict in Yemen will not be reduced by the CSSF programme alone. However, there is evidence that the programme can make a difference as an enabler in discrete areas where HMG chooses to prioritise effort, in line with UK interests. Whilst ambition is to be commended, the team should ensure Outputs and Outcomes are realistically within the CSSF’s sphere of influence.
- Need for cross-government involvement in CSSF: Coupled with improved understanding, there are benefits to be gained from improved policy and programme cohesion. Bringing these interests together from the concept stage boosts collective ownership, followed by using ongoing feedback to maximise the outputs of each project, thus enhancing overall impact. There are examples within the programme, particularly with regards to the economic file, which could be used as reference for a programme-wide approach.
- Costs of high performance: Being adaptive, delivering at pace and being flexible in programming are not cost-free CSSF strengths. Additional output was only generated by robust reprioritisation and significant extra effort by staff. There is a need to ensure that resourcing is adequate to support the ambition of the programme.

Key Recommendations for FY 21/22

- A cross-office review should be undertaken to scrutinise the direction, content and delivery of the CSSF programme, with a view to understanding how the CSSF can be best utilised by FCDO Yemen and HMG. This review should include examining the mixture of project types and methods to balance management of the programme. The benefits and trade-offs of flexibility and ad-hoc opportunities, longer-term programming (including pilots and project pipelines) and multi-year planning need to be considered.
- Additional attention should be invested in monitoring, evaluation, and learning across the CSSF programme; including how cross-cutting issues such as gender, conflict sensitivity, risk, and value for money are monitored and managed. Given the FCO/DFID merger, developing integrated approaches for FCDO Yemen could offer an opportunity for systemisation and sharing of best practice.
- Equipping projects with designated policy and technical/advisory leads should become the norm to better embed projects within FCDO Yemen. Ensuring buy-in across the office offers opportunities to maximise impact, ensure greater relevance to HMG objectives, and to improve value for money.