Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Migration – Collaboration Against Trafficking and Smuggling between Nigeria and Niger Programme
Programme ID	C-MIG-0002
Country and Region	Nigeria, Niger.
IATI Unique ID	CSSF-01-000023
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Home Office (HO)
Total Budget	ODA: £3,800,000	Non-ODA:£0
Budget this FY	ODA: £2,663,549*	Non-ODA: £0
Spend this FY	ODA: £1,662,861**	Non-ODA: £0
Time Frame	Start Date: August 2019	End Date: March 2022 (for Phase 1)

*The financial reporting from International Organization for Migration (IOM) is not broken down into sufficient detail to extract a number for the budget for this FY; this figure therefore represents the amount disbursed by FCDO to IOM from the start of the project until the end of last FY (August 2019-March 2021).
** This is spend to date since August 2019, not just last FY, as figures are not available from the IOM reporting provided for only the last FY.

Outputs	Scale of Delivery
1.1 3 border posts and 1 training centre in Niger are equipped with the MIDAS system (25%)	1
1.2 Border officers in Nigeria have access to MIDAS mobile border control means (and architecture plug & play) (25%)	1
1.3 Border officers demonstrate capacities to use the MIDAS system in Niger and to train other border officers on MIDAS use (30%)	1
1.4 Nigerien and Nigerian authorities are informed about key issues related to national data management (5%)	1
1.5 The development of national legal and operational data management frameworks is advocated in Niger and Nigeria (15%)	1
Overall Scale of Output Delivery	1

Outcome Assessment	When assessed against the indicators in the results framework, none of the outcomes have met the intended milestones for this stage of the programme. This is a complex, ambitious programme, and while good progress has been made over the past year in spite of the challenges posed by Covid-19, it is not clear at this stage if the outcome targets will be met by the end of this first phase of the programme in March 2022.
Overall Outcome Progress Rating:		Amber/ Red (Off-track, several outcome targets unlikely to be met without action)
Overall Risk Rating:		Medium/ high

Summary of Programme Performance
Year					2019/20b		2020/21c
Programme Rating					A	B	1	Amber/ red
Risk Rating					High		Medium/high
Programme changes during this period		None
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- This programme build on Anglo/French agreement to work in partnership on migration issues including by addressing human trafficking and smuggling upstream of European borders; this programme, which spans the border between Niger (where France has greater reach) and Nigeria (where the UK has significant interests) is part of this cooperation, and a key component of HMG efforts to tackle unsafe and illegal migration and help strengthen regional security and stability.
- The programme assists Nigerian and Nigerien authorities to build robust border management procedures through new technology, training and increased collaboration, benefitting security and stability in the region. It will also assist the victims of people trafficking and smuggling in the region, helping to better integrate development and security work in West Africa.
- Last year was the first year of this programme, with activities (mainly assessments) starting in October 2019. Activities during this review period (April 2020-March 2021) have been severely delayed by the impact of Covid-19-related restrictions in both Nigeria and Niger, including draw down of international HMG and IOM staff.
- A second phase of this programme, which will build on the first phase, is due to start this financial year and will end in September 2024. This review focuses on second year of the first phase of the programme, which ends in March 2022.

Key Results for FY 20/21:
- Construction/ rehabilitation of two border control posts in Niger largely completed.
- Two Nigerian state commands (Zamfara and Sokoto) supplied with MIDAS equipment.
- MIDAS training provided to 55 NIS staff from HQ, Zamfara, Sokoto, and Jigawa states

Key Lesson
This programme aims to effect institutional and systemic change across two countries in sub-Saharan Africa in challenging operating environments – it is unrealistic to expect this sort of programme to be able to show results at outcome level after less than two years of implementation. On reflection, outcomes within the results framework were overly ambitious and are now unlikely to be met. These should be revised, especially in the light of delays caused by the Covid-19 pandemic.

Key Recommendation for FY 21/22
Review programme Theory of Change, results framework and intervention logic as soon as possible, drawing on recommendations from the consultant report of March 2021.