Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Migration – Eastern Route (Turkey) Programme
Programme ID	C-MIG-0005
Country and Region	Turkey
IATI Unique ID	CSSF-01-000006
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Home Office
Total Budget	ODA: £12,477,811	Non-ODA: £132,937
Budget this FY	ODA: £3,959,115	Non-ODA: £0
Spend this FY	ODA: £2,927,352	Non-ODA: £0
Time Frame	Start Date: 1 April 2017	End Date: 31 March 2022

Key Outputs (of 3 Programme Outcomes)	Scale of Delivery
Directorate General for Migration Management (DGMM), Ministry of Health (MoH) and Ankara Municipality staff acquire knowledge on trafficking, reproductive health for refugee women and girls, regular and irregular migration issues	3
DGMM's capacity in processing the current asylum caseload improves in a human rights compliant and gender sensitive way	3
Syrian school girls take part in pilot research programme on targeted interventions that will assess how to maintain their school attendance and provide evidence-based policy tools to the Ministry of National Education in a gender and conflict sensitive way	4
To promote social cohesion, refugees are informed about civic life, roles and responsibilities of key government institutions, and accessing services provided by institutions in Turkey	4
Systems set up nationwide to increase Turkish Government’s capacity to handle returns and reintegration of irregular migrants from Turkey (AVR)	3
DGMM and Removal Centre (RC) staff have the skills and knowledge to enhance operations of and human rights standards in RCs	3
Cooperation mechanism between Turkey and Countries of Origin established	4
Overall Scale of Output Delivery	3

Outcome Assessment	Green: The programme showed solid progress against the vast majority of outcome indicators despite the very challenging year. This is testament to the agility of the programme, made possible by the close relationship established by the programme team with implementers and institutional stakeholders. Consideration should be given as to whether some objectives were ambitious enough or whether the best impact measurements were captured. It is crucial attention remains focused on capturing outcome-level change as and when it emerges.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	Amber/Red	B	B	A	A	A	A	3	Green
Risk Rating	High	Medium		Medium		Low/Medium		Medium
Programme changes during this period		The programme has adapted to the pandemic to deliver the intended outcomes. This meant introducing novel delivery methods (online, hybrid or open-air) and additional support (psychosocial, protection, etc).
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide?
The programme is fully aligned to the Prime Minister’s Global Agenda and the NSC Irregular Migration Strategy (with Turkey a priority country). Together with the (separate) €465.5m multilateral funding deployed through the EU Facility for Refugees in Turkey (FRIT (II) - and the deployment of HMG experts and political levers - this programme is the mechanism by which HMG meets migration-related objectives. The programme continued to support the strengthening and capacity building of Turkey’s frontline migration institutions. It sought to strengthen human rights compliance in the provision of services to vulnerable refugees, as well as the management of irregular migrants, particularly those held in Turkish Removal Centres.

Key Results for FY 20/21:
- The programme directly supported the Turkish government’s social cohesion policy priorities that are aimed at strengthening migrants’ integration within host communities, through policies focused on health, education and labour market access. By the end of FY 2021-22, the social cohesion project will help 100,000 refugees in 6 Provinces, including Istanbul (a major refugee hub), access key skills learning and information on support services.
- Support to the creation of Turkey’s first wholly national Assisted Voluntary Return (AVR) mechanism. The programme has developed and proven the concept for a national AVR mechanism (with external oversight by the Turkish Red Crescent to ensure safe & dignified returns) that can be used for returns to Afghanistan, Pakistan or other priority upstream countries.
- The programme led to the strengthening of engagement between Turkey and Countries of Origin (CoO), most notably Pakistan and Afghanistan. This allowed Turkey to continue charter flights to Afghanistan and scheduled returns to Pakistan (even during the pandemic). The CSSF has supported a new data-sharing system (NADRA) that has improved the Turkey-Pakistan returns process turnaround from 6 months to 2 days.
- The programme has supported handling of irregular migrants at the Removal Centres in a human rights compliant manner. There has been a considerable decrease in disciplinary actions at the RCs, as well as positive national and international reports.
- A research project on the integration of Syrian schoolgirls in Turkey carried out by a research team from a Turkish university is underway, endorsed by the Ministry of National Education (MoNE) and working in collaboration with the EU-funded PICTES project (Promoting Integration of Syrian Children into Turkish Education System).
- A programme of training on irregular migration, legal frameworks and migrants' rights issues including gender sensitivity was conducted with the Turkish Coast Guard (TCG) and resulting in a 29% improvement in TCG’s SAR operations, particularly in the area of human rights-based migrant processing.
Key Lessons
- Strong local knowledge leads to projects with clear buy-in from government and implementing partners, and ‘richer’ insight and programming results.
- Training has most impact when implementing partners are flexible and adaptive to the political and operational context. The capacity of IPs to flex is crucial in this regard.
- The complex and long-term challenge of creating social cohesion requires more than training and incorporating other methodologies and approaches, such as action research and pilots.
- Ongoing monitoring through close contact with IPs and beneficiaries has significant value and importance in achieving and articulating results.
- Recognising the complexity of the political environment and ensuring strong connections between policy and programme, drawing on robust local understanding, is critical.

Key Recommendations for FY 21/22
1. Strengthen the strategic coherence of the programme: consideration should be given to the prioritising programme strands in line with its impact statement, and the direction set by the Integrated Review.
2. Strengthen sustainability and subsidiarity: the programme team should ensure the programme doesn’t fund running costs for core services, which would endanger the programme’s agility, but also risk displacing Turkish service provision.
3. Prioritise strategic GoT ministries’ engagement: Strategic partnerships between the programme and Turkish Government agencies is notable; however, consideration should be given as to which Ministries the programme should prioritise its support.