Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	CSSF Migration – Nigeria Border Covid 19 Response Programme (NBCRP)
Programme ID	C-MIG-0006
Country and Region	Nigeria
IATI Unique ID	CSSF-01-000022
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £606,000	Non-ODA: £0
Total Spend	ODA: £606,000	Non-ODA: £0
Time Frame	Start Date: August 2020	End Date: March 2021

Outputs	Scale of Delivery
1.1 Needs assessment/fact-finding at Nigeria Port Health Service (NPHS) and Nigerian Immigration Service (NIS) is carried out for strategic planning for immediate, mid-term and long-term intervention.	4
1.2 Points of entry (POEs) are provided with equipment and PPE materials for processing/screening travellers and protection of front-line officers.	3
1.3 Front-line officers can correctly and consistently use PPE and travellers have access to information, education, and communication (IEC) materials.	4
Final Overall Scale of Output Delivery	4

Outcome Assessment	Strengthening Nigerian Government’s Covid-19 response at points of entry through increased capacity and collaboration between Nigerian Immigration Service (NIS) and Nigerian Port Health Service (NPHS).
Final Overall Scale of Outcome Achievement:		4
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	N/A	N/A	4	4
Risk Rating	N/A	N/A		N/A		N/A		Medium-Low
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
The objective of the Nigeria Border Covid-19 Response Project (NBCRP) is to support the Federal Government of Nigeria’s (FGN) response to the COVID-19 pandemic by building capacity in, and collaboration between, the two main frontline agencies responsible for implementing health and immigration controls at Nigeria’s borders, the Nigeria Port Health Service (NPHS) and Nigerian Immigration Service (NIS).

What Results Did the Programme Deliver?
- Four border control posts (Illela, Jibiya, Maigatari and Kamba) supplied with solar powered isolation units, and boreholes for improved wash facilities.
- Five international airports supplied with thermal scanners for arriving and departing passengers.
- Information, Education, and Communication materials delivered to 19 Nigerian points of entry (7 seaports, 7 land crossings, 5 international airports).
- Infection Prevention and Control (IPC) training of trainers was delivered to 17 frontline PHS officers and cascaded further by them to colleagues in their respective PoEs.

What Lessons Have Been Learnt?
- Starting the programme quickly meant that the needs assessment was not as detailed as the programme team would have liked. The issues that were discovered during delivery e.g. difficulty in accessing some areas, getting necessary permissions from authorities and World Health Organisation advice on sanitation tunnels, had to be dealt with during real-time delivery. The programme team learned to be flexible as information became clearer, therefore ensuring that the programme adapted to the realities of the situation.
- During the Covid period face to face engagement stopped, causing a feeling of being disconnected, therefore the programme team had to change their stakeholder engagement strategy. The delivery team used various e-tools (MS Teams, Webex, Whatsapp etc) to maintain relationships between the implementing partner and programme team. This methodology reduced programme bureaucracy; however, it was not applicable to government correspondence as government officials are not keen to engage informally.
- The use of the ambulances was delayed, in future it might be beneficial to explore the procurement of such equipment in country; to include the various government officials into the programme activities to reinforce the importance of the intervention; consider the dropping of that activity; and bringing in British High Commission representation at an early stage.
- On sustainability, the programme delivered computers and other equipment. Given the short nature of this intervention, a plan for monitoring the use of this equipment could be included in longer-term Nigeria programming
- It would have been useful to have monitored the wider government's response to Covid to track whether this intervention had an impact in future deliveries of PPE to the programme’s stakeholders.