Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Reintegration and Support for Returnees Programme
Programme ID	C-MIG-0007
Country and Region	Afghanistan and Pakistan
IATI Unique ID	CSSF-01-000005
HMG Partners / (Lead in bold)	Home Office and Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA:£8.75m	Non-ODA: £0
Total Spend	ODA: £4.19m	Non-ODA:£0
Time Frame	Start Date: 1 April 2017	End Date: 31 March 2021

Outputs	Scale of Delivery
Individuals are provided with access to practical reintegration assistance	4
Individuals are supported in re-engaging with their local communities	4
Final Overall Scale of Output Delivery	4

Outcome Assessment	Outcome 1 - Individuals receive assistance and are starting to sustainably reintegrate. / Outcome 2 - Individuals are contributing to and participating in their local communities. / Target numbers were set before the effects of Covid were known and as a result the programme did not achieve all intended outcome targets. Covid aside, the Programme met the key outcome aims with the returns that were achieved.
Final Overall Scale of Outcome Achievement:		4
Overall Risk Rating:		Medium/High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	Amber/Red / Outputs moderately did not meet expectation	B	B	B	B	A	A	4	4
Risk Rating	High	Medium		Medium		High		Medium/High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?

During the previous two financial years, the programme comprised of two pilot projects in Afghanistan and Pakistan. These provided immediate assistance on arrival at the destination airport and longer-term sustainable reintegration support to individuals returning from the UK. Reintegration activities included job placement or creation, education and training, accommodation and referral to relevant local organisations and amenities.

What Results Did the Programme Deliver? Will they be Sustained?
The overall objective of the programme was to return and sustainably reintegrate returnees back to their communities, and support the returnees directly and their families, communities and the host Government indirectly, providing them means for sustainable income generation. This was achieved through the programme consistently ensuring returnees in both countries remained employed through in-kind reintegration support they received.

- Despite contract delays to the project in Pakistan and returns being severely affected by Covid, 80 returnees were provided with reintegration support over the duration of the programme. Of these, 45 returnees received longer term reintegration support.
- The programme managed to sustain operations and achieve the results it did in the face of the pandemic and political/security issues. This was the result of good co-ordination with partners in the UK and in country with consistent monitoring and evaluation.
- Case studies in both countries highlighted excellent examples of good outcomes where our support has helped returnees establish their own business and continue to maintain themselves and their families.
- The pilot delivered on its aim of demonstrating that long term sustainable reintegration is possible and enables the Home Office to consider this against other models for future programming.
- Both projects have successfully transitioned from CSSF to the Home Office baseline which provides an opportunity to monitor the longer term impacts and benefits.

What Lessons Have Been Learnt?

- Covid severely impacted the Programme but successful reintegration was still possible.
- Effective relations with implementing partners, host Government and other key stakeholders can help overcome Covid related obstacles and reduce admin costs.
- CSSF Migration can provide a useful source of evidence for piloting new programming which can then be taken forward on departmental baselines.
- Providing accurate estimates on numbers being returned can help deliver more effective programming and better value for money.
- Sustainable reintegration for returnees is achievable and remains an important part of the UK’s wider commitment on returns work led by the Home Office.