Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Championing Our Values
Programme ID	C-MLS-0001
Country and Region	Multilateral Strategy Fund - CSSF
IATI Unique ID	CSSF-01-000001
HMG Partners / (Lead in bold)	FCDO, MoD
Total Budget	ODA: £31.79M	Non-ODA: £0
Total Spend	ODA: £31.52M	Non-ODA: £0
Time Frame	Start Date: 1 April 2016	End Date: 31 March 2021

Outputs	Scale of Delivery
1. Strengthened cooperation between UN Office and intergovernmental organisations on Children and Armed Conflict (CAAC).	3
2. (Human Right and Conflict Prevention (HRCP)). The creation of Colombia-specific gender- and age-responsive assessment tools (e.g. surveys, interview scripts) informed by the rigorous multi-method approach taken by the Managing Exits from Armed Conflict (MEAC) Framework and related survey templates.	4
3. (Human Right and Conflict Prevention (HRCP)). Conduct assessment missions, on request, and to priority countries based on the Office’s monitoring, with the aim of identifying risks of atrocity crimes, with a particular focus on hate speech, and providing recommendations for mitigating action.	3
4. (Human Right and Conflict Prevention (HRCP)). Develop a mapping, relevant to the reprisals context, of the type of interactions between civil society and the Security Council and its subsidiary bodies, identifying actors involved and their role, modalities of interaction, degree of exposure for civil society, and possible risks to those cooperating with the UN.	4
5. (Preventing Sexual Violence in Conflict Initiative (PSVI)). Quality and gender-sensitive investigations and reporting of sexual and gender-based violence are produced by OHCHR field presences, including human rights components of peace operations, and international investigative bodies supported by OHCHR.	4
6. (Preventing Sexual Violence in Conflict Initiative (PSVI)). Support to OHCHR on initiatives on accountability and access to justice, including transitional justice, for victims of sexual and gender-based violence.	4
7. (Preventing Sexual Violence in Conflict Initiative (PSVI)). Political will to promote accountability for CRSV at national, regional and international levels enhanced.	4
8. (Women Peace and Security (WPS)). Executive Office of the Secretary-General (EoSG). Strengthened EoSG external messaging on gender equality as part of all core priority areas - climate, the SDGs and peace and security - including during and post-COVID-19.	4
9. (Women Peace and Security (WPS)). Elsie Initiative Fund for uniformed women in Peace operations (Elsie Initiative). Proposals taken from first programming round taken forward.	4
10. (Women Peace and Security (WPS)). Department of Political and Peacebuilding Affairs (DPPA). Women indigenous leaders have adequate knowledge and are provided with a meaningful space to develop strategies and have active participation in the conflict claims for indigenous territories in the area of Buenos Aires highlighting the role of women in peace and conflict resolution processes.	3
Final Overall Scale of Output Delivery	4

Outcome Assessment	The Championing Our Values Programme has undoubtedly matured and as a result narrowed its focus over the duration. Aligned to deliver sub-objective 2.6a of the NSC Strategy, it has been a good example of promoting the application of Fusion Doctrine and has included strategic, operational and tactical development, with the UK being a desired partner/donor. Whilst the various projects have built and continuously developed strong relationships across and between UN departments, awareness, engagement and then consensus, is a complex and all-consuming endeavour; stakeholder engagement and coordination, outreach and expectation management. Consequently, the lack of staffing uplift to support the programme manager in New York has been unfortunate. Policy engagement has developed over the course of the programme and all programme stakeholders have taken on the requirement for project frameworks and establishing M&E, at great pains from the Programme team. With the Outcomes, three aligned projects are newly adopted, and whilst still at the Output level, are being continued beyond this programme closure; they very much represent how far the programme and the UK has come in its understanding of the UN and how to use projects for better access, understanding and influence, to drive forward UK objectives.
Final Overall Scale of Outcome Achievement:		Green
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	A		A	A	A	A	4	Green
Risk Rating	Medium	Medium		Medium		Medium		Medium
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
The Multilateral Strategy Programme (MuSt) concentrates on areas that are not tackled through other funding streams, and where policy leads see the greatest opportunities for driving reform in combination with wider influencing.

The Championing Our Values (CoV) Programme, within the broader MuSt portfolio, was designed to deliver sub-objective 2.6a of the NSC Strategy: ‘Multilaterals better able to promote a reduction in human rights violations, mass atrocities, recruitment and deployment of child soldiers, sexual violence in conflict, sexual exploitation and abuse, and better protection and participation of women and girls.’

The CoV Programme has provided support to:
- Increased capability of several UN Departments, and their staff, to prevent and mitigate drivers of conflict through more focused early warning and preventive diplomacy.
- Stronger UN Secretariat oversight and delivery achieved through financial support and technical assistance on policy and standards.
- Tackling sensitive, underfunded issues in line with UK WPS, Human Rights, Protection and Participation objectives at the UN.
- Improved capability of UN Missions, promoting inter-operability and higher efficiency, whilst driving gender equality.
- Stronger mechanisms for the prevention and protection of those individuals willing to step forward in cooperation with the UN in the field of human rights.
- Strengthened system-wide response and implementation of zero-tolerance policy for UN personnel committing incidents of sexual exploitation and abuse in complex operating environments.

What Results Did the Programme Deliver? Will they be Sustained?
- Professionalisation of Sexual Exploitation and Abuse (SEA) investigations in the UN.
- Improved early warning system on CRSV developed through key peacekeeping missions of MINUSMA (Mali), MINUSCA (Central African Republic), UNSOM (Somalia) - by strengthening their Monitoring, Analysis and Reporting Arrangements, and developing information sharing protocols and other tools.
- Strengthened coordination between all the UN departments and agencies on response to victims of SEA.
- In-country action plans to make ‘countries of concern’ accountable for Children and Armed Conflict (CAAC) and the development of National Prevention Plans through de-listing of countries in employing armed children.
- The perspective that the UK is a desirable and serious partner/donor in the areas that this programme covers; through the UK’s ability to engage ministers at the right levels, underpinned by consistent and pro-active programming and policy support and engagement.
- The programme has made strong influence on modelling international agenda, and prioritising themes that are key HMG policy objectives in the multilateral sphere and configure towards the UK National Action Plan (NAP) on Women, Peace and Security (WPS). Further to advancing UK national interests the selection of projects and prioritisation of activity has mobilised other donors and allowed implementers to better demonstrate outcomes and impact.
- UK Leadership on Women Peace and Security via support to the UN Elsie Initiative Fund, which seeks to accelerate the pace of change towards increased meaningful participation of uniformed women in United Nations peace operations and be translated into policies and action.
- Contributing to Trust Funds that deliver in particular thematic areas (e.g. Preventing Sexual Violence Initiative and the UN Elsie Initiative Fund).
- Political and Defence Engagement leading to consensus, and as a result some significant change, specifically in Sexual Exploitation and Abuse, PSVI and CAAC.

What Lessons Have Been Learnt?
- Policy engagement. Process and results of the programme have improved significantly where there has been regular engagement by policy holders with their programme team and with implementers (R1). For instance, where there has been cross-government policy engagement in support of the Elsie Initiative Fund, this has likely enhanced and enabled the bid for the UK to be on the Steering Committee.
- Funding in the UN. Start-up of projects within the UN take much longer than anticipated, generally due to funding and the processes involved, further complicated by different financial years for the UN and UK. This impacts the ability for projects to deliver on the originally planned timeframe and should be factored in from the inception of a project. Our investments therefore need to be for a reasonable length of time to see results.
- Programmatic requirements. The programme over its duration has proven to be at the forefront of thinking and planning in areas that more often than not ask difficult questions of the Member States and the UN and its constituent organisations. It has complimented the UK’s lead on WPS. And whilst it is attributable, partially or otherwise, to some systemic changes across the UN, its major contribution has been in changing attitudes and behaviours - a long term process. However, the UK still requires the programme to conform to process driven reporting and tick-box exercises, to satisfy and justify its spend. This approach, in this instance, means that those involved are not facilitating / engaging / building relationships / seeking opportunities, but ticking boxes and have consistently been unable to report / evidence the real value of a programme like this - its Political, Access and Influence and the leverage this allows. Apparent blueprinting of programmatic requirements for the ease of a central processes is not helpful and misses the point of such a programme. Devise what is absolutely necessary and then allow innovation at the programmatic level to devise the best way to represent the Outputs, Outcomes and Impact of such a programme, in a consultative way. Re-evaluate whether Results Frameworks are useful for capturing progress in this context (R2a).
- Trusted partner. This hinges on HMT. The current yearly spending review, the out of synch UN and UK financial years mean early decisions need to be made by the UK programme team on prioritisation of projects; this hinges on decisions being made centrally and in Treasury and so is further complicated when spending review timelines shift to the right. The specific risk being that the UK, with its new drive from the Integrated Review where Multilaterals have been designated a priority, is not seen as a trustworthy partner/donor and therefore does not hold the political leverage and influence it might have.
- Narrowing the Programme’s focus over its duration has enabled the Programme to better seek to achieve its Outcomes, has enabled enhanced strategic coherence and better engagement internally, as well as externally. Important to recognise that it takes time to understand where to narrow to.