Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	CSSF MuSt Peacekeeping Programme
Programme ID	C-MLS-0007
Country and Region	Multilateral
IATI Unique ID	CSSF-01-000003
HMG Partners / (Lead in bold)	FCDO & MOD
Total Budget	ODA: £3,120,000	Non-ODA: £1,950,000
Budget this FY	ODA: £3,120,000	Non-ODA: £1,950,000
Spend this FY	ODA: £2,237,936	Non-ODA: £1,345,445
Time Frame	Start Date: 01 April 2016	End Date: 31 March 2022[1]
[1] A decision was taken at the end of 2020 to continue the programme on the basis of single year funding. At the time of writing this review it continues to run in FY21/22.

Outputs	Scale of Delivery
1.1 Regular monitoring and evaluation of mission impact, based on objective performance data and other evidence, feeds into mission planning and decision-making and is shared transparently across the Secretariat and with the Council.	3
1.2 The UN and other Member States recognise the contribution made by the UK to peacekeeping, and can clearly identify its focus on performance, planning and pledges in accordance with the UK PK reform agenda.	3
2.1 Military and civilian personnel are better equipped to fulfil protection of civilian mandates.	3
2.2 Greater accountability of UN Peacekeeping Personnel through embedded mechanisms of checks and balances.	3
3.1 DEPLOYMENTS: Demonstrable contribution of UK expertise in peacekeeping missions planning, structure and training.	4
3.2 Mechanisms for missions to support planning inter-operate creating increased efficiencies.	4
4.1 Reporting clearly indicates gender consideration including in disaggregation of data and conflict analysis.	3
4.2 Sustainable increase in recruitment of women into senior positions of peacekeeping missions.	4
Overall Scale of Output Delivery	3

Outcome Assessment	Reform in the UN takes time. The operating environment for the programme is challenging. The programmatic framework has improved significantly since the last review. More can still be done to improve overall coherence. Hence the focus in this review on continuing to improve the Programme Document, Theory of Change, and Results Framework. The programme also faces the additional challenge of being assigned single year funding, which could make longer term forecasting and planning for realistic longer term (slow) pace of change difficult.
Overall Outcome Progress Rating:		GREEN/AMBER
Overall Risk Rating:		Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	A	B	A	A	B	B	3	GREEN/AMBER
Risk Rating	Low	Low		Low		Low
Programme changes during this period		COVID-19 significantly affected delivery of projects.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

- The MuSt Peacekeeping programme aims to make UN peacekeeping operations more effective and efficient, with better capabilities to deal with the challenges of modern peacekeeping. This contributes to conflict containment, the reduction of violence and ultimately the resolution of conflicts to create the stability necessary for peace to flourish. The programme started delivering in 2016 following the UN Peacekeeping Defence Ministerial in London, with 74 nations and international organisations endorsing a UN reform agenda based on '3Ps': better mission planning, increasing the number of meaningful pledges of troops and equipment, and improving the performance on the ground – followed in 2018 by the UN Secretary-General’s Action for Peacekeeping (A4P) initiative.[2] The programme currently provides: (i) Dedicated extra-budgetary (XB) funding to the UN on improving the delivery of Peacekeeping Operations, and (ii) Deployment of UK military and police officers to UN missions and headquarters.
  [2] A4P commitments span: politics; women, peace and security; protection; safety and security; performance and accountability; peacebuilding and sustaining peace; partnerships; conduct of peacekeepers and peacekeeping operations. See https://peacekeeping.un.org/en/action-for-peacekeeping-a4p.
- The programme was delivered through a combination of funding to UN bodies and financial support for 17 projects implemented by: UN Department of Peace Operations; UN Office for Information Communication and Technology; HMG Stabilisation Unit; HMG UN Peacekeeping Joint Unit; UK Permanent Joint Headquarters and Ministry of Defence.
- It is currently funded on a renewable single year basis and the total budget for FY20/21 was £5.07m.

Key Results for FY 20/21:

18 deployed UK Military Staff Officers in 5 UN Peacekeeping and Special Political Missions conducted a range of influential roles relating to senior advisory services, planning, intelligence, operations and gender.
- Peacekeeping Intelligence capabilities made missions more resilient and better equipped. Guidance and training were adapted to more online accessibility due to COVID-19.
- Data and Evidenced Based Decision Making. The Data Analytics Project established data connections with WHO, OCHA and others to collect and distribute COVID-19 data across peacekeeping missions. A project aimed at collating recommendations for MINUSCA from multiple data streams established the MINSIGHT APP, which was successful in its pilot with senior leadership across the UN and showed ability to be replicated to a number of peacekeeping missions in future.
- The Protection of Civilian team engaged with NATO and are now coordinating workshops and lessons of best practice. Their work from UNAMID is continually being fed into the establishment of UNITAMS –particularly on unarmed approaches to POC which has resulted in a report due to be published shortly.
- Zero tolerance for Sexual Exploitation and Abuse. The SEA Risk Management Toolkit is under implementation in all missions, with two other toolkits under development and due for rollout.

Key Lessons

- Outputs and Indicators need to have clear and measurable correlation with Strategic Objectives. Outcomes need to better refer to what changes are being seen in Mission and HQ practice, not results of project activities.
- Reporting on Political Access and Influence (PAI) should evidence the added value of how project activity is used by wider diplomatic engagement, and exploit linkages between projects such as MSO deployments and support for DPO.
- The programme needs closer working relations between the Programme Team and HMG Policy Leads in London, UKMIS New York, and DPO to improve evidence of programme-policy synergy.

Key Recommendations for FY 21/22
- Review and revise the Programme Document, Theory of Change, and the Results Framework.
- Organise a workshop for UN Secretariat staff/implementing partners in New York to improve understanding of the programme-level objectives and to strengthen reporting.
- Improve data collection for Political Access and Influence (PAI).