Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Security Capacity Building CSSF Multilateral Strategy (MuSt)
Programme ID	C-MLS-0008
Country and Region	Multilateral institutions (NATO, UN, OSCE, IAEA, OPCW, WHO and Commonwealth Secretariat) to deliver UK peace and security objectives in NSC priority areas and countries
IATI Unique ID	CSSF-01-000004
HMG Partners / (Lead in bold)	FCO; plus MOD.
Total Budget	ODA: £1.15m	Non-ODA: £1.8m
Budget this FY	ODA: £1.15m	Non-ODA: £1.8m
Spend this FY	ODA: £0.96m	Non-ODA: £1.77m
Time Frame	Start Date: April 2020	End Date: 31 March 2021

outputs	Scale of Delivery
NATO
1. NATO Voluntary National Contribution	4
2. NATO Voluntary National Contribution	4
3. NATO Voluntary National Contribution	4
4. NATO Voluntary National Contribution	3
5. NATO Voluntary National Contribution	4
6. NATO Voluntary National Contribution	4
7. Resilience Manager, UK Delegation NATO	4
Counter Proliferation
8. IAEA Joint Comprehensive Plan of Action (JCPoA)	4
9. OSCE Conflict Prevention Centre, Small Arms & Light Weapons (SALW) and Stockpiles of Conventional Ammunition (SCA)	4
10. Organisation for the Prohibition of Chemical Weapons (OPCW)	3
11. World Health Organisation (WHO)	3
Countering Violent Extremism
12. UNOCT – UN Office of Counter-Terrorism	3
Commonwealth Secretariat
13. P/CVE - preventing/Countering Violent-Extremism	4
Overall Scale of output Delivery	3

Outcome Assessment	The inputs for this programme have improved, with better preparation of secondees, and their impact has been effective. It is not far off a Green rating. However coherence within the programme remains an issue, specifically the link between activity and policy outcomes through the Results Framework. There could be significant value in this programme if it were used to signal intent, understand the multi-lateral environment and help vector core activity to deliver Political Access and Influence (PAI) more purposefully. This is particularly the case post-Integrated Review, where the SCB could be used to rapidly find our way in new and emerging multi-lateral relationships. As it stands, the programme seems quite output focused.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	A	A	A	A	A	A	3	Amber
Risk Rating	Medium	Medium		Medium		Medium		Medium
Programme changes during this period		Transfer and/or end support to Counter Terrorism/Countering Violent Extremism projects to be managed by relevant thematic teams.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The Security Capacity Building (SCB) programme aimed to develop the capacity and capability of multilaterals to respond to and counter growing threats in National Security Secretariat / Strategic Defence and Security Review priority areas including hybrid threats, violent extremism and Chemical, Biological and Nuclear threats.

The programme attempted to achieve these objectives through a mixture of secondments (known as voluntary national contributions or VNCs to NATO) and funding which is leading to improved policy formation and delivery on the ground by the multilaterals. The UK supports multilaterals selected by their relevance to UK national security strategies. With the aim that multilaterals will be better at responding to, and countering, growing threats in national security priority areas.

Key Results for FY 20/21:
- Publication of the Deterrence playbook by the Hybrid Centre of Excellence, an important contribution to the literature on countering hybrid threats (Annual report 2020)
- Mapping of UN Counter-Terrorism activities against UK priorities completed and MOU between UNOCT and UNDP signed off
- NATO messaging on tactical and strategic level noticeably improved with central communications
- NATO cyber threat Intelligence and Defence Matrix introduced
- NATO Action plan to implement the policy on preventing and responding to sexual exploitation and abuse agreed

Key Lessons for FY 21/22

- Improvements have been made with the link between secondees, policy and mission teams, but more clarity is required in what the general support function looks like and the offer between FCDO and NATO
- Programmes are not static, which means Results Frameworks can flex and need to adapt to the changing context (such as Covid)
- A programme suite of reporting can help better monitor performance and progress against outputs
- Political Access and Influence is not just about being an ‘enabling factor’ and needs to be better defined for the secondees and whether this is being reported. Understanding an organisation and where HMG fits are as important as delivering influence. SCB potentially delivers understanding which policy leads and other CSSF and HMG Departments-funded programmes can then use to deliver PAI both with multilaterals and internally to HMG.

Key Recommendations 21/22

Revised and updated Results Framework with consideration on how to get more consistent programme reporting
Further improvement on VNC support and Duty of Care (DoC). This should include a policy on what the VNC ‘Offer is’ and how issues such as DoC are handled.
Reduce indicators where possible, and consider better programme coherence across the pillars so the outputs add up to outcomes.
Programme needs to be more adaptive to changing context and reporting, such as the Results Framework, to be regularly updated and revised.
Clearer finance reporting and requesting consistent detail from partner organisations. This will help with Value for Money.
Articulate Political Access and Influence as a delivery objective