Annual Review (C-19 Vers.) - Summary Sheet
PROGRAMME TITLE: UN Reform
Country and Region:	Multilateral
IATI Unique ID:	CSSF-01-000019
HMG Partners / (LEAD in bold)	FCO, MOD, Stabilisation Unit
Total Budget:	ODA: £3,134,000			Non-ODA: £1,600,000
Budget this FY	ODA: £3,134,000			Non-ODA: £600,000
Spend this FY	ODA: £2,682,753			Non-ODA: £290,000
Original Programme Start Date: Apr 19		Planned End Date: Mar 22
Outputs					Score
1. DATA CUBE: The UN (and its Facilities and Commercial Activities Service) have improved systems that lead to greater transparency on where resources are allocated.					A
2. STRENGTHENING GOOD GOVERNANCE AT THE SENIOR LEADERSHIP LEVEL: Good practice financial management and promote transparent and effective accountability for the implementation of the expanded and direct delegations of authority under the Secretary-General’s management reform.					A
3. INDEPENDENT SYSTEM WIDE EVALUATION: Improved system-wide capacity and mechanisms for independent evaluation of the UN development system established					A
4. ONE HR: UN jobs are opened up to a wider pool of applicants, with a wider range of skills and experience to draw upon.					B
5. ACTION FOR LEARNING CONFLICT ANALYSIS: UN organisations working on humanitarian issues do better conflict analysis, utilising other UN resources, and use it to inform their work.					A
6. FLEET MANAGEMENT, COMMON PREMISES / UN organisations are able to share resources more effectively in country					A
7. FINANCING PEACEKEEPING TRANSITIONS / 1. The Financing for Peacekeeping Transitions report completed / 2. Dissemination strategy produced					A
8. HUMANITARIAN DEVELOPMENT PEACEBUILDING & PARTNERSHIP FACILITY / Increased UN/World Bank cooperation to deliver joint strategic priorities: / 1. Improving data, joint analysis and developing the evidence base for programming / 2. Enabling Joint Assessments and joint planning frameworks / 3. Design and implementation support to scale up impact					B
9. INTEGRATING CONVENTIONAL ARMS CONTROL INTO CONFLICT PREVENTION / Improved UN guidance for integrating and implementing conventional arms control into UN conflict prevention and management activities.					B
10. RESIDENT COORDINATER OFFICE SUPPORT / 1. The Strengthened RCO provides timely and effective political facilitation, accompaniment and good offices support with a view to mitigating potential conflicts and sustaining peace in Liberia. / 2. The Strengthened RCO supports and coordinates the UN’s continued efforts to address the root causes of conflicts after UNMIL’s departure.					B
Overall Output score					A
Outcome Assessment: / The first year of the UN Reform programme faced challenges due to capacity being drawn away from programme management to provide support to Exiting the EU and Covid-19 response. Despite the projects being in implementation for only 6 months by the end of FY 19/20, collectively the 10 projects within the UN Reform Programme are starting to achieve a broader catalytic effect through experiential testing and proving concepts. The narratives and evidence presented within some of the project-level Quarterly Reports was of a high standard. However, the programme could be managed more coherently to demonstrate this effect at the programme level. This raises the question of whether the programme-level management tools are being used to capture and analyse evidence that allows the programme team to report on detailed progress towards outputs, objectives and outcomes. It draws into question the utility of the Results Framework (RF) as a management tool for this programme. / The issues with the RF as a management tool are amplified by the challenge of capturing the positive effect of the Political Access and Influence (PAI) created through the projects in the UN Reform Programme. It is clear that for any project to be successful there has to be a strong policy lead that links back into the programme management team. The policy lead can have a significant role in translating tactical project level outputs into strategic programme level outcomes through engaging with stakeholders, promoting successes and advocating for greater UN Reform through proof of concept. However, the mechanisms for monitoring and evaluating PAI need to improve as at the programme and policy level the significant cumulative effect of the projects is not being articulated to demonstrate the UK’s innovative contribution to UN Reform. The programme team should consider how the nuances that demonstrate PAI within Multilateral Institutions is captured through different M&E frameworks, as DipTels were highlighted by the programme team as important evidence of progress. / It is clear that the projects within the UN Reform programme are led by innovative and enthusiastic implementers who are genuinely passionate about reform. Whilst it is understood that Covid-19 hit at the end of FY 19/20 and there were capacity issues within both the programme team and the policy leads, due consideration must be given to how the programme documentation and reporting processes guarantees that the projects gain the exposure required for PAI and VfM to be realised.
Outcome Score: C			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	NA/A	N/A	N/A	N/A	N/A	A	C
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	N/A	N/A	Low	Medium
*Output/Outcome scores
How has the Programme changed during this period?			This was the first year of the UN Reform programme.

What support did the UK provide in FY 19/20?
Peace and Security Architecture Reform: The goal of this reform pillar is to create greater coherence by integrating, enhancing and supporting systems that prevent conflict and sustain peace.
1. Integrating Conventional Arms Control and Conflict Prevention: Funding contributed towards dedicated research with the aim to better integrate conventional arms control into conflict prevention approaches.
2. Support to Empowered Resident Coordinator Offices (RCOs): Funding contributed towards supporting the RCO in Liberia. Whilst the proposal was to support a select number of RCOs, Liberia was the only RCO to receive the funding.
3. Financing Peacekeeping Transitions: Funding contributed to the project “Principles for Development Finance to Support Transitions from Peacekeeping missions”. This project aimed to help cultivate principles for development finance to ensure that the potential negative economic impacts of drawdown and withdrawal of UN peacekeeping missions are mitigated.
Development Reform: The goal of this reform is to create sustainable development solutions for countries affected by conflict by helping development activities to become more efficient and effective.
1. Action for Learning Conflict Analysis (ALCA): Funding contributed to a study into existing conflict analysis tools used by OCHA and its partners in order to produce more practical training materials and design a better-tailored training course for humanitarian practitioners in the field.
2. Independent System Wide Evaluations (ISWE): Funding contributed towards a secondee within the UN Transition team to undertake a review of UNDS capacity for cross-system evaluation and scope the feasibility of an Independent Evaluation Unit.
3. Humanitarian Development Peacebuilding & Partnership Facility (HDPP): Funding contributed to the HDPP Facility which aims to provide advisory support and grant funding to UNCTs to establish strategic and operational frameworks with partners across the humanitarian, development and peace nexus in crisis-affected situations. The focus is primarily enabling UN operations to leverage partnership with World Bank to increase impact on the ground.
Management Reform: The goal of this reform is not only to improve the UN’s own HR procedures, but to move decision-making closer to the point of delivery, align accountability with responsibilities and simplify process and policy.
1. Fleet Management & Common Premises, Business Innovation Group (BIG): Funding contributed to the large-scale SG initiative to deliver business operations reform to have a direct and positive effect on Country Office operations. The focus is on creating One UN Fleet and Common Premises to make large savings of logistical support.
2. Reform of UN HR Procedures (One HR): Funding contributed to the large-scale SG initiative to bring multiple agencies working on One HR programme. The funding has specifically contributed to expansion of the service lines of One HR to include a centralised recruitment portal for the UN system, and develop an artificial intelligence and robotics tools to improve the efficiency of the service lines.
3. UN Transparency and Accountability ‘Data Cube’: Funding contributed to the large-scale project aiming to enable greater transparency of UN System-wide resources for internal and external stakeholders, which will in turn drive stronger UN accountability, coherence and impact. The project has three core elements: Data Strategy, Dataset on UN system financial statistics, and a transparency portal.
4. Strengthening Good Governance at the Senior Leadership Level: Funding contributed to DOS development and delivery of an integrated capacity development package for UN Senior Leaders to successfully exercise their expanded delegations of authority and drive strong governance and resource stewardship in the implementation of mandates.

Key results for FY 19/20:
1. Political Access and Influence – Whilst not reported in the RF at the outcome level, the endorsement and continuation of some of these UK projects by other donors and entities is a testament to the catalytic effect of the UN Reform Programme. These successes also encourage future PAI for the UK within the UN and bolster the UK’s reputation in donor circles.
2. Fleet Management – The Fleet Management project was a key result for FY 19/20 as the outputs achieved in-year have created the conditions for the project to be taken forward by 2 of the biggest UN agencies: UNHCR and WFP. The project has highlighted the UK’s intent to support the SG in terms of Management Reform. It has also helped the UK in Geneva, as it is seen to have a focus on innovation and is ambitious to try new things.
3. Reform of UN HR Procedures (One HR): One HR also only scored a ‘B’; however, it was a key result for FY 19/20 because, similarly to Fleet Management, it is the perfect example of where UK programmatic interventions can be used to improve the UN processes. This project would have benefitted from better policy and programme management to demonstrate how it links to the goals set out in the programme documentation and amplify UK involvement to the UN.
4. UN Transparency and Accountability ‘Data Cube’: The Data Cube project is clearly a highly valued project within the UN. It has had significant UN SG personal endorsement and it is therefore valuable to have the UK involved in the funding of such important UN Reform work.
5. Strengthening Good Governance at the Senior Leadership Level: This project has had a very positive impact on senior leadership training and has delivered just below the intended 30 training courses that are uniquely tailored to client’s needs. It has plugged a gap in leadership training and is targeting missions successfully.
6. ISWE: This project is a good example of where a small amount of funding has ensured long term access into a vital part of UN Reform, which has the SG’s personal interest. Whilst other donors are interested in taking on the project, it has ensured the UK has a link into ISWE for the foreseeable future.
Key Lessons
1. Use of the RF as a Management Tool: Within the Terms of Reference (ToR), the RF is highlighted as the key document for M&E of the UN Reform Programme. However, the RF has not been used effectively in FY 19/20. The RF is only as good as the data within it, and this programme needs to dramatically improve the recording of results. If the RF template does not have the space to capture results, then the programme management need to place links within the RF to templates that do capture results e.g. DipTels, interviews transcriptions, meeting records. This will allow for the systematic capture and recording of information and results for analysis.
2. Senior Level Endorsement: Management Reform has been the most successful element of the UN Reform programme. This is not surprising given the importance the SG has placed on improving Fleet/Premises Management, HR processes, Data management, Senior Leadership governance and ISWE. It demonstrates that the success or failure of a project in the UN is highly dependent on senior level endorsement.
3. Virtual meetings: The geographical separation of the UN means that it is difficult for departments / agencies based in New York and Geneva to get together for seminars, workshops and other similar types of activities to share information and ideas. Due to the Covid pandemic, the UN switched to remote and digital working practices, which increased the use of virtual meetings at the end of FY 19/20 and demonstrated the value of taking business online. This is particularly notable when promoting research to key stakeholders, such as in the Integrating Conventional Arms Control and Conflict Prevention project, where the project lead secured better attendance from key stakeholders based in New York, who otherwise would not have travelled to Geneva. This enhanced awareness of the project.
4. Policy lead engagement: Throughout all the projects it is clear that a more engaged policy lead will ensure that the intangible UK support to UN reform is understood through greater communication of the UK’s contributions and the resulting project successes. Advocacy of projects would help to ensure they gain recognition within HMG and the UN. Key projects that would have benefitted from a stronger policy lead are the One HR project, the RCO Support project and the HDPP Facility project.
5. Programme team capacity: This programme requires strong management and a fully staffed team to ensure that the projects are able to demonstrate their value through accurate reporting. In FY 19/20, staff were taken away from programme management to support Brexit and then Covid-19 response. For PAI and VfM to be recognised on this complex programme, there needs to be strong management supported by a fully staffed team.
6. Communication between Implementers and Programme Team: It is essential that communication is strong between the programme team and the implementers. Implementers commented during AR interviews that they felt well supported by the programme management team. However, a more structured communication plan needs to be put in place to ensure the programme team are aware of the opportunities to amplify or link projects, as well as ensuring the right data is collected throughout the course of the year.
7. The significance of quarterly reviews: The programme should be conducting regular (quarterly) reviews. By doing so the programme management team can assess and analyse evidence to date, ensure indicators remain valid, review finances etc. This would ensure that preparation for next year’s Annual Review is better organised. The quarterly reviews along with a populated RF, will also help the team prepare for the programme annual review since much of the collation of evidence is already in place.

Summary of Recommendations for FY 20/21

1. UN Reform ToC and RF: The UN Reform ToC and RF must be reviewed and rewritten to ensure the indicators/milestones either more closely align to the 3 Pillars of UN Reform, or to link the project outputs to the programme outcomes.
2. Reform Pillar Stakeholder Board: The UN Reform programme would benefit from a ‘Reform Pillar Stakeholder Board’ held at a suitable time within the UN reporting calendar, which provides a forum for implementers, policy leads and programme management to discuss the progress of the projects within the context of the Pillar and allows stakeholders to identify complimentary projects across the MuSt Portfolio.
3. M&E tool for Political Access and Influence (PAI): The programme requires a mechanism for capturing PAI continuously over time, even if this is recorded through anecdotes and qualitative methods, such as Outcome Harvesting.
4. Interoperability in UN Reform and wider MuSt Programme Portfolio: All projects within both the UN Reform programme and the wider MuSt programme portfolio should be internally reviewed to find opportunities to link individual UK funded projects to amplify their effect in the wider Multilateral environment.
5. Virtual Communication Plan: Capitalising on the increased use of digital communication, a structured communication plan needs to be created to ensure the programme team, policy leads and implementers are consistently engaging, updating and identifying opportunities to progress projects.
6. Quarterly Reviews: Quarterly Reviews need to be completed. Evaluation, oversight and scrutiny of the programme needs to inform the programme management board, and inform the ToC assumptions, constraints and opportunities.
7. VfM Evaluation: The programme would benefit from a VfM evaluation, which would lead to a VfM framework. This would help to capture the ‘added value’ and positive effects that projects are acquiring and ensure more transparency to align the programme with financial requirements in use of the funding.
8. Policy Lead engagement: The role of policy leads should be determined, especially advocating for projects within New York, Geneva and London to ensure that opportunities are sought and the UK’s engagement is communicated to stakeholders. This needs to be communicated back to the UN Reform programme team.