Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	National Security Communications Team
Programme ID	C-NST-0001
Country and Region	United Kingdom (EMEA)
IATI Unique ID	N/A
HMG Partners / (Lead in bold)	Cabinet Office / Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £500,000	Non-ODA: £3,000,000
Budget this FY	ODA: £500,000	Non-ODA: £3,000,000
Spend this FY	ODA: £500,000	Non-ODA: £3,006,000
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs	Scale of Delivery
Countering State Threats (CST) - Evidence of output statements and indicators which contributed to associated outcomes being achieved	3
China - Evidence of output statements and indicators which contributed to associated outcomes being achieved	3
Diversity and Inclusion - Evidence of output statements and indicators which contributed to associated outcomes being achieved	3
Overall Scale of Output Delivery	3 - Did not fully meet all output milestones / targets.

Outcome Assessment:	NSCT routinely builds an evaluation and research insights component into its campaigns. These evaluation and research products demonstrated a short-term change of behaviour for target audiences for the following campaigns: China digital tech; counter state threats, SHARE Checklist, Diversity and inclusion and communications support to the publication of the Integrated Review. Looking forward, NSCT should track behaviour change in target audiences over a long period (e.g. commissioning evaluations 6-12 months after a campaign has ended) to demonstrate sustained impact.
Overall Outcome Progress Rating:		Green - fully on track to meet or exceed outcome targets / outcome targets already met.
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	-	-	-	-	-	C	C	Green	3
Risk Rating	-	-		-		Medium		Medium
Programme changes during this period		FY19/20 was the first year the NSCT Programme completed a formal Annual Review. In FY18/19, a rapid review was completed which did not have a mark associated with it. Recommendations from the FY19/20 annual review have sparked a complete refresh of NSCT’s Theory of Change for FY21/22.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY20/21?
Communication is a critical tool in delivering national security objectives. It can be a cost-effective way of: increasing UK influence; deterring adversaries; reassuring allies; shaping behaviours to for example improve resilience to security threats; bringing in new perspectives to national security policy-making; or shaping the context of our security activity. Rapid technological change and the diversification of the threat mean the Government cannot protect the UK without partners, in the UK and overseas, and communication is critical to making sure that those partners are aware of their role, and ultimately have the motivation, capability and opportunity to fulfil it.
The NSCT supports the CSSF objective to ‘support delivery of the National Security Strategy, using the full range of government capabilities and expertise in tackling conflict, instability and insecurity.’ Given the cross-cutting nature of strategic communications, NSCT’s work has links to all four of CSSF’s Fund Level Outcomes, with particular contributions to the State Threats outcome.

Key Results for FY 20/21:
- Integrated Review: To increase public engagement on national security, the NSCT team conducted a lessons learning exercise on activity around publication of the IR. NSCT provided the Board with a full evaluation of its communication support to the IR. Feedback from senior customers in No 10 and Cabinet Secretariat has been positive throughout, including around the Prime Minister’s statement on defence spending (November 2020). A Whitehall policy director noted that NSCT’ support to the IR is the “most comprehensive communications and engagement plan I’ve seen for a paper of this type”.
- China, DigiTech: China’s business environment and practices present UK Digital and Tech small and medium-sized enterprises (SME) with legal, commercial and ethical risks. The DigiTech campaign developed guidance to shift SMEs behaviour so that they mitigate the risks of engaging with China. Key results for FY2020/21:
- With over 7,000 site visitors, above average dwell times of 2 minutes and 18% return visitors, campaign outputs are performing above industry benchmarks. NSCT’s partnership achieved: 35,000 unique users’ vs a 30,000 benchmark.
- Website users reported improved understanding of the key legal, ethical and commercial risks of doing business with China. Website users also reported greater confidence in the prospect of doing business with China, and greater awareness of the sources of guidance available. Users have reported that they aim to take-up suggested security behaviours.
SHARE Checklist: Originally launched in 2019 to build audience resilience to disinformation by educating and empowering those who see, inadvertently share and are affected by false and misleading information, the campaign pivoted in 2020 to tackle the threat posed by false information about COVID-19. Key results from FY20/21:
- A fifth of all UK adults said they recognised the campaign. Campaign recognisers were confident in their ability (14% increase) to spot untrue stories appearing on social media than non-recognisers.
- Campaign recognisers (19% increase) were confident in their ability to spot fake social media profiles set up to deliberately distort or misrepresent news stories than non-recognisers.
Diversity and Inclusion: The Joint Intelligence Committee’s report[1] described the National Security Community as one of the least diverse and inclusive areas of the public sector. This highlighted a need to challenge perceptions, raise awareness and attract diversity of thought/talent. NSCT’s overall objective is to increase knowledge and awareness of national security among ethnic minority students aged 16-20 and positively shift their perceptions to encourage them to consider a career within national security. Key results for FY2020/21:
[1] January 2020
- Launched the National Security Race Strategy with external partners (Nov 2020). The event brought together over 120 attendees from 16 universities, 11 charities and 8 D&I organisations.
- Launched a Diversity and Inclusion website, which included 8 case studies of staff from diverse backgrounds, and associated social media adverts (Feb 2021). The website aims to increase awareness and positively shift perceptions that National Security is not a diverse or inclusive place of work. The site has 15,848 total views since launch.
- Initial findings show positive reactions and unprompted recall of the diversity of case studies in the ads, which helped alleviate concerns that the audience wouldn’t fit in within National Security because of their ethnicity, gender or personality type.

Key Lessons
- Mandate and resources. During the AR interviews, NSCT stakeholders consistently noted that there is a mismatch between NSCT’s level of resourcing and its broad mandate. Several interviewees noted that the team is not large enough to respond effectively to the range of priority areas that the team get drawn into. One policy customer noted: “I would be looking to increase the capability of the team, build the capability and promote the capability. In light of the Integrated Review, I would be asking whether the mandate is right and whether that should be revisited.” Indeed, a key lesson from this annual review is that most of the issues and challenges that were surfaced (e.g. too focused on short-term campaigns; stemmed from NSCT mandate and resourcing.
- Process improvement requires senior level buy-in. In the past, the NSCT team functioned primarily as a communications team rather than as a programme. This was reflected in the culture of the team, as well as its processes. Under the leadership of Mikey Hoare (Director) and Henry Collis (Deputy Director), the team’s culture and processes have been transformed. Over the review period, NSCT have made significant improvements to its risk management, monitoring and evaluation systems, and governance. These process improvements have helped to drive to a substantial step up in score (green, 3) for the 2020/21 annual review.
- Prioritisation of outcomes. In NSCT’s 2020/21 results framework, the team had eight outcomes. Outcome monitoring is extremely resource intensive and the team found it difficult to track all eight outcomes. Indeed, it is good practice to have two to four outcomes. NSCT team have learnt that fewer outcomes would help to strengthen their focused on evidencing sustained behaviour change in target audiences.
- Capturing and demonstrating policy coherence. During the AR interviews, policy customers from CO, DIT, BEIS and FCD noted that NSCT is uniquely placed to bring policy narratives together and drive a more coherent cross Whitehall policy response. However, in the past, NSCT have struggled to capture and communicate the impact of its policy coherence work. To move this forward, NSCT have learnt that they need (a) a results framework that articulates and monitors its policy coherence work; (b) to use qualitative monitoring approaches (e.g. outcome harvesting) that are suited to capturing hard-to-measure intangible outcomes.

Key Recommendations for FY 21/22
- Alignment to CSSF strategic review: NSCT’s strands of work on China and counter state threats are Integrated Review priority outcomes that align to CSSF’s increased focus on counter state threats and China. However, NSCT’s campaign work around Sexual Abuse, which isn’t a national security issue, is not aligned to the CSSF review and NSCT should seek other funding mechanisms to pay for this work. The diversity and inclusion campaign is focused on diversifying the national security community and provided valuable communications support to the publication of the IR. However, it is not clear whether the D&I campaign is a good fit for the CSSF and more conversations should be held between the NSCT board/leadership and the JFU on whether D&I should be funded by CSSF in the medium-to-long term.
- Programme mandate: to further resolve an enduring tension between planned, proactive projects and ad hoc tasking from senior stakeholders, consideration to be given to either; explicit recognition of NSCT as a national security communications trouble shooting function, with appropriate resources and sufficiently flexible KPIs or; Provide greater prescription to NSCT’s mandate in order to empower them to push back on tasking which does not align with agreed priorities.
- Monitoring and evaluation: when designing their M&E framework and commissioning an evaluation, the NSCT team should ensure that evaluators uses the right methodology to evidence progress against the indicator/target that is specific in the NSCT results framework. NSCT should track behaviour change in target audiences over a long period (e.g. commissioning evaluations 6-12 months after a campaign has ended) to demonstrate sustained impact.
- Working with Other Government Departments (OGD): streamline cooperation with OGDs through an engagement programme in order to build NSCT’s profile, whilst at the same time enhancing NSCT’s understanding of OGDs’ organisational culture and clearance processes.
- Value for money: to improve economy, NSCT should appoint suppliers for their own use where possible, to ensure suppliers are contracted at the right price and represent value for money. To improve efficiency, NSCT should continue to assess the cost-benefit ratio between inputs to outputs, drawing on suppliers’ expertise to identify feasible and relevant cost-benefit measures. To improve effectiveness, the team should organise commercial training to improve the commercial capability across the team.