Annual Review - Summary Sheet

Programme Title	Ascension Island Programme
Programme ID	C-OTS-0002
Country and Region	Ascension Island, South Atlantic, UK Overseas Territories
IATI Unique ID	CSSF-07-000006
HMG Partners / (Lead in bold)	Foreign Commonwealth and Development Office (FCDO)
Total Budget	ODA: -	Non-ODA: £5.00m
Budget this FY (20/21)	ODA: -	Non-ODA: £0.80m
Spend this FY (20/21)	ODA: -	Non-ODA: £0.78m
Time Frame	Start Date: March 2018	End Date: March 2021

Outputs	Scale of Delivery
1 Critical island infrastructure improved with risks to life and single points of failure to island operations reduced	4
1.2 Increased capacity and operational resilience on island	4
2.1 Long term recovery and maintenance strategy	3
Overall Scale of Output Delivery	4

Outcome Assessment	The programme has delivered key upgrades and investment to Ascension Island’s critical infrastructure and has supported the Ascension Island Government (AIG) in delivery and planning to address management of these assets in the long term. It also addressed several major risks to life and to key operations projects, despite delays and uncertainties. The funding available to meet the programme requirements was significantly reduced as part of a wider CSSF reprioritisation exercise to fund a COVID-19 response. For the programme to have maximum impact, long term planning and greater clarity on future funding and the outcome of the Future of Ascension Review is required. This remains a political decision, which the programme cannot address.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A		A	A	A	A	4	Green
Risk Rating				Medium		Medium		Medium
Programme changes during this period		-
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The programme provided funding for critical island infrastructure projects to reduce the risk of single points of failure and risk to life from existing infrastructure and equipment unfit for purpose. This built on the work completed in the two previous years of programming. UK support was split across six areas:

1. Sewage treatment work
2. Asset refurbishments
3. Asbestos removals and treatment
4. Hospital design study
5. Barge purchase
6. Fire Service report

All six areas fall into the category of infrastructure development, repair or remedial work, which are critical to operations on the island. Whilst these have all been successful, there remains an outstanding question as to whether the CSSF is the correct place to provide this funding, given the largely FCDO led nature of the programme.

Key Results for FY 20/21:
Excellent results were achieved across the six key areas in challenging circumstances: the remote location of Ascension Island and the pandemic. Each area required significant improvements, all scoped to be deliverable within year, noting logistical challenges.

Sewage treatment works
The consultant completed the project (a report and recommendations on the technical requirements for new replacement systems at two island locations) and produced a comprehensive report into Ascension requirements regarding new wastewater treatment facilities for Georgetown and Two Boats Village. The report has been accepted and the focus moved to CSSF 2021/22 bids for the replacement plants.

Asset refurbishments: electrical rewiring
All materials and works completed within timescales.

Asbestos removals and treatment
All works completed.

Hospital design study
Final design and cost report received and accepted. New hospital facility is estimated to cost in the region of £16.88m.

Barge purchase
Marine barge to support cargo logistics on Ascension received 1 February 2021 as planned. Final costs agreed and invoicing completed.

Fire Service report
Final report accepted and a service solution is now being worked on.

Key Lessons
- Logistics remain a challenge, including for materials or personnel to reach the island. Early planning and ordering are essential to ensure timely completion of projects.
- COVID-19 impacted the cost of some projects due to compulsory isolation time. Creative use of resources was achieved by electrical contractors being housed in properties they were able to work on during quarantine, reducing costs.

Key Recommendations for FY 21/22
Early announcement of budget allocations would enable timely planning of projects, including materials being ordered on time, and projects being delivered within the correct timescale.