Annual Review - Summary Sheet

Programme Title	British Virgin Islands Territory Programme (BVITP)
Programme ID	C-OTS-0003
Country and Region	British Virgin Islands (BVI), UK Overseas Territories (OTs)
IATI Unique ID	CSSF-07-000007
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office, Government of the Virgin Islands (GOVI), Virgin Islands Recovery and Development Agency (RDA)
Total Budget	ODA: -	Non-ODA: £10.00m
Budget this FY	ODA: -	Non-ODA: £1.77m
Spend this FY	ODA: -	Non-ODA: £1.67m
Time Frame	Start Date: April 2018	End Date: March 2022

Outputs	Scale of Delivery
Operational funding to the RDA contributes to the recovery of the BVI.	4
Security and justice infrastructure improves territory’s law enforcement capabilities.	3
Territorial Search and Rescue Team (TSART) has staff trained to Emergency Management Accreditation Program (EMAP) standard and the equipment necessary to conduct safe and effective large-scale search and rescue operations.	2
Enhanced capacity, processes and technology promote transparent and organised public service.	4
Overall Scale of Output Delivery	3

Outcome Assessment	The BVITP has made progress following a re-setting of the programme earlier in the year. However, new projects that started within FY20/21 required substantial revision of the original outcome indicators and targets. This should be seen against a performance period of unprecedented challenges and several external factors which hampered the delivery of activities. The primary challenge was the COVID-19 pandemic and the impact it had on travel (especially for incoming technical assistance), training (lockdowns, social distancing) and shifts in priority functions for key partner/beneficiary groups. The programme was flexible enough to increase security capability in a very short period.
Overall Outcome Progress Rating:		Amber/Red
Overall Risk Rating:		Medium-high

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	-	-	-	B	B	B	B	3	Amber/Red
Risk Rating	-	-		Medium/High		Medium/High		Medium/High
Programme changes during this period		The programme spent the year flexing and adapting to the shifts in the political environment as well the unprecedented challenges presented by the COVID-19 pandemic. The UK closed operational support for the RDA and shifted focus to projects which linked directly to the Governor’s constitutional responsibilities.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- Financial support to the RDA for operational costs and to deliver specific projects, disaster preparedness, security and justice infrastructure, and public sector reform.
- Technical assistance and capacity building in public services.
- Equipment and training for the Territorial Search and Rescue Team.
- Support to the Royal Virgin Islands Police Force main police station infrastructure, Marine Unit perimeter, and repairs to Marine Unit fleet.

Key Results for FY 20/21:
- Financial support to the RDA for operational costs resulted in effective delivery of 35 projects with 6% funded through fundraising efforts. Capacity building strategy approval resulted in 10 competitive internships and tender processes resulting in 90% locally awarded contracts. Four reports produced to monitor finances and programme framework indicators.
- Provision of secure perimeter for the Marine Base and Road Town Police Station and the refurbishment of administration offices.
- Comprehensive package of documents and systems completed to facilitate a 3-5 year roll out of the Public Sector Transformation Programme (PSTP) across the public service.
- Disaster response capability enhanced through delivery of key land and water search and rescue equipment and medical training.

Key Lessons
- Rehabilitation and recovery projects need higher contingencies to account for unexpected global and local challenges as well as emerging technical challenges.
- Approaches to ensure sustainable programme impact should be negotiated with the partner government in the early stages of activity identification and embedded in project design.

Key Recommendations for FY 21/22
- Explore opportunities to leverage funding in order to protect UK investment to date and “Build BVI Stronger: Smarter, Greener and Better“.
- The programme should transition this support to an internal, experienced project manager to consolidate gains and coordinate activities under the Public Sector Transformation Programme across the public service.
- The programme should encourage GOVI to recruit an experienced Programme Manager as a priority, to spearhead a change management unit in a central authority, to consolidate gains and coordinate activities under the PSTP across the public service.
- To ensure sustainability of activities, encourage the Government of the Virgin Islands to revamp the Department of Disaster Management (DDM) training programme in line with funding and availability of equipment. The purpose would be to create a professional development programme that accounts for staff turnover and deployment schedules.
- The Results Framework (RF) should continue to be revised to improve consistency and make outcomes, outputs and milestones more clearly linked and measurable. It should also reflect the new realities of funding, governance, post-COVID priorities and a revised reporting template.