Annual Review - Summary Sheet

Programme Title	Overseas Territories Border Security Programme
Programme ID	C-OTS-0005
Country and Region	UK Overseas Territories (OTs)
IATI Unique ID	CSSF-07-000013
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office, Home Office and Ministry of Defence
Total Budget	ODA: £0.19m	Non-ODA: £0.32m
Budget this FY	ODA: £0.19m	Non-ODA: £0.32m
Spend this FY	ODA: £0.21m	Non-ODA: £0.25m
Time Frame	Start Date: April 2020	End Date: March 2021

Outputs	Scale of Delivery
1. Identification of critical infrastructure, skills to identify gaps and vulnerabilities, and risk mitigation in cyber security in St Helena, Turks and Caicos Islands and Cayman Islands	2
2. Establish policies and guidance in St Helena to support border control and immigration with local staff trained and a plan in place for the sustainability of training.	2
3. The holistic and sustainable strengthening of the Turks & Caicos Islands’ approach to border security, with a specific focus on the key threat presented by irregular migration.	2
4. Build the capability of marine units in the five Caribbean OTs and Bermuda and Customs and Immigration departments (five Caribbean OTs, Bermuda, Falkland Islands and St Helena) towards internationally recognised standards of delivery.	2
5. Identification of current maritime capability and required development in the five Caribbean OTs and Bermuda.	2
6. Progress towards standardisation of training, tactics and procedures in the maritime domain across the Caribbean region – five Caribbean OTs and Bermuda.	2
Overall Scale of Output Delivery	2

Outcome Assessment	Given the scale of output delivery, there has clearly been progress against outcomes. However, as required by the guidance, in the absence of targets the level of outcome progress must be assessed as RED – Urgent action required. In this case the RED assessment relates to the recommendation to put targets in place rather than an assessment of the performance of the programme.
Overall Outcome Progress Rating:		RED
Overall Risk Rating:		Not possible to assess

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A		B		B		2	Red
Risk Rating	Medium	Medium		Medium		Medium		N/A
Programme changes during this period		In 2020, the Justice, Security and Governance Programme was split into individual programmes including a separate Border Security Programme.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- Border Force secondees provided to St Helena and Turks & Caicos Islands (TCI).
- Border Force personnel deployed to TCI from Jamaica to conduct a Customs review in support of the Border Transformation Plan.
- Subject matter expertise, and Royal Yachting Association Training and Accreditation provided to the Bermuda Coast Guard Academy.
- Cyber subject matter expertise provided for needs assessments.

Key Results for FY 20/21:
- Increased cooperation between Bermuda and British Virgin Islands on border security issues affecting both territories.
- Delivery of draft Asylum and Immigration policy in St Helena.
- Delivery of an immigration control strategy for TCI.
- Significant unplanned support to TCI on uncontrolled migration driven by COVID-19.
Cyber risk reviews conducted in St Helena and TCI.

Key Lessons
- Setting outcome and output targets is much more difficult without a clear strategic vision for border security in the Overseas Territories, approved by the three UK Government Departments involved.
- Clear targets and reporting in the same format as the results framework are important to allow adequate assessment of the programme and its successes.
- The programme team has shown significant adaptability in the face of competing stakeholder priorities, COVID-19 impacts and operational imperatives. This adaptability and responsiveness should be maintained and the next Annual Review, whilst ensuring targets are in place, should allow significant latitude for targets to be adapted in response to unforeseen changes.
- Beneficiaries are clear that valuable support has been delivered in the face of considerable challenges.
- MOD financial systems are unwieldy in the CSSF context. This is not unique to this programme.

Key Recommendations for FY 21/22
- Develop a long-term policy vision for the level of border management capability needed in the Overseas Territories, the current baselines, and the specific departmental responsibilities for delivering the vision. In the absence of such a vision the programme needs to make explicit assumptions on these questions.
- Consider developing a theory of change that places a greater focus on the evidence and assumptions on which the link between outputs and outcomes is based.
- Put in place a completed results framework with targets and baselines.
- Ensure quarterly reporting maps to the results framework.
- In some OTs, consider introducing programming on professional standards as well as technical and operational skills, in order to reduce the risk of corruption and improve sustainability.