Annual Review - Summary Sheet

Programme Title	Overseas Territories COVID-19 Programme
Programme ID	C-OTS-0006
Country and Region	UK Overseas Territories (OTs) / UK OTs supported by this programme: Anguilla; Bermuda; British Virgin Islands (BVI); Cayman Islands; Falkland Islands; Gibraltar; Montserrat; Pitcairn Islands, St Helena, Ascension and Tristan da Cunha; Turks and Caicos Islands (TCI)
IATI Unique ID	CSSF-07-000012
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), / Department of Health and Social Care (DHSC), Ministry of Defence (MoD), OT Governors, Public Health England (PHE)
Total Budget	ODA: N/A	Non-ODA: N/A	Total: N/A
Budget this FY (20/21)	ODA: £2.13m	Non-ODA: £13.00m	Total: £15.13m
Spend this FY (20/21)	ODA: £1.88m	Non-ODA: £11.85m	Total: £13.73m
Time Frame	Start Date: March 2020	End Date: March 2022

Outputs	Scale of Delivery
1.1 PPE and public health expertise enable effective disease control to limit the effects and outbreak of COVID-19	4
1.2 Inhabited OTs can test for COVID-19 on island to enable effective public health measures	3
1.3 Healthcare operations and infrastructure have the resilience to cope with increased demand due to COVID-19	3
2.1 Security deployments and continued border security operations provide a deterrent effect and resilience to reduce the risk of uncontrolled COVID-19 spread and civil unrest	3
3.1 Financial and logistical support enables territories to function	4
Overall Scale of Output Delivery	3

Outcome Assessment	The COVID-19 Programme was created urgently to address the threats posed by an unprecedented global COVID-19 pandemic. The programme was established rapidly at a time when many factors were unknown including the severity and length of the pandemic. Whilst at times the programme may have been more reactive than proactive, it overcame significant challenges to ensure the UK’s OTs, spread across the globe and in some remote locations, were supplied with healthcare, security and financial support. / Despite the novel challenge of implementing a multi-OT response to a global pandemic, the programme addressed logistical challenges e.g. global supply chain issues and border closures. Whilst some OTs were financially and geographically better placed to deal with the pandemic, even these were assisted by the programme to address weaknesses and address gaps in knowledge and skills.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A		N/A		N/A		3	Green
Risk Rating	N/A	N/A		N/A		N/A		Medium-Low
Programme changes during this period		Budget changes. Transition from emergency PPE supply to vaccination programme.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- PPE (all OTs)
- Expert medical advice: weekly PHE-OT calls and access to telemedicine service (all OTs)
- COVID-19 testing equipment & training (8 OTs) and test kits (all OTs)
- Medical equipment (9 OTs)
- Healthcare staff (4 OTs)
- COVID-19 vaccinations (9 OTs)
- Support for border and internal security, including military deployments (3 OTs)
- Fiduciary Risk Analysis (1 OT)
- Repatriation flights (2 OTs)

Key Results for FY 20/21:
- Overcoming global and logistical challenges to supply all OTs with PPE, equipment and testing capabilities, and most OTs with vaccines.
- Support provided to the OTs through the provision of expert medical advice.
- The impact of COVID-19 was mitigated by providing tailored support to those OTs with additional financial, security and staffing capacity needs.

Key Lessons

1. Healthcare Support
- Important to establish OTs’ resource and capability needs (e.g. PPE and testing requirements) early on and test these with independent expertise (PHE).
- Value of deploying (senior) PHE personnel to OTs to provide essential public health and technical support (e.g. testing laboratories) where OTs have capacity challenges.
- COVID-19 has acted as a catalyst for the existing CSSF-funded PHE-delivered programme to improve healthcare laboratories in OTs.
- OTs need to be included in UK regulatory approvals of vaccines early on to avoid the need to change regulations later.
- There are numerous logistical issues to consider for transportation of vaccines to OTs.
- There is value in sharing experience on vaccine roll-out between OTs in the early stages, particularly where take-up is low.

2. Security Support
Security deployments of military and police support to OTs enhanced internal capability and border security resources.

3. Financial Support
Anguilla’s public finances were heavily impacted by the loss of tourism due to COVID-19 lockdowns. Programme support to the territory’s healthcare system and border security helped mitigate the impacts on services from COVID-19.

4. Programme Management
A full-time programme manager would benefit updating of programme documentation.
A faster invoicing system with MoD would support more accurate budget forecasting.

Key Recommendations for FY 21/22
- Programme team to review and update key programme documentation and ensure progress against milestones and indicators is regularly recorded in the programme’s Results Framework.
- Programme team to consider how a review of the overall healthcare capability of each OT could be undertaken to determine what is needed (immediately and in the longer term) to build up OTs’ resilience to pandemics and healthcare system risks of commensurate scale. Recommend option(s) for undertaking such reviews to Overseas Territories Directorate (FCDO).
- Programme team to work with OT governments to review the procurement lessons gained from the COVID-19 experience to support preparedness for future pandemics.
- Programme team to ensure it has a consolidated record of the resources provided to the OTs by the programme (resource type and numbers provided to each OT).