Annual Review - Summary Sheet

Programme Title	Overseas Territories Governance Programme
Programme ID	C-OTS-0008
DAC Code	15130 (DAC)
Country and Region	Anguilla, Bermuda, British Virgin Islands, Cayman Islands, Falkland Islands, Gibraltar, Montserrat, St Helena, Turks & Caicos Islands, Ascension Island, Tristan da Cunha, Pitcairn Islands, British Sovereign Territories
IATI Unique ID	CSSF-07-000010
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), / Public Health England (PHE), / Commonwealth Parliamentary Association (CPA UK), / National Audit Office & Government Internal Audit Agency, / Maritime Coastguard Agency (MCA).
Total Budget	ODA: £0.65m	Non-ODA: £3.53m
Budget this FY	ODA: £0.65m	Non-ODA: £3.53m
Spend this FY	ODA: £0.62m	Non-ODA: £3.12m
Time Frame	Start Date: April 2020	End Date: March 2021

Outputs	Scale of Delivery
Processes and polices are implemented by public institutions in order to prevent harm to vulnerable groups in OTs.	2
Legislative frameworks are modernised in line with international standards, implemented and followed by public sector institutions.	1
OT networks are established and actively sharing knowledge and expertise.	2
Key figures in OT public institutions are trained and qualified to carry out core governance functions effectively.	2
Overall Scale of Output Delivery	2

Outcome Assessment	Whilst there has been progress against the outcome indicators, the OTs and the programme have been required to focus on the COVID-19 response. This has meant an acceleration of some areas (e.g. public health) and more limited progress on others (e.g. improving legislative oversight); and in some instances, resources have been re-deployed to the COVID-19 response at short notice.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance*
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	N/A	N/A	2	Amber
Risk Rating	N/A	N/A		N/A		N/A		Medium
Programme changes during this period		N/A
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

* Prior to 2020, the Governance programme was a component part of the Justice, Security and Governance Programme.

What Support Did the UK Provide in FY 20/21?
The programme provided technical assistance and capacity building support in five thematic areas.
- Child safeguarding: improving effectiveness of child safeguarding practices, to amplify the voice of children in decision making, policy and law.
- Beneficial ownership: supporting the inhabited OTs to introduce publicly accessible beneficial ownership registers (PARBOs) by the end of 2023, in line with the amendment to the 2018 UK Sanction and Money Laundering Act.
- Maritime governance: supporting a stabilised and continuous approach to marine activities in territorial waters and building resilience and sustainable capacity and capability.
- Public health: increased compliance with International Health Regulations, to improve health security in the OTs, the UK and globally.
- Public financial management: supporting good governance in the OTs through legislative and scrutiny capacity building, elections support and bolstering the oversight of public finances by enabling Public Account Committees (PACs), Supreme Audit Institutions (SAIs) and Internal Audit Institutions (IAIs) to deliver their functions effectively.

Key Results for FY 20/21:
- Child safeguarding: i) Partnerships in place between social services departments from UK local authorities and their equivalents in St Helena and Anguilla, with partnerships in place for other OTs. ii) Positive behaviour management training for parents and educators in the Eastern Caribbean to change social norms away from corporal punishment of children.
- Beneficial ownership: i) A Company Registry was completed in Anguilla. ii) FCDO has worked with Open Ownership, an external partner, to provide guidance documents to all OTs on developing publicly accessible beneficial ownership registers and engage with three OTs on the specific challenges in those territories.
- Maritime governance: Provision of co-funding for a BVI Search and Rescue vessel which enabled the Virgin Islands Search and Rescue organisation to improve their facilities on Virgin Gorda.
- Public health: i) Biomolecular testing facilities (PCR platforms) put in place in multiple OTs for COVID-19. A separate COVID-19 programme funded hardware.
- Public financial management: virtual election observation missions completed in Turks and Caicos Islands and the Cayman Islands.

Key Lessons
- Child safeguarding: Practice partnerships are an effective (and cost effective) mechanism for supporting and building capacity of OTs on safeguarding, but the sustainability of partnerships needs to be considered.
- Beneficial ownership: There are significant political challenges surrounding the implementation of publicly accessible beneficial ownership registers by 2023, and the programme needs to carefully navigate these sensitivities.
- Maritime governance: the programme should sustain preparation for the International Maritime Organisation’s Audit and incentivise OTs to comply with the audit in future years.
- Public health: the programme should use the increased momentum on public health to build broad capability on healthcare, including setting medium-term objectives for the International Health Regulations (IHR) and FCTC.
- Public financial management: future programming should cover the broad range of democratic practices and processes, including civil society engagement and media freedom. Policy leads may wish to consider non-financial levers for improving democratic governance in OTs that would sit alongside this programme.

Key Recommendations for FY 21/22
- The logic behind the Theory of Change should be strengthened to ensure activities, outputs and outcomes are coherent. The new Business Case for the upcoming Spending Review should help to improve programme coherence and enable long-term thinking on impact.
- A Monitoring, Evaluation and Learning expert should be engaged to help with the revision of the Results Framework.