Annual Review - Summary Sheet

Programme Title	Overseas Territories Justice Programme
Programme ID	(DAC) 15131
Country and Region	UK Overseas Territories (OTs)
IATI Unique ID	CSSF-07-000009
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), / Ministry of Justice (MoJ)
Total Budget	ODA: £0.72m	Non-ODA: £1.95m
Budget this FY	ODA: £0.72m	Non-ODA: £1.95m
Spend this FY	ODA: £0.76m	Non-ODA: £1.91m
Time Frame	Start Date: April 2020	End Date: March 2021

Outputs	Scale of Delivery
Increased OTs’ understanding of barriers to achieving international standards in the justice system.	3
Increased understanding and expertise within OTs on rehabilitation and policing by consent.	3
Police and prison officers across the OTs are trained to UK standards including understanding of professional standards.	2
Roadmap agreed between the OTs and UK on standards improvement including creation of formal standards and their implementation.	4
Priority risks to security and rule of law are mitigated through infrastructure and capability building.	3
Overall Scale of Output Delivery	3

Outcome Assessment	Whilst there has been progress against all the outcome indicators, this is within the context of a low base in law enforcement and prison standards. The programme may need to intensify its efforts on meeting outcomes on human rights compliance and pooling of operational assets if outcomes are to be realised in the next two to three years. COVID-19 restrictions and the redirection of programme resources to urgent operational work has limited the programme’s potential to deliver impact in 20/21.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A		B		B		3	Amber
Risk Rating	Medium	Medium		Medium		Medium		Medium-Low
Programme changes during this period		In 2020 the Justice, Security and Governance (JSG) Programme was split into individual programmes including a separate Justice Programme. The above scores reflect that change. There was also substantial unplanned activity over the review period relating to operational law enforcement responses.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The intended impact of the Overseas Territories Justice Programme is for the OTs to have ‘effective, human rights-compliant criminal justice systems that gain increased public confidence through implementation of an agreed roadmap to meet shared minimum standards, creating a safe justice system that reduces reoffending’.

This programme falls into two components, a ‘justice’ component implemented through the Ministry of Justice (working on courts, prisons) and a law enforcement component working on OTs policing, administered by a Law Enforcement Adviser managed through FCDO, but liaising with UK police for support on substantive issues. The programme undertakes a wide range of activities working with law enforcement agencies, judges, prosecutors and courts, prisons and probation services, to encourage human rights-compliant justice processes that reduce harm to victims and enhance rehabilitation and a reduction in crime.

Combining both ODA and non-ODA elements (only Montserrat and St Helena are ODA-eligible), law enforcement work is the larger programme component, spending £1.86m as compared to the prisons component of £0.81m.

Key Results for FY 20/21:
- Transformation of the Turks & Caicos Islands prison environment, through a combination of intensive prison officer training, some infrastructure improvements, liaison with law enforcement officials, and close monitoring with the MoJ.
- Construction of the St Helena police custody suite to budget and accompanying custody training to address previously raised human rights concerns.
- Deployment of investigators: (i) to assess the allegations of criminal conduct associated with the collapse of British Virgin Island Airways; and (ii) to Montserrat to support local police in dealing with serious and complex fraud casework.

Key Lessons
- MoJ will reconsider the length of future deployments to mitigate the risk of over-dependence on deployed personnel
- MoJ will consider a range of options for deployments to the OTs to ensure delivery stays on track.
- The effectiveness of visits by UK prison experts is dependent on good cooperation and buy-in from the local OT’s prison Superintendent and/or senior leadership team, including unrestricted access to the prison.
- Balancing urgent OTs’ operational needs/demands from UK Governors against the longer-term objectives of the programme will require further consideration.

Key Recommendations for FY 21/22
- Revise the results framework, for example tightening milestones/targets and disaggregating data by gender.
- Assign a dedicated Monitoring, Evaluation and Learning resource to the programme, and ensure structured data collection including through enhanced local OTs data collection capability.
- Recognise that this programme fits within a long-term approach to building justice sector capability. Therefore, develop indicators that track progress over the long-term.
- Distinguish between i) capabilities that can be sustainably developed within OTs; and ii) specialist expertise likely to be drawn from the UK; and develop a more efficient and appropriate UK offer.
- Ensure strong local political support for prison reforms and clear plans for improvement.
- Risks: ensure Value for Money is monitored systematically, including how changes in the local political landscape may impede delivery.