Annual Review - Summary Sheet

Programme Title	Overseas Territories Environmental Sustainability and Climate Change (ESCC) Programme
Programme ID	OTD Environmental Sustainability and Climate Change
Country and Region	UK Overseas Territories (OTs)
IATI Unique ID	CSSF-07-000011
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), / Department for the Environment, Food and Rural Affairs (DEFRA), / Department for Transport (DfT), / Ministry of Defence (MoD)
Total Budget	ODA: £1.05m	Non-ODA: £2.50m
Budget this FY	ODA: £1.05m	Non-ODA: £2.50m
Spend this FY	ODA: £0.59m	Non-ODA £3.13m
Time Frame	Start Date: April 2020	End Date: March 2021

Outputs	Scale of Delivery
Assessment of oil spill response capability through reviews, priority needs identified, and procurement of assets and training made available to address recommendations ahead of III Code audit.	3
Seabed mapping data collected to support Safety of Navigation (SoN), an increase in the capacity of OTs to provide Maritime Safety Information (MSI). Increase in access to seabed mapping data by OT governments to support activities on climate change resilience, sustainable environmental management and economic diversification.	3
Increasing biosecurity capability of all OTs through comprehensive biosecurity strategies enabling them to take preventative actions, including support for Gough Island restoration.	3
Create a Blue Belt of marine protection around the Overseas Territories.	4
Overall Scale of Output Delivery	3

Outcome Assessment	The new ESCC programme replaced the Maritime Governance and Environment (MGE) programme (which finished in 2019/20) in addressing critical needs in environmental sustainability. These include promoting sustainable environmental policies, coherent management of marine pollution and pollution response activities, continued seabed mapping operations and tackling invasive species. / The overall aim of the programme is to protect the prosperity and people of the OTs by greater sustainable development and management and preservation of their unique natural environments. / COVID-19 meant interventions were much reduced as funding was transferred to supporting the OTs in a new COVID-19 programme. Nevertheless, good progress was made across the different programme components, especially in the second half of the financial year. However, such progress will necessarily take time, for example several of the components have revealed the scale of the gaps in local capacity, as well as the fact that local capabilities are at different levels of development and require greater uniformity and local government funding.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	N/A	N/A	3	Amber
Risk Rating					Medium-High
Programme changes during this period		Initial programme allocation reduced due to funding for COVID-19 funding. In-year funding provided to COP26-specific projects.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- Development of OTs’ capabilities in managing pollution incidents, including through the purchase of basic response equipment and development of oil spill contingency plans in all OTs.
- Continued work on hydrography studies and plans, introduction of the seabed mapping data portal designed to improve data collection and accessibility, and upgrading of tidal level measuring gauges in Turks & Caicos Islands.
- Improved management of storm surges and floods through development of models of the Cayman Islands, which identify key areas at risk from climate related natural disasters.
- Continued delivery of vital biosecurity technical assistance.
- Support and technical advice to OT governments to maintain and enforce marine protection areas.
- British Virgin Islands (BVI) – installation of solar panelling on public buildings and monitoring and treatment of Stony Coral Tissue Loss Disease on BVI’s coral reefs.
- Mice eradication on Gough Island (dependency of Tristan da Cunha).

Key Results for FY 20/21:
- Maintaining engagement and momentum of seabed mapping work despite COVID-19 limiting activities led by UK Hydrographic Office. New ways of working and the use of available technology enabled engagement.
- The Invasive Non-Native Species (INSS) project provided contingency advice, management plans, technical support and draft legislation to improve the OTs’ capacity to deal with the threats posed by non-native invasive species.
- OTs’ capabilities in managing pollution incidents improved, including through the purchase of equipment to manage a small, localised incident and development of oil spill response plans.
- Marine protection and sustainable management measures in place for over four million square kilometres of the OTs' waters, underpinned by suitable legislation.

Key Lessons
- The small biosecurity capacity in the OTs, though improving, will require continued access to the wealth of expertise from the UK going forward.
- COVID-19 travel restrictions enabled delivery partners to take on additional important work including the Maritime & Coastguard Agency’s preparation for the International Maritime Organisation Instruments Implementation Code audit in autumn 2021.

Key Recommendations for FY 21/22
- Consideration should be given to a more sustainable funding model for seabed mapping and improving biosecurity capacity in the OTs, including through the provision of long-term support from relevant UK Government department baselines as part of their shared responsibility to the OTs.
- There is scope to improve collaboration between delivery partners on data collection to avoid duplication, increase value for money and prevent over-stretching limited capacity within the OTs.
- In terms of improving pollution control in the OTs, further work is needed on improving local understanding of the importance of Port Waste Reception Facilities (PWRF) and the environmental and economic risks of dumping at sea.
- Results Framework should be reviewed to ensure outputs have clear target dates and measurable milestones and outputs/outcome indicators support monitoring of gender and inclusion impacts.