Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Afghanistan Peace and Reconciliation Programme
Programme ID	C-SAA-0008
Country and Region	Afghanistan, South Asia
IATI Unique ID	CSSF-02-000006
HMG Partners / (Lead in bold)	FCDO
Total Budget	ODA: £4,500,000	Non-ODA: £0
Budget this FY	ODA: £4,500,000 / (original allocation, later reduced to £3,382,000)	Non-ODA: £0
Spend this FY	ODA: £2,302,991	Non-ODA: £0
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2023

Outputs	Scale of Delivery
Strand 1
Prepared and representative Afghan Government team	4
Coordinated messaging to support a peace process	3
Negotiating parties have clear and well understood positions	3
Provision of expert technical input to inform negotiations	4
Strand 2
Women and civil society are able to share their views on peace and involved and visible in community peacebuilding decisions	2
Local-level conflict drivers are understood, informing activity	4
Overall Scale of Output Delivery	3

Outcome Assessment	This programme is built on the premise of intra-Afghan peace negotiations having a reasonable prospect of proceeding. The programme plays a (very) minor role in shaping the environment for this; due to other factors the programme is unable to have significant direct influence. Determining whether the programme can realistically expect to see the desired changes at the outcome level by the end of the programme (2023) will depend on the politics around peace negotiations. In addition, three of the six outcome indicators have no specified target. A realistic outcome assessment is therefore not possible.
Overall Outcome Progress Rating:		N/A
Overall Risk Rating:		HIGH

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	n/a	n/a	n/a	n/a	n/a	n/a	n/a	3	N/A
Risk Rating	n/a	n/a		n/a		n/a		HIGH
Programme changes during this period		This was the first year of the programme. A total of £631,292 in funding was approved for projects which did not proceed to implementation due to heightened operating difficulty. The total programme allocation was also reduced in year, from £4,500,000 to £3,382,000.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

A total of £2,255,898 in funding – a combination of administration, staff costs, grants and direct support of HMG secondments – was provided in FY20/21. Excluding staff costs (£35,060), the following support was provided:

- Under Strand 1 of the programme (‘Credible and inclusive negotiations between the Afghan Government the Taliban start and sustain’):
  - £671,809 to the European Institute of Peace to support the Afghan republic in conducting a high-quality, inclusive peace process.
  - £74,389 to InterMediate to support intra-Afghan negotiations to advance a just, sustainable and gender-sensitive political settlement.
  - £8,493 to support the Afghan Peace Negotiations secretariat, including short term secondments of HMG staff and an SU expert

- Under Strand 2 of the programme (‘Strengthened and inclusive peacebuilding and reconciliation mechanisms’):
  - £1,002,262 to BBC Media Action to support radio, television and online discussions on democracy and other issues of national importance in Afghanistan.
  - £309,982 to Cordaid for creating sustained, meaningful and informed participation of women in the Afghan peace process.
  - £100,687 to Norwegian Church Aid to support religious actors in contributing to inclusive, just, and sustainable peace in Afghanistan by influencing the peace process with civil society perspectives and promoting social cohesion and trust-building at all levels.
  - £42,374 to the Afghanistan Analysts Network for development of case studies on security, institutions and diplomacy
  - £10,843 to the Stabilisation Unit for a study on women’s involvement in peace processes

Key Results for FY 20/21:

A contribution towards more coherent functioning of the Afghan peace architecture.

A contribution towards improved trust – at times – between negotiating parties.

Key Lessons

Implementing Partners noted:
Project effectiveness and efficiency could be improved through greater flexibility in budgets and activity plans.

More could be done to manage GIRoA expectations. Implementing Partners (IPs) need to engage early with key counterparts to align expectations.

Delays in project approval impact on project effectiveness. With 12 month CSSF funding cycles, delays in approval lead to a concentration of activity at the back-end of the year, which increases delivery pressure on IPs and consequent risk.

Key Recommendations for FY 21/22

Pause all existing ‘Strand 2’ programming.

Advocate for (or develop) a coordination strategy for all external technical support provided to the Afghan peace architecture.

Increase programme management capacity.

Refresh the Risk Register, Theory of Change and Results Framework.