Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Afghanistan Security and Assistance Programme (ASAP).
Programme ID	C-SAA-0009
Country and Region	Afghanistan
IATI Unique ID	CSSF-09-000006
HMG Partners / (Lead in bold)	Foreign Commonwealth and Development Office (FCDO), Ministry of Defence (MOD), British Council (BC)
Total Budget	ODA: £50.016m (Approved by Ministers Sept 20 – first years funding only)	Non-ODA: £6.6m
Budget this FY	ODA: £50.016m	Non-ODA: £6.6m
Spend this FY	ODA: £49.5m	Non-ODA: £6.65m
Time Frame	Start Date: September 2020	End Date: approved until March 2023

Outputs	Scale of Delivery
International community approaches to Security Sector Reform are increasingly harmonised ​	3
Improved leadership skills among alumni in positions of leadership in Afghan Security Institutions​	4
Improved internal structures and systems (e.g. payroll) and willingness to support key reforms within MoIA	3
A more representative, motivated and Human Rights compliant Afghan National Police ​	3
The Afghan National Army and Afghan National Police are better equipped and have strengthened operational capability​	2
Overall Scale of Output Delivery	3

Outcome Assessment	The programme has delivered slightly below the outcome aims, as set out in the Results Framework (RF). Though the reporting period is short and there are some aspects of the outcomes which have delivered well. The wider narrative of delivery, including more qualitative and anecdotal evidence, captured through the PAI (Political Access and Influence) framework generate a more positive picture. / Overall contribution to security sector reform has been achieved, with a number of milestones being met, however a continuation of the programme would be required to ensure these changes became enduring. This review has reflected on progress during the period Aug 2020 – Mar 2021, however delivery cannot be viewed without taking in to consideration the overwhelming impact of drawdown uncertainty, impending security and political changes and COVID restrictions. With slow deterioration in security, reduced activity within Afghan peace negotiations and the potential for the Taliban to try and seize the Afghan state by force, all change implemented by the programme, will be tested. With the expected US and NATO Resolute Support Mission (RSM) withdrawal (confirmed April 21), likely reduction in platform and resourcing, engagement and capabilities, many of the outputs and outcomes of this programme will become harder to implement and measure. / Future development of the Assisting Security in Afghanistan Programme will need to consider the feasibility of delivery and outcomes, as well as how best to ensure continued value for money of UK financial contribution. Impact of remote delivery and reduced in country footprint will need to be understood in terms of monitoring and evaluation, if the programme is to continue output delivery and retrieve data to measure success.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

	Summary of Programme Performance
Year		Legacy	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating			N/A		N/A		N/A		N/A	B	B
Risk Rating			N/A	N/A		N/A		N/A		M-H
	Programme changes during this period			Technical Assistance Mission (TAM) work strand – In Nov 20, nine objectives were translated in to nine project initiation documents. These nine projects were contested by NATO Ministerial Advisory Group-Interior (MAG-I) lead, General Murchison (M2), owing to competing and misunderstood leadership and direction of TAM resource more generally. Jan 21, M2 chose to reduce the objectives from nine to three and for TAM to be retrograded from April 21. These changes are still to be authorised by the Programme SRO or CSSF Board. As such, a degree of contingency planning was undertaken to determine how the objecives could be achieved using less resource and from a new location. While options and recommendations were reviewed in the February and March 21 Boards, changes have still yet to be agreed and new planning formally recorded.
	Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The Assisting Security in Afghanistan Programme (ASAP) programme brings together five previously separate CSSF (Conflict, Stability and Security Fund) work-strands, managed by the British Embassy Kabul (BEK) Pol-Mil and CSSF programme teams, with the overall objective to provide greater strategic coherence to delivery and outcomes. The five legacy work strands include; The Afghan National Defence and Security Forces (ANDSF) Professionalisation Programme, The Security Sector and Peacebuilding Support Programme (Law and Order Trust Fund Afghanistan (LOTFA) and TAM projects only), The UK Contributions to Afghan National Army trust Fund (ANATF) programme and Strategic Communications - (the fifth work strand on Strategic Communications was officially paused over the reporting period).

In summary, the following support was provided:

The ANDSF Professionalisation strand seeks to sustain support for a cadre of capable, professional military and civilian leaders in the Afghan Security Sector through UK-based training opportunities, short duration deployments of UK trainers/experts to Afghanistan, and support to English Language Training at the Afghan National Army Officer Academy (ANAOA), Kabul Military High School (KMHS) and female officers at the National Military Academy Afghanistan (NMAA).

- UK-based training programmes delivered at the Royal Military Academy Sandhurst (RMAS), the Royal College of Defence Studies (RCDS), and the UK Defence Academy (Advanced and Intermediate Command and Staff Courses - ACSC and ICSC(L) and the Defence Centre for Language and Culture (DCLC).
- Short Term Training in Kabul (“Capstone” Course), delivered by the UK Defence Academy, comprising Senior Leadership Programme (SLP) and Building Integrity for Senior Leaders (BISL). Aimed at Col/1* level, as a springboard to advance selected officers. Four days for each course (split between SLP and BISL with the same students) delivered twice a year, in November 2019 and February-March 2020.
- English Language Training at the Afghanistan National Army Officer Academy (ANAOA), the Kabul Military High School (KMHS) and the National Military Academy (NMAA) delivered by the British Council.

The UK Contributions to ANAFT strand seeks to contribute to a number of non-kinetic projects to sustain ANDSF such as;

- Funding gender-related programming including a female police town and female barracks.
- Improvements to the defensive capabilities of the Afghan National Army (ANA) and the Afghan National Police (ANP) through increased force protection for Kabul and ANA garrisons throughout Afghanistan.
- Building of hospitals for the treatment of injured ANA and ANP personnel.
- Counter-improvised explosive device (C-IED) training and equipment, conducted both overseas and in Kabul.
- Development of an intelligence system called the National Information Management System (NIMS) which provides the Government of Afghanistan the ability to consolidate, analyse and share human intelligence.
- Renewal of a CCTV system in the Enhanced Security Zone of Kabul.

The two Security Sector and Peacebuilding Support strands carried over to ASAP included;

1. The Law and Order Trust Fund Afghanistan (LOTFA) sees an annual payment of up to £70 million (up to £280m 2016-2020) to the ANDSF, delivered through the Trust Fund, LOTFA. The FY 20/21 commitment is up to £70m (previous years commitments; £35m in 2017/18, £11.25m in 18/19, and increased to £27m in 2019/20).
2. The Technical Assistance Mission (TAM) places UK Police and Subject Matter Experts (SME) Secondees into a number of teams within NATO Resolute Support (RS) Mission (RSM), in support of the development of expertise and civilianisation in the Afghan Ministry of Interior (MoIA). (£4m over 4 years).

All strands of work brought together within ASAP align with the UK’s National Security Council (NSC) Afghanistan Strategy in relation to supporting a viable Afghan state, specifically Objective 2.1: Develop and sustain the capability for the Afghan state to fight insurgency; manage security and counter violent extremism, with reduced reliance on international support.

Key Results for FY 20/21:

ANDSF Professionalisation strand;
- 15 Afghans graduated from a number of UK courses – Royal College of Defence Studies; Advanced Command and Staff Course; Intermediate Command and Staff Course (Land); Royal Military Academy Sandhurst Officer Commissioning course; Defence Human Security Advisers’ Course; International Intelligence Directors’ Course.
- 2 Capstone Courses delivered to 39 senior officers.
- English Language Training: nearly 1,000 students were trained in three ANAOA Kandaks (battalions), with an average pass rate of over 90%, 110 students at KMHS and up to 50 students at NMAA.
- Alumni from UK courses continued to be placed in key positions within the security ministries, empowering these key organisations whilst also maintaining the UK’s strategic influence and continuing access.

Many of the Afghans who undertake UK-based training are placed in key, often senior, positions within their departments and are keen to apply what has been learned to positively impact the security situation in Afghanistan.

UK Contributions to ANATF strand;
- UK funded infrastructure has improved efficiency and effectiveness of security operations.
- Over 2700 female police recruited.
- Design completed for the Kabul National Military Hospital.
- Over 1200 people trained on C-IED skills.
- 36% progress of construction of women’s police facilities.
- Enhanced NIMS system with over 6500 active accounts (exceeding plans) and generating over 280k reports from provinces.
- 994 Electronic Counter Measure (ECM) systems delivered plus training on system usage for 58 people.
- 15% completion of the Kabul CCTV system.
- Coordinated approach by NATO allies to supporting reform, building NATO cohesion.

Sustainability largely rests on the availability of ongoing funding, though in some cases, such as supply of ECM systems, work has already begun to develop local capacity which may increase sustainability. In other areas, such as construction of facilities, the sustainability will depend both on the ongoing usage and upkeep of this by the Afghan government.

Security Sector and Peace Building Support strand;
- (LOTFA) Successfully provided contributions to LOTFA for the payment of ANP and General Directorate for Prisons and Detention Centres (GDPDC) salaries.
- (LOTFA) HMG successfully took on the role as LOTFA Lead Donor and Co-Chair of the International Policing Coordination Board (IPCB), which has enhanced donor coordination on policing reform and increased UK influence with international and Afghan partners.
- (LOTFA) Increased MoIA capacity to independently manage all non-fiduciary aspects of its payroll and pushed for independent assessments to better understand the Ministry’s ability to take on this function.
- (TAM) Successfully funded and coordinated the delivery of expert police advisory support to the NATO RSM Train Advise Assist (TAA) building capacity and capabilities within the MoIA. This has also supported UK national security objectives in Counter-Serious and Organised Crime (C-SOC) and Counter Terrorism (CT) through improved coordination between UK and Afghan stakeholders on these issues.
- (TAM) Significantly improved its ability to Monitor and Evaluate, most significantly in the delivery of the police secondee element. The development of the PAI Framework has allowed for a more thorough assessment of progress, which can be sustained in the next iteration of the programme.

Sustainability for LOTFA rests on the availability of ongoing international funding. While funding is expected to be maintained close to current levels throughout at least 2021, there is a possibility that changes to the political and security landscape could significantly impact future donor confidence, as well as monitoring and oversight.

Police advisory sustainability will likely be dependent on the provision of an outside-in delivery mechanism or a follow-on multilateral advisory mission (civilian), in addition to permissive security environment and host government. The sustainability of TAMs results will also be dependent on staff turnover in the MoIA, succeeding any change in state leadership and whether staff mentored by the secondees remain and are able to continue implementing the systems and skills imparted to them.

Key Lessons

The realities and specifics of delivery continue to need to be honestly factored into programme delivery, with regular reviews, so that project outputs and delivery can be adjusted accordingly. When discussing the strands of activity within this programme, many contributors noted; high changeover of personnel, matrix management and uncertainty over RSM drawdown/contingency plans, having impacted continuity, led to tension between stakeholders and created a reduction in momentum.

The current biggest challenges to delivery stem from the increasingly deteriorating security situation, reduced oversight, reduced in-country resource (both UK-Based and Country-Based Staff), and the political risk of a future Taliban/dominated government.

The binding constraint of the political commitment to spending up £70m per annum, combined with the inherent challenges to delivering projects and programmes in Afghanistan, COVID and the downward turn in security trajectory, mean it has been a challenge to assess value for money of the UK funds invested.

Success will often be determined by the extent of Afghan buy-in, to any particular line of activity. UK Ministerial direction is to focus on UK national interests, but this is best delivered where there are synergies in UK and Afghan goals.

The process of influencing is key to much of what the UK can achieve, both as a means and end in itself, and as a support to other specific results. This continues to need to be better understood, captured and programmed for future programming. The Programme and CSSF Afghanistan teams have developed the PAI framework with specialist Monitoring and Evaluation (M&E) advisors, which should the political and security situation allow, will enable UK influence to be maximised in both respects.

Within the TAM work strand more specifically, there has been a need for a more joined up approach between key stakeholders across; strategy, deliverables and reporting chains. Police Secondees, funded by British Embassy Kabul (BEK), have played an important role in delivering programme outputs, but were embedded within NATO RSM teams. This created a duel reporting hierarchy, where the Secondees needed to engage regularly with BEK so that evidence could be gathered in line with CSSF M&E requirements, but also reported to their respective NATO RSM chains of command. This at times lead to confusion of effort and ASAP programme M&E, as well as morale of resources assigned, suffered as a result. Improved engagement between BEK, the Police Secondees and NATO RSM leads in the Ministerial Advisory Group-Interior (MAG-I) team has helped, but should be closely monitored, especially if future prospects for delivery involve further matrix management through outside-in mechanisms, as the clarity of the civilian footprint remains uncertain. At the heart of this challenge was a mis-understanding that secondees were NATO resource and could be tasked accordingly. It will be important to ensure that leading stakeholders are aligned in their understanding of resourcing and delivery, to prevent day-to-day operational delivery being hindered, by tasking at cross purposes. UK leadership of MAG-I have subsequently supported improvements, including a joined up strategic review, with follow-up check-in reviews planned, and helped design the results framework to better capture shared objectives. Momentum of these mitigations however has been to some degree lost as a result of drawdown implications and contingency delivery methods needing to be enacted.

Key Recommendations for FY 21/22

Future programme development should continue to be underpinned by flexibility and work to identify what is still achieveable, in a likely inherently different political and physical environment. Taking in to consideration continued ministerial steer to support the ANDSF, future programme development should work to record changes and descoping made to the programme, so that future reporting fairly reflects feasible delivery beyond RSM drawdown. In particular the wider political and physical security context in Afghanistan will significantly impact oversight of delivery such as through LOTFA and ANATF trust funds. When submitting for ministerial approval, the challenges to oversight of the funds should be clearly outlined.

As it is likely that some delivery will be executed remotely, this will reinforce the need for clear understanding and control of resources and tasking. Delivery which involves matrix management of resources should be carefully defined at the start in terms of tasking, approach to delivery and reporting. Any agreed embedding of resources in teams outside of UK government in particular, should have clear terms of reference agreed from the start and any additional requirements from a host department should also be captured, formally agreed and planned for.

- Qualitative evidence should be strengthened. All four strands of work delivered qualitative outcomes which were harder to identify and measure. While quantitative evaluation does act as a considerable indicator of achievement, longer term and less tangible qualitative assessment of outcomes has been harder to obtain. Strengthening the qualitative evidence further (beyond that of previous recommendations) could become more systematic and realistic in terms of timescales. Should programme delivery continue in its current form and content, options for achieving this could be undertaken as follows;
  - A light touch “Outcome Case Study”, such as that undertaken within TAM, once every two quarters.
  - A more detailed annual “PAI (Political Access and Influence) Study” could seek to identify influence beyond the individuals trained by, for example, looking at UK government stakeholder engagement with key organisations. Planning should take in to consideration what can realistically be achieved during each quarter, so as not to set ambition too high.
None of these options (or indeed a combination of them) would require a significant investment in time or resources by the programme team, but as a first step capacity, requirements and priorities would need to be agreed with the Monitoring, Evaluation and Learning (MEL) partner, in consultation with the BEK Strategic Board.