 Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Sri Lanka CSSF: Delivering increased stability and reducing the risk of a return to conflict
Programme ID	C-SAA-0010
Country and Region	Sri Lanka, South Asia
IATI Unique ID	CSSF-09-000003
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) and Ministry of Defence (MoD)
Total Budget	ODA: £10.05m	Non-ODA: £700,000
Budget this FY	ODA: £3,199,678	Non-ODA: £150,000
Spend this FY	ODA: £3,165,645	Non-ODA: £61,443
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Scale of Delivery
UK is able to support democratic institutions to take steps to modernise and become more inclusive and accountable, supported by diplomatic, technical and financial investments / [Actors: Parliament, Police, MoD & Judiciary]	3
UK is able to promote social cohesion and support civil society to respond to drivers of conflict supported by diplomatic, technical and financial investments / [Actors: UN JPP, Civil Society]	3
UK takes steps to resolve the legacy of the previous conflict supported by diplomatic, technical and financial investments / [Actors: reconciliation institutions – OMP, ONHRC; victims of conflict]	4
UK is able to tackle gender barriers, drivers of conflict supported by diplomatic, technical and financial investments / [Actors: police, parliament, civil society, Sri Lankan women and victims of SGBV]	3
Overall Scale of Output Delivery	3

Outcome Assessment	The Conflict, Stability and Security Fund (CSSF) programme in FY 20/21 has adjusted well to significant change in the local operating environment, principally linked to the COVID 19 (C19) pandemic and the political context in Sri Lanka (SL). As expected therefore, the ability of the programme to effectively deliver all of its intended outcomes in FY 20/21 has been challenged, although the portfolio remains largely functional and intact. Indeed, despite the pausing of some CSSF activities in FY 20/21, some notable CSSF successes and tangible results have been achieved this year. Hence the CSSF portfolio remains operational which is testament to the resilience of project design, partner engagement and the dedication of CSSF staff alike. Not surprisingly, since most CSSF areas of focus have been, to some degree, negatively impacted by the C19 pandemic, certain programme outputs have been rendered unachievable during this review period. The overall performance outcome score reflects that the programme is on track but there are understandable doubts as to whether the portfolio’s outcome targets for FY 20/21 can be fully met. Nonetheless, it is clear that the Sri Lanka CSSF programme has weathered significant change in FY 20/21 and, by demonstrating flexibility, creativity and adaptive management, has delivered good progress during a uniquely challenging year.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	B	A	B	A	A	3	Amber
Risk Rating	M	M		M		M		Medium-High
Programme changes during this period		Anti-Bribery and Corruption (ABC) project terminated. Activities pivoted to respond to COVID-19, including tackling sexual and gender based violence (SGBV) which was exacerbated during COVID-19, and tackling COVID-19 disinformation which targets minorities.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The CSSF programme in Sri Lanka is designed to support reconciliation and strengthen democracy and the rule of law to ensure long-term stability. During FY20/21 the Programme adapted to major changes to the context, namely the changing political landscape in Sri Lanka and the COVID-19 pandemic. Support was provided in the following areas:
- Peacebuilding: support to the UN Joint Programme for Peace (JPP), including the government’s commitment to Sustainable Development Goal 16 (on peace, justice and strong institutions) and sustainable resettlement of Internally Displaced Persons (IDPs).
- Demining: clearing high density mine contaminated land and delivering mine risk education in the North and East enabling the resettlement of IDPs.
- Parliamentary strengthening: support to parliament on integrating gender and promoting engagement with civil society.
- Policing: support to promote gender equality within the Sri Lankan Police force (SLP), and strengthening approaches to tackle gender-based violence
- Defence: targeted, capacity building, professional military education and high level dialogue in order to foster greater awareness of the importance of human rights and gender, through professionalisation and modernisation.
- Anti-corruption: sharing UK expertise to strengthen government capability to tackle bribery and corruption.
- COVID-19 response: CSSF support for stakeholders to pivot to online delivery and direct assistance, including provision of hygiene kits, C19 awareness raising materials and greater safeguarding services to deal with Domestic Violence/Sexual and Gender Based Violence (DV/SGBV) including through support to civil society.

The majority of this work is Overseas Development Assistance (ODA) eligible under the Organisation for Economic Co-operation and Development (OECD) Development Assistance Committee's (DAC) revised directive on peace.

Key Results for FY 20/21:

- Overall: Despite considerable challenges and constraints to effective programme delivery, the British High Commission (BHC) CSSF portfolio demonstrated sufficient resilience and agility to remain almost fully operational throughout FY20/21.
- CSSF Demining destroyed 5,759 explosive items, making a significant contribution to the Government of Sri Lanka’s (GoSL) aim of achieving national mine free status in the coming years.  This benefitted 9,055 people directly and a further 46,092 people indirectly with access to land and livelihood opportunities.
- The UN Joint Programme for Peace (JPP) supported the publication of a list of missing persons from the Sri Lankan war by the Office of Missing Persons and coordinated provision of mental health and psychosocial support (MHPSS).
- The Policing project increased empowerment of Community-Based Organisations (CBOs) to address domestic violence (DV) and Sexual and Gender based Violence (SGBV) at community level through GoSL Women and Children’s Desks, schools, religious organisations and social service referral networks.
- Defence Engagement remotely delivered the ‘Managing Defence in the Wider Security Context’ (MDWSC) training course to 38 staff and students of the Sri Lankan Armed Forces (SLAF) National Defence College, with a focus on International Humanitarian Law (IHL), human rights and accountability.
- The Anti-Bribery and Corruption (ABC) project produced a Manual of Operations for the GoSL Legal Drafting Department, implementing a key policy priority. This project also supported the GoSL to re-establish the court recordership system to help reduce the judicial case backlog.

Key Lessons:

The CSSF FY 20/21 Annual Review covers a period of significant change within the operating environment in Sri Lanka most notably linked to effects of the C19 pandemic and national elections. Nonetheless, the BHC programme team, and to a large extent its implementing partners, have demonstrated significant resilience and a strong willingness to learn and adapt throughout this reporting period which has been characterised by a number of largely unforeseen challenges to addressing conflict, stability and reconciliation in the country.

However, there is strong evidence of meaningful engagement by the BHC both internally and with partners to monitor and reassess approaches considering the dynamic context of operating in Sri Lanka during FY 20/21. Indeed, the CSSF portfolio has adapted well to ensure its continued relevance and effectiveness. To this end, the AR Team would like to mention the dedication of the BHC CSSF Team in ensuring that the programme remained largely operational during a year of significant challenge.

Therefore, the overall lesson from FY 20/21 is that the CSSF programme has had sufficient resilience and flexibility to endure considerable stresses and yet remain largely intact.
Although some areas of the CSSF portfolio were paused in FY 20/21 due to risk issues, future analyses and research may allow a resumption of those activities, demonstrating the adaptive ability of CSSF programme design. Other interruptions have largely been due to the constraints of operating under Sri Lanka’s robust C19 lockdown protocols, which have been mitigated wherever possible.

The AR Team are confident that the Sri Lanka CSSF portfolio is fully capable of adapting further should new challenges in the operating environment emerge in FY 21/22 and that it will consolidate its core aims and activities into the upcoming CSSF programme cycle of FY 22/25.

Key Recommendations for FY 21/22:

The AR Team are confident that the Sri Lanka CSSF portfolio is fully capable of adapting further should new challenges in the operating environment emerge in FY 21/22. And that it will consolidate its core aims and activities into the upcoming CSSF programme cycle, expected to commence with the new financial year.

- Design for future programming should consider the breadth of programming against any fragility introduced by having a broader portfolio of activities.
- With a dynamic context, the programme should ensure it dedicates time and resources to analysing, understanding and evaluating the evidence base.
- Design for future programming should consider scope of programme building in an approach that allows for adaptive programming.
- Noting dynamic context, CSSF programme should consider drafting a monitoring evaluation and learning plan and scaling up monitoring, evaluation, and learning efforts to reflect this.
- Noting challenges for partners operating in Sri Lanka due to COVID-19, the programme should continue to assess the effectiveness of remote delivery, including considering opportunities to address gaps in IT capacity and knowledge of key stakeholders.
- Project-level priorities suggested by this review should be considered within programming approach for CSSF programme expected for upcoming financial year.