Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Consolidating Democracy in Pakistan (CDIP)
Programme ID	C-SAA-0011
Country and Region	Pakistan, South Asia
IATI Unique ID	CSSF-08-000001
HMG Partners (Lead in bold)	The Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £35.5 million	Non-ODA: £0
Total Spend	ODA: £35.5 million	Non-ODA: £0
Time Frame	Start Date: July 2016	End Date: March 2021

Outputs	Scale of Delivery (FY20-21)
1: Election management and election oversight processes are more credible, transparent and inclusive – Not active in FY20-21	N/A
2: Increased capacity of parliamentary institutions and parliamentarians to perform their roles and to hold the government to account during crises such as Covid-19 and beyond	4
3: Political parties across the mainstream political spectrum better represent, respond to and deliver for their constituents. Political parties have increased capacity for inclusive and grassroot policymaking, including in response to Covid-19	4
4: Capacity and capability of citizens, Civil Society Organisations (CSO), media and HR institutions and women access to social safety programmes enhanced to engage effectively in democratic process and public discourse	3
Final Overall Scale of Output Delivery	4

Outcome Assessment	The outcome of the programme was to contribute to a democratic system in which government institutions are capable, parliament is more accountable, and the state as a whole is more responsive to the needs and aspirations of the Pakistani people. The programme has met 6 of 10 outcome milestone targets set in the logframe. In its last year of implementation, it demonstrated it was able to pivot quickly to address the immediate impact of Covid-19, supporting Pakistani representative institutions to respond to the crisis. It did so in a highly complex and at times politically charged environment, showing adaptability and flexibility. The review team found that it was less successful, however, in identifying and targeting the drivers of limited accountability and responsiveness towards citizens.
Final Overall Scale of Outcome Achievement:		3
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	NA	A	NA	A	B	A	B
Risk Rating	Medium	Medium		Medium		Medium		Medium-Low
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
The Consolidating Democracy in Pakistan programme provided £33.5 million from 2016 to 2021. The programme invested in activities aimed at increasing the capacity, accountability and responsiveness of democratic institutions. From 2016-2020 the programme was delivered through a commercial contract, with local NGOs: the Trust for Democratic Education and Accountability (TDEA) with the Pakistan Institute of Legislative Development and Transparency (PILDAT) as a subgrantee; and a Memorandum of Understanding (MoU) with UNDP, with Democracy Reporting International (DRI) as subgrantee. For 2020-2021 implementation shifted to accountable grants with DRI, TDEA, PILDAT and an extension of the MoU with UNDP.

In its first four years, the programme provided targeted support to the Election Commission of Pakistan (ECP) to manage elections in a more transparent, efficient and inclusive manner. It targeted the oversight function of the Senate, National Assembly (NA) and Provincial Assemblies, and it set out to help parties be more inclusive and accountable to their constituents.[1] With CSOs and the media, it promoted more and broader participation in electoral processes, advocated for electoral reforms and improved public confidence in the civilian leadership. The programme had a cross-cutting emphasis on increasing participation of women, young people, minorities, and people with disabilities in democratic processes.
[1] Engagement with parties included briefing papers, dialogues and consultations. Interventions ahead of the 2018 General Election focused on briefings on the Elections Act 2017 and design of policy wings/research on the status of inclusion within parties. A cross-party Women in Politics Support Group (WPSG) and Young Politicians Fellowship Programme (WPFP) were initiated after the election. During the final year the programme supported political parties’ work on grassroots policy forums.

In March 2020 the programme was granted a one-year cost extension (£2 million). Following external and mission-wide internal consultations, key programme activities, outputs and outcomes were pivoted to respond to Covid-19 for September to March 2021. As a result, this review will report against progress made on the updated logframe indicators and on the last year of CDIP. Whenever possible, however, it will refer to the wider CDIP programme, particularly in relation to programme focus and strategies.

What Results Did the Programme Deliver? Will they be Sustained?
- Supported the Election Commission of Pakistan to conduct the 2018 general elections, contributing to 53% voter turnout and 40% (registered) women turnout[2];
  [2] The EU election observation report acknowledges proactive measures taken by the ECP to improve its openness, capacity, transparency and accountability. PILDAT reported that, compared to 2013, the 2018 elections demonstrated improvement in polling staff competency, conduct and management, facilitating citizens in polling stations and maintaining impartiality.
- 21 publicly articulated positions and parliamentary actions on issues of public health, social protection, education and interprovincial coordination[3]. This demonstrated the significance of the role of parliamentary scrutiny but it is unclear whether this will be sustained.
  [3] This includes letters or parliamentary questions raised by parliamentarians on issues relevant for the Covid-19 response, from the procurement and distribution of vaccines to education and learning losses and internet connectivity issues.
- 8 political parties used evidence from CDIP policy briefs and grassroots policy forums to inform Covid-19 policies. The initiative has shown the benefits of a more consultative and inclusive model but it is unclear whether it will be picked up by parties going forward.
- 47m people reached through social, print and electronic media campaign on the importance of free media for democratic, transparent, and inclusive governance.
- Brought together media, CSOs and politicians on journalists’ safety, working with the Pakistan Federal Union of Journalists (PFUJ). Led to a draft common position and plan to present a Bill at the NA.
- Guidelines on business continuity for the Senate, national and provincial assemblies. Whether this will improve functioning in emergencies will depend on whether recommendations are taken up.
- 2 million new Computerised National Identity Cards (CNIC) for women through a registration campaign in 55 marginalised and low-income districts. In partnership with ECP and the National Database and Registration Authority (NADRA). This will allow newly registered women to access government programmes to mitigate economic hardship brought on by the ongoing pandemic.
- Six governance monitoring reports released monthly focused on Covid-19 healthcare response based on district-level information collected across 35 districts by civil society monitors.
- Ministry of Human Rights (MoHR) supported to operationalise human rights indicators and develop an annex of emergency-sensitive indicators for its Human Rights Information Management System used for ongoing tracking.

What Lessons Have Been Learnt?
In a hybrid system like Pakistan it is critical to support representative institutions, which remain fragile. These have a critical role to play to fend off an interventionist military, keep a strong executive in check and meaningfully fulfil their representative function. Future programmes should focus on targeting the drivers behind low accountability and responsiveness to constituents, including with activities that have a greater focus on shifting incentives and institutionalising innovations. Underpinning democratic transitions is the imperative of meeting expectations of fairness and delivering tangible benefits that materially improve the lives of people.
- Whilst political economy analyses have been conducted and trends monitored, these have mainly focussed on day-to-day developments. In future, this should include an analysis of root causes of weak accountability, insufficient evidence-based policymaking, etc. and formulation of associated recommendations.
- System and institutional reforms are a long-term and iterative process that may not be appropriate for CSSF as a funding mechanism (short term, high risk and catalytic programming). It may make sense to consider including aspects of accountability programming under the broader FCDO development portfolio.
- The programme evaluation should have started earlier to make an evidence-based assessment of programme’s contributions toward outcomes and impact but was hampered by Covid-19.
- For the overall programme, the coordination amongst implementation partners and donor has been effective but was less strong during the Covid-19 repivot, primarily due to the short time frame of the project.
- Relying on local partners or partners with extensive experience in Pakistan has been critical in allowing partners to build on existing relationships and achieve results in a short period of time. Working with local organisations or organisations with extensive reach and experience in Pakistan has allowed the programme to make headway on key politically sensitive areas.
- Covid pivot including a much tighter requirement to fit with cross-mission priorities leading to significant reduction of scale and scope of the programme in its final year. This had a positive side-effect of leading to more focused programming from partners. It also offered higher potential for synergies, although the team was not fully able to take advantage of this opportunity due to staff workload limitations.
- The programme needed to invest more in developing SMART indicators and ensuring a clear distinction between outputs and outcomes to support assessment against milestones.