Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Maldives Support to promotion of Jazeera Dhiriulhun Programme
Programme ID	C-SAA-0012
Country and Region	Maldives, South Asia
IATI Unique ID	CSSF-09-000005
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) and Ministry of Defence (MoD)
Total Budget	ODA: £3.2m	Non-ODA: : £0.082m
Budget this FY	ODA: £783,212	Non-ODA: £ 32,000
Spend this FY	ODA: £795,383	Non-ODA: £ 31,586
Time Frame	Start Date: January 2019	End Date: March 2022

Outputs	Scale of Delivery
1. Support for strengthening governance structures to deliver services more effectively, increasingly through local governance structures, with greater accountability and transparency, underpinned by improved capacity for government communications, legislative branch oversight, independent media and media regulators.	4
2. Support to capability of Deaths and Disappearance Commmission (DDCom) to bring swift closure to high profile cases of disappearances and deaths, and support to Government of Maldives (GoM) for strengthened (more modern, resilient, professional, and integrated) security and justice sector, more capable of meeting needs of community, countering violent extremism, and delivering effective, accountable, and transparent justice for all.	4
3. Support to design an evidence-based approach to establishing a mechanism for Community-driven Development investment (e.g., in community-level infrastructure and capacity building to increase economic opportunity and community services as part of decentralisation and Preventing Violent Extremism policies).	NA
4. CSSF programme contributes to British High Commission (BHC) political access and influencing in support of progress in governance, security and justice and community development.	4
Overall Scale of Output Delivery	4

Outcome Assessment	This is a well-conceived, designed and managed programme and is closely aligned to GoM Strategic Action Plan and delivers on HMG’s Country Business Plan. Its interventions support initiatives that are central to GoM’s plans to stabilise democratic institutions and restore public trust in the rule of law. There is evidence that some of the intended change has happened or is starting to happen, such as the drafting of new legislation on family law, improved performance of parliamentary committees and the creation of a Maldives Independent Policing Board. The level of risk is moderate and the potential gains for both Maldives and UK citizens are high relative to the cost. While the pandemic has affected delivery in some areas, the programme has adapted and remains on track. It therefore represents excellent value for money.
Overall Outcome Progress Rating:		Green (Fully on track to meet or exceed outcome targets)
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a		2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	-		-	-	-	-	B	A	4	G
Risk Rating	-		-		-		Medium		Medium
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating
Programme changes during this period		A fourfold increase in funding and an extended delivery period were agreed, allowing for greater ambition. Significant time was invested in strengthening the evidence base through a Joint Assessment of Conflict and Stability (JACS) and, subsequently, the theory of change and the results framework. Increased funding mid-year allowed a short term scale up of assistance, including the provision of IT equipment to allow magistrate courts to hear cases online. The pandemic necessitated adaptation, such as the moving of training activity to online delivery, or of technical assistance to remote working. New programmes and implementing partners were brought online, including the International Federation of Journalists, and stakeholder networks within the Maldivian system and the donor community were strengthened.

What Support Did the UK Provide in FY 20/21?
The programme provided £783,212 of ODA and £32,000 of non-ODA to the Maldives to support Maldivian government reforms outlined in the National Action Plan of 2018. £167,000 was devoted to governance reforms, including support to improve the performance of parliamentary committees; institutional support to strengthen the Maldives Journalists’ Association; and training to local government to increase the skills of officials and elected representatives in developing decentralised, island-level development plans and budgets. £524,000 supported security and justice: to increase the accountability of the Judiciary and the Maldives Police Service, for example through performance management, investigations of complaints, and the establishment of publicly accountable policing board and a Women in Policing Network; to support the standardisation of law school training; to support the drafting of new legislation on family law, providing new protections for women and children; and to enable a female officer of the Maldives Defence Force to attend a three month training course at Sandhurst (facilitated by MOD). Implementing partners included the Westminster Foundation for Democracy, United Nations Development Programme (UNDP) and the International Federation of Journalists.

Key Results for FY 20/21:
Programme activities have contributed to the following achievements of Maldivian partners, where the UK implementing partner was the primary provider of technical assistance:
- Parliamentary committees are operating in a more consistent and effective way. During the period, committees began inquiries around social and economic issues, including a ventilator procurement related corruption scandal; and work-place accidents at the national harbour.
- Following completion of a Family Law review, a Family Law bill has been drafted and is expected to be submitted to the Parliament by the end of this year. The review and drafting were completed with technical assistance from UNDP, as part of the overall support to the government’s legislative agenda in partnership with the Attorney General’s Office.
- Police reform: The establishment of an independent policing board, enshrined in legislation, with the role of scrutinising police service. Seven board members were appointed and inducted into their roles at the end of Q4. One of the first tasks it has commissioned is an integrity review of senior police officers.

Key Lessons
- Institutional strengthening activity is more a process, than an activity. This requires sufficient time for the process to unfold and develop with local stakeholders to ensure a strong result.
- Utilizing existing human resources within the stakeholder network is a stronger strategy than open recruitment for new staff, particularly when the project period is extremely short.
- When Parliament is busy, officials can be more difficult to reach, requiring the scheduling of meetings training sessions well in advance and with alternative (reserve) meeting dates/times.
- Having an SC-cleared Stabilisation Unit (DCE) advisor working over an extended time period with BHC provided essential technical assistance to the team, while passing on knowledge and building capacity through mentorship.

Key Recommendations for FY 21/22
- Work with the regional monitoring and evaluation partner to develop a detailed monitoring, evaluation, research and learning (MERL) plan for the remaining years of the programme.
- Devote more time to engaging directly with Maldivian partners to provide additional information for monitoring purposes and strengthen relationships.
- Strengthen the risk register to increase its utility as a management tool, referring to examples of good practice from elsewhere in the CSSF network.