Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Countering Extremism (CE) Programme
Programme ID	C-SAA-0015
Country and Region	Pakistan, South Asia
IATI Unique ID	N/A
HMG Partners (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £5.23m	Non-ODA: £0
Total Spend	ODA: £ 4.489m	Non-ODA: £0
Time Frame	Start Date:1 April 2017	End Date: 31 March 2021

Outputs	Weighting 2017-20	Weighting 2020‑21	Scale of Delivery (2020-21)
1. Reduced flow of extremist people, money and ideology between Pakistan and the UK	10%	5%	4
2. Enhanced capabilities of selected public sector institutions of Government of Pakistan (GoP) to counter extremism in Pakistan	50%	20%	2
3. Political will in Pakistan promoted to counter extremism	15%	10%	3
4. CE research and reporting products delivered, and cross HMG coordination on CE enhanced	25%	20%	4
5. Covid-19 Response supporting strategic communications	0%	45%	4
Final Overall Scale of Output Delivery	100%	100%	3

Outcome Assessment	The Countering Extremism (CE) programme can be assessed as having contributed successfully to 1) increased action against threats to the UK, but has made only more limited traction towards 2) increasing capacity and resilience to extremism in Pakistan. / Over its life time the programme has had some significant successes at the output level, making significant contributions to public service messaging in counter-extremism and contributing to counter extremism research. However, it has not consistently been able to translate those steps into sustained outcome level achievements. During FY 20/21, the programme pivoted to undertake strategic communications support in combatting Covid-19, where it played a major part supporting the Government of Pakistan’s response.
Final Overall Scale of Outcome Achievement:		3
Overall Risk Rating:		High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	A	A	A	A	A	A	3	3
Risk Rating	High	High		High		High		High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
The CSSF Counter Extremism (CE) 2017-2020 programme was developed to reduce extremist threats to the UK and support Pakistan political will to counter extremism. The programme was designed to build on the political will to counter extremism generated through CSSF funded work in 2016/17 in the form of a government partnership on research, analysis and strategic communications. The CE Programme sought to build on these successes through a range of cross-departmental activities, notably strategic communications directly with the GoP and later contributing to GoP’s efforts on registering all the religious seminaries in country through supporting UNDP’s project on madaris reforms.  It also included elements focused on tackling extremism with direct links to the UK with a large element on conducting CE research. The programme generated a volume of research documents examining the extremist landscape of Pakistan that were used to better understand the extremist threat and target responses. The programme was extended in 2020 for a further year to March 2021 as part of the whole CSSF Pakistan portfolio. The programme was extended in 2020 for a further year to March 2021 to allow an evaluation of the UK’s support to the Pakistan Peace Collective (PPC) a UK sole funded strategic communications led by the Pakistan Ministry of Information and Broadcasting (MoIB) and to assess its sustainability. Whilst the evaluation and engagement over sustainability of the PPC was the primary focus of the extension of the programme, the programme’s strategic communications role proved a vital capability in supporting Covid-19 strategic communications to the people of Pakistan.

What Results Did the Programme Deliver?
- Helped reduce the flow of extremists to the UK informing the UK security processes to better target disruptions of travellers and migrants with known extremist ideology. Dissemination of Programme CE research was utilised by Her Majesty's Government (HMG) departments to better target threats to the UK, and continues to be used for UK security. Development of a referrals system is a major sustainable part of this output.
- Delivered comprehensive research products – used to inform the Pakistan National Counter Terrorism Authority’s (NACTA) National Counter Extremism Policy guidelines that form the basis for ongoing CE discussions. This research is sustainable and has continued to be utilised both by the GoP and UK departments.
- Supported the development of the Safer Giving Legislation through the collaboration of the PPC and Pakistan authorities to reduce funding to extremist organisations which continues to help degrade extremist capability. This legislation remains an enduring legacy of the programme.
- Presented multiple national strategic communication campaigns promoting safer giving and promoting tolerance through the PPC broadcasting of over 100,000 minutes to the Pakistani population. The sustainability of this result is harder to verify, particularly as the PPC is no longer continuing. However, this result did contribute to the continuing national dialogue on extremism.
- Informed HMG understanding of extremism, increasing HMG’s understanding and co-ordination to improve its countering of extremism. The learning of this programme has continued feeding into the design of new interventions.
- Trained and reinforced capacity of over 2,900 law enforcement, government officials, madaris’ and journalists to counter extremism. The sustainability of this result is not verifiable without follow up analysis.

Alongside other CSSF and HMG programmes the CE programme pivoted in March 2020 to support the Pakistan Government with the Sars Covid-19 (C-19) pandemic response:
- PPC messaging reached 1.6 million people through safer worship protocols in 153 mosques across 11 districts.
- Covid-19 messaging on public transport reached 1 million people across Pakistan.
- Ramadan broadcasts on safer charitable giving and C-19 were broadcast on radio, TV and social media through the PPC involving MoIB, Ministry of Religious Affairs, and Council of Islamic Ideology. Estimated viewership was 8.4 million with strong post-programme polling demonstrating a change in public perceptions on C-19 issues.
- PPC produced public service messages on TV and social media on safer worship, C-19 related myths and misinformation and valuing frontline workers, which were watched by 262 million times by 39 million people.
- Through UNDP facilitated and issued safer worship guidelines and C-19 standard operating procedures through 15 Madaris reaching over 1,000 students, and undertook youth perceptions surveys on C-19 messaging.

What Lessons Have Been Learnt?
The programme embodied an adaptive and innovative approach at the outset to help support the GoP in developing its CE capability. While it sought to capitalise on political will generated from an earlier communications project, the programme inherited a pre-existing communications mechanism in the form of the PPC. Given the extremely political nature of the environment and the divergence of wider CE strategy in the UK, regular reviews of the Theory of Change (TOC) and Results Framework (RF) is important to verify that underpinning assumptions are valid and the programme remains adaptive.