Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK
Programme Title	CSSF Regional Programme
Programme ID	C-SAA-0016
Country and Region	Pakistan, South Asia
IATI Unique ID	N/A
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: BC £7.766m	Non-ODA:
Total Spend	ODA: £6.424m	Non-ODA:
Time Frame	Start Date: 01 April 2017	End Date: 31 March 2021

Outputs	Scale of Delivery
A greater level of structured contact amongst influential individuals through track 2 and 1.5 [1]dialogues, and conferences on key thematic areas	3
Identification and progress on areas where increasing economic bilateral and trilateral integration and connectivity is possible; and mapping of areas which need advocacy from international community	3
Coherent Strategic Communications strategy increases influencing and monitoring capacity of the overall programme	1
Final Overall Scale of Output Delivery	3
[1] Track 1.5 dialogues are conversations that include a mix of government officials—who participate in an unofficial capacity—and non-governmental experts, all sitting around the same table. On the other hand, track 2 diplomacy brings together unofficial representatives on both sides, with no government participation. Neither track 1.5 nor track 2 discussions carry the official weight of traditional diplomacy, as they are not government-to-government meetings. What they offer is a private, open environment for individuals to build trust, hold conversations that their official counterparts sometimes cannot or will not, and discuss solutions.

Outcome Assessment	There has been increased Government to Government dialogue in areas covered by the programme. Beneficiaries, without exception, spoke highly of the programme’s ability to bring Pakistan, Afghanistan and India influencers together. In the case of Pakistan and India, these dialogues were the only known form of high-level dialogue for most of the programme’s duration. Their impact is difficult to assess, but senior leaders interviewed reported that issues raised in the dialogues had been reflected back to governments in Delhi and Islamabad, who had subsequently taken positive action. This points to the utility of the UK having sponsored the initiative and justified the risks. It was also noted internally that the programme afforded access and influencing opportunities unavailable through any other means. These are said to have benefited a range of BHC efforts in Islamabad. The Economic Connectivity elements of the programme supported persistent work on opening and maintaining the Kartarpur corridor in summer 2019 at a time when almost all formal engagement between India and Pakistan had broken down. On the Afghanistan-Pakistan front, the programme was able to contribute to changes in visa policies for Afghan students and businesspeople travelling to Pakistan, as well as protecting refugees through securing extensions for Afghan refugees in Pakistan.
Final Overall Scale of Outcome Achievement:		3 (Did not fully meet all outcome targets)
Overall Risk Rating:		High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating		A	A	B	B	B	B	3	3
Risk Rating		High		High		High		High
Note: an output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
This programme was designed to reduce the potential for conflict in the region through 1) a dialogue process and 2) economic connectivity.
The UK provided support for ‘regional security’ and ‘nuclear doctrine and deterrence’ dialogues through 2017-21, both financially and by ensuring high level attendance from key influencers. The dialogues enabled exchanges of perspectives and ideas on stabilising the regional conflict dynamic through the India-Pakistan-Afghanistan (IPA) Dialogue and the India-Pakistan Military-to-Military (Mil-Mil) Dialogue, enabling participants to work collaboratively, design strategies for overcoming current political challenges, generate recommendations for improved stability and aid the prevention of escalation. The security dialogues brought together top diplomats, military officers and security officials from Pakistan, India and Afghanistan, to discuss measures to seek regional stability amidst competitive trilateral relations. The participation of serving officials took place despite the absence of official India-Pakistan peace dialogue during the life of this programme.

Through a wider network, the programme supported constructive engagement around the Line of Control (LoC) when diplomatic engagement was non-existent. It addressed misinformation and engaged in fact-checking around incidents such as at Pulwama in Feb 2019[2] and crucially, the programme supported peaceful responses, offers of state-to-state dialogue and de-escalation in the face of a deteriorating situation in Kashmir. It is possible that recommendations will be adopted by governments piecemeal and without attribution. Partners believe India/Pakistan ceasefire announced in March 2021 was in part attributable to the programme.
[2] The 2019 Pulwama attack occurred on 14 February 2019, when a convoy of vehicles carrying Indian security personnel on the Jammu–Srinagar National Highway was attacked by a vehicle-borne suicide bomber at Lethapora in the Pulwama district of the erstwhile state of Jammu and Kashmir.

The Economic Connectivity outcome targets across the India-Pakistan strand were often not met as the targets focused on government policy changes which, in this period, saw a complete ban on trade between both countries. Afghanistan-Pakistan targets were achieved in almost all years, with major breakthroughs around border closures and time-sensitive trade issues. This was managed despite an extremely challenging context. Conventional or other escalation was managed through the crisis management platforms under this programme. New platforms were developed and implemented across both strands to expand participation and initiate transfer of knowledge about the process and issues to a younger generation.

The Strategic Communications output of the programme was closed in March 2020 following sustained under-performance. Previous reviews saw little evidence of value having been achieved from this output.

What Results Did the Programme Deliver? Will they be Sustained?
The headlines for the programme’s effectiveness include:
- The nuclear dialogues were the only nuclear doctrine and deterrence dialogues that took place between Pakistan and India. No other UK/US/EU think tank has been able to convene such bilateral dialogues.
- The programme appears to have contributed to conflict prevention and management across the India-Pakistan bilateral relationship and has been used as a shock absorber at a time of sharp deterioration in relations between the two countries, particularly around incidents such as Pulwama (Feb 19) and the revocation of Article 370 [3](Aug 19).
  [3] On 5 August 2019, the Government of India revoked the special status, granted under Article 370 of the Indian Constitution to Jammu and Kashmir—a region administered by India as a state which consists of the larger part of Kashmir which has been the subject of dispute among India, Pakistan, and China since 1947. Among the Indian government actions accompanying the revocation was the cutting off of communication lines in the Kashmir Valley, and thousands of security forces were deployed to curb any uprising. Several leading Kashmiri politicians were taken into custody, including the former chief minister, Government officials described these restrictions as designed for preempting violence, and justified the revocation for enabling people of the state to access government programmes such as the right to education and the right to information.
- Although it is difficult to claim impact for policy outcomes as a result of the ‘regional dialogues’, this was the only forum where serving intelligence chiefs from the Inter-Services Intelligence (ISI) and India’s Research and Analysis Wing (RAW) met (once/twice a year for the past several years). It is possible that the off-the-record meetings between these intelligence chiefs that this programme enabled helped bring about discrete channels of communication that reportedly facilitated the February 2021 ceasefire on the LoC in Kashmir.
- Many of the changes around visa policies were announced by Pakistani and Afghan government officials during programme events or side meetings and sequential work around the opening of the Torkham border and the procedural hindrances to trade across this border – all of which have been a flashpoint for conflict – have led to sustained changes in border management policy by the Government of Pakistan.

What Lessons Have Been Learnt?
There has been repetition across dialogues and participants due to objectives not always being clear. Feedback mechanisms so that one dialogue may inform the next have been difficult to achieve.

The need to ensure that under performance is identified early so that appropriate action can be taken. This is evidenced by the lack of results achieved by the Strategic Communications activity.
Changes in personnel have critically impeded lesson learning. Four separate SROs covered the programme’s final sixteen months. This was worsened by a similarly rapid and unpredictable churn in colleagues in political sections. This damage was only alleviated by the reliable input of LECs / SAIC staff in permanent roles, to whom a great deal of decision-making should have been devolved.

Beneficiary interviews have identified that the inclusion of intelligence chiefs has benefitted messaging on dialogues. It is believed that there are more opportunities to enhance this inclusion in future.