Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Strengthening the Rule of Law in Pakistan (RoL) Programme
Programme ID	C-SAA-0017
Country and Region	Pakistan, South Asia
IATI Unique ID	CSSF-08-000002
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MoD), Home Office (HO), Crown Prosecution Service (CPS), National Crime Agency (NCA)
Total Budget	ODA: £48.0m	Non-ODA: £3.3m
Total Spend	ODA: £47.7m	Non-ODA: £2.6m
Time Frame	Start Date: 1/4/2016	End Date: 31/3/2021

Outputs	Scale of Delivery
1. Improved cross-institutional policy frameworks to support safer security and justice outcomes (25%)	3
2. Improvement in institutional governance, including, systems & structures, of targeted criminal justice institutions (25%)	4
3. Improved capability of targeted criminal justice actors and institutions to comply with agreed organisational and/or professional standards (25%)	3
4. Rights violations are prevented, and rights promoted and increasingly protected, of victims, witnesses, defendants and convicted persons, especially women and juveniles (25%)	4
Final Overall Scale of Output Delivery	4

Outcome Assessment	The Strengthening the Rule of Law in Pakistan (RoL) programme has registered important successes in: improving the utilisation of data to reform policies and procedures; building cross-institutional cooperation around commonly shared problems, such as illicit financial flows; delivering substantial training programmes in-country and remotely; and strengthening protections for women and children. However, in relation to the high ambition set at the beginning of the programme to drive systemic changes that increase public confidence and trust, it is assessed that the programme has not met these expectations. Future programming in this sector will need to aim for greater coherence between activities, adaptation to the political context and leveraging of diplomatic and development expertise within the British High Commission.
Final Overall Scale of Outcome Achievement:		3
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2015/16a	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A+	A	A	A	A	A	A	B	4	3
Risk Rating	Moderate	Moderate	Major		Major		Major/High		Medium-High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
The CSSF Strengthening Rule of Law in Pakistan (RoL) Programme aimed to increase public confidence and trust in the Rule of Law in Pakistan. It focused on delivering outputs which improved the justice system for victims, witnesses and offenders, including vulnerable women and girls. Over time the programme has accumulated components related to the functioning of the criminal justice system, including: support for more human rights-compliant prosecutions; tackling financial and economic crime; and supporting victims among more vulnerable populations. The programme has been delivered through six government departments, adding to the complexity of these interventions. In its earlier phase, it included a number of projects that have since closed, including with UNDP, GIZ and a commercial partner. The projects being delivered at the time of the RoL programme closure on 31 March 2021 included the following:

Justice System Support Programme (JSSP): Used a roadmap approach[1] plus targeted technical assistance to help criminal justice institutions improve performance, deliver priority reforms and strengthen coordination in Punjab and KP.
[1] The roadmap approach was built around the principles of: a) prioritisation of a limited set of shared indicators, b) ensuring system leadership and political buy-in, c) investing in data-driven policy-making, d) establishing clear routines to sustain these ways of working, and e) emphasis on learning and iterative adjustments en route.

United Nations Office on Drugs and Crime (UNODC) in Balochistan and Sindh: Supported roll out of the roadmap approach in Balochistan and Sindh.

Strengthening Accountable Justice in Pakistan (SAP): Supported inclusion of vulnerable groups in criminal justice reform, around child-sensitive justice and survivors of gender-based violence (GBV).

Counter Terrorism-Associated Prosecutorial Reform Initiative (CAPRI): Improved civilian capacity to investigate, detain, prosecute and try terrorists in line with international standards and human rights norms. Focused on Punjab.

Counter-Improvised Explosive Device project (CIED): Improved military and civilian capacity to disarm Improvised Explosive Devices (IED) and collect forensic evidence for criminal investigations.

Financial & immigration crime professionalisation project (“SOC project”): Improved Pakistan’s capability to address illicit financial flows and immigration crime.

Extradition & mutual legal assistance: Building Pakistan’s capability to use mutual legal assistance (MLA) and extradition.

What Results Did the Programme Deliver? Will they be Sustained?

- Significantly improved the use of data by target criminal justice institutions in KP and Punjab to strengthen cross-institutional coordination around shared problems. In Punjab based on data driven analysis, procedures were adjusted to ensure that more than half of crime scenes are now being processed by the forensic authority. In KP a prison census to identify prisoners in custody for non-heinous crimes led to 39% of those presented being released.
- Strengthened policies and procedures within criminal justice institutions to deliver positive concrete outcomes for victims, witnesses and offenders. This includes changes to referral processes and systems in the Punjab police that led to an increase in referrals for victims of domestic violence to almost 100% from a baseline of zero with protocols in place to sustain the shift.
- A fully functioning Centre for Professional Development (CPD) to build the capability of prosecutors and ensure broader human rights compliance which is now delivering customised modules under a new curriculum, and delivered through eCAPRI, the online training system now run by the CPD.
- Increased cooperation and information-sharing between the Financial Monitoring Unit and federal law enforcement agencies (LEAs) on economic and financial crimes and incremental progress towards removing Pakistan from the Financial Action Task Force’s ‘grey list’.
- Piloting 13 child courts at federal and provincial levels to ensure children are able to gain access to child and gender-sensitive services, which has led to 1,921 children being channelled through these bodies. Juvenile justice and child protection policies have been formally adopted and courts are active.
- New standards, policies and procedures are being piloted to improve the quality of services to victims of sexual and gender-based violence, with new human rights-based approaches being implemented in four government shelters across KP and Punjab, and a Sexual Violence Response Framework now in place in Sindh.
- Landmark legal reforms have strengthened adherence to international human rights standards in Pakistan, including support for initiatives that led to a ban on the practice of ‘virginity testing’ in response to allegations of sexual assault, and technical advice to overhaul colonial-era legislation on prisons in Punjab, providing a foundation for improving prison conditions.
- Training and equipping 2,233 military and civilian personnel on countering IED activity and creation of an internationally recognised Counter IED Explosives, Munitions and Search School (CEMS) and a world-class canine centre. This work contributed to a reduction in loss of life and injury from IEDs from 1,583 in 2018 to 599 in 2020.

What Lessons Have Been Learnt?
- The impact and outcome-level ambition of the RoL programme was not matched by the resourcing, timeframe or implementing partner capacity. Deeply embedded resistance to change within key institutions in Pakistan meant that a more modest, pragmatic and experimental approach was required.
- Earlier and more direct HMG engagement in the programme design could help avert future problems and delays in implementation. Decisions to outsource design work to suppliers can ease immediate pressures on resources, but delays and misteps in the earlier implementation can be attributed to an arms-length approach to commissioning programme design.
- The criminal justice system is a difficult sectoral context to apply the institutional framework of a Roadmap approach. System leadership and top-down accountability is harder to embed in the justice sector than it is in health and education because of higher levels of institutional competition where the judiciary prizes its independence. A fixation on the ‘form’ of institutional development can overshadow an important focus on the ‘functions’.
- Identifying immediate material problems, and developing data-sets and systems to analyse and solve them, is a more productive starting-point for interventions. In the final year of implementation, the JSSP team began working with counterparts in Punjab and KP police and prosecutions, using data and results as the entry point. Rapid progress was enabled through this more pragmatic approach.
- The COVID-19 pandemic generated opportunities as well as challenges for programme partners. UK-based delivery partners were forced to adapt quickly to remote training and meetings. However, it also led to new demand for support from JSSP on issues such as tackling the levels of prison overcrowding, and interest in CAPRI’s virtual training system. Systematised adaptive programme management was best-placed to identify the risks and opportunities.
- The success of projects within the RoL programme that supported vulnerable populations can be attributed to a more experimental approach and willingness to scale innovations. The cultivation of entry points around, for instance, the childrens’ court system and improvements of shelter standards provided a foundation for scaling up and broader institutional change.
- Opportunities may have been missed to leverage diplomatic and policy influence behind programme activities. Earlier attempts to bring together different government departments in a strategic coordination cell, and link more effectively to diplomatic levers, were partially successful but more consistent engagement might have unlocked programme potential.
- Coherence of a complex and multi-dimensional programme might have been aided by the development of a single unified Theory of Change. The programme Theory of Change was last updated in 2018, as the BHC and implementing partners focused on the log-frames for guidance on progress. However a more systematic use of the Theory of Change might have tested flawed assumptions earlier, and identified opportunities for cross-project working.
- Gender needs to be mainstreamed through all rule of law and justice programming, with the programme’s experience on forensics offering a useful template for similar programmes. One of the common themes that cut across projects was the use of new forensic tools and skills to improve criminal investigations. For women who are consistently excluded and mistreated by Pakistan’s criminal justice system, the increased use of Sexual Assault Evidence Collection (SAEC) Kits and strengthened forensic capacity is a concrete and meaningful step forward, and should be built upon.
- A broad and complex programme such as this needs to be supported by adequate resourcing. In some cases, such as the CIED component, implementation was stalled by the lack of staff. Resourcing for future programmes might consider how strategic management might be combined with specialist HMG operational expertise to deliver optimum effect.