Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Stabilisation Programme
Programme ID	C-SAA-0018
Country and Region	Pakistan, South Asia
IATI Unique ID	N/A
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MoD)
Total Budget	ODA: 13.88m	Non-ODA: 3.22m
Total Spend	ODA: 12.5m*	Non-ODA: 2.58m
Time Frame	Start Date: 1 April 2016	End Date: 31 Mar 2021

Outputs	Scale of Delivery
Revised Output 1 for 2020-21: Improved understanding of conflict, citizens priorities and (in)stability drivers in the Newly Merged Districts (NMDs) to create an evidence base for Government policy formulation, international community decision-making and programming in the NMDs.	3 / This is an average score across all years of the programme
Revised Output 2 for 2020-21: / Conflicts with potential to fuel protests and/or violence identified, prioritised and conflict resolution capability tested and strengthened to address one or two disputes in selected districts.	3 / This is an average score across all years of the programme
3. High Level International Engagement (HLIE) activities influence PakMil Senior Leadership on UK approach to mil-civ transition to stabilization in FATA	3 / This is an average score across all years of the programme
Final Overall Scale of Output Delivery	3

Outcome Assessment	The programme’s output and outcomes were adjusted to deliver to the changing context throughout the life of the programme. The main driver for these adjustments throughout this programme, was to ensure effective delivery in line with the progress that was made with the merger of the Federally administered Tribal Areas (FATA) with Khyber Pakhtunkhwa (KP) and ensured adaptation to the context of the time. This flexibility allowed the programme to deliver against the outcome whilst ensuring that priorities of the time were supported to increased confidence and trust between the population of ex FATA and the Government. The evolving political context (as the districts merged and settled) and the more recent impacts of COVID-19 affected progress at different times throughout the life of the programme. However, reporting, surveys, analysis and beneficiary discussions highlight that progress was made against the achievement of outcomes, along with a real contribution to the Impact that this programme was set up to support (Improved stability in FATA), the impact was adjusted in 2019/20 with an extension to Improved stability in ex FATA. / The MOD elements of this programme were delivered as almost a separate programme and, although hard to demonstrate, analysis into this type of Access and Influence does show that influencing entities such as Pakistan Military can only have any traction if delivered through this type of intervention. Beneficiaries stated that these military interventions helped bring about a more effective military approach to the Merged Districts (MDs). / Outcome Indicators 4 and 5 were deleted from March 2019. Output 3 (in its entirety) was not delivered in 2020/21 due to COVID-19.
Final Overall Scale of Outcome Achievement:		3 (Did not fully meet all outcome targets.)
Overall Risk Rating:		Major

* This is a provisional figure and will be updated once the final financial reports are received from UNDP.	.

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	A	A	A	A	A	A	3	3
Risk Rating	Major	Major		Major		Major		Major
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
Since 2016, the UK has provided support to reform efforts in the former Federally Administered Tribal Areas (FATA) aimed at increasing stability and reducing the citizen-state trust deficit.

Over its life the programme has delivered 71 development projects including skills training and livelihood support which benefitted 427,211 individuals. A Strategic Communications Unit was established which remains operational and is providing communications support to the Government of KP (GoKP) informing Merged Areas (MA) residents about a wide range of key issues from development initiatives to COVID-19 SOPs.

The programme also completed public polling including the Tribal Barometer survey (the largest survey of its kind in the MA), which is informing GoKP officials of the views and priorities of the people of the MA to help close the communication gap between the government and citizens.

In addition, UNDP capacitated the (ex) FATA Development Authority (FDA) through the provision of technical and financial resources for the setting up and operationalisation of the Job Placement Center (JPC). The JPC remained operational for around 10 months. During this time, valuable recommendations were provided to the FDA for the improvement of its workforce development programme. Following the FATA merger in the Khyber Pakhtunkhwa province, restructuring of different institutions including FDA took place.

On 30th April 2019, with the help of advocacy from the programme, the Local Government Act was passed extending elected political representation at the community level to the MA. With this legislation, all 702 villages will have a council, and every council will have a seat each reserved for women, youth, peasants and minorities. The first local government elections are scheduled to take place on 15 September 2021.

What results did the programme deliver? Will they be sustained?:

As stated in the Annual Review 2020, ‘The progress that has been made in the Newly Merged Districts is fragile. Whilst significant steps have been taken to provide an enabling environment that could support long-term stability in the region, this is by no means certain.’

Across the life of the programme, Defence Education has been reduced from 8 Tier 1 courses to retain focus on senior level education funding places on Royal College of Defence Studies (RCDS) and Advanced Command and Staff Course (ACSC) and then further reduced in line with direction to RCDS only.

The Stabilisation Conference, having morphed to broaden scope from The Counter Insurgency (COIN) Conference at its inception, was postponed at the last minute due to COVID-19 in Mar 20 and again in Mar 21, the full planning cycle, however had been undertaken alongside the Pakistan Military.

Under Defence medical cooperation, Op PANAKA[1], the UK Military worked with the PakMil Surgeon General (SG) to strengthen Pakistan Armed Forces Medical Services (PAKAFMS) understanding of linkages between Integrated Disease Surveillance and Response systems and share best practise on clinical and nursing excellence.
[1] Op PANAKA is a Medical Defence Engagement project.

What Lessons Have Been Learnt?

1. Building and maintaining relationships with key stakeholders is essential.
2. Adaptability proved paramount due to the high risks of delivery due to security and the ever changing context as the NMDs were initiated and bedded in.
3. An emphasis on broadening the focus of the programme away from just High level Government interactions would have been beneficial from the start.
4. Internal management mechanisms such as Theories of Change and logframes must adapt, and if necessary their formats be revised entirely, to reflect the fluidity and volatility of the programming environment. Undue rigidity of process impedes flexibility.