Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Commonwealth Litter Programme (CLiP) 20/21
Programme ID	C-SAA-0022
Country and Region	Core CLiP: Maldives and Sri Lanka / CLiP revisits/continuation: India, Belize, Vanuatu, Solomon Islands and South Africa / Waste and Resources Action Programme (WRAP): Pacific, Malaysia, South Africa, India
IATI Unique ID
HMG Partners / (Lead in bold)	Centre for Environment, Fisheries and Aquaculture Science (Cefas) and Waste and Resources Action Programme (WRAP)
Total Budget	ODA: £2,034,884	Non-ODA: N/A
Total Spend	ODA: £1,899,672	Non-ODA: N/A
Time Frame	Start Date: July 2020	End Date: March 2021

Outputs	Scale of Delivery
Output 1: Tools for the collection of data on marine litter and microplastics abundance, composition and sources are established in country.	4
Output 2: Increased awareness of the plastic pollution problem within target communities.	3
Output 3: Improved knowledge is available to government to develop future policy interventions.	4
Output 4: (WRAP) – Countries are supported in developing collaborative actions and have access to international knowledge, best practice and innovation through the established global network of Plastics Pacts.	4
Final Overall Scale of Output Delivery	4

Outcome Assessment	Summary of achievements by outcome. / Outcome 1: Increased capacity and ability to tackle land and sea-based litter sources within selected Commonwealth countries. / CLiP developed training webinars, online workshops, written guides and videos with sub-titles; to achieve direct and in-direct training with a range of stakeholders in country. CLiP also provided new infrastructure and equipment to study the impact of microplastics. CLiP not only worked with in country scientists/experts but also NGOs and Government Agencies. Overall, this has led to a widespread increase in capacity to deliver locally relevant research, sampling and data gathering relating to microplastics and marine litter monitoring, as-well as helping to develop new innovative techniques in partner countries, for example in the satellite monitoring of floating litter. These elements have helped to inform countries of plastic pollution issues and possible solutions, so leading to improved capacity in tackling land and sea-based litter sources. / Outcome 2: Local communities better understand the problem of marine litter, which results in long term behavioural change. / CLiP has developed bespoke community packs, specialised environmental educational programmes, a collection of e-learning modules, and a live YouTube broadcast; in a variety of languages to directly increase local understanding of the problem of marine litter. This work was spread not just by various departments of education but by NGOs with feet on the ground, ensuring the knowledge was shared not just to the younger generation, but to a wide range of people in a variety of communities. Whilst it is too early to measure the long-term impact, informing a multitude of communities of the issue and its impact on their local culture and environment is the first step in fostering behavioural change. / Outcome 3: Lack of coordination and knowledge gaps are addressed for selected countries, that can move towards implementation of national and regional actions against marine litter. / CLiP has established regional groups (e.g South Asia Marine Litter Colloquium) to share capabilities and increase action against marine litter. These regional bodies held workshops that have led to recommendations for future policy in a variety of countries. Where gaps in national expertise were identified, we provided enhanced training and provided specialist equipment to ensure they were no longer lacking. CLiP also engaged directly with individual governments and implemented key actions around outreach and waste management, along with with agreement for future collaboration in this area. / Outcome 4: (WRAP) - Local leaders and small nations are connected to the wider international community and regional actions and increase their influence over business and government practice which impact them disproportionately. / The Pacific and South Africa Plastic Pacts (ANZPac and SAPP)co-ordinated by WRAP provide key stakeholder engagement between governments, local leaders and business for a wider region, allowing enhanced collaboration and shared capacity building. This has led to strong collaborative work on solutions on the issues which affect them directly. These Pacts are not just tackling existing marine litter reactively, but on preventative measures regarding the import of plastics into the nation in the first place.
Final Overall Scale of Outcome Achievement:		4
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating					4	4
Risk Rating					Medium
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?

Core CLiP

Marine litter is found in all the oceans of the world, both in densely populated and remote areas, far from obvious sources and human contact. Globally, it is estimated that 6.4 million tonnes of marine litter enter the oceans each year, with about 8 million items entering the oceans every day. Up to 90% of marine litter is made up of plastics, originating from both land and sea-based sources (UNEP and GRID-Arendal, 2016).

CLiP has been active since 2018 and through its original £6m investment, successfully delivered in five countries (Belize, South Africa, Solomon Islands, Vanuatu and India), as well as further activity to set up Plastic Pacts in South Africa, the Pacific and Malaysia. In FY 2020/21, CLiP expanded the programme to South Asia (Sri Lanka primarily, with a smaller technical assistance workstream in the Maldives), whilst finalising work from previous countries (primarily India), and under the WRAP Plastics Pact.

- CLiP Sri Lanka- Rolling out a full CLiP programme into Sri Lanka utilising key elements of success from CLiP 18/20 delivery, including education, outreach and capacity building efforts.
- CLiP India- Completion of CLiP work from 2019- finalising reports establishing initial findings and providing technical assistance to facilitate implementation and further monitoring.
- CLiP Maldives- Technical assistance following the Maldives joining CCOA in May 2020 reflective of in country priorities on the issue of marine litter.
- WRAP Plastics Pact- providing follow up support with the launch of Plastics Pacts in Malaysia, Pacific and South Africa in March 2020.
- Other- Ongoing technical assistance in historic CLiP countries to monitor implementation of 18/20 work streams, and dependent on Covid-19, re-organising the Commonwealth Clean Ocean Conference.

WRAP

Malaysia: Support the secretariat of MaSPA with technical and governance matters as requested by the Ministry of Environment, KASA, and support the business members of MaSPA, who formed an industry-led subgroup called the Packaging Recovery Association (PRA), to progress on increasing the collection and recycling of plastic packaging.

ANZPac Plastic Pact: Develop a clear plan for how the Pacific Islands can participate in the regional Plastics Pact (ANZPac) giving them access to influence the plastic packaging being shipped from Australia and New Zealand. This will enable them to reduce the burden of plastic waste arriving at their shores and increase the value of the plastic which does arrive so that an economically viable solution for recycling can be implemented. Support governments on key islands to implement collection and recycling systems to meet the targets of the ANZPac and reduce marine pollution.

South Africa Plastic Pact (SAPP): Provide additional and immediate technical support and capacity to the existing South African Plastics Pact, including the development of a communication campaign to be disseminated by all its members.

India Plastic Pact: Support the development of a website for the Indian Plastic Pact.

What Results Did the Programme Deliver? Will they be Sustained?

Core CLiP

Over three years, CLiP has:

- Supported publication of numerous locally generated scientific papers and hosted international stakeholder events. Result- Local scientists gain international exposure, governments are provided with globally acknowledged scientific evidence to inform policy change, countries are supported to become regional hubs of expertise (for example Belize is working to offer support across Caribbean countries on marine litter science).
- Provisioned nine new marine litter laboratories in country, as well as provision of specialist marine litter monitoring equipment. Result- Countries are no longer prevented from developing locally relevant marine litter science due to a lack of essential equipment
- Delivered bespoke educational materials (primary, secondary and teachers’ packs, as well as beach cleaning kits for local NGOs), rolling out in all seven countries. Result- Local communities understand the impact of plastic pollution and are empowered to take action to reduce pollution and the connected economic and health impacts.
- Delivered expert training sessions to embed expertise in use of equipment, monitoring techniques (e.g. training sessions for surveying beach litter using OSPAR protocol), and funding of local studentships to develop skills. Result-Local people are upskilled to identify sources of marine litter and advise governments on implementation of locally relevant solutions.
- Convened cross-stakeholder workshops with key industries (fishing, port authorities, waste and recycling sectors). Result- effectively convening local stakeholders to pool knowledge and present recommendations to local governments to effect change.
- Designed multimedia campaigning material to raise awareness of new legislation in Sri Lanka banning single use plastics. Result- Directly responding to country need, in this case ensuring Government was equipped with necessary tools to publicise new plastic reduction legislation and ensure its success.

Sustainability:
All results are designed to be sustainable over time: by ensuring high quality training and collaboration to create new locally relevant science and evidence, CLiP is working to ensure that local people (scientists, government official and communities) have the knowledge and resource required to continue generating evidence, policy and management systems in future. As a result countries are equipped with tools to independently reduce marine plastic pollution and the social, environmental and economic challenges related to it. Defra will continue to work with CLiP countries through the Blue Planet Fund to further initial successes of CLiP and to monitor further impact.

WRAP

Malaysia: Due to political changes in the country and an initial slow response from the current government, the scope of the project had to be adapted and changed in the business case halving the funds allocated and delaying the start of implementation. Nevertheless, WRAP managed to engage the new government and local organisations and successfully adapt project purpose and activities to their request. After the work delivered there is appetite and interest from the government to continue this collaboration.

ANZPac Plastic Pact: The COVID19 crisis has presented big challenges for this project causing a general delay in the ANZPac Pact development. Nevertheless, WRAP has successfully focused main efforts in providing technical advice to the implementing organisation, APCO, for the development of ANZPac Plastic Pact, and in engaging the Pacific Island ensuring their representation for the upcoming launch in May.

South Africa Plastic Pact:The South Africa Plastic Pact continues to be one of the strongest plastic pacts and funding support from Defra has helped to accelerate the delivery of the SAPP targets through the sharing of WRAP’s technical expertise, resources and methodology trialled in the UK Plastics Pact by WRAP and being adopted in other countries.

India Plastic Pact: The website has been developed in time for the soft launch on the 15th of April 2021.

Sustainability:
Across all countries, plastic pacts, or the principles of the plastic pact, were established and embedded. Working closely with stakeholders in country to ensure buy in ensures that after launch, these projects and principles will continue tosupported and continued.

What Lessons Have Been Learnt?

Core CLiP

Having not previously worked remotely there was uncertainty about how well the approach would be accepted by in county stakeholders. Through regular engagement and transparency with country partners, as well as flexibility to adapt aspects of the programme that could not be delivered in a Covid environment, a remote delivery approach was successful and many of the targets were exceeded, as exemplified in the results framework and narrative. Longer engagement time should be considered whilst delivering remotely due to the pace of virtual communications as opposed to face-to-face meetings. Virtual meeting and workshops should be included in the engagement plan and communications and should not rely exclusively on emails. The importance of alternative ways of communications (e.g. use of WhatsApp) should be considered in the engagement plan.

As supported by the findings and recommendations of the ITAD The Value for Money report commissioned to review CLiP from inception to the end of the last financial year, the need for longer term, sustained activities and funding is critical to ensuring ongoing success, engagement and implementation of actions to reduce and prevent marine litter.

Scope and timeframe creep during in country scoping phase has meant that key activities such as MoU have not been completed and these have overlapped with operational phase, creating considerable uncertainty and delays. It is important that any future deployment regard these as two separate stages, with specific goals for each, agreed with key stakeholders. This will help manage expectations of host countries and stakeholders whilst also ensuring that there is a clear scope for work to deliver against.

WRAP:

Malaysia:
Malaysia underwent political changes since the project plan was developed which delayed the commencement of activities because we had to reengage once the new government settled in. Although this is out of WRAPs control for future projects this type of potential situation could be taken into account in the risk assessment.

The timings considered for government response were not accurate, the same teamwork in various different projects at a time and when Covid restrictions take place it becomes a bigger issue.

Engaging with SMEs is a key issue in Malaysia, it is needed but their engagement also requires long timings that need to be considered in the planning of a similar project.

There are certain sensibilities we have learnt of that will help us adapt future projects about the relationship of Malaysian government and private sector. There is high informality in the waste sector, so the government is very careful with their approach to businesses, this dynamic is very different to other countries where we implement these public-private platforms.

ANZPac:
Engagement in the Pacific Islands has proved challenging not only due to the Covid-19 impacts but also with local stakeholders fatigue. Local stakeholders indicated that they are a bit exhausted of different foreign organisation coming to the islands to prepare reports with recommendations whilst little action take place afterwards due to lack of knowledge or resources to implement those recommendations. When trying to engage them is important to understand what they want/need which is interventions action/impact driven, as we did highlighting the benefits of joining the Plastic Pact, which is action focused, to overcome their current issues with plastics.

Local businesses prefer to talk to local stakeholders and face-to-face, therefore having local champions is key to obtain better engagement results.

Island stakeholders do not see most of the plastic pact benefits relevant to them. The development of a business case to highlight specific benefits for small islands/countries would be a useful tool for engagement of the Pacific Islands to join ANZPac or similar countries involved in future plastic pacts.

South Africa:
South Africa is a very advanced Pact with many activities going on in parallel, however, the implementing partner can only handle so many with their current staffing for this platform. There needs to be a good timelne to manage timing of delivery when proposing additional activities or assigning a budget for them to be able to cover it from their side as well.