Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Global SOC Programme (now Enablers Programme)
Programme ID	C-SOC-0001 and C-SOC-0005
Country and Region	Global excluding Western Balkans
IATI Unique ID	CSSF-12-000001 and CSSF-12-000002
HMG Partners / (Lead in bold)	Home Office, NCA, FCDO
Total Budget	ODA: £6.075m	Non-ODA: £1.285m
Budget this FY	ODA: £6.075m	Non-ODA: £1.285m
Spend this FY	ODA: £5,362,795	Non-ODA: £1,931,360 / increase in non-ODA was due to requirement to change platform costs from ODA to non-ODA for SOCnet and NCA staff.
Time Frame	Start Date: April 2020	End Date: March 2021

Outcome Assessment	In a standard Annual Review, the usual practice is to assess performance against defined indicators linked with a programme’s outcomes and subsequently outputs. The Global SOC programme had just one ‘indicator’ at the outcome level – number of change stories. To be able to conduct the annual review the review team devised a framework of questions to guide our assessment under each outcome and more clearly articulate exactly what type of changes might be expected under the four outcome statements, and then used this to assess whether/how change stories provided demonstrated evidence of such change. The change stories provided helped demonstrate positive change across several areas within the individual ‘change statements’ the reviewers created against outcome statements. However, three outcomes are marked as ‘on track but some doubts about whether outcome will be fully met’ because of the lack of clear assessment benchmarks for change stories against outcomes laid out from the outset. A fourth is marked as ‘off track, with outcome unlikely to be met without action’ due to the specific wording adopted in the outcome statement. Overall, as a result, we have scored the programme as ‘Amber’ at outcome level.
Overall Outcome Progress Rating:		Amber: On track but some doubts about whether outcome will be fully met
Overall Risk Rating:		M

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating					B	B	No score assigned	Amber
Risk Rating					M		M
Programme changes during this period
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The Global Serious and Organised Crime (SOC) programme was comprised of a series of interventions to:
- continue to build the evidence base around global SOC dynamics (via the production of a series of Serious Organized Crime Joint Analyses (“SOCJAs”) analysing different parts of the world)
- promote an improved and more coherent cross government and host nation response to SOC globally (through the ongoing deployment of SOC focused policy leads globally within the SOC Network (“SOCNet”))
- deliver activity against a number of SOC priorities within different countries, including the building of technical capacity to tackle Child Sexual Exploitation and Abuse (“CSEA”) in “Pursue” interventions as well as smaller pilot activities to build the foundations for more ambitious “Protect, Prepare and Prevent”[1] programmes.
  [1] To pursue offenders through prosecution and disruption; to prepare for when SOC occurs and mitigate impact; to protect individuals, organisations and systems; and to prevent people from engaging in SOC.

Key Results for FY 20/21:
- Philippine law enforcement units working on CSEA have significantly increased inter-agency cooperation because of HMG funding and support, which ensured that agencies were incentivised and supported to work collaboratively. Formalised structures and agreements have now been implemented to sustainably embed cooperation and intelligence sharing.
- HMG funding has led to improved policies and processes to protect vulnerable communities and victims. For example, the Namibian Police Service Gender Based Violence Police Unit are now using a custom-built premises, jointly staffed by police and social services, which allows child victims of sexual abuse to attend discreetly and be interviewed by a police officer and/or social worker in a child focused manner, which minimises risk to the child. In the Philippines, the House of Representative of Congress has expanded its consideration of legislative amendments beyond the Anti-Child Pornography Act and to respond to the escalating reports of online CSEA. This was made possible because of the systematic legislative advocacy efforts carried out via Global SOC funded programming.
- As a result of project activity in Guinea Bissau community members in a region heavily affected by illicit logging engaged for the first time with local government representatives about illicit finance dynamics, impacts, and responses. In Uganda and Tanzania, citizens are increasingly speaking up against and reporting images and videos of CSEA - thanks to an HMG-funded campaign, the issue is now much more widely discussed in the media and awareness is spreading of methods for reporting material online.
- At least 98 UK missions now have specific SOC and Illicit Finance objectives embedded within their Country Business Plans. Other results included enabling countries to develop national strategies; and work with cross-sector partners to commit to a whole-system ‘4Ps Response Plan’ to tackling money flows associated with illegal wildlife trade.

Key Lessons
- In 2020/21 the Global SOC programme was able to achieve greater conceptual clarity on overall desired outcomes for the programme and made demonstrable progress in articulating how the programme fits with HMG strategic priorities on SOC, which were reflected in the design of the 21/22 portfolio. These solid foundations now require building on in the current financial year, particularly with regards to underlying programme management processes.
- The programme’s innovative approach to monitoring and evaluation and in particular the use of ‘change stories’ has generated demonstrable benefits: individual projects and HMG partner agencies, as well as external CSSF implementers operating under/funded via the programme, have been able to articulate important behavioural/institutional changes generated under their interventions rather than focus on narrower metrics such as number of arrests or number of trainings. However, such an approach necessarily requires time to ‘bed-in’ given the time that needs to be invested with individual project leads to ensure they are bought into, and contribute to, the underlying assessment and performance tracking systems.
- The impact of Covid-19 on the programme’s ability to forward plan, as well as manage day to day tasks, was significant. Key programme staff were drawn into Covid-19 crisis management responses. Evacuations of project staff back to the UK and the lack of travel has made it harder for projects to deliver where face-face engagement is expected and where relationship building is a key prerequisite for subsequent capacity building or other activity. Some projects were delayed or could not be started due to Covid-19. However, an impressive amount of activity still took place despite these challenges. Programme and project teams demonstrated significant flexibility in adapting programming whilst ensuring value was still being delivered, albeit often through different channels resulting in a remarkably small underspend given the circumstances.

Summary Recommendations for FY 21/22 (see full recommendations for internal use under B6)
- Consider further adjustments to the programme board structure for the now Enablers programme in 21/22.
- Ensure the revised programme board structure is underpinned with a clearly laid out information management/reporting cycle – up to the boards but also back down to projects and other relevant stakeholders at Post.
- Ensure programme and project assessment/performance tracking mechanisms are more clearly defined during the coming year.
- Consider further how Home Office SOC programming and policymaking intersects with FCDO-led processes and in particular what role SOCnet can and should play across HMG SOC structures.