Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Organised Immigration Crime Taskforce (OICT)
Programme ID	CSSF-01-000007
Country and Region	UK, Europe, Africa (North, West and East), Turkey
HMG Partners / (Lead in bold)	National Crime Agency (NCA), Home Office (HO), Crown Prosecution Service (CPS), Immigration Enforcement (IE), Immigration Enforcement International (IEI)
Budget this FY	ODA: £3,228,979 (post winter supps)	Non-ODA: £9,215,000 (post winter supps)
Spend this FY	ODA: £2,384,564	Non-ODA: £10,165,166
Time Frame	Start Date: June 2015	End Date: March 2021

Outputs	Scale of Delivery
UK1: Intelligence Collection	4
UK2: Intelligence Analysis	4
UK3: Social Research and Campaigning	4
UK4: Cross-Agency Learning, dissemination of best practice, harnessing innovation	4
UK5: Provide niche and specialist capability	4
UK6: Mechanisms for cooperation and coordination set up	4
OP1: Build Technical Capability	4
OP2: Build Investigation Skills	4
OP3: Build Command and Control Capacity	4
OP4: Provide interpreters support to operations	4
OP5: Provide guidance and support to prosecutors and investigators	4
OP6: Build, maintain and leverage our relationships with key host institutions	4
OP7: Raise awareness and capacity on OIC and promote legislative changes	4
OP8: Encourage and facilitate cooperation with or between partner countries and private sector	4
Op9: Promote the UK approach and best practice, influence other countries doctrinal approach	4
Overall Scale of Output Delivery	4

Outcome Assessment	Due to COVID 19 this annual review has been conducted by undertaking interviews using “Teams call” and through a review of documents and reports compiled by the programme team. / It is apparent to the review team that there has been a lot of progress made over period 20/21. This progress has embedded the Theory of Change and Results Framework at its core. The Results Framework demonstrates progress through quality based indicators identifying successful outcomes across the upstream theatre of operation. This success is underpinned by strategic assessments for identifying emerging threats. Evidence from the annual review indicates that the outcomes are being achieved in terms of disruption of criminal activity. Intelligence collection and analysis is demonstrably underpinning the disruption strategy.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	U	U	U	A	A	4	Green
Risk Rating					Medium		Medium
Programme changes during this period		The programme has been put on a much more solid footing with the refreshing and embedding of the Theory of Change, and the finessing of the Results Framework. Gender and Conflict Sensitivity are now being increasingly addressed and outcomes will be reportable in the next review. Overseas posts have been filled developing an effective network despite the ongoing COVID restrictions. Financial management of the programme has been significantly strengthened. Law Enforcement cooperation was affected by Brexit with the loss of access to databases and legislation. Mitigation of the loss is apparent and ongoing. Overall there has been good progress and successful outcomes achieved in a challenging operating environment.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- Overseas Capacity and Capability building for a predominantly Pursue based approach has been provided using both in person and online delivery mechanisms.
- An understandably more limited Prevent and Protect capability has been established and utilised.
- Enhanced intelligence sharing has been re-established post Brexit to target OCG’s especially in the near border area.
- The development of strategic intelligence assessments are providing sound knowledge products on which decisions can be made.

Key Results for FY 20/21:
- The Theory of Change and the Results Framework have been further developed and are evidently being used in decision making. This is led by the SRO, programme team and senior managers.
- The establishment of coordinated intelligence collection and dissemination with France is yielding operational outcomes through the Joint Intelligence Cell (JIC) supported by reporting from the Joint Debriefing Team (JDT).
- The overseas posts have been filled during 2020 in spite of COVID restrictions and following necessary training, vetting and funding being put in place.
- Disruptions of criminal networks overseas and in the UK have increased, with notable successes in France, Belgium and Greece.
- Quality Strategic Assessments have developed on which senior managers and government officials can make informed decisions.
- Financial management of the project has been strengthened with robust processes in place.

Key Lessons
- The long term upstream strategy suffers from the uncertainty and delay of funding mechanisms.
- The response to OC is more successful where UK agencies are coordinated and responsive.
- The post Brexit operating environment requires cooperation mechanisms being prioritised.
- M&E approaches to managing thematic OC issues provide direction and understanding.

Key Recommendations for FY 21/22
- Governance, monitoring and reporting structures to be reviewed.
- A mapping exercise to identify OIC response across UK and intelligence flow upstream.
- The project move to “business as usual” by carrying out a baseline exercise.
- Intelligence and evidence sharing opportunities for overseas outcomes to be mapped
- Identify additionality and complementarity opportunities from each overseas OICT hub.
- HR, gender and conflict sensitivity to be mainstreamed.
- Carry out an external evaluation of the OICT for future learning on catalytic interventions.
- The management of risk be reviewed and brought under central oversight.