Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Western Balkans Covid-19 response
Programme ID	C-WBK-0001
Country and Region	Western Balkans
IATI Unique ID	CSSF-10-000005
HMG Partners / (Lead in bold)	FCDO
Total Budget	ODA: £1.94m	Non-ODA: N/A
Total Spend	ODA: £1.94m	Non-ODA:
Time Frame	Start Date: September 2020	End Date: March 2021

Outputs	Scale of Delivery
1.1 (Kosovo): Increased Covid-19 testing capability for women and men in Kosovo	4
1.2 (Kosovo): Access, including by marginalised groups, to EHS through e-health services and vaccinations	3
1.3 (Kosovo): Increased acceptance of community transmission measures through messaging	4
2.1 (Kosovo): Schools are open and operating according to WHO standards	4
2.2 (Kosovo): Access to education (remote and/or school) by those most at risk of dropping out of education system	4
3.1 (North Macedonia): Provision of crucial training to health workforce necessary to provide safe, effective quality patient care and clinical management of Covid-19 patients and other essential health needs and to face public health Covid-19 challenges	4
Final Overall Scale of Output Delivery	4

Outcome Assessment	Outcome-level data was not collected for two out of the three outcomes on the results framework, which makes it impossible to provide an overall score. This was reasonable given the emergency response nature of the programme and its short timeframe for delivery. Observation of outcomes would require a longer period for results to mature and actualise.
Final Overall Scale of Outcome Achievement:		N/A
Overall Risk Rating:		N/A

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	N/A		N/A	N/A
Risk Rating	N/A	N/A		N/A		N/A		Low
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
The programme supported short-term emergency responses to Covid-19, to establish medical facilities, provide equipment, train staff, and to support education and awareness of the disease.

Key Results for FY 20/21?
- In Kosovo results included: 26 epidemiologists, public health specialists and microbiologists trained; 1,400-1700 additional Covid-19 tests conducted on a daily basis increasing Kosovo authorities testing abilities up to 4,700 tests per day; the provision of 1,206 vaccine carriers donated to the MoH; immunisation of 4,121 children and 5,645 families reached; 16 family medicine centres in Pristina providing e-health services; an 11% increase in the number of men and women who reported to be ‘very informed’ about Covid-19; 1,020 schools provided with essential hygienic supplies for prevention from Covid-19; 948 children and women with disabilities provided with tablets/laptops with assistive learning technologies; 68 teacher assistants for children with disabilities deployed in at least six municipalities; 28 teaching assistants deployed for girls with disabilities; 190 assistive technology devices distributed to young girls; 1,140 teachers trained in using assistive technologies; and completion of a digital mapping report of school dropouts of young women and girls from Roma, Ashkali and Egyptian communities.
- In North Macedonia results included: four OpenWHO training courses translated and adapted into Macedonian and Albanian languages with over 3000 health practitioners accessing the training as of March 31, 2021; development of three training modules in the area of Mental Health and Psychosocial Support During Covid-19 Preparedness, Response and Recovery; a feasibility study on accelerating basic nursing training solutions.

Key Lessons
- For a short-term, emergency response programme, the importance of selecting the right implementing partner(s) cannot be understated. The UK embassy’s choice of selecting UN agencies and the WHO to deliver project activities enabled successful delivery of the overall programme. This was due to UN agencies/WHO’s strong networks on the ground at both national and local levels; a deep contextual understanding of the Kosovo and North Macedonia Covid-19 landscapes and country needs, their ability to mobilise and implement swiftly in part as it was a continuation of pre-existing work; and strong internal coordination amongst the UN and UK embassy programme team.
- Streamlining processes in decision-making and approval is crucial in successful delivery of short-term emergency response programmes. There were some initial delays at the beginning of the programme which shortened actual implementation time to just over three months. Not all areas of implementation were limited. For example, there was significant activity around International Disabilities Day on December 3, 2020. However, stakeholders reported that any further delay would have likely resulted in a less successful programme unable to achieve its targets.
- The programme has delivered political capital. At times, particularly at the beginning of the Covid-19 outbreak and response in Kosovo and North Macedonia, this programme was the only visible international support in the region. Public awareness around the UK was heightened due to its support to the response, and strengthened the UK’s profile and reputation both at the national level as well as within minority communities. This is especially important as UKAid is perceived internationally to be shrinking back due to recent ODA budget cuts.
- The lack of a programme-level ToC and formal evaluation makes sense given its structure of being two independent projects in Kosovo and North Macedonia. Documentation at the project level did not indicate individual ToCs, though each had clear objectives. However, if UK HMG are interested in understanding higher level outcomes, dedicated time and adequate resource must be allocated to understanding what is realistic for the programme to achieve at the outcome level for a short project of this nature from the outset, and ensuring there are robust ways to measure it. Investment in more formal MEL processes will also ensure the design of the programme is cohesive.

Key Recommendations for FY21/22
- Streamline approval and financial processes for short-term emergency response programmes.
- Ensure collaboration, complementarity and synergies with other donors in-country on programme activities.
- Consider allocating dedicated time and adequate resource for more formal and/or nimble monitoring, evaluation and learning activities.
- Consider ways to further streamline processes and decision-making at the central down to in-country levels around approvals in design, budget allocation and disbursements for short-term emergency response programmes to ensure successful achievement of targets.
- Continue ensuring visibility of UK embassy staff (e.g. the ambassador, deputy head of mission) during programme implementation as this will help raise the UK’s profile & reputation in-country.
- Consider follow-up on activities from a sustainability perspective to ensure that the successes of implementation are not lost six months (and later) down the line.