Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Western Balkans Stability Programme
Programme ID	C-WBK-0005
Country and Region	Western Balkans: Albania; Bosnia-Herzegovina (BiH); Kosovo; Montenegro; North Macedonia and Serbia
IATI Unique ID	CSSF-10-000002
HMG Partners / (Lead in bold)	Foreign Commonwealth and Development Office (FCDO)
Total Budget	ODA: N/A	Non-ODA: N/A
Budget this FY	ODA: £16,678,623	Non-ODA: N/A
Spend this FY	ODA: £13,481,745	Non-ODA: N/A
Time Frame	Start Date: 04/2020	End Date: 03/2021

Outcomes[1]	Scale of Delivery
DJ1: Citizens and civil society are better able to ensure their governments deliver equitable and accountable service provision	3
DJ2: Political parties that act in the interest of citizens and are responsive to their demands	3
DJ3: Increased transparency, accountability and meritocracy of the democratic system	4
DJ4: RoL institutions increasingly provide equitable justice to the standards demanded from citizens; with opportunities for corruption reduced	4
R1: The foundations of division – real or perceived – become less relevant to communities, who place greater emphasis on working across these divides on issues of shared importance	4
R2: Youth and communities vulnerable to violent extremism demonstrate increased resilience to violent extremism influencers	3
R3: Those most affected by social trauma (CRSV/Missing) of conflict receive the necessary support to reintegrate into daily life	4
R4: Increased acknowledgment and accountability of crimes committed in the conflict	3
R5(T): Increased ability of vulnerable communities to cope with the immediate impact of C-19 crisis	U
Overall Scale of Outcome Delivery	4
[1] For the purposes of this annual review (AR), the report template has been altered to match the Stability Programme’s results framework. AR ‘Outputs’ have become ‘Outcomes’ and AR ‘Outcomes’ have become ‘Higher Outcomes’.

Higher Outcome Assessment	There is good evidence at Outcome level and from across the portfolio of projects that make up the Programme that progress towards the Higher Outcomes was made in 2020/21. This was achieved despite significant challenges to the Programme’s effectiveness and the resilience of the teams managing projects across the region.
Overall Higher Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	B	A	B	A	B	4	Amber
Risk Rating	Medium/ / Low	Medium		Medium		Medium		Medium/ / Low
Programme changes during this period		A new Theory of Change and Results Framework were developed for 2020/21 and following the emergence of the COVID-19 (C-19) pandemic, the Programme was reprioritised and many of its projects adapted to respond to C-19 impacts.
Note: a output scores; b output / outcome scores; c scale of outcome delivery / higher outcome progress rating

What Support Did the UK Provide in FY 20/21?
The Stability Programme spent £13.48m in 2020/21 across 36 projects covering six countries in the Western Balkans in support of building citizens’ trust in the functioning of the state and judiciary, and increased community/societal resilience to divisive discourse.

Key Results for FY 20/21:
- In BiH, of the 67 women that participated in the ‘More Than A Quota’ programme, 63 ran for local elections and 29 were elected.
- In BiH project activity persuaded the government to adopt the UN Committee Against Torture’s 2019 ruling that the state was responsible for compensating survivors of conflict-related sexual violence (CRSV) if there was no reparation by an offender.
- Project activities provided the only source of information on results on the night of Montenegro’s August 2020 elections, contributing, as part of multi-dimensional UK support, to a peaceful transition of power for the first time in 30 years.
- In Kosovo, because of push from the UK seconded expert, the secretariat overseeing the implementation of the strategy against informal economy, money laundering and financing of terrorism met for the first time in five years.
- In Kosovo, a key step was taken towards improving the quantity and quality of translation from Albanian into other official and minority languages, improving minority groups’ access to and engagement with the state, with revision of regulations of the Language Centre at the University of Pristina.

Key Lessons
- Capacity to be flexible and adaptive: The Programme’s ability to respond effectively to C-19’s impacts demonstrated the benefits of adaptive programming.
- Need for greater policy prioritisation: Tension between the regional Programme’s aims of common objectives for the region and country priorities means that a different structure for programming in the WB could be beneficial.
- Administrative/management burden: While Posts reported that they were not under-resourced, having fewer, larger projects would be a more efficient use of resources.
Key Recommendations for FY 21/22:
- Overhaul how progress towards the Programme outcomes is monitored.
- Analyse costs versus benefits of contracting out management of parts of the Programme to deliver better synergy across projects, produce more measurable results and reduce the administrative burden across the Network.
- Consider the programme’s approach to CRSV and missing persons through the lens of strengthening community inclusion, to build resilience against future conflict while encouraging other donors to support some of the projects previously funded by HMG.
- Identify and seek to adopt learning from the programme’s C-19 response and embed learning generated on adaptive management throughout the Network.
- Keep under consideration the regional platform approach under Outcome DJ1 currently on hold, given the possibility of a future emphasis on Open Societies programming.