PROSPERITY FUND – INDIA
BUSINESS CASE
18/03/2019

Title: / ECONOMIC REFORM & PROSPERITY PROGRAMME
Project Purpose: / To deliver inclusive economic growth and poverty reduction in India and increased bilateral trade and investment between India and the UK.
Programme Value: / £60 million (initially)		Country/ Region: / Indifa
Project Code:	Start Date: / 1 September 2017	End Date: / 31st March 2023
Approval by PF Portfolio Board	Submitted: / 15 March 2017	Approved: / 21 March 2017
Approval by IIOC at SBC	Submitted: / 31 May 2017	Approved: / 31 May 2017
Approval by IIOC at OBC	Submitted: / 1 November 2017	Approved: / 1 November 2017
Approval by FCO Management Board (write-round)	Submitted: / 2 November 2017	Approved: / 24 November 2017
Approval by EXCO	Submitted: / 1 December 2017	Approved: / 14 December 2017
Approval by FCO Ministers	Submitted: / 15 February 2018	Approved: / 20 February 2018
Approval by HMT / Approval by CO (+£10m contracts)	Submitted: / 26 February 2018	Approved: / 23 March (HMT); 4 April (CO)
FBC with Financial Services Commercial Case approved by IIOC	Submitted: / 5 December 2018	Approved: / 12 December 2018

EXECUTIVE SUMMARY
Rationale / India’s economy has grown more than ten-fold since the 1990s. The opportunities for creating mutual prosperity for India and the UK by driving sustainable, inclusive economic growth are rising. However, there remain significant challenges. GDP per capita remains low at around $2,000. India is the third largest emitter of greenhouse gases and is one of the countries most vulnerable to the impacts of climate change. India a challenging place for businesses to set up and operate. How India continues to grow and develop impacts not only its 1.3 billion citizens, but how the planet responds to global challenges such as climate change and biodiversity threats. / The Economic Reform and Prosperity Programme in India provides technical assistance to address current market failures and weaknesses that impede India’s inclusive economic growth, reducing poverty in India, addressing global challenges such as climate change, and unlocking increased prosperity for both the UK and India. / What is the focus of the programme? / The programme focuses on where the UK’s expertise and strengths match India’s reform priorities and development needs. These include climate and green growth (including working with India on taking a sustainable, low carbon approach to urbanisation) and advocating free and fair trade through work on ease of doing business, skills, and financial services. The areas of focus are also well aligned with UK commercial strengths as identified by DIT. / Energy & Low Carbon (£10m) – We are working with India to address climate change and promote clean energy, supporting the UK’s ambitions as the hosts of COP26. The programme focuses on working with India to expand use of renewable energy, increase energy efficiency and the use of electric vehicles, and support green finance mobilisation. / Urban Development (£12.4m) – Helping key Indian cities design major infrastructure projects to tackle the significant environmental and poverty challenges they face, reducing CO2 emissions and creating opportunities for UK and international companies. By focusing on cutting-edge projects in selected cities, we aim to create a demonstration effect for others. / Ease of Doing Business (£8.2m) – This programme aims to improve India’s business environment to unlock economic growth within India and open opportunities for UK and international programmes. We are building government capacity and supporting the implementation of improved administrative systems in the areas of market regulation, trade facilitation, tax and e-governance. / Skills (£4.7m) – We are supporting the Government of India’s ‘Skill India’ initiative by developing the skills market in mutual priority sectors through institutional capacity building, promoting international standards and demonstrating sustainable commercial models for the provision of high quality skills training. / Financial Services (£6.55m) – Helping India to develop and reform its financial markets. Well-functioning financial services are crucial for India’s growth and is an area of UK expertise. In particular, the programme focuses on developing the markets in pensions and insurance, through the use of FinTech. This strand supports the implementation of India’s new bankruptcy law – one of India’s most significant economic reforms. / Activities: / There are four broad types of activity to deliver the programmes: (i) capacity building of government, institutions, and labour market; (ii) policy reform of market regulations, frameworks and standards; (iii) market development via demonstrating new technologies and commercial models and project/ investor pipeline development; and (iv) partnership coordination including commercial ventures. / What are the expected results? / We have already had some strong outcomes. Scoping work for the Tranche 1 Energy programme has led to the UK building a partnership with India on electro-mobility. As a result, a UK electric vehicle charging company is setting up smart charging points in India that will help reduce transport sector emissions and in bringing healthier air to cities across India. The financial services strand has led to a successful UK partnership with India to design its new insolvency regime, which has been crucial to tackling India's acute banking crisis and which has already unlocked billions of capital for new investment that will help drive India’s growth. / Going forward, development or primary benefits are expected to include: / Improved trade and business environment (what metric for this?); / Better functioning financial markets including an increase in the value of long term financing (bond and equity); / Better skilled labour market via improved training and accreditation capacity (approx. 1m learners benefitting); / Better functioning energy markets and up to 0.8GW additional cleaner generating capacity; / Increased investment in urban infrastructure. / Commercial benefits to the UK are also expected during the same period: / Improved business environment and labour supply in India for UK firms and investors; and / Additional UK-India trade and investment opportunities. / How will the programme be delivered? / The programme is primarily delivered through each strands’ single multi-million pound multi-year contract using Primary Service Delivery Partners (PSDPs) with relevant expertise. Alongside these are smaller, shorter ‘Tranche 2’ projects. / The programmes take place at central government level and with a small number of high potential Indian city and state governments, where it is assessed that the impact will be greatest. To maximise value for money and impact, the majority of our state engagement will be focused within seven priority Indian states. We continuously monitor and review progress and adapt the programmes where necessary to ensure that they continue to deliver value for money and impact. / The UK’s network of Deputy High Commissions in India play an important role by i) using local knowledge to inform development and leverage synergies across programme strands in the focus states and ii) using their local presence and networks to support delivery. / Risks to success, including covid / Risks to the effective delivery of the programme’s impacts have been anticipated, tracked, and mitigated wherever possible. These are set out in the relevant section, and include: / Changes in state or central host governments and their priorities leading to reduced engagement. Mitigated by targeting systemic issues with high demand and cross party consensus, and developing programmes in close consultation with relevant ministries. / Delays in procurement due to challenges in the PF Framework Agreement, or capacity of team to manage numerous tenders concurrently. Mitigation includes building capacity of in-country team to relieve burden from CPG centrally. / Implementer weaknesses leading to delays or poor quality delivery. Mitigation by rigorous selection, contracting, and monitoring arrangements througout. / Weak private sector response, particularly take up of secondary benefits. Mitigated through private sector engagement and consultation to ensure the programme is delivering what businesses want and there is sufficient demand for take-up. / Change of resourcing needs for delivery of the PF India programme as it moves into the next phase of delivery. Resource structure, capacity, levels and skills will be kept under review to ensure the team and individuals are fit for purpose for delivering best practice programme management and technical oversight and impact. / Originally unanticipated issues have been the direct and indirect impacts of covid: / The most immediate direct effect was India’s sudden national lockdown and the move to remove working and virtual rather than physical engagement. / The portfolio moved swiftly to adapt programme delivery to changed priorities. For example by incorportating pandemic resilience into the Urban Development criteria, and considering the pandemic’s impact on delivery of financial serves. This is ongoing, and changes are set out in detail in the relevant Annual Reviews. / A significant indirect effect has been the impact on UK GNI, and the consequent ODA budget reduction. The India PF took this opportunity to streamline and prioritise elements of the programme, taking into account delivery to date and time remaining in which to delivery. As such, of the original portfolio budget of £60m, Energy & Low Carbon strand was reduced by £10.5m, and Financial Services by £1.65m, giving a revised total of £47.85m. The analysis throughout is based on the original allocation, except where commercial updates are indicated. / Reader’s note: The content of this Business Case was written between 2017-18 and reflects the analysis made with the information at the time. Despite some contextual changes, the analysis, main problems to be addressed, and proposed solutions remain valid. Some sections, in particular the Commercial Case for each strand, have been updated as commercial delivery models have been confirmed. The dates of these updates are indicated in the Contents and headers. / This document was written before the merger of FCO and DFID into FCDO, and therefore contains references to these organisations as separate.

CONTENTS

ACRONYMS
AMRUT	Atal Mission for Rejuvenation and Urban Transformation
BDS	Business Development Support
BEIS	Department for Business, Energy and Industrial Strategy
BHC	British High Commission
CSR	Corporate Social Responsibility
DHC	Deputy High Commission(er)
DIT	Department of International Trade
GDP	Gross Domestic Product
GoI	Government of India
HMG	Her Majesty’s Government
HMRC	Her Majesty’s Revenue and Customs
IDA	International Development Act
ILO	International Labour Organisation
IMF	International Monetary Fund
INR	Indian Rupee
IUKFP	India-UK Financial Partnership
IUKUP	India-UK Urban Partnership
KPIs	Key Performance Indicators
MoU	Memorandum of Understanding
NCR	National Capital Territory
NIIF	National Infrastructure Investment Fund
NSC	National Security Council
ODA	Official Development Assistance
OJEU	Official Journal of the European Union
PFDU	Prosperity Fund Delivery Unit (FCO)
PFMO	Prosperity Fund Management Office (Cabinet Office)
PSDP	Primary Service Delivery Partner
RBI	Reserve Bank of India
RCUK	Research Councils UK (now UK Research & Innovation, UKRI)
RDD	Regulatory Delivery Directorate (part of BEIS)
SAAD	South Asia and Afghanistan Directorate (FCDO)
SDG	Sustainable Development Goals
SME	Small Medium Enterprise
SRO	Senior Responsible Officer
UKEF	UK Export Finance
UKIBC	UK-India Business Council
UKIERI	UK-India Education and Research Initiative
UNFCCC	United Nations Framework Convention on Climate Change

STRATEGIC CASE

Context
India is the seventh largest economy in the world ($2.4tr) and the third largest by purchasing power ($8.0tr)[1]. However, India’s middle income status has not yet translated into an end to poverty and the country still faces huge inequality and development challenges.
[1] World Bank (2015), India country data

A1. Economic structure and performance
1. India is the world’s fastest growing major economy, projected to become the third largest economy in the world after China and the USA by as early as 2030[2]. Growth in output has been driven by the services sector whose share rose to almost 60% of GDP in 2014 from less than 50% in 2000, while agriculture dropped to below 20% (fig. 2). The contribution of industry has been relatively stable at around 25%[3].
  [2] Centre for Economics and Business Research (2015), World Economic League Table 2016
  [3] Govt of India Planning Commission via Statistics Times (2015), Sector-wise contribution of GDP of India
2. A vibrant private sector has driven increases in investment and capital formulation. While India has benefited from a strong and relatively stable domestic consumption base (about 59% of GDP in 2014), the period of rapid economic growth is explained by rising investment and capital formation, from 21% of GDP in 2002 to 38% in 2012. Private sector drove much of this, with its share of capital formation doubling from 22% in 2003 to 44% at its peak in 2008[4].
  [4] Indian Central Statistics Organisation (2015)
3. Important economic and structural reforms have been initiated, but further reforms are needed to boost India’s growth potential. Since May 2014, the Indian Government has gradually introduced numerous economic reforms including subsidy reforms, steps to create more flexible labour and product markets, agricultural reforms (including the new crop insurance scheme), enhancing financial inclusion, relaxing FDI limits in several key sectors and improving the ease of doing business, raising Foreign Portfolio Investment limits in public debt securities, and increasing public infrastructure spending. Flexible inflation targeting was also adopted by the Reserve Bank of India (RBI) in February 2015. Reform has not always been easy and the passage of some key legislation has been stalled or delayed[5].
  [5] Ibid.

A2. Poverty analysis
Despite its positive economic growth story, India still faces enormous development challenges:
- India is home to one third of the world’s extreme poor (circa 300m people)[6];
  [6] UN (2015), India and the MDGs: Completing the Task
- India ranks 131th on the UNDPs Human Development Index[7];
  [7] UNDP (2015), Human Development Report
- India ranks 100th on the Global Hunger Index, out of 119 (in the ‘Serious’ category)[8];
  [8] International Food Policy Research Institute (2017), Global Hunger Index
- 240m Indians have no access to electricity[9];
  [9] International Energy Agency (2016), World Energy Outlook 2016
- India is already the third largest carbon emitter and is set to double emissions by 2030[10];
  [10] World Resources Institute (2015), CAIT climate data explorer
- Inequality is high and increasing. India’s Gini coefficient of inequality is 51, up from 45 in 1990, and amongst the highest in Asia[11].
  [11] IMF Working Paper (2015), Sharing the growth dividend: analysis of inequality in Asia
1. Maintaining India’s growth will be important for continued poverty reduction. India’s phase of high growth from 2002 to 2012 has seen a reduction in poverty reduction both in ratio and headcount terms. Poverty measures in India vary, but although estimates differ, all agree that the trajectory has been strongly downward. World Bank data indicates that the extreme poverty rate (people living on less than $1.90 per day) fell from 46% in 1993 to 38% in 2004, and then faster to 21% in 2011. The absolute headcount has fallen from over 400m in 2004 to less than 300m today[12]. India’s official poverty figures are similar[13].
  [12] World Bank (2016), Poverty and equity databank
  [13] Planning Commission of India (2013), Poverty estimates
2. Reduction in extreme poverty has been associated with high GDP growth rates across most Indian states. However, some groups have benefited less than others. In particular, five segments, while having seen improvement in living standards, have lower incomes, productivity or access to services than others: (i) GDP growth in rural and transition districts was slower than semi-urban and urban districts; (ii) workers reliant on agriculture experienced lower productivity than non-farm workers and the same was true for workers in small enterprises (with less than 50 employees) compared with those in enterprises with more than 200 employees; (iii) women are grossly under-represented in the labour force; (iv) Scheduled Castes, Scheduled Tribes and Muslims continue to have a higher proportion of people in extreme poverty; and (v) eight India states are identified as low income states[14] reflecting significant differences at a district level despite increased government spending on social programs.
  [14] Bihar, Chhattisgarh, Jharkhand, Madhya Pradesh, Odisha, Rajasthan, Uttar Pradesh and West Bengal

A3. Social-political context
1. India is the largest democracy in the world, with a population of 1.3bn people, and forecast to become the most populous by 2022. It has a well-established competitive democratic system which has facilitated regular peaceful regime changes over the past six decades.
2. India’s federal system means considerable power rests at the state level. A large number of areas for legislation, apart from near-comprehensive administrative powers, are vested in states, and 32% of shareable central tax receipts flow back to the states to be dispensed per their priorities. The direction of travel is towards greater devolution of powers which, together with an increased focus on growth, is encouraging a form of competitive federalism. The federal system in India also allows scope for the co-existence of different political settlements at state and national levels[15].
  [15] Sen, Kar, Sahu (2014), The political economy of economic growth in India, 1993-2013 (Effective States and Inclusive Development Research Centre, University of Manchester)
3. A difficult regional political economy constrains effective cross-border integration on issues like trade, connectivity and water, which could increase economic and resource security in the whole subcontinent and beyond. These challenges consistently drive India’s position on key global development issues in international fora.
4. Women’s rights remain an issue with India ranking 131th on the Gender Inequality Index[16]. India’s female work force participation, at 29%[17], is one of the lowest in the world and women constitute only 10% of the total number of entrepreneurs[18]. According to a report by McKinsey, India could add $700 billion of additional GDP by 2025 – upping the country’s annual GDP growth by 1.4% – by ensuring gender equality alone[19].
  [16] UNDP (2015), Human Development Report
  [17] World Bank (2016) – Women, Business and Law.
  [18] M. Balaji et all: Women Entrepreneurship - Opportunities and Challenges in South Asia; IJEMLS, 2016.
  [19] McKinsey (2015), The Power of Parity: Advancing Women’s Equality in India

Development Constraints
High administrative burden on businesses, including trading across borders
1. India’s complex regulations, rules and procedures pose a significant cost, especially for micro, small, and medium sized businesses, discouraging both investment and their move into the formal economy. For example, it takes some 1,400 days to enforce a contract in India, as opposed to 500 days in the average Organisation for Economic Co-ordination and Development (OECD) country. Getting a construction permit requires 35 procedures in India (versus 16 in South Asia). The World Bank ranks India 100th on its overall Ease of Doing Business Index (a significant improvement from 131 in 2016)[20]. A study in 2015 focused on Asian economies has demonstrated that Ease of Doing Business has a significant effect on economic growth, with trading across borders identified as the single most important factor, implying that India’s poor performance is a significant growth constraint[21].
  [20] World Bank (2017), Ease of Doing Business Index
  [21] Asia Pacific Journal of Multidisciplinary Research, vol.3, no.5 (2015), Effect of ease of doing business to economic growth among selected countries in Asia
2. Prime Minister Modi has set a target of improving India’s overall Ease of Doing Business ranking to 50 by 2020. This will require India’s state and central governments to implement a road map for administrative reform, starting with quick wins to improve business sentiment in the near term, such as electronic platforms for business-related interactions with government, and more robust reforms in the medium to long term, such as performance management systems for the bureaucracy and phasing out outdated legislations. It would also need more women responsive systems including norms of paid-in minimum capital and ways of registering business and property as well as access to information on product and services tailored to women owned enterprises to help more women enter the market and promote their businesses. Achieving this would require addressing limited state capacity to reform, regulate and implement regulations.
Inadequate skills and productivity in the workforce
1. Less than 10% of India’s workforce has any vocational training, compared to 68% in the UK[22]. There is significant shortage of vocational, technical and professional skills training capacity. Around 12m people are expected to join the workforce every year over the next decade, yet India only has a total training capacity for around 4.3m[23]. Moreover, evidence suggests a serious gap between the output of existing skill development institutions and industry requirements. For example, out of around 0.4m engineering students graduating every year in India, only 20% are readily employable. As a result, by 2020 India is expected to face a shortage of 13m medium-skilled workers, posing a big impediment to labour-intensive sectors[24]. 67% of employers in India struggle to find workers that meet their requirements[25]. The National Policy on Skill Development and Entrepreneurship 2015 estimates an incremental requirement of about 110m skilled personnel in 24 key sectors by 2022. Tackling this skill shortage is vital for economic growth and for poverty reduction, particularly amongst women whose labour force participation is only 29%, compared with 80% for men[26].
  [22] EY (2012), Knowledge paper on skill development in India: learner first
  [23] EY / FICCI (2014), Reaping India’s promised demographic dividend – industry in driving seat
  [24] Ibid.
  [25] ICEF Monitor (2013), To upskill 500 million workers, India goes international
  [26] ILO (2013), India: why is women’s labour force participation rate dropping
2. Achievement of the Government’s ambitious skilling targets requires integrated delivery at State level, industry participation, establishing quality standards, developing a pool of trainers, integrating skills with education, and inclusion of women and the informal sector[27].
  [27] EY / FICCI (2014), Reaping India’s promised demographic dividend – industry in driving seat
3. At the same time, India faces the challenge of job creation. Research by the Asian Development Bank suggests that in India: (i) very small establishments seem unable/incapable of expanding, i.e. the transition from micro to small enterprise; and (ii) the transition from small to medium size also seems difficult. As a result the Indian economy is characterised by many very small enterprises and a “missing middle” in comparison with other middle income countries in the region. This impedes growth and productivity: literature suggests average wages and labour productivity are much lower in small firms compared to large firms[28]. Labour productivity in India is around $3,000 per employee per year; in the United States it is around $155,000[29].
  [28] ADB Economics Working Paper Series (2010), The distribution of firm size in India: what can survey data tell us?
  [29] Business Standard (14/03/13), Low labour productivity harming manufacturing in India: Boston Consulting Group
4. India is poised to become the world’s youngest country by 2020, with an average age of 29 years, and account for around 28% of the world’s workforce[30]. Overcoming the skills and productivity constraint will unlock this demographic dividend and drive global growth and prosperity over the next decades.
  [30] EY / FICCI (2014), Reaping India’s promised demographic dividend – industry in driving seat

Incomplete financial markets
1. India realises less than its potential for domestic resource mobilisation because of incomplete markets in financial services and instruments. Despite a very respectable savings rate (c30%), India is not able to translate this into productive investment because of imperfect capital markets and inadequate financial instruments. Most savings therefore go into assets like gold or property – with inflationary impact – rather than into e.g. infrastructure investment. As a result, access to finance is a major constraint to India’s growth across all sectors of the economy, particularly large-scale project financing. Companies (both Indian and international) also struggle to navigate issues around insolvency; India ranks 52nd on the World Bank’s Resolving Insolvency index[31].
  [31] World Bank (2018), Ease of Doing Business Index
2. Meanwhile, as of 2017, the World Bank’s Global Findex data highlights that the Government of India through its hugely successful Jan Dhan drive has resulted in more than 320m bank accounts opening and 80% of adults in India now having an account. However, nearly 38% OF bank accounts in India have been inactive in the past year compared to 12% in China and 3.8% in advanced economies[32]. This significantly impairs the ability of the poor to receive financial benefits, access credit, and for income. The Intermedia Financial Inclusion Insight Survey (2017) of 47,000 Indian adults found that 3% had access to mobile money, compared to 87% in Kenya, 61% in Uganda, and 45% in Bangladesh[33]. The use of digital money may have gone up in the wake of the 2016 demonetisation of high value currency notes, however use of mobile money still remains low compared with many other developing countries.
  [32] World Bank (2017), Financial Inclusion Data / Global Findex
  [33] CGAP (2015), 2015 Set to be Big Year for Digital Financial Inclusion in India http://www.cgap.org/blog/2015-set-be-big-year-digital-financial-inclusion-india
3. Deepening of financial markets, including attracting further international capital, as well as improving access to international sources of finance and improving resolution procedures will be critical to addressing the macro constraint. At the same time improving pension coverage, access to and delivery of financial technology, and insurance markets will help deliver greater security across social groups and enable them to contribute more effectively to inclusive growth across India. In particular inadequate flows of finance towards the service sectors predominated by women and the high administrative costs of extending and recovering small loans act as major barriers to financial inclusion. A decade ago, McKinsey estimated that with full financial services reform and liberalisation, India’s GDP could expand by an additional 3% per year[34]. Progress has been made since then, but there is still work to be done.
  [34] McKinsey Global Institute (2006), Accelerating India’s growth through financial system reform

Inadequate and high carbon energy supply
1. India needs energy to power its rapidly growing economy and meet the needs of a young and aspirational population with a growing middle class but also a massive residual off-grid population. There is structural dependence on imported supply (32% of primary energy supply was imported in 2013, including 82% of oil consumed in the year 2013) and fossil fuels (73% of primary energy demand is met from coal, oil and gas consumption)[35]. The International Energy Association estimates that $3.6 trillion of investment is needed by 2040[36].
  [35] IEA (2015), World Energy Outlook 2015 – Factsheet India
  [36] OECD/IEA (2015), World Energy Outlook Special Report – India Energy Outlook
2. India’s energy consumption per capita is only around one-third of the global average. Some 240m people have no access to electricity[37]. Women are particularly disadvantaged; for example, women-led businesses face more impediments in accessing grid electricity[38] and household electrification benefits women less as they continue to use wood fuel for cooking and heating[39].
  [37] International Energy Agency (2016), World Energy Outlook 2016
  [38] Gender and Energy; Training Module four, UNDP, 2013.
  [39] Gender Tool Kit Energy: Going beyond the meter, Asian Development Bank; 2012.
3. India’s power deficit is a huge barrier to growth. Estimates of the costs to India’s economy vary from 0.4-0.7% of GDP[40], [41]. India is already the world’s third largest greenhouse gas emitter and emissions growth is among the highest in the world[42]. India’s industries and cities are on a high carbon path, with associated impacts on environment and health that India will struggle to pay for. Vulnerability to climate risks are also growing. Cleaner energy offers multiple benefits for powering India’s growth, boosting indigenous supply security, and expanding delivery to unconnected citizens in ways that offer less negative impacts than hydrocarbons.
  [40] FICCI (2013), Power transmission: the real bottleneck
  [41] World Bank feature story (2010), India’s power sector
  [42] BP Energy Economics Statistical Review (2015)
4. India recognises the challenge and government is taking action to manage expansion in energy supply with a target of $1trillion investment in the energy sector by the 2030[43]. India also sees the potential security-sustainability synergies of a lower carbon growth model. India has ratified the UNFCCC Paris Agreement, with a commitment to reduce emissions intensity by 33-35% from 2005 levels. The key measures underpinning this are a significant rise in the share of non-fossil fuel energy (40% levels through renewables and nuclear), energy efficiency and afforestation.
  [43] India Power Minister quoted (2016) - http://www.livemint.com/Industry/I0XF1duNziNZ4axD9gWNCN/1-trillion-investment-in-power-sector-by-2030-likely-Piyus.html
5. To achieve this, concerted action in four linked areas is needed:
1. Clarify and implement a roadmap for India’s transition to a low carbon economy, especially in context of the country’s federal system, complex institutional arrangements and nascent culture of consultative policymaking between governments, businesses and citizens;
2. Reform the policies and regulations needed to improve the conditions for investment by reducing transaction costs and improving incentives, pricing and procedures for procurement, approvals and clearances as well as institutionalising gender within the energy policy making and management systems;
3. Accelerate the development of pipelines of viable and sustainable projects;
4. Broaden the range of investors and finance sources (especially private sources such as long-term debt finance and institutional investor capital) and reducing the cost of capital.

Unplanned urbanisation and inadequate core infrastructure provision
1. India’s infrastructure gap, especially in power and transportation, hinders economic growth most notably in the manufacturing sector. India has historically under-invested in infrastructure relative to its pace of growth. From 1992 to 2010, infrastructure spending constituted 4.7% of GDP, compared with 7.3% across countries like China, Indonesia and Vietnam[44]. A lack of adequate focus on infrastructure investment in the past is reflected in India’s ranking of 87th out of 144 countries in the World Economic Forum’s (WEF’s) Global Competiveness Report 2014-15 in terms of infrastructure quality. The report identifies ‘inadequate supply of infrastructure’ as one of the most difficult factors in doing business in India[45]. As a result logistical costs in India are two to three times current global benchmarks, a distinct disadvantage for manufacturers[46]. The World Bank notes that a mere 0.5% decrease in logistics costs could result in a 2% increase in trade and 40% increase in the range of exported products[47].
  [44] City of London Corporation (2015), Attracting private capital for Indian infrastructure – rejuvenating and expanding the PPP programme
  [45] World Economic Forum (2014), Global Competitiveness Report 2014-15
  [46] World Bank (2014), India Development Update
  [47] Ibid.
2. As a result the provision of basic urban services is also poor. India’s urban population has increased from 222m (26% of the population) in 1990 to 410m (32%) in 2014 and is expected to reach 814m (50%) by 2050. Total investments of at least $640bn are needed for urban infrastructure and services until 2031 to meet the needs of the growing urban population and improve the standard of living of the existing urban population[48]. Handled well, cities have the potential to generate 70% of India’s new jobs and produce 70% of India’s GDP by 2030[49]. Smaller cities also serve as the link between larger markets and rural areas, as medium sized cities become centres of manufacturing.
  [48] World Economic Forum (2015), The future of urban development and services: urban development recommendations for the government of India
  [49] McKinsey Global Institute (2010), India’s urban awakening: building inclusive cities, sustaining economic growth
3. However, poor coordination between various ministries and departments leads to delays in project implementation as projects face land acquisition difficulties, right of way constraints, and slow environmental clearances. Often there is no integrated planning, leading to mismatches between elements of the value chain (such as generation and transmission in the power sector, inadequate fuel supply linkages for approved power plants, and lack of off-take from state utilities companies due to tariff regulations at the state level). PPP models in infrastructure have not been robust and/or not enforced. In the web of bureaucratic dependencies, Infrastructure providers are often not held accountable for project delays and cost overruns and there is a perception of asymmetrical risks and returns. Lack of effective and transparent public procurement, contract enforcement and delayed or non-payment of goods and services are challenges that need to be addressed[50]. Two surveys conducted by the WEF among business leaders and international investors revealed that both groups consider funding and financing, as well as policy and regulation, as main obstacles to investing in India[51].
  [50] UK-India Business Council (2015), Doing business in India: the UK perspective
  [51] World Economic Forum (2015), The future of urban development and services: urban development recommendations for the government of India
4. Estimates suggest that a lack of proper infrastructure pulls down India’s GDP growth by 1-2% per year[52]. The Government of India is committed to raising $1 trillion of finance for infrastructure over the medium-term. In June 2015 PM Modi launched the ambitious 100 Smart Cities Mission (2015/16-2019/20) which aims to turn 100 cities into engines of inclusive economic growth and job creation. Over four years the Government will provide INR500 crore (approx. £6m) to each selected city to implement their approved urban proposals. State governments are also required to match fund the central government’s allocations. Additional financing will still be required to implement the projects and is expected to be sourced through Public Private Partnerships, multilaterals and municipal bonds. In the same year the Atal Mission for Rejuvenation and Urban Transformation (AMRUT) was launched. This programme aims to provide urban solutions related to water and waste management, green spaces and pollution. Other smaller urban schemes with attached funding include Housing for All; Swachh Bharat Mission; Digital India; and HRIDAY. With all these schemes, additional financing will be required for full implementation. Funding is expected be sourced via through Public Private Partnerships, multilaterals and municipal bonds.
  [52] Agrawal, Pradeep, ed.(2015), Reviving Growth in India

The Case for the UK as a Development Partner
C1. Why India is important
1. The UK and India have a shared history, a thriving modern partnership and a bright future. The National Security Council (NSC) has committed us to develop a strategic partnership with India based on shared prosperity, security and the links between our peoples. The Prosperity Fund is a critical tool for making that happen. The ambition to strengthen and deepen our engagement with India’s economy matches HMG’s ambitions to place India at the heart of the strategy for a Global Britain.
2. At the heart of our prosperity ambitions is the bilateral commercial relationship with India that delivers huge amounts today. India is the fourth largest investor in the UK and the second largest job creator (second only to the US)[53]. At the same time we are the largest G20 investor in India and UK trade with India exceeds £15bn – we export more to India than to any other ODA-eligible country except China. But there are challenges, and although India’s economy has grown impressively, lifting many out of poverty, it remains home to one third of the world’s poor. A prosperous and secure India is also seen as an essential element for successful growth in neighbouring countries (Nepal, Pakistan, Burma, Afghanistan, and Bangladesh) – also priority countries for the UK.
  [53] UKIBC (2015), India and Britain: making great things together
3. The interventions set out in this programme are designed to respond to key economic development challenges including economic reforms, which will improve the business environment and support better functioning markets, as well as improvements to infrastructure delivery. Our programme responds to India’s economic development priorities embodied in PM Modi’s key initiatives (including Make in India, Smart Cities, Start-up India, Skill India, and 24x4 Power for All) and the ambitious targets he has set (such as raising India on the World Bank’s Ease of Doing Business ranking from 100 to in the top 50 and installing 175 GW renewables by 2022). We have also taken into account UK expertise and strong potential for high value (commercial) opportunities.
4. We have therefore designed a programme that will both support India’s reforms and create opportunities for UK business, maximising the benefit to both our nations. This approach will have a direct and positive impact on helping the UK achieve its goal of improving the relationship with India and in doing so improve the potential to deliver secondary benefits for the UK. In short, promoting India’s economic growth is in the UK national Interest.
5. If the UK does not intervene, the counterfactual scenario for India is a lower growth rate related to business environment reforms in the targeted states, lower quality of skills training delivered and lower growth rate in SMEs, smaller annual increase in the size of the Indian bond market, lower levels of cleaner energy brought online and over a longer time-frame and significantly less investment in urban infrastructure with less likelihood of this delivering ‘smart cities’ (see Economic Appraisal for full details).

C2. Alignment with UK policy and strategies:
1. The India PF Programme is a central pillar of our NSC strategy for India, combining policy advocacy, technical assistance, and commercial outcomes as part of a wider drive to secure the UK’s long term strategic partnership with India. It will focus on the two most critical enablers that underpin the capacity of the Indian economy (Ease of Doing Business, Skills, and Entrepreneurship) and three key interlocking sectors that will determine our shared prosperity (Financial Services, Energy & Low Carbon, and Cities).
2. All five themes are driven by India’s inclusive growth diagnostic, speak to PM Modi’s reform agenda, and match UK expertise to requests from the Indian Government for our support.

C3. Where can the UK add value?
1. The UK is well placed to support India’s next phase of growth. In particular, several of the areas that are constraining India’s continued development are strongly aligned with UK areas of world-class expertise and are areas where the Indian government has requested our support which make them a good fit for the PF programme. These are: Ease of Doing Business, Financial Services (including entrepreneurship), Energy and Low Carbon, Urban Development, and Skills.
2. The UK has a strong history of supporting India’s development and economic growth through government ODA programmes and trade and investment between the two countries. In addition, the UK is the largest G20 investor in India and creates more jobs in India than any other G20 nation: between 2000 and 2015, UK FDI worth US$22.2bn has generated around 138,000 direct jobs, 7% of the 1.96m jobs generated by FDI in India[54]. Taken together – UK expertise, our historic development support, our networks, and our commercial interests – gives us an excellent understanding for how to work with India and extensive outreach which will be critical to the success of this programme.
  [54] CBI (2015), Sterling Assets India: UK investment creating jobs in India

Ease of Doing Business
1. The UK can assist India to improve its business environment to attract investment and increase trade, and in doing so support Modi’s ‘Make in India’ campaign. While India ranks 100th on the World Bank’s Ease of Doing Business index, the UK ranks 7th[55]. This high ranking is a result of a real political focus on improving the UK ranking; the UK has been a world leader in costing new regulation, abolishing unnecessary administrative burdens and consolidating government requirements, including online. For example, the UK has introduced a ‘One in Three Out’ approach to new regulations and the UK’s ‘Cutting Red Tape Programme’ allows businesses to tell Government how it can reduce bureaucratic barriers to growth and productivity within sectors. The World Bank ranks the UK as 28th out of 190 economies on its Trading Across Borders index. In the UK 92% of goods are released within five seconds; only 6% are subject to documentary checks and 2% subject to physical examination. In comparison India ranks 133rd with high rates of documentary and physical checks.
  [55] World Bank (2017) Ease of Doing Business index
2. The UK has already had a successful PF-funded programme of government-to-government engagement on Ease of Doing Business with India. For the last two years UK experts on better regulation and risk assessment in particular have been embedded in state governments, developing risk assessment toolkits and identifying unnecessary regulation. The UK is the only major economy working so closely with the Government of India in this space, resulting in a Memorandum of Understanding (MoU) on Ease of Doing Business – endorsed by Prime Ministers May and Modi – setting out how the UK will go further in sharing expertise with India. The first joint UK-India Ease of Doing Business Conference was held in Delhi in November 2016 bringing together UK experts in tax, regulation, land registry, trade facilitation and standards with more than 200 senior Indian officials from over 20 states and central government departments to share expertise. India’s Department of Industrial Policy & Promotion cited the UK MoU and UK-India Conference as one of its “major initiatives and achievements” of 2016.

Skills
The UK can work with India to help give young Indians internationally recognised skills, and to provide businesses with the workforce they need to excel. The UK offers cutting edge vocational skills training and innovative ways to structure delivery, including online, to get trainees workforce ready, including English language skills. The UK boasts many of the world’s top universities in the world, a strong apprenticeships focus, experience in quality assurance systems (QAA and SQA etc.) and digital education (Open University since 1971. Future learn since 2012). Other countries including Germany, Singapore and Australia are active in skills development. However, the UK is the Indian Ministry of Skill Development & Entrepreneurship’s most established partner and Prime Minister May announced a new commitment of up to £12m to support India’s Skill India mission, focusing on UK strengths – e.g. assessment and certification – and on sectors of mutual UK-India commercial interest. The UK-India Education Research Initiative (UKERI)
Services & Entreprenuership
The City already focuses on the integration of skills within education.

1. Financial centre of London has an unrivalled depth of capital markets for Indian companies seeking to raise finance – in addition to expertise across supporting industries including pensions, insurance, legal and actuarial – and shares a common law system with the UK. £2.2bn of rupee-denominated bonds were issued by Indian firms on the London Stock Exchange between July 2016 and October 2018, showing that London is the place to raise capital for Indian investment and infrastructure. Although the US, Singapore, and Australia are active on influencing policy, they do not have the same shared legacy, nor a high-level forum similar to the India-UK Financial Partnership that has already developed detailed policy recommendations shared with the Government of India.
2. The UK is also the global FinTech capital, with hubs in London, Edinburgh, Manchester, and Leeds. The industry employs over 60,000 people – more than Singapore, Hong Kong and Australia combined – and contributes £6.6bn annually to the UK economy[56].
  [56] Ernst & Young (2016), UK FinTech: on the cutting edge
3. The UK is consistently ranked among the top ten nations in the world on the Global Entrepreneurship Index and London tops the European Digital Cities Index as the best place to start a digital business[57]. The UK is seen as a launch pad to global markets, with a vibrant network of investors and entrepreneurs and is third in the Global Innovation Index[58]. Prime Minister May committed an additional £20m for a Start-Up India venture capital fund, administered by DFID. The fund will support 30 enterprises and leverage £40m capital from other investors including UK venture capital funds.
  [57] http://www.nesta.org.uk/news/london-tops-list-best-eu-cities-digital-entrepreneurs
  [58] http://www.wipo.int/publications/en/details.jsp?id=4064

Energy & Low Carbon
1. India sees the UK as an important energy partner because of its innovation, skills, and financial services. The UK has valued experience of organising and regulating energy markets, is home to major energy companies, and offers a range of goods and services that have the potential to meet India’s priority needs. India also recognises the UK’s distinctive green credentials (e.g. energy efficiency and decarbonisation).
2. France, Germany, Japan, the US, and others are active but the need is large and the Government of India has requested UK support. To drive forward the next phase of bilateral collaboration on the shared strategic priority of secure, affordable and sustainable energy, Prime Ministers Modi and May noted an enhanced UK-India energy for growth partnership during the latter’s visit in 2016, and welcomed the decision to hold the first India-UK Energy Summit in early 2017. Subesquent Dialogues have affirmed strong collaborative action plans on clean energy, creating demand and support for the actions set out in this Business Case.

Urban Development
The UK has strong capabilities (e.g. transport, water and waste management, smart solutions, design and planning) which can provide effective solutions to India’s needs. Activities in the UK’s current partner cities – Pune, Amravati, and Indore – have already demonstrated strong results. These interventions were all driven by requests from the Indian Ministry of Housing & Urban Affairs (MoHUA) and the relevant state governments. While other countries such as Singapore and Japan are active in urban development, this is a large market with space for a number of players. The UK has the potential to expand its long-standing relationship in urban development and become one of India’s top urban partners. Building renewed momentum, in autumn 2016 Prime Ministers Modi and May announced the India-UK Urban Partnership which will bring together governments, business, investors and urban experts to build smarter and more inclusive cities. The Partnership will be delivered by the FCO, DIT, and DFID – providing a comprehensive and coherent urban UK offer to India.

C3. Commercial opportunities for the UK
1. As a secondary benefit, India offers significant commercial opportunities for UK companies. Ernst & Young estimate that 200m Indians will qualify as global middle class (earning over $10 per day) by 2020[59], other estimates are lower but concur that India’s consumer middle class is growing[60],[61]. India’s population is young and increasingly urban, with 50 cities now housing over a million people. The country also acts as a gateway to other South Asian markets. UK businesses operating in India enjoy the benefit of sharing a common language and shared legal and administrative histories[62].
  [59] Ernst & Young (2013), Hitting the sweet spot: the growth of the middle class in emerging markets
  [60] Pew Research Centre (2015), Despite poverty’s plunge, middle class status remains out of reach for many
  [61] Boston Consulting Group (2012), The tiger roars: capturing India’s explosive growth in consumer spending
  [62] Dept for International Trade (2016), Doing business in India: India trade and export guide
2. India has opportunities in all sectors as it expands and develops. The UK offers goods, technology, services, and expertise in the areas that India has identified as critical for rapid economic development. DIT highlights these as including:[63]
  [63] Ibid.
3. Ease of Doing Business: Wider trade and investment. UK businesses cite legal and regulatory impediments as their greatest barrier to doing business in India; administrative and bureaucratic hurdles around business approvals are costly and time consuming. Regulatory frameworks are viewed as difficult and inefficient, including Intellectual Property[64]. The UK will benefit disproportionately from ease of doing business reforms as the single largest G20 investor in India. British companies account for revenue of over $54bn and almost 10% of all foreign direct investment[65].
  [64] UK-India Business Council (2015), Doing business in India: the UK perspective
  [65] CBI (2015), Sterling Assets India: UK investment creating jobs in India
4. India invests more in the UK than the rest of the EU combined, is the UK’s second largest international job creator, and third largest source of foreign direct investment. Last year India helped to create 140 new investment projects and 7,105 new jobs in the UK[66]. There are more than 800 Indian-owned businesses in the UK, employing more than 110,000 people[67]. This includes the Tata Group, the largest manufacturing employer in the UK. Mahindra too are investing heavily, including in development of next generation electric vehicles. Nevertheless it is smaller and medium sized companies that are fastest growing. Of the 63 Indian-owned companies in the UK growing at over 10% in 2016, 30 were small and 27 medium sized[68]. Encouraging more Indian SMEs to invest in the UK is therefore beneficial to UK growth.
  [66] Department for International Trade (2016), UK still Europe’s top investment destination, with help from India
  [67] UKIBC (2016), UK-India economic relations: the current landscape
  [68] Grant Thornton (2016), India meets Britain: tracking the UK’s top Indian companies
5. Skills: Vocational skills and capacity development. The value of the Indian vocational education sector is estimated to reach US$20n by 2020[69]. Building in international and UK standards will help UK companies to capture some of this market. UK companies also spend an average 7% of their total revenue on training and re-skilling their employees in India[70]. UK companies will therefore benefit from an improved labour supply: 1 in 20 jobs in the formal Indian economy are created by UK companies, largely in higher skilled sectors[71].
  [69] ICEF Monitor (2013), To upskill 500 million workers, India goes international
  [70] CBI (2015), Sterling Assets India: UK investment creating jobs in India
  [71] CBI (2015), Sterling Assets India: UK investment creating jobs in India
6. Financial services contributed approximately 5.7% to India’s GDP in 2017 and is one of the country’s fastest growing sectors. The UK is the leading exporter of financial services across the world. The UK’s trade surplus in financial services was nearly the same as the combined surpluses of the next three leading countries[72]. Reform of India’s financial markets will increase opportunities for the UK’s world class financial services firms including UK majors as well as specialist and FinTech firms. Better functioning financial markets will also facilitate growth in other DIT focus sectors in India e.g. energy, infrastructure.
  [72] The City UK (2018), Key facts about the UK as an international financial centre
7. Energy & Low Carbon. The potential for business partnerships is huge. As the fastest growing major energy market in the world, India’s energy path will be the biggest influence on global energy markets over the next 20 years. Meeting those needs will open major opportunities for international companies. It is estimated that the total market size of relevance to the UK would be at least £1tr by 2022, of which the UK market share could be between £15-30bn[73]. The UK is already the largest overseas investor in India’s energy sector, and has the sixth largest global market share in the low carbon goods and services market[74]. The UK is also strongly placed to tap the opportunities arising on green finance, leveraging the strengths of the City of London as the world’s premier international financial centre. India is now the 7th largest labelled green bond issuer with $2.7bn issued by October 2016. According to the UK-based Climate Bonds Initiative, Indian project developers and financiers plan to raise $5-7bn of green bonds over the next five years, primarily to raise capital for renewables and energy efficiency projects[75].
  [73] ICF International (2016), Internal study for BHC New Delhi [unpublished]
  [74] BIS (2013), The size and performance of the UK low carbon economy
  [75] Climate Bonds Initiative(2016), Bonds and climate change: the state of the market - India
8. Urban Development. Urbanisation in India is expected to reach 40% by 2030, with over 600m people living in urban areas. Smart urbanisation is crucial for India’s development and if handled well its cities could generate 75% of India’s GDP. UK companies find the lack of infrastructure a business constraint and would benefit from its improvement4. India’s cities will require over $1 trillion in capital investment by 2030 in order to meet the projected demand for urban services[[5]]. This commercial opportunity matches the UK’s competitive advantage in design, infrastructure, planning, finance, and climate resilience[[6]. The U]K is also well placed to enhance the business climate and create investable urban projects which attract international business, including UK companies.
  [[5]] McKinsey (2010), India’s urban awakening: building inclusive cities, sustaining economic growth
  [[6]. The U] or International Trade (2016), Doing business in India: India trade and export guide
9. In addition, the ‘100 Smart Cities Mission’ led by PM Modi aims to turn India’s cities into engines of inclusive and sustainable economic growth and job creation. These Indian cities will create an additional estimated market of £25bn by 2022.

Programme Focus
D1. Areas of focus
1. Given the development and growth constraints, areas of UK added value and commercial opportunities identified above, we assess that there is a strong strategic case for focusing on ease of doing business, skills, financial services & entrepreneurship, energy & low carbon, urban & smart cities, and infrastructure.
2. Infrastructure financing is addressed through the UK-India sub-fund of India’s National Infrastructure Investment Fund (NIIF), which forms a separate bid to the PF. The remaining sectors form the Economic Reform & Prosperity Programme, through which we focus on the critical enablers that underpin the capacity of the Indian economy (Ease of Doing Business, Skills) and key interlocking sectors that will determine India-UK shared prosperity (Financial Services & Entrepreneurship, Energy & Low Carbon, and Urban Development).

D2. Programme design
1. The UK Prosperity Fund will provide technical assistance to address market failures that impede India’s growth via improving government capacity and regulation, tackling information and coordination failures, supporting incomplete and missing markets and combating negative externalities and inequality. The resulting better functioning markets will help to drive India’s inclusive growth and poverty reduction and increase bilateral trade and investment.
2. The India Economic Reform & Development programme will support four types of activity:
- Capacity-Building of government, institutions and the labour market;
- Policy Reform of market regulations, frameworks and standards;
- Market Development via demonstrating new technologies and commercial models and developing a pipeline of projects and investors
- Partnership Coordination including of UK-India commercial ventures
The programme will focus on the following sectors:

Ease of Doing Business
1. The PF is the key vehicle for facilitating engagement between the UK and India on improving ease of doing business and will be complemented by DFID India’s work in this space. The PF programme will assist the Government of India to improve the business environment by using UK government expertise to build capacity within Indian state and central government departments and support them to implement reforms in the areas of business regulation, tax, trade, and land registry. This will build on the existing Ease of Doing Business programme which has already seen notable success.
2. The central plank of this programme will procure technical expertise for a series of short and medium-term projects. UK experts will work with Indian officials to understand the challenges faced, offer insights into what works in the UK, developing roadmaps and toolkits for reform, train officials and provide support during implementation. A biannual conference will be held to bring together state officials with UK experts to workshop reforms, building on the success of the 2016 event.
3. We will focus on four themes where the UK has expertise that is needed in India, selected based on engagement with the Indian Government and a series of scoping visits:
1. Better regulation – experts from the UK Regulatory Delivery Directorate have already worked with officials to implement risk assessment frameworks on inspection reforms with officers at central government and in states. For example, in Maharashtra, our team designed a risk assessment toolkit, identifying categories of risk and cross-referenced this with the type of building work, to determine the number of site visits. As a result of adopting this toolkit, the number of inspections for low-risk buildings will reduce, freeing businesses to focus on products and services. We have also helped identify regulations to be removed from legislation in central government and states.
2. Tax – India’s Goods & Services Tax (GST) reform provides a crucial opportunity to reduce administrative burdens across India, and HM Revenue & Customs has considerable expertise, particularly around risk analytics and customer service. Risk analytics allows authorities to focus inspections on those more likely to be non-compliant, freeing the compliant to spend more time on building businesses. UK experts will develop toolkits and help build the skills of state officials. They will also work with tax authorities to develop a more customer-focused approach to taxpaying, including the development of tools for segmenting customers and designing more effective customer journeys.
3. Trade – HMRC experts have already begun a dialogue with India’s central government on how India’s Trading Across Borders ranking can be improved through better practice on risk management, customs efficiency, and post-clearance audit. Scoping visits have been initiated – particularly in states with large ports – where policies on post clearance audit will also be developed. The programme will work with states to improve standards regimes which will ensure a consistent quality of products and services, allowing markets to function more effectively, including for UK businesses.
4. E-governance – a lack of clarity over land ownership is a significant barrier to doing business in India. Experts from the UK Land Registry will work with states to design more efficient and reliable systems. The programme will work with states to develop effective e-procurement processes, where well-designed systems such as used by the UK Government Digital Service allow public procurement via a single window.
This activity will take place both within central government and, most importantly, within states. To date, the most detailed work has been focused in Delhi and Maharashtra, the areas on which the World Bank’s Ease of Doing Business rankings focus. Additional work has involved a wider group of states which have considerable investment potential, UK business interests, and administrations that are highly engaged with the reform process. As a key deliverable of the design phase, Private Sector Delivery Partners (PSDPs) will be required to asses and recommend which themes and states to focus on as part of the assessment of the regional focus of the programme. This will take into account existing UK business interests in states, UK investment potential, and the level of political engagement – we will only engage where there is interest and enthusiasm for the agenda, and a willingness to take forward reforms.

Skills
1. DFID has worked on increasing enrolment and quality of primary and secondary education in India for 15 years. Access to quality vocational training is the next area to tackle to complete the link with income and growth benefits. India’s skilling agenda is ambitious and implemented through a complex web of public and private sector institutions. The National Skills Development Corporation (NSDC) is tasked with training 150m of the 400m people that the Government of India has pledged to train by 2022. This timeframe is challenged by knowledge and capacity constraints. UK technical assistance will bring international best practices to improve efficiency and effectiveness and enable the provision of quality services on a sustainable basis through establishing workable private sector models. International (including UK) businesses can benefit from the opportunities arising within this evolving market.
2. This programme of technical assistance will be funded jointly by DFID (£7.3m) and the PF via the FCO (£4.7m), working in partnership with the relevant public and private sector stakeholders. Outputs for the combined £12m programme will include:
- End-to-end offer on UK priority sectors – this will include curriculum development, training of trainers on international standards, assessment and certification and institutional partnership. Pilots will be undertaken in states, supporting technology and innovative solutions and promoting good practice. This will increase vocational training capacity in at least five high demand sectors.
- Capacity building of relevant institutions – support to strengthen the skills ecosystem and aid implementation of the Skills India mission across multiple stakeholders including the Ministry for Skills Development & Entrepreneurship, National Skills Development Council, Sector Skills Councils.
- Roll-out of the Government of India apprenticeships scheme – this will use UK companies as brand ambassadors, who are eager to be involved via the UK-India Skills Pledge. (So far 11 UK companies have committed to support by training approximately 350,000 people).
- Assessment and certification – support the establishment of a new accreditation framework based on international standards and UK models, increasing the assessment capacity, rigour and quality in high demand sectors.
- Policy reforms that strengthen the operating environment and improve conditions for international and UK companies, including procurement processes, payment systems, cost norms and scheme requirements.
- Co-ordinating UK involvement – building a portfolio of suitable UK partner institutions and training service providers and brokering joint ventures, facilitating dialogue to improve the links between UK corporates and Indian programmes and increase the scale and quality of UK-Indian contractual arrangements.
- A scoping study has identified the following sectors as potential candidates for UK engagement based on demand, UK added value, UK competitive advantage, labour supply constraints faced by UK firms, and commercial opportunities for UK skills providers: (i) infrastructure (ii) aerospace (iii) financial services (iv) automotive (v) healthcare (vi) food processing and (vii) oil and gas. As a key deliverable of the design phase, PSDPs will determine the precise activities to support and industrial clusters to focus on. A government-to-government UK-India Skills forum will provide strategic oversight. The programme will contribute to the delivery of cross-HMG objectives on skills in India and complement the work of other stakeholders including the British Council (research and promotion of UK best practice) and UKIERI (facilitating UK-India education partnerships and financing pilot projects).

Financial Services
1. The India PF Programme will develop a UK-India Finance Corridor, ensuring the development of India’s infrastructure through international financing and developing Indian financial markets. There will be two broad areas of work:
2. Raising international finance for infrastructure, including through the City of London. Creation of infrastructure is vital for India's economic future: according to India’s 2018 Economic Survey, it is estimated that India needs to invest US$4.5tr in the next 25 years to develop infrastructure. Bringing domestic savings into the formal financial system and attracting long-term investment from overseas – including the UK – will help India achieve this.
3. Over £11.5bn billion in rupee-denominated bonds have been issued in London since July 2016 by Indian organisations, establishing London as the leading global centre for offshore rupee finance. Many more Indian corporate and public sector organisations have indicated that they are considering similar issuances.
4. The UK and India have collaborated to create the Green Growth Equity Fund, under the National Investment and Infrastructure Fund, which – with a seed investment of £120m from each Government – is expected to leverage additional City finance to invest in green and renewable energy projects in India.
5. Alongside India’s National Infrastructure Investment Fund, state governments are developing their own infrastructure funds e.g. the Tamil Nadu Infrastructure Fund Management Company. These are also looking to access international capital markets through instruments including bond issuances. Many municipalities are also considering options for raising finance overseas. The India PF programme will therefore provide technical assistance to national, state and local Indian organisations setting up a one-stop shop in India to provide advice and support to Indian organisations – private and public sector – looking to raise infrastructure finance in international markets including London. It will also help develop a mechanism for providing information to investors on how to assess the potential investability of Indian projects. The PF will also support to these organisations to develop finance plans and project pipelines, and coordinate international investor roadshows for Indian organisations looking to raise infrastructure finance in London, in particular state infrastructure funds and municipal bodies as they go through the process of listing bonds.
6. Developing India’s financial markets. We will support the development of India’s domestic financial markets, driven in large part by the recommendations of the India-UK Financial Partnership (IUKFP). The FCO will work closely with the Indian government (including the Ministry of Finance and Ministry of Corporate Affairs) and financial regulators (including RBI, SEBI, IRDAI, PFRDA and IBBI) to bring the best of UK and global expertise to strengthen policy frameworks and best practices in India.
7. Reporting to the Finance Ministers of both countries, the IUKFP is an industry-led independent group that brings together financial sector CEOs and experts from India and the UK. The group has published recommendations for reforming nine areas of India’s financial system, including the development of the corporate bond market, India’s new insolvency regulations, pensions, the development of the reinsurance industry, infrastructure financing, financial inclusion, green finance, and rupee internationalisation. Each of these marketsfaces particular access challenges. For example, the previous Indian insolvency regime contributed to a significant problem in non-performing assets.
8. The India PF will take forward these recommendations and develop India’s financial markets through sharing information, best practices and expertise, building capacity, supporting development of policy and market frameworks, and provision of advisory services. Partnerships with UK institutions are particularly welcomed, in order to draw on UK professional and technical services, technologies and innovations. Technical assistance will also complement and lay foundations for commercial activity in areas matched to UK expertise, in order to harness the contribution that UK businesses can make to our shared objectives.
9. IUKFP recommendations have already been influential in helping India design a landmark new bankruptcy code, introduced in 2016, and the challenge now is implementation. The PF is currently funding the development of a curriculum for insolvency professionals and over the next four years we will develop this into a training programme to support new professionals. In addition, through the fund we will build capacity for Indian officials through training programmes and share UK experience and research on insolvency laws and procedures, with a focus on resolution professionals, valuers and information utilities.
10. In addition, the PF will support development of the FinTech market in India, which is growing swiftly, especially following the Government of India’s move to demonetise much of the country’s cash in late 2016[76]. The UK is a world leader and previous PF work has set out recommendations for further developing the market, which will now be pursued.
  [76] https://www.ndtv.com/india-news/did-demonetisation-help-digital-payments-back-to-pre-notes-ban-levels-1744688

Entrepreneurship
1. Using the PF, there is a significant opportunity to support entrepreneurship and the development of SME enterprises in particular in India. This would build on DIT’s previous Tech Rocketships competitions, which enabled top young Indian entrepreneurs to raise their profile with investors via business trips to experience the UK’s world-leading tech ecosystem first hand. Expanding from a single event to a programme of continuous support will provide more promising Indian SMEs with access to skills and resources that will help them scale up and realise their growth potential both in India and abroad. Support is likely to include assistance with business and financial planning, connecting enterprises with finance, investors and joint venture partners as well as incubators in the UK. Where relevant the support will also complement DFID India’s new £20m capital start-up fund.
2. Scoping has identified FinTech and Biotech & Lifesciences as the most mutually beneficial sectors in which to focus. It may therefore be appropriate to embed this element within the financial services strand of the PF programme. Any geographic focus and the design and delivery model will be a key deliverable of the PSDP’s design report and will be guided by the following principles on how business development support can be provided cost effectively, informed especially by the Donor Committee on Enterprise Development (DCED) BDS Guiding Principles[77] and the International Labour Organisation’s (ILO’s) BDS Primer[78]. These include:
  [77] Business Development Services for Small Enterprises: Guiding Principles for Donors. DCED, 2001.
  [78] Developing Commercial Markets for BDS, BDS Primer, ILO, 2003.
1. Targeting Transformative Entrepreneurs that have the required attitudes and abilities to grow their businesses and create jobs.
2. Linking business development support to access to finance. Support is most effective when it is provided alongside access to finance. The programme will therefore work alongside DFID’s capital fund as well as private investors and other lines of credit.
3. Cluster based services. The programme will provide support to clusters of SMEs. By serving geographical concentrations of small businesses in the same industry the programme can benefit from economies of scale in service provision and developing products and services suited to the needs of a homogenous group of businesses.
4. Use of Business Associations. The programme could explore supporting business associations to provide more development support to their members, taking advantage of ready-made channels for outreach.

Energy & Low Carbon
1. This strand will support the delivery of priorities agreed under the India-UK Energy for Growth Partnership which aims to enhance energy security for both countries and supporting the development of India’s low carbon economy. The programme will complement technical assistance being provided through DFID programmes, but focus on separate priority areas and geographies.
2. Technical Assistance will focus on priorities in two energy sub-sectors; smart power and renewables and storage. Action in both areas will also support electric mobility. FCO-supported scoping studies[79],[80] have identified these as offering a close fit with UK policy and market expertise and with significant commercial opportunities for UK business. Oil and gas was explored as a potential area for partnership in the scoping phase of the partnership but was later dropped due to the UK’s global policy decision not to support the sector in order to align development assitrance with climate change objectives and commitments. DIT has complementary campaigns on clean energy to catalyse exports and partnerships between businesses; the secondary benefit of this programme is to create a market environment that attracts such commercial partnerships.
  [79] Low-carbon energy study, ICF International, March 2017
  [80] Clean tech export opportunities from the UK to India, Carbon Limiting Technologies, March 2017
3. Technical Assistance covering smart power and renewables and storage will be targeted at specific priorities that have been agreed through India-UK joint working groups. These include reform and modernisation of electricity sector utilities, energy efficiency, planning and deployment of renewable energy, support for electric mobility and mobilising finance for clean energy, leveraging the strengths of the City of London. These balance Government of India priority requests with the UK’s policy priorities and capabilities (e.g. on energy security, low carbon growth and trade flows).
4. The key constraints the programme will aim to address are:
- Gaps between policy and implementation – by developing plans and strengthening operational systems required to turn policy into action;
- Capacity gaps – by strengthening skills, developing guidelines, handholding;
- Market gaps – by enabling demonstration of technologies and plugging information gaps to unlock action at state and city level;
- Finance gaps – by providing support on how to access resources and innovative financing mechanisms.
Technical assistance will be structured around three main areas of intervention:
- Policy development and implementation: strengthen leadership, policy frameworks and systems at central and/or state level that help markets to function better, using international best practice including from the UK. Technical assistance will be tailored for each of the sub-sectors, responding to specific issues faced by the private sector in terms of market design, regulations, incentives, capacities or other market failures. Illustrative activities include evidence and analysis building for the development of sector roadmaps (e.g. offshore wind, , solar, electricity distribution, energy efficiency, energy storage, electric mobility, action plans for low carbon cities); options for licensing and fiscal regimes; design of incentives schemes and other conditions for investment.
- Tailored support for state/city energy planning and project delivery: build capacity and markets to drive implementation of plans and policies in a prioritised set of up to five states around tailored energy solutions matched to UK commercial expertise. Technical assistance will also focus on accelerating the development of pipelines of energy sector projects that the private sector can invest in and implement; progressing transparent tendering and procurement for projects; brokering private sector partnerships that leverage Indian and UK strengths; and support proof of concept pilots and technology incubators to demonstrate viability of new technologies/business models, in areas matched to UK capabilities.
- Commercial and knowledge partnerships: design and deliver knowledge exchange projects between India and international partners in lcuding from the UK in areas including policy, regulation, financing, operation and maintenance, logistics and engineering, procurement and construction, testing/demonstration/resource assessment facilities and centres of excellence. This may include but not be limited to training, events, physical exchanges and analytical reports.
- Green finance was also explored as a focal area for energy sector companies and projects: to develop the market for private sector led green finance in India and catalyse significant amounts of green finance for India’s needs, including through the City of London. Technical assistance will support development of an eco-system for the green finance market in India (through regulations, ratings, indices etc.); mobilise significant market players and green finance deals to catalyse market development; broker partnerships that will facilitate the deployment of UK expertise on Indian projects such as financial structuring, certifications and verifications; and provide strategic support to Indian companies for raising capital internationally, including in London. The final decision was to channel this support largely through the financial services strand above.
1. To maximise prospects for primary and secondary benefits within the project timeframe, it is anticipated that the majority of the resources will be channelled through a tailored package of support to up to five focal states and up to five focal cities. This package of support will take into account the best prospects for impact, proportionality of effort, fit with UK objectives, and the ability to deliver matched against demand for specific support by the Government of India and state level stakeholders.
2. States will be chosen from the geographical areas determined at the overall India PF programme level, with large market potential for investments. As a key deliverable of the design phase, a recommendation of states and cities will be made and take into account:
1. Enabling environment: the existence and political support for interventions to deliver energy sector projects;
2. Appetite to engage with delivery partners of the PF;
3. Alignment with locations chosen by other strands of the PF.

Urban Development
1. The Urban Development programme will support the India-UK Urban Partnership set out in the MoU on Sustainable Urban development signed during PM Modi’s visit to the UK in April 2018. The Partnership will also look at ways to raise project finance for example which can be used to leverage higher financing from financial markets.
2. The urban strand will help tackle constraints in:
- Urban governance and procurement planning and implementation.
- Sector level skills and expertise – particularly in transportation, urban services and urban planning and the built environment.
- Applied urban innovation and research.
- Accessing finance.
1. The urban strand will help the Government of India to create a pipeline of investable projects and provide targeted business environment support – including with accessing finance – that result in economic and inclusive growth (including for women and girls) and more UK commercial opportunities.
2. We will focus support in cities which demonstrate high returns on poverty reduction and potential UK opportunities. We look to support existing urban partnerships as well as to expand in additional cities. As part of the design phase, we will work with the selected PSDSP, DIT and DFID to develop a strategic framework to prioritise our support in the highest potential sectors, geographies and activities. We will also take into account any broader assessment of the regional focus for the overall programme.
3. Our support will include:
- Strategic government advice on urban policy and implementation: Targeted external expertise to central, states, municipal government officials (including SPVs and other associated bodies) to formulate and translate urban-related strategies into robust roadmaps. This will include guidance on financing models, social impact assessments, programme management, governance, and procurement.
- Expert technical advice at the project sector level: We will build on technical assistance already provided in partnership cities and continue to provide expert advice on proposals in key UK industry sectors. This may include proposals related to design and planning; buildings; water and waste management; transport; smart solutions. Core activities will cover sector and socially inclusive analysis, stakeholder and engagement; business missions; project financing; and action plans.
- Urban innovation and research generation and exchange: Building partnerships between India and centres of urban excellence, especially with the UK. We will explore the creation of urban hubs at the national and city level which generate analysis, best practice and private to government innovation. We will bring together think tanks, academia and start-up companies. We will also mainstream social inclusion considerations. This will help to shape and inform urban planning practices, policy-making and develop more robust and dynamic approaches.
- Targeted up-skilling of officials: We will help government officials build their technical expertise in our key industry sectors. This will ensure our technical assistance is sustainable and leads to lasting and transformative change. We will look to focus our support in areas where the UK has strong capabilities, particularly in transportation, urban services and urban planning and the built environment. We will also work closely with the skills strand to ensure alignment and avoid any duplication.

D3. Stakeholders and Partnerships
1. Effective partnerships with key stakeholders will be required to deliver this programme. Internally, this includes HMG partners (DFID, DIT, BEIS, UKRI, British Council and others) to ensure the India PF Programme complements existing activities to maximise impact and value for money. These partnerships are already well established at both a working level and within governance structures, for example, several HMG partners have a seat on the India PF Board. We will also ensure coordination with UK Export Finance, with CDC – the UK government’s development finance institution – and any other PF programmes operating in India, particularly the proposed UK-India sub-fund of the National Infrastructure Investment Fund (NIIF).
2. Externally, the Government of India is the key stakeholder. The BHC has good relationships with relevant central ministries (including many MoUs), including:
Ministry of Finance	Ministry of New & Renewable Energy
Ministry of Commerce	Ministry of Power
Ministry of Housing & Urban Affairs
Ministry of Law & Justice	Ministry of Skill Development & Entrepreneurship

1. The UK also has good relations with the relevant state governments, ministries and municipal authorities via our network of Deputy High Commissions, who have experience of supporting projects locally either directly or in partnership with DFID.
2. The private sector, especially UK firms, will also be crucial to realising secondary benefits. DIT is heavily engaged with UK businesses and business groups, such as UKIBC and the British Business Group, ensuring that BHC strategy reflects the demands and insights of the business community. DIT is represented on the India PF Board.
3. Multilaterals are another important player. The BHC has good relations with World Bank, Asian Development Bank and others, particularly in the fields of Ease of Doing Business, and Skills.

Expected Outcomes and Impact
The primary objective of the India PF Programme is inclusive economic growth and poverty reduction in India. In order to achieve this, the programme will contribute directly to all five intermediate outcomes of the global PF theory of change:
- Investment in infrastructure and human capital
- Innovation and knowledge transfer, including of low carbon technologies
- Trade, financial and economic reform
- Policy and regulatory capacity
- Ease of doing business
1. The programme will address issues of gender inequality by identifying opportunities where positive benefits can be delivered for women and girls. A do no harm approach will also be adopted by all strands.
2. Secondary benefits that will also accrue from the intervention are increased UK-India trade and investment. High level indicators of secondary benefits include:
- Increased UK exports to India
- Increased UK investment returns in India
- Increased Indian FDI into the UK
These contributions are outlined in the high level Theory of Change below (fig. 6)

Figure 6: High Level Theory of Change

Better understanding and roadmap for required reforms
Positive influence on legislation
Improved institutional capacity
Promotion of UK standards and regulatory frameworks
Demonstration of improved public administration systems
Finance and business models developed
Increased skills training capacity
Enterprise and technology incubation
Pipeline of investable projects
UK-India commercial and development partnerships
Increased UK-India trade and investment
UK companies view India as a better place to do business
UK and Indian companies find it easier to trade and invest bilaterally
UK companies/ consortia compete for more Indian business
Boosting skills
Developing Smart cities
SECONDARY BENEFIT
ACTIVITIES
OUTCOMES
OUTPUTS
IMPACT
Increased investment in infrastructure and human capital
Greater innovation and knowledge transfer, including of low carbon technologies
Trade, financial and economic reform
Strengthened policy and regulatory capacity
Improved ease of doing business
Inclusive economic growth and poverty reduction
Improving ease of doing business
Reforming financial markets
Delivering cleaner energy and low carbon growth
PRIMARY PURPOSE

Strand level, primary and secondary expected outcomes are summarised in table 3:
Table 3: Primary outcomes and secondary benefits (full SMART objectives/ indicators and time-frames for delivery will be included within final strand level logframes agreed as a key deliverable from design phases.
STRAND	PRIMARY OUTCOME	SECONDARY BENEFIT
Ease of Doing Business	Significant improvement in World Bank Ease of Doing Business ranking. / Significant improvement in ‘Trading Across Borders’ sub-indicator. / Improvement in Economic Freedom Index from present category of Mostly Unfree (Score: 56.2%) to at least Moderately Free (60%). / Significant improvement in business environment of India in the three pillars: better regulation, tax administration, trade facilitation. Evidenced through increased job growth in the SME and MSME segment of Indian industry and sustainable reforms within GoI institutions.	UK firms view India as a better place to do business (third party survey data). / Share of additional growth resulting from improved business environment.
Skills	1m people receiving better training and assessment in priority sectors. / Increase in apprentices employed by UK companies.	£30m skills contracts opened up to UK firms by 2022. / New skills partnerships formed between UK Sector Skills Councils, Indian government bodies and UK training providers. / Increased skilled labour supply in UK priority sectors.
Financial Services	The size of Indian capital markets: bond market to increase from £330bn to £500bn by 2023. / State and municipal infrastructure funds supported by the UK raise over £500m from international capital markets. / India moves up the World Bank Ease of Doing Business ‘Resolving Insolvency’ Rankings from 108 in 2019 to below 60 in 2020. / At least 1% annual improvement of insurance coverage as a result of programme interventions by end of the programme.	25% of the finance raised by India to be raised out of London. / UK exports in financial services of £300m by 2020. / UK exports in FinTech: £20m by 2020.
Entrepreneur-ship	250 SMEs increasing their turnover and 400 additional jobs created.	50+ scaling Indian firms investing in the UK.
Energy & Low Carbon	£400-600m increased private investment leveraged. / 0.8GW equivalent additional clean energy capacity.	£80m additional business for UK firms. / More UK firms enter the Indian energy and low carbon market. / At least 1000 jobs created. / At least 5mn tonnes CO2 equivalent per year of GHG emissions avoided.
Urban Development	Five high value (min. £500m total) infrastructure projects in partner cities. / £1b increased infrastructure investment in partner cities (of which min. £500m directly generated from PF programme).	Five major urban infrastructure projects in partner cities yielding new commercial opportunities for international/ UK companies. / £200m in additional international/ UK commercial wins as a result of changes in the business environment.

E1. Ease of Doing Business
1. The primary outcome will be an improved business environment in India which will support growth in targeted Indian states. Specifically, the adoption of risk assessment toolkits by states on e.g. inspection, tax and trade facilitation (post clearance audits) will lead to reduced burdens on low-risk businesses, giving them more time to focus on their products and services. Consistent standards will support competitive markets – and better land registry systems will allow property transactions to take place more effectively. All of this will promote competitive markets, supporting economic growth.
2. This should manifest itself as improved rankings for overall Ease of Doing Business, Trading Across Borders and Economic Freedom. There should also be an improvement in India’s relevant state level business environment indicators. A secondary benefit will be the improved conditions for international and UK companies operating in or considering entering the Indian market, accompanied by cost savings. As significant exporters to and investors in India, international and UK firms are expected to also share in the additional growth that will result from India’s improved business environment.
3. The World Bank Doing Business methodology now also includes a gender dimension in four of its eleven topics sets: starting a business, registering property, enforcing contracts and labour market regulation. This focus will be reflected in the outputs and outcomes of the programme, as refined during design, and in monitoring and evaluation.

E2. Skills
1. Primarily this will result in 1m people being up-skilled via an increase in India’s vocational training capacity in selected high demand sectors of mutual benefit to both India and the UK. This will improve the labour market for both Indian and international firms, resulting in a secondary productivity benefit for UK companies operating in India who will benefit from an improved labour supply. The programme will also open up the Indian vocational skills sector for UK training providers by placing UK accreditation at the heart of Modi’s Skill India drive. The full DFID intervention (£7.3m) is expected to result in £45m (£13m attributed to PF) additional commercial opportunities for UK firms by 2022, increasing to up to £140m (£52m attributable to PF) by 2027.
2. The programme will adopt a phased approach to gender inclusion, involving a) collecting gender/ social group disaggregated data, b) tracking progress on gender and social inclusion across the key sectors, c) developing a gender strategy based on the findings, which may include setting targets if appropriate.

E3. Financial Services
1. The primary outcomes of this programme will include increased depth and liquidity in Indian capital markets (proxied by the size of the bond market, where we will target an increase from £330bn currently to £500bn). India moves up the World Bank Ease of Doing Business ‘Resolving Insolvency’ Rankings from 108 in 2019 to below 60 in 2020. There will also be an indirect impact on gender equality. Increased financing for infrastructure – in particular transport and energy - will provide women with greater opportunity for labour market participation. More efficiently functioning markets for insurance, pensions and FinTech products will also support financial inclusion, which has the potential to disproportionately benefit women.
2. The secondary benefit to the UK will be the positioning of the City of London at the heart of India’s economic development, with City finance and expertise used to accelerate India’s economic growth. We will aim for 25% of Indian finance to be raised in London, with financial services exports of £330m over five years and FinTech exports of £20m over 3-4 years.

E5. Energy and Low Carbon
1. The programme will influence the design and implementation of at least three major policies or regulations that will support the growth of clean energy markets. A pipeline of more viable renewable energy and smart power projects will also be developed for tendering and procurement in up to five key Indian states. This will support stronger political will and progress on implementation of India’s Nationally Determined Contributions pledged in UNFCCC Paris Deal. As a result approximately £400-600m additional investment in cleaner energy is expected to be leveraged, leading to an additional 0.8GW of energy capacity installed by the end of the ten-year appraisal period. This will deliver benefits to both men and women and where possible this data will be monitored to inform iterative programme design.
2. The secondary benefit to the UK will be the proportion of this additional investment that flows to UK companies via exports or sales to UK owned companies operating in India (estimated at approximately £80m). The number of UK businesses operating in the Indian energy sector is also expected to increase.

E6. Urban Development
1. The programme will result in accelerated and improved urban strategy and planning in partner cities, which together with increased government capacity and improved governance, should increase the investment climate in cities and in turn a pipeline of investible projects. Project level support, for example, will contribute further to both ensuring projects are delivered. As a result the programme is expected to catalyse up to £0.5bn additional urban infrastructure investment in partner cities by overcoming barriers to implementation in five high-value (approx. £100m each) projects.
2. The programme will ensure that marginalised groups – including women and girls – are mainstreamed into both the design process to ensure the outcomes are inclusive. For women, better infrastructure can result in higher productivity, e.g. through greater physical mobility and more direct and indirect job opportunities. In India specifically, there is evidence that women are employed in large numbers in construction projects[81]. In addition, well designed urban environments can reduce perceived or actual risk of gender-based violence[82]. Where possible the gender implications of the programme will be monitored and reviewed to feedback into ongoing design.
  [81] Mohun, R & Biswas, S. (2016) Infrastructure: a game changer for women’s economic empowerment
  [82] Taylor, A. (2011) Women and the City: Examining the Gender Impact of Violence and Urbanisation.
3. The programme will help to overcome barriers faced by international and UK companies and investors in accessing the Indian urban market profitably. Improvements in the business environment will encourage international companies and support their involvement. This is expected to lead to an additional £200m in commercial benefits for the UK over ten years. PF support will also be used to scale the effects of this intervention nationally, beyond just the UK’s partner cities.

E7. Contribution to SDGs and climate change
As reflected in the overall PF theory of change, the India PF Programme will contribute to the following Sustainable Development Goals:
- Goal 1: End poverty in all its forms everywhere.
- Goal 4: Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all.
- Goal 5: Achieve gender equality and empower all women and girls
- Goal 7: Ensure access to affordable, reliable, sustainable and modern energy for all.
- Goal 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all.
- Goal 9: Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation.
- Goal 11: Make cities and human settlements inclusive, safe, resilient and sustainable.
- Goal 13: Take urgent action to combat climate change and its impacts.
- Goal 16: Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels.
The programme will also contribute to India’s national commitments on climate change under the UNFCCC Paris Agreement.

APPRAISAL CASE

Assessing Delivery Options
The strategic case has presented the five thematic strands where the India PF Economic Reform & Prosperity Programme will intervene in order to achieve the greatest primary and secondary objectives. A number of delivery routes can be considered to implement such interventions. At a broad level, the following funding and implementation options have been considered in principle for each strand:

Table 5: High level delivery options
	Transfer funds to multilateral or NGO	Primary Service Delivery Partner (PSDP) for each Strand (commercial/ NGO)	Multiple implementers (Commercial/ NGO)
Unilateral funding	Transfer PF money to a partner organisation to support their work via an MoU.	Procure a supplier to manage the PF Fund programme via contract.	Commission a number of organisations to deliver different elements of the programme via appropriate agreements.
Co-funding with one or more other organisations	Combine with other funding sources (e.g. DFID, GoI) and transfer to a partner organisation to support their work via a joint MoU.	Combine funds with other sources and jointly procure a supplier to manage the programme via contract.	Combine with other sources of funding and jointly commission different organisations to deliver different elements of the programme via appropriate agreements.

The different contexts of each strand mean that each has its own set of different delivery choices. Therefore, for each strand the viable delivery options have been appraised against the following criteria:
- Capability and capacity of likely implementing partners to deliver the intended outcome and manage risks;
- Cost effectiveness – overall costs required to deliver satisfactory intervention and scope to manage them;
- Control over risk and delivery as determined by opportunities available to measure and manage performance, and the scope to transfer delivery risk from FCO;
- Early benefits relative to upfront cost – timing and resources required before the programme can start, and implications on the timing of benefits;
- UK commercial focus – ability and inclination of likely implementing partners to deliver outputs tailored to UK commercial interests.
1. Where options score similarly overall, priority is given to capability and capacity and UK commercial focus, as these criteria are most closely related to primary purpose and secondary benefit. The assessment of each strand is summarised below with a detailed assessment provided in Annex B.
2. Contracting a single implementer for the entire portfolio has been ruled out because the scope of the programme is too complex for any one implementer to adequately manage and deliver. There is a need to maintain an element of control and direction in order to maximise impact given the secondary benefit sought, which is less suited to a single contract. Precise expertise and therefore specific consortia will be required for the different strands. Furthermore, splitting implementation by strand limits exposure to any single organisation, avoiding an unnecessary level of implementation risk.

A1. Delivery Options
Analysis of the potential delivery options for the programme strands is presented below. For the purposes of the Appraisal Case (and summary budget) staff costs, admin and contingency are included within the strand total budgets. For the budget presented in the Financial Case, these are separated out.

Ease of Doing Business (£8.2m)
The following delivery options have been considered:
1. Do nothing – £0m
2. Deliver through the World Bank
3. Deliver through DFID programmes
4. Deliver through multiple project partners
5. Deliver through a single Primary Service Delivery Partner (PSDP)
1. Option 1: Do Nothing - £0. This is a critical issue for India. By discontinuing our support, we would lose an opportunity to tackle these issues with the support of the Indian government. In areas like inspection reform, better regulation, tax administration and trade facilitation it would mean a swift end to work that was having an impact on India’s regulatory climate. It would also risk the sustainability of previous projects and risk losing the traction that has been gained.
2. Option 2: Deliver through the World Bank. FCO could end bilateral support and instead channel funds into other multilateral programmes, of which the World Bank (WB) would be the obvious partner. The WB (via the International Finance Corporation) already has a successful programme with the GoI, focused on developing the state rankings system. However, this programme was heavily focused on central government initiatives and had limited engagement at the state level. Furthermore, while delivering though the World Bank would enable us to leverage their resources and reach, it would not allow the potential cost savings achieved through a competitive tendering i.e. limited ability to negotiate with the World Bank on costs which are agreed centrally. Control over risks and delivery would also be reduced. Since multilaterals generally have clearly defined objectives and act apolitically, steering programme design and implementation towards HMG secondary benefits would also be challenging. The Government of India has also specifically asked for UK government support and places a high value on direct government-to-government knowledge exchange.
3. Option 3: Deliver through DFID programmes. The FCO could provide funding to DFID’s existing Economic Policy & Prosperity Partnership Programme or Ease of Doing Business programmes. DFID India is well-established and has experience in developing the business environment in some of the poorer states. Combining resources with DFID may also result in economies of scale. However FCO’s work on ease of doing business over the last several years with central and state governments places it in a unique position to leverage contacts. This potency may be diluted, particularly if there are differences with DFID on scope or geographical focus. The ability to ensure a secondary benefit focus may also be reduced.
4. Option 4: Deliver through multiple project partners. The FCO could contract directly with several project partners based on their ability to deliver different aspects of the programme. This will maximise control over the programme and ensure UK branding, as well as limit our exposure to any one implementer. Through extensive stakeholder engagement over the past year, we identified the targeted interventions sought by both GoI and state government. To maximise impact and VfM, and have the widest geographic (and political) coverage, the programme aims to have three distinct, complementary, delivery models:
  1. Deliver through IFC: The IFC have a good existing programme of engagement with GoI. They sought UK support for a distinct capacity-building programme for the newly formed Reforms Secretariat of India. This programme will sustain the business reform momentum adopted by GoI, through additional capacity building of regulators in the long run.
  2. Deliver through a PSDP: While the above is focused on central government capacity building, there is a need to deliver fundamental reforms across both state and central government. We will carry out the majority of the programme through a PSDP. The PSDP will bring UK and international expertise to respond to central and state governments’ asks for policy reform, toolkits, pilot programmes and communication initiatives. Deeper engagements may also be identified through the design phase.
  3. Deliver through HMG Government Departments: some niche interventions requested by GoI will require specific interactions with HMG departments (e.g. BEIS, HMRC, etc) who the PSDP are unlikely to be able to access directly. We will therefore sign bilateral engagements directly with HMG departments – though our interventions as a whole will be coordinated by the PSDP. Additionally, it secures the goodwill of GoI who are keen to work with their direct counterparts in the UK as opposed to private PSDPs on some sensitive areas (e.g. enforcing contracts, resolving insolvency)
1. This approach will significantly enhance our VfM, bringing in private sector expertise (through the PSDP), wider international expertise (through IFC) and deepening our bilateral impact (through OGDs). It also allows us to cover both central and state government requirements, demonstrating the responsiveness of our programme. While this may lead to marginally higher transaction costs (e.g. using internal capacity), the overall programme cost has remained largely unaffected.
2. The GoI’s focus on Ease of Doing Business has evolved. This has been driven by India’s rapid rise in EoDB rankings (131 to 63 since the programme was conceptualised) and has generated a demand for more targeted interventions and the need for capacity-building in select areas. The PF was set up to be adaptive and responsive, and therefore delivery through multiple project partners, including the World Bank, has been chosen as the appropriate model. An over-arching Steering Committee will be convened to facilitate complementarity across the delivery partners once programme is in full implementation.
3. Option 5: Deliver through a single Primary Service Delivery Partner. The FCO could launch a bilateral ease of doing business programme through a single agency that runs the overall programme with the GoI. The annual agenda and review would be held jointly by FCO, the management agency, and the Department of Industrial Policy & Promotion, with regular meetings between FCO, DFID and representatives from UK business groups to share learning and ensure complementarity.
4. There are some obvious advantages of this approach. As the simplest model, transaction costs will be reduced and control retained, with flexibility to adapt to the changing needs of the regulatory landscape and UK and India priorities. However, GoI have also requested specific interactions with UK Government departments which would be difficult for a PSDP to access. Furthermore, it would not provide good VfM for the PSDP to contract directly with other parts of HMG. GoI have also requested the IFC to build their programme of capacity building drawing on wider international expertise.

	Capability & capacity (5)	Overall cost effectiveness (5)	Control over risk & delivery (4)	Early benefits relative to upfront costs (3)	UK commercial focus (5)	Overall
Do nothing	Low	Low	Low	Low	Low	Low
World Bank	High	Medium	Low	Low	Low	Low
DFID	High	High	Medium	Medium	Medium	Medium
Multiple partners	High	High	Medium	Medium	High	High
Single PSDP	Low	High	Low	Low	Medium	Low

2. Recommendation: Based on the above, option 4 – delivering through multiple project partners – is recommended. India has witnessed a recent rapid rise in Doing Business Rankings (131st to 63rd). This has called for a deeper set of interventions sought by GoI and the breadth of expertise needed has significantly increased. A single PSDP would not be able to cater to this, especially where GoI is requesting bilateral exchanges with HMG counterparts. Equally, State Governments are keen on deepening their reform agenda, keeping in mind the competitive federalism which the present Government is promoting in India. A combination of multiple delivery partners allow us to allocate resources across state and central government with greater impact.

Skills (£4.7m)
The following delivery options have been considered:
1. Do nothing (£0m)
2. Divert funds to other PF strands
3. Deliver through Asian Development Bank and/or Word Bank
4. Deliver through DFID by co-funding a skills programme
5. Deliver through a single Primary Service Delivery Partner
1. Option 1: Do Nothing - £0. The FCO could stop its support once its current skills projects end. The skills deficit in India is a huge issue which requires significant resources and technical assistance. Doing nothing would slow the improvements to India’s training capacity and skills ecosystem, which are crucial to both growth and poverty alleviation. It would also significantly reduce the UK’s offer on skills and potential benefits and opportunities for UK businesses.
2. Option 2: Divert funds to other PF strands. As a relatively small programme, Skills would be the most obvious strand to drop to reduce fragmentation across the portfolio, especially since DIT India have de-prioritised skills as a sector. Distributing the £5m across the remaining strands would be likely to yield at least an equal and possibly higher return since skills has a lower benefit-cost ratio (both primary and secondary) than some other strands, according to the economic appraisal. This would however reduce the UK’s offer on skills and risk signalling that the UK has de-prioritised this important issue for India.
3. Option 3: Deliver through the Asian Development Bank and/or World Bank. The FCO could end its bilateral support and instead channel funds into multilateral programmes. These organisations have significant expertise and experience which could ensure robust and effective programming with clear poverty reduction impacts. However, experience suggests that opting for delivery through multilateral organisations without going through competition is often costlier, with high administration charges and potential upfront costs. This option provides the least control over risks and delivery and will be much less likely to promote UK commercial interests. This option is unlikely to contribute towards secondary benefits.
4. Option 4: Deliver through DFID by co-funding a skills programme. DFID India is well-established and has experience in skills development in India and good relationships with relevant government stakeholders. The FCO can transfer up to £5.5m to DFID to augment their ‘Skills for Jobs’ programme – such a combined skills programme would provide approximately £12m of funding. This should enable a higher impact programme by taking advantage of economies of scale and strengthened networks. A proposed UK-India MoU on skills engagement provides a platform for this.
5. This avoids the risk of confusing key stakeholders by working separately on delivering a common agenda. As the larger partner, DFID would be responsible for the programme and would contract a management agency to manage delivery. The FCO would transfer funds to DFID, which may impact on FCO control, but good governance arrangements should allow the FCO to maintain some oversight of delivery and ensure UK commercial focus. DFID will report on programme outputs and primary and secondary benefits. This option would deliver strong primary and secondary benefits based on DFID India’s experience and on increased emphasis on UK commercial benefits.
6. Option 5: Deliver through a single Primary Service Delivery Partner. The FCO could directly contract a management agency to manage the PF programme on its behalf. This would allow better control over risk and delivery and would achieve cost effectiveness through competition. However, the result would be a relatively small programme (£5m) that would not benefit from DFID’s strong relationships and expertise and would not maximise the synergies between the two programmes.

	Capability & capacity (5)	Overall cost effectiveness (5)	Control over risk & delivery (4)	Early benefits relative to upfront costs (3)	UK commercial focus (5)	Overall
Do nothing	Low	Low	Low	Low	Low	Low
Redistribute funds	High	High	Medium	Medium	High	High
Multilateral	High	Medium	Low	Low	Low	Low
DFID	High	High	Medium	High	High	High
Single PSDP	Medium	Medium	High	Medium	High	Medium

Recommendation: Based on the above assessment, option 4 – partnering with DFID – is recommended.

Financial Services (£6.55m)
The following delivery options have been considered:
1. Do nothing (£0m)
2. Deliver directly through BHC resources (‘in house’)
3. Deliver through a single Primary Service Delivery Partner
4. Deliver through World Bank
5. Deliver through a hybrid model (combination of Primary Service Delivery Partner, In-house BHC resources and multiple project partners)

1. Option 1: Do nothing. This would significantly reduce the UK’s ability to support financial market reform in India, and the UK’s offer to Indian entities wanting to access finance. It would also risk current interventions not being sustained and developed into more substantive projects that deliver transformative change. FCO funding would be conserved and made available to the other PF programmes, either in India or globally. This would likely lead to a reduction in mutual prosperity, with Indian companies losing out on the opportunity to access UK markets and the UK losing out on potential foreign direct investment.
2. Option 2: Deliver directly through BHC resources as per current PF model. The FCO could scale up its current model of going out to the market for a large number of projects to deliver the overall objectives of this strand. This would require a number of small contracts and suppliers to be managed directly by the BHC, which would need either additional internal resources or some re-prioritisation. Transaction costs would likely reduce the relative cost-effectiveness compared to other options. However, direct delivery will allow the FCO to retain a high level of control over delivery and ensure maximum UK focus. Based on previous performance it is expected that this option would deliver medium to strong primary and secondary benefits.
3. Option 3: Deliver through a single Primary Service Delivery Partner. The FCO could design a bilateral Financial Services programme by engaging a single contracted service delivery partner who would manage the intervention. Depending on the flexibility of the implementer, this would allow a tailored package of support, with the service delivery partner sub-contracting to particular providers as appropriate. It would achieve economies of scale, with the implementer having greater flexible capacity than internal BHC resources.
4. Transaction costs for the PF team in India would be less than for direct management. Whilst active contract management will be required, the supplier will be responsible for undertaking activities with appropriate staffing structures and skills. It is expected that buying in expertise under a single contract will best deliver primary and secondary benefits, whist reducing the burden of work on the PF team in Delhi. However, a single contract could also mean that there is a risk if the selected delivery partner does not provide quality delivery or lacks internal capacity, particularly when delivering specialised services.
5. Option 4: Deliver through World Bank. The FCO could provide funding to the World Bank to support programmes that focus on financial services and infrastructure. The World Bank is well established and respected in India, though it has not focused to the same extent as the UK on financial market reform – and would not be able to focus on the UK-India Finance Corridor and the City of London’s role in financing India’s development in particular. Leveraging World Bank resources and expertise could prove impactful, although it may not leverage UK world leading expertise as effectively or benefit from the downward cost pressures brought by competitive procurement. Additionally, by transferring funds to the World Bank, the FCO would also lose out on formal control over risk and delivery. The FCO’s ability to ensure impact and also achieve a UK commercial focus would therefore be compromised. It is expected that this option could deliver medium primary benefits, but secondary benefits may be constrained in the short to medium term, with fewer benefits for the City of London.
6. Option 5: Deliver through hybrid model (combination of Primary Service Delivery Partner, In-house BHC resources and multiple project partners).
The FCO could use a hybrid model to deliver the three pillars of the programme (Financial Market Development, FinTech, Raising Finance for Infrastructure) by using a combination of: (i) A contracted Primary Services Delivery Partner, (b) Leveraging in-house BHC resources, and (c) using specific project partners for defined strands of the programme. This would allow for the delivery of a tailored package of support, ensuring efficiency and valye for money, while achieving secondary benefits for the programme. The contracted Primary Services Delivery Partner could continue to deliver well-defined activities under the Financial Market Development pillar, with a particular focus on Insolvency Resolution. For specialised areas within the FMD and RFI pillars, the FCO could contract directly with several project partners. Given in the in-house expertise of the PF programme team and staff expertise from the DIT, the fintech pillar could be managed and delivered in-house. The hybrid model set out here will maximise control over the programme and ensure UK branding, as well as limit our exposure to any one implementer’s poor performance.

Transaction costs for the PF team in India, would be less than the ones suggested in option 2 and 3. The primary service delivery partner and multiple project delivery partners will be responsible for undertaking the activities with the appropriate staffing structure and skills set. However, active contract management will be required by the PF team, as the time will be required to directly manage different suppliers and work in close co-ordination with other HMG departments such as the DIT. While the programme team has sufficient resources to manage the same, some increase in internal capacity utilisation in expected in this delivery model.

	Capability & capacity (5)	Overall cost effectiveness (5)	Control over risk & delivery (4)	Early benefits relative to upfront costs (3)	UK commercial focus (5)	Overall
Do nothing	Low	Low	Low	Low	Low	Low
Internal resources	Medium	Medium	High	Medium	High	Medium
Single PSDP	High	High	Medium	Medium	High	High
World Bank	High	Medium	Low	Medium	Medium	Medium
Hyrid Model	High	High	High	Medium	High	High

Recommendation: Based on the above, option 5 – delivering through a Hybrid model – is the recommended option.

Entrepreneurship (£1m)
The following delivery options have been considered:
1. Do nothing (£0m)
2. Deliver directly through BHC resources as per current TechRocketships model
3. Deliver through a single management agency
4. Deliver through DFID by supporting their start-up capital fund
5. Deliver as part of the Financial Services programme, capitalising on the strong FinTech focus
1. Option 1: Do nothing. Achieving scale up is a big problem for SMEs in India and so it is expected that many would lose out as they would be unable to overcome the existing constraints. FCO funding would be conserved and made available to the other PF programmes. This would lead to a reduction in mutual prosperity, with Indian companies losing out on the opportunity to access UK markets and the UK losing out on potential foreign direct investment.
2. Option 2: Deliver directly through BHC resources as per current TechRocketships model. The FCO could scale up its current model to deliver a larger more comprehensive intervention providing a package of enterprise support to selected companies managed by the BHC. Delivering in this way will require directly managing several different suppliers, which would require either additional internal resources or some re-prioritisation. BHC does not have the expertise, which is more widely available in market. It is expected that transaction costs involved would reduce the relative cost-effectiveness. However, direct delivery will allow the FCO to retain a high level of control and ensure maximum UK focus. The VfM element will reduce given the management overheadd. Based on previous performance it is expected that this option would deliver medium to strong primary and secondary benefits.
3. Option 3: Deliver through a single Primary Service Delivery Partner. The FCO could design a bilateral entrepreneurship programme based on a scaled-up version of the Tech Rocketship model, providing a package of enterprise support to selected companies delivered by a single contracted implementer who would manage the intervention. Depending on the flexibility of the implementer, this may allow a more tailored approach to the support, as well as economies of scale. Transaction costs for would be less than for direct management. If procurement is successful, the implementer should have greater flexible capacity than the BHC. Direct control will be relinquished and so active contract management will be required to ensure that outcomes and UK focus are achieved. It is expected that this option would deliver strong primary and some secondary benefits.
4. Option 4: Deliver through DFID start-up capital fund and associated technical assistance. The FCO could provide up to £2m of funding to DFID India to top up the technical assistance available to support its new Start-Up development capital fund. DFID is well-established and well-regarded in India, although this approach (returnable capital) to private sector development is less tested. Augmenting this larger instrument may achieve greater leveraging of resources and economies of scale, but will also bring increased risks through a loss of control.
5. If successful, leveraging DFID resources and expertise could prove cost-effective. However, by transferring funds to DFID, the FCO would also transfer contract management responsibilities resulting in limited formal control over risk and delivery. The FCO’s ability to ensure impact and achieve a UK commercial focus would therefore be compromised. There would also be less control over which companies are supported and which sectors since it would be linked to the Venture Capital Fund which may have different priorities to the FCO and DIT.
6. It is expected that this option would deliver strong primary benefits, but that secondary benefits may be significantly constrained in the short to medium term if the focus is on investment returns rather than inward investment into the UK.
7. Option 5: Deliver as part of the Financial Services PF programme, capitalising on the strong FinTech focus. The FCO could increase funding to the Financial Services strand to run a bilateral entrepreneurship programme based on a scaled up version of the Tech Rocketship model with a particular focus on FinTech entrepreneurs. This would maximise synergies with the rest of programme, including market reforms intended to develop the FinTech market in India. The intervention would be managed by the same implementer as the Financial Services strand, making it a single programme. This should still allow alignment with and leveraging of DFID interventions in this space, particularly with the DFID’s start-up capital fund, which will also have a strong FinTech focus.
8. Transaction costs for this option will be similar or less than the separate single management agency suggested in option 3, if there are economies of scale to be leveraged. Nonetheless, as a distinct element of the Financial Services programme, some internal resource will still be required to oversee delivery. It is expected that this option would deliver strong primary and secondary benefits.

	Capability & capacity (5)	Overall cost effectiveness (5)	Control over risk & delivery (4)	Early benefits relative to upfront costs (3)	UK commercial focus (5)	Overall
Do nothing	Low	Low	Low	Low	Low	Low
Internal resources	Medium	Low	High	Medium	High	Medium
Single PSDP	High	Medium	Medium	Medium	High	High
DFID	High	High	Low	Medium	Medium	Medium
Embed within FS strand	High	High	Medium	Medium	High	High

Recommendation: Based on the above, option 5 – embedding within the Financial Services strand – is recommended, although delivering through a single Primary Service Delivery Partner also scores highly and provides a viable alternative.

Energy & Low Carbon (£10m)
The following delivery options have been considered:
1. Do nothing (£0m)
2. Deliver through multilaterals like Asian Development Bank, World Bank, or UN Agencies
3. Deliver through DFID by funding existing or new DFID Technical Assistance programme
4. Deliver through Primary Service Delivery Partner
1. Option 1: Do Nothing. The FCO could stop its support once current PF projects under this theme end. But the GoI and most of the high potential states have limited policy frameworks and market responses to deliver energy investment sustainably. Without support from the PF, government ministries would not benefit from increased technical skills and implementation support, which may lead to weaker energy sector strategies and projects that are not investable. Energy sector investment and market growth will be achieved more slowly as a result. Opportunities for UK companies will also be of a lower scale and quality as a result.
2. There would be large indirect environmental impacts. A reduction in support to the sector in Indai would risk current interventions not being sustained and developed into more substantive projects delivering transformative change. This will lead to slower growth of lower carbon energy sources in the energy mix (and greater usage of fossil fuel based energy to meet growing demand), leading to negative environmental outcomes.
3. Option 2: Deliver through multilaterals like Asian Development Bank, World Bank, or UN agencies. FCO could end its bilateral support and instead channel funds into other energy sector multilateral programmes. Multilateral agencies have significant expertise and experience in energy sector programming. The FCO could reasonably influence their programme design and delivery. However, multilateral projects take time to get off the ground, thus limiting or delaying delivery. Upfront costs can also be significant. A large amount of control would be lost, making it particularly difficult to ensure a UK commercial focus. Delivery through multilaterals may also reduce visibility of the UK’s technical assistance to India and thereby any resulting relationship benefits. Technical energy sector support should lead to indirect positive environmental outcomes around avoided greenhouse gas emissions due to use of cleaner energy. Overall, this option could potentially deliver limited primary benefits in the timeframe and moderate secondary and UK-India relationship benefits that could otherwise be larger from a programme of this scale.
4. Option 3: Deliver through DFID by funding existing or new DFID Technical Assistance programmes. The FCO could provide funding to DFID, who have the experience and capability to deliver such a programme and is already delivering a £10m technical assistance programme supporting structural reforms in the Indian power sector and integration of renewable energy into the electricity network. However, the FCO will lose an element of control over the programme, which is likely to reduce the focus on secondary benefits for the UK. Overall, this option has the potential to deliver strong primary benefits, but with moderate UK commercial focus.
5. Option 4: Deliver through Primary Service Delivery Partner. The FCO could launch bilateral energy and low carbon programmes that provide strategic and technical advice and support on market and commercial partnerships development. The FCO does not have the resources to deliver such a programme directly and so the programme would be delivered by PSDPs who could procure downstream service providers. The FCO programme would support the wider UK-India Energy for Growth Partnership and work closely with DIT and DFID to maximise impact and avoid overlaps.
6. This option provides the FCO with the greatest level of control over risk and delivery. Technical energy sector support should lead to indirect positive environmental outcomes around avoided greenhouse gas emissions due to use of cleaner energy alternatives. Overall, the FCO is well placed to deliver strong primary and secondary benefits from the programme.

	Capability & capacity (5)	Overall cost effectiveness (5)	Control over risk and delivery (4)	Early benefits relative to upfront costs (3)	UK commercial focus (5)	Overall
Do nothing	Low	Low	Low	Low	Low	Low
Multilateral	High	Medium	Medium	Low	Low	Medium
DFID	High	High	Medium	Medium	Medium	Medium
PSDPs	High	High	High	Medium	High	High

Recommendation: Based on the above, option 4 – delivering through Primary Service Delivery Partners – is recommended.

Urban Development (£12.4m)
The following delivery options have been considered:
1. Do nothing
2. Deliver through the Asian Development Bank and/or World Bank
3. Deliver through DFID urban programmes
4. Deliver through a Primary Service Delivery Partner
1. Option 1: Do Nothing. This would significantly reduce the UK’s offer on urban development resulting in reduced development and opportunities for UK businesses. This would also risk current interventions not being developed into more substantive projects. This might also be interpreted as a signal that the UK has de-prioritised the urban agenda. Without UK support, fewer Indian cities will have access to technical assistance. Government officials will not increase their technical skills which may lead to weaker urban projects that are not investable.
2. Option 2: Deliver through the Asian Development Bank and/or World Bank. The FCO could end its bilateral support and instead channel funds into other urban multilateral programmes. The World Bank and Asian Development Bank are undertaking significant work in this area. They have strong expertise and experience which would ensure robust and effective programming. The UK could influence the objectives and scope. It would be challenging however, to facilitate secondary benefits to the UK. Delivery through multilaterals may also reduce visibility of the UK’s technical assistance to India and thereby relationship benefits. This option would effectively contribute towards primary benefits on poverty reduction. It is expected funding would not effectively support UK secondary benefits.
3. Option 3: Deliver through DFID urban programmes. The FCO could provide funding to current DFID-led urban programmes. DFID India has a strong knowledge and contact base in urban development in India and has begun to consider secondary benefits to the UK. Transferring funds, however, will heighten the risks around achieving specific outcomes and impact the programme. DFID’s larger urban development portfolio has a stronger focus on national and state levels of governance within India while the PF programme has been designed to focus at project-level to achieve its outcomes, including those with an enhanced commercial focus. This option would deliver strong primary benefits based on the previous results achieved by DFID. It is expected the intervention would deliver moderate secondary benefits.
4. Option 4: Deliver through a Primary Service Delivery Partner. The FCO would launch a separate programme that provides strategic and sector-level advice, up-skilling, and access to urban innovation and research. The programme would focus on urban sector constraints which are also aligned to skills and expertise. The FCO would leverage its cross government priorities and expertise to effectively deliver primary and secondary benefits. The programme team would work closely with DIT and DFID to ensure HMG activities were complementary and avoid duplication. In addition, the programme would remain fully responsive to the India PF’s other strands. Based on year one performance, it is expected the programme would deliver strong primary and secondary benefits.

	Capability & capacity (5)	Overall cost effectiveness (5)	Control over risk & delivery (4)	Early benefits relative to upfront costs (3)	UK commercial focus (5)	Overall
Do nothing	Low	Low	Low	Low	Low	Low
Multilateral	High	Medium	Low	Low	Low	Low
DFID	High	High	Medium	Medium	High	High
PSDP	High	High	High	Medium	High	High

Recommendation: Based on the above, both options 3 and 4 score highly. At present there is uncertainty around how a combined DFID/FCO programme would work in practice. Consequently, it is recommended that we proceed on the basis of option 4 – delivering through a Primary Service Delivery Partner.

A2. Recommendations
A summary of recommended delivery options are set out in table 6 below:
Table 6: Recommended delivery options
STRAND	AREA OF ACTIVITY	PROCUREMENT DELIVERY
All	All stated below	Up to 10% of each Strand budget will be available outside of the PSDP contract (except for EoDB). This could take the form of grants/ MoUs/ contracts made through the PF Framework Agreement or the open market. This will build flexibility and resilience into programmes to start work during procurement for the PSDPs (and during design) or for specific work that falls outside of PSDP contracts, but which are required to ensure the programmes’ relevance and responsiveness to new opportunities.
Ease of Doing Business	Central government support	Delivery through multiple delivery partners (including WB) / Three main stakeholders will be involved in delivering the programme – a single PSDP, IFC, and select UK Government Departments. The PSDP will be procured via a competitive tender through PF Framework Agreement. IFC will be brought on board through a bilateral agreement (MoU). Select OGDs will be retained for the programme through bespoke MoUs in line with departmental requirements. An overarching Steering Committee of relevant stakeholders will ensure complementarity across programmes.
	State level assistance
Skills	Skills market enabling and training capacity in five or more sectors	Transfer funds to DFID, who will undertake procurement to implement a co-funded programme. / The PF and DFID will co-fund a technical assistance programme. DFID, as the majority-funding partner, will procure and contract the programme. DFID will oversee the programme with involvement of FCO in governance arrangements. An MoU between the two departments will facilitate the transfer of funds and define roles, responsibilities, and the nature of the agreement.
Financial Services	Raising finance for infrastructure through the City of London	Deliver through a hybrid model / A hybrid model will be used to deliver the three pillars of the programme, using a combination of: (i) A contracted Primary Service Delivery Partner engaged via competitive tender through the PF framework agreement; (ii) Leveraging in-house BHC resources; (iii) Using specific project partners for defined strands of the programme, engaged via competitive tenders.
	Developing India’s financial markets
	FinTech Policy Development and Entrepreneurship in India
Energy & Low Carbon	Policy development and implementation	Contracting Primary Service Delivery Partner/s / PSDP(s) will be engaged via a competitive tender through the PF Framework Agreement. They are expected to comprise of a single agent or consortia with knowledge and expertise of Indian and UK energy markets and policy environments. The agency will sub-contract specific areas to partner organisations. Additional implementers may need to be contracted to deliver smaller complementary activity commissioned during the programme in order to adapt to opportunities as they arise, if these are outside the scope of the primary implementer.
	Tailored support for state/ city energy planning and project delivery
	Commercial and knowledge partnerships
Urban	Strategic state and city support (including on finance)	Contracting a Primary Service Delivery Partner. / A single PSDP will be engaged via a competitive tender through the PF Framework Agreement. They are expected to be either a single agent or a limited consortium of partners offering urban expertise and knowledge of the Indian and UK markets. The Agency will sub-contract specific areas of delivery to partner organisations.
	Project level expert advice
	Urban innovation and research and up-skilling of officials

Regional Focus
1. It is important to ensure that interventions are geographically focused to maximise the programme’s impact in the context of the size of the Indian economy. This means focusing support on cities and states where the potential for impact is higher. Targeting a coherent programme of support at a manageable number of states will maximise impact at both the strand and overall programme level. However, too narrow a focus will limit our ability to take advantage of India’s competitive federalism; we need the flexibility to pick several winners and respond to changing circumstances. We expect up to seven geographies to provide the necessary balance.
2. As demonstrated in the strategic case, the level of need across India is huge. The regional focus will therefore be guided by where the programme can achieve the most impact. This will be based on a number of factors including state size and economic potential, the location of burgeoning metropolitan clusters, opportunities within focus sectors, demand for UK technical support, political climate and governance, strength of the UK relationship with the state government, and UK commercial interests. It will also take into account which other donors and programmes are active in states, particularly DFID, in order to avoid duplication and leverage synergies. Early Market Engagement has already been used to test our choices. The decisions will be finalised, following recommendations delivered as part of the design phase of the strands.
3. This does not preclude working outside of the focus states, nor the addition or removal of states in light of changing circumstances. It does however mean that the focus states should be the first considered for this programme, and any work outside of these states will have to demonstrate a high level of opportunity. In practice, we expect the vast majority of funding to be disbursed in the focus states, with the remainder available to capitalise on high potential opportunities elsewhere.
4. The UK’s network of Deputy High Commissions and Trade Offices across India will play a crucial role in developing the programmes, using their local knowledge to inform programme design and leverage synergies across the strands, as well as using their local presence and networks to support delivery.

Theory of Change
The programme will use the UK’s knowledge, international network, convening power, brokering ability, relationships, and technical assistance blended with inputs from partners including contracted implementers, Government of India and HMG departments to deliver transformational change across the five strands. The programme will contribute to inclusive economic growth and poverty reduction, as well as increased UK-India trade and investment via the PF’s five intermediate outcomes. The full theory of change underpinning the five strands is set out below.

Urban Development
Improved climate and pandemic resilient urban infrastructure leading to reduction in urban poverty.

Energy and Low Carbon
Catalyse increased investment (both public and private) in renewable energy and storage deployment, electricity distribution, industrial energy efficiency/industrial decarbonisation and electric mobility leading to low carbon inclusive economic growth.

Financial Services
Expanded and deepened financial sector that protects financial stability and consumer interest by developing suitable regulatory framework whilst unlocking new financing opportunities.

Skill for Jobs
Improved Skill levels in the Indian labour market resulting into joint prosperity.

Ease of Doing Business
Improved participation of Indian and international businesses (including MSMEs and women-led/owned enterprises) in the formal economy, by fostering a harmonized, transparent business environment.

PRIMARY PURPOSE
Inclusive economic growth and poverty reduction in India through improved energy security and clean energy access, climate resilient cities, improved skill for jobs, private sector growth and job creation, increased tax base, and access to welfare support.
SECONDARY BENEFIT
Increased UK-India trade, and investment, exports in India and increased Indian FDI into the UK.
IMPACT
OUTCOME
OUTPUT
Urban Development
1. Planning, development and delivery of large scale, high-value, exemplar urban intervention projects (Invitation to Tender) developed and brought to the market.
2. Indian urban agencies have embedded new skills in the delivery of urban interventions to international standards.
3. Major innovation partnerships that foster collaboration between national and international urban actors announced.
Energy and Low Carbon
1. Increase investment in project themes of solar energy, off shore wind energy and energy storage through policy products, analytical tools.
2. Innovative new technologies and business models ready for commercial scale deployment.
3. New long-term partnerships established between Indian and international entities, academic, institutional and commercial actors, as well as women-led organisations, local actors.
Ease of Doing Business
1. Reduced regulatory and compliance burden and improved regulatory capacity and service delivery leading to more accessible markets and increased participation of Indian and International businesses.
2. Stimulating the formal tax base, particularly with respect to MSMEs and women-led/owned businesses, through reduced compliance burdens and improved perceptions resulting from an efficient and customer centric tax administration system.
3. Improved access to global markets for Indian businesses (particularly MSMEs and women-led businesses) through reduced customs procedures and harmonization of standards, aligned to international best practices.
Financial Services
1. Improved regulatory capability and capacity in savings and insurance.
2. A consistent and transparent insolvency framework; enhanced regulator and professional capability.
3. Increased interest of international and domestic investors for Indian infrastructure opportunities.
Skill for Jobs
1. Strengthened Skills eco system for selected sectors.
2. Expeditious & effective implementation of government skilling schemes.
3. Enhanced contributions to skilling in partnership with private sector including with UK businesses and institutions.
4. Skilling through innovation and piloting in up to 3 states, especially in the selected sectors.
5. Demonstrate / disseminate good practices / lessons learnt.
Context
The programme will use the UK’s knowledge, international network, convening power, brokering ability, relationships and technical assistance blended with inputs from partners including contracted implementers, Government of India and HMG departments to deliver transformational change across the five strands identified in the strategic case.
Assumptions 1. Initiatives /commitment and buy in from central and state government continues. 2. Buy in from HMG partners continues. 3. Access to the right legislators, regulators and officials. 4. Capacity and skills are used and retained after the programme ends. 5. Suitable private sector partners are found and are responsive towards the opportunity. 6. Availability of finance 7. UK firms /consortia/ joint ventures are competitive. 8. Scale up beyond specific project benefits.

C1: Outcomes to Impact
Does investment in infrastructure and human capital lead to sustainable economic growth?
Evidence: medium to strong
1. Investment in infrastructure and human capital creates the conditions for growth by providing businesses with access to the services and resources they need to expand production and access markets. All of the economies that have achieved high and sustained growth post-WW2 have had high rates of investment. Counting both public and private expenditures, these economies had investment rates of around 25% of GDP or above and often spent a further 7-8% of GDP in education, training and health[83]. Within the 25% figure, all of the economies displayed high rates of public investment in infrastructure at over 5% of GDP[84].
  [83] Commission on Growth and Development (2008), The Growth Report: Strategies for Sustained Growth and Inclusive Development, www.growthcommission.org p.34
  [84] Ibid.
2. Conceptually, infrastructure may affect aggregate output in two main ways: (i) directly, considering the sector contribution to GDP formation and as an additional input in the production process of other sectors; and (ii) indirectly, raising total productivity by reducing transaction and other costs allowing a more efficient use of conventional productive inputs.
3. A review of the literature[85] found that the weight of evidence shows a positive correlation between availability of economic infrastructure services and economic growth. While difficult to prove definitively due to methodological issues such as endogeneity and time-lags, the link is broadly accepted as no country has reached an advanced stage of development without good infrastructure. An International Institute for Sustainable Development study indicates that infrastructure development is key to achieving the Sustainable Development Goals[86]. Improved infrastructure accelerates growth in manufacturing, improves access to markets, reduces costs and supports smart urban development. IMF, World Economic Outlook document that infrastructure improves the quality of life and prosperity of people[87]. India ranks 80th of 148 countries on infrastructure[88], which is cited by firms as a major barrier to doing business. Increasing investment in infrastructure can therefore be expected to contribute towards economic growth.
  [85] DFID, GRD (2013) Infrastructure Thematic Review for the Growth Portfolio Review. Mimeo
  [86] International Institute of Sustainable Development - iisd.org/blog/why-infrastructure-key-success-sdgs
  [87] IMF (2014), World Economic Outlook
  [88] World Economic Forum (2015), Global Competitiveness Report
Energy & Low Carbon
Energy is key infrastructure where investment is required to drive economic growth. Any nation that wants to grow its economy and improve living standards must secure a robust energy supply[89]. The Government of India estimates that for GDP to grow at 9.0% pa, commercial energy supplies will have to grow at a rate between 6.5-7.0%[90]. However, GDP growth will only be sustainable if expanding energy supply is low carbon and avoids dangerous climate change. Additionally, there is substantial evidence that lower carbon transition in many green sectors, including energy, provide significant opportunities for investment, growth and jobs. For this to occur, however, new enabling conditions are required to promote investments.
[89] The Global Commission on the Economy and the Climate (2014), Better Growth, Better Climate: The New Climate Economy Report
[90] Government of India (2011), Faster, Sustainable and More Inclusive Growth, An Approach to the Twelfth Five Year Plan
Urban
The theory behind the potential of urbanisation to drive growth is ‘agglomeration’: the improvement in productivity of firms and populations from clustering as a result of economies of scale from lower transaction and transport costs and knowledge spill-overs between firms. There is good evidence of a positive relationship between firm productivity or employment and urban density. The economic literature also demonstrates a strong link between economic growth and poverty reduction[91]. It is therefore possible to demonstrate a medium-strong body of evidence that improving economic development planning in cities will lead to poverty reduction and job creation.
[91] DFID (2015), Infrastructure and cities for economic development
Skills
The international evidence on the links between better skills training leading to jobs and poverty reduction is as follows:
- There is positive evidence of increased income due to training, for example from Cambodia, where beneficiaries of the Training Grant Fund (TGF) had higher than average national wages[92].
  [92] Messerli. S (2012). Presentation: Skills for a Better Life. A brief overview of the Employment Fund Nepal, Helvetas/SDC.
- In Nepal, graduates of the Employment Fund reported a 2.6 times increase in income with contributions to household income increasing by up to 67%[93].
  [93] Review of Employment Fund Project Nepal. May 2013.
- A World Bank evaluation of Turkey’s ISKUR Fund found that the impact of training on the general population of unemployed was positive but not significant. The same study, however, says that results were significant where training was market-oriented and delivered through private providers.
Regarding apprenticeships, 75% of UK apprenticeship employers report that it helped their business improve product or service quality, while 46% of apprentices received a pay rise after completing their apprenticeship and the majority felt it had had a positive impact on their career[94]. Investments in skills are justifiable not just from a growth and productivity perspective but also for welfare, since improvements in education and skills are ends in their own right.
[94] https://www.gov.uk/government/publications/key-facts-about-apprenticeships/key-facts-about-apprenticeships

Does innovation and knowledge transfer, including of low carbon technologies, lead to sustainable economic growth?
Evidence: medium to strong
Reforms and interventions to promote innovation and knowledge transfer will create the conditions for sustainable growth by increasing the efficiency of production and raising firms’ and countries’ competitiveness. Moreover, innovation helps address global challenges, such as climate change, which otherwise act as a drag on growth.
- Both the quantity and quality of inventive activity within a country have a statistically significant positive impact on economic growth (Hassan & Tucci, 2010).[95]
  [95] Hassan, I. and Tucci, C. (2010), The innovation–economic growth nexus: Global evidence, Research Policy 39 (2010) 1264–1276
- Research and development activities within a country both stimulate domestic innovation and enhance technology transfer by improving the ability of firms to learn about advances in the leading edge (‘absorptive capacity’) (Griffith, Redding & Reenen, 2000).[96]
  [96] Griffith, R.; Redding, S.; Reenen, J.V. (2000): Mapping the two faces of R&D: productivity growth in a panel of OECD industries, IFS Working Papers, No. W00/02, http://dx.doi.org/10.1920/wp.ifs.2000.0002
Low-carbon and environmental technology
New technologies allow firms and consumers to cut emissions and reduce their impact on the environment without sacrificing production/ consumption. Growth strategies should take account of the cost of pollution from the outset, delaying the adoption of climate friendly technologies means locking in to technologies, infrastructures and behaviours that will be more costly to reverse or retrofit at scale later.
- Failing to address climate change could lead to 5-20% lower GDP per annum, forever (Stern et al, 2006).[97]
  [97] Stern et al. (2006), The Stern Review on the Economics of Climate Change
- Green growth pathways deliver faster growth than conventional growth pathways within 10 years (UNEP, 2011).[98]
  [98] UNEP, Green Economy Report, 2011
- 70-80% of the world’s resource productivity opportunities are in developing countries (McKinsey Global Institute, 2011).
Urban Development
Smart cities create conditions for growth by maximising the benefits of urbanisation and minimising costs. Strong urban planning can promote greater interconnectedness, knowledge transfer and access to infrastructure and services. Well planned cities can also minimise the negative impacts of congestion and pollution, which lower productivity. There is good evidence that there is a positive relationship between firm productivity or employment and urban density[99].
[99] Miller, H. (2014) What are the features of urbanisation and cities that promote productivity, employment and salaries? Evidence review commissioned by DFID under the Professional Evidence and Applied Knowledge Services (PEAKS) Framework.

Does trade, financial and economic reform lead to sustainable economic growth?
Evidence: medium
Structural reforms are policies that encourage more efficient use of resources and increase the ability to adapt to change. Such reforms create the conditions for sustainable growth by raising long-run supply potential, productivity and sustainability, and raising aggregate demand. A country’s comparative advantage will evolve over time. Structural reforms help to create more efficient markets where resources can respond to these shifts and a process of creative destruction can take place, with productive firms and industries growing and replacing obsolete ones.
Trade reform
Openness to trade allows greater competition, specialisation, idea transfers, and improves the business environment, reducing barriers to business and stimulating efficient production patterns.
- Overall, the long-term evidence from a broad sample of OECD countries indicates that an increase of 10% in trade exposure (trade as a % of GDP) was associated with a 4% increase in output per working-age person[100]. To the extent that wages are linked to productivity growth, greater openness also means a rising standard of living.
  [100] OECD. 2003. The Sources of Growth in OECD Countries, Paris
- Over the 1950–98 period, countries that liberalized their trade regimes experienced average annual growth rates that were about 1.5 percentage points higher than before liberalization (Wacziarg and Welch, 2008).[101]
  [101] Wacziarg, R. & Welch, K. (2008), Trade Liberalization and Growth: New Evidence, World Bank Econ Rev, Vol. 22 (2): 187-231
- Estimates using cross country evidence suggest that switching from being a closed to an open economy raises a country’s growth rate of real GDP per capita by 1.4%[102].
  [102] Wacziarg, Romain and Karen H.Welch (2008), \Trade Liberalization and Economic Growth: New Evidence," World Bank Economic Review, 22, 187-231.
Investment and financial market reform
Financial market development can help raise investment, spur innovation, facilitate technology transfer, and lead to a more efficient allocation of capital across sectors. The right institutions, regulations and supervision processes are needed to help avoid systemic risks. In addition, reforms to regulations on foreign direct investment (FDI) can create the conditions for growth by maximising the potential for positive spill-overs from investment. While there is debate in the literature about the direction of causality between growth and financial sector development, there is consensus that although financial market development may not be a sufficient condition for sustainable development, it is a necessary condition[103],[104]. For example, Alfaro et al. (2004)[105], conclude that FDI only has a significant impact on growth in countries with well-developed financial markets. Beck, Demirgüç-Kunt & Levine (2007) also find that financial development disproportionately boosts incomes of the poorest quintile and reduces income inequality[106].
[103] Alfaro, L., Chanda, A., Kalemli-Ozcan, S., Sayek, A. (2004). FDI and Economic Growth: The Role of Local Financial Markets, Journal of International Economics, 64, 89–112.
[104] World Bank (2007), Finance, Inequality and the Poor
[105] Alfaro, L., Chanda, A., Kalemli-Ozcan, S., Sayek, A. (2004). FDI and Economic Growth: The Role of Local Financial Markets, Journal of International Economics, 64, 89–112.
[106] World Bank (2007), Finance, Inequality and the Poor
Economic reform – competition regulations
1. Fostering competition generates growth by creating incentives for firms to increase efficiency, rewarding innovation; and driving efficient resource allocation. The cost and complexity of regulatory processes play a major role in deterring new businesses or their expansion. Gaps in competition policy enforcement also hinder effective competition between businesses, both domestically and internationally.
2. While competition features prominently in policy dialogue, its economic effects – in particular the relationship between competition and growth – are not well understood. Theoretical arguments and empirical evidence indicate that the impact of competition is complex and can be positive or negative depending on initial conditions[107].
  [107] For a summary of the evidence see Aghion, P. & Griffith, R. (2005), Competition and growth: Reconciling Theory and evidence, MIT Press
- Evidence from 24 transition economies, showed that firms facing 1-3 competitors saw sales grow by almost 11% over three years while monopolists saw sales decline.[108]
  [108] Carlin, Schaffer, and Seabright (2004), A Minimum of Rivalry: Evidence from Transition Economies on the Importance of Competition for Innovation and Growth, Contributions to Economic Analysis and Policy, vol. 3, p.1-42
- Buccirossi, et al. (2011) find a significant causal link between competition policy and total factor productivity growth for 22 industries in 12 OECD countries between1995-2005. The effect is strengthened by good legal systems, suggesting complementarities between competition policy and the efficiency of law enforcement institutions.[109]
  [109] Buccirossi, P., Ciari, L., Duso, T., Spagnolo, G., & Vitale, C. (2013). Competition policy and productivity growth: an empirical assessment. Review of Economics and Statistics, 95(4), 1324-1336.
- Examining the impact of the cartel law in the UK in the late 1950s Symeonidis (2007) finds strong evidence of a negative effect of collusion on labour productivity growth[110].
  [110] Symeonidis, G. (2008). The effect of competition on wages and productivity: evidence from the United Kingdom. The Review of Economics and Statistics, 90(1), 134-146.
Does increased policy and regulatory capacity lead to sustainable economic growth?
Evidence: medium
Ease of Doing Business
Capacity refers to a range of issues including technical knowledge and financial resources. Increases in capacity and capability enhance governments’ abilities to enact and implement successful policies and regulations that support sustainable growth, including through maintaining macroeconomic stability and the rule of law. Evidence shows the costs of a lack of government capacity to select and implement productive spending programmes:
- Public investment may not create productive capital in developing countries due to inappropriate use.[111]
  [111] Pritchett, L. 1996. “Mind Your P’s and Q’s: The Cost of Public Investment is Not the Value of Public Capital.” World Bank Policy Research Working Paper 1660.
- Public Infrastructure effectiveness is important in explaining growth differentials across countries.[112]
  [112] Hulton, C. (1996). “Infrastructure Capital and Economic Growth: How Well You Use it May be More Important than How Much You Have.” NBER Working paper 5847; Aschauer, D. (2000). “Public Capital and Economic Growth: Issues of Quantity, Finance and Efficiency.” Economic Development and Cultural Change, 48, 391 - 406.
- Both size and quality of government are important for economic growth.[113]
  [113] Cooray, A. (2009). Government expenditure, governance and economic growth. Comparative Economic Studies, 51 (3), 401-418.
Does improved ease of doing business lead to sustainable economic growth?
Evidence: strong
Ease of Doing Business
1. Increasing the ease of doing business improves market efficiency and increases incentives for domestic and international firms to invest by reducing uncertainty and creating a level playing field for firms. Levelling the playing field and strengthening property rights is crucial to developing the inclusive economic institutions that are key to the open economies strand of the ‘golden thread of development’. Increasing rules-based transparency,
2. protecting the rights of entrepreneurs, and lowering rents reduces the incentives for elites to hold on to extractive political institutions, creating a virtuous circle of self-reinforcing inclusive economic and political institutions. Evidence supporting these impacts includes:
- A study focused on Asian economies demonstrated that ease of doing business has a significant effect on economic growth, with trading across borders identified as the single most important factor, implying that India’s poor performance in these areas is a significant growth constraint[114].
  [114] Asia Pacific Journal of Multidisciplinary Research, vol.3, no.5 (2015), Effect of ease of doing business to economic growth among selected countries in Asia
- Djankov et al (2006)[115], using data from the Doing Business report for 136 countries, found that improving from the worst to the best quartile of business regulations within their sample implied a 2.3% increase in average annual growth.
  [115] Simeon Djankov, Caralee McLiesh and Rita Ramalho, ‘Regulation and Growth’, Economics Letters 92 (3): 395–401, 2006
- A 2002 study[116] of companies in post-communist countries (Poland, Romania, Slovakia, and Ukraine) found that firms that believed that their property rights were secure re-invested between 14% and 40% more of their profits in their businesses.
  [116] Johnson, Simon, John McMillan, and Christopher Woodruff. 2002. “Property Rights and Finance.” American Economic Review, 92(5):1335–56.
- Freund and Bolaky (2008)[117] found using data from 126 countries over 5 years that trade leads to higher living standards in countries with good regulatory environments (as measured by Doing Business scores), but not in those with poor environments (and that the regulatory environment is more important in this regard than financial development, education, or the rule of law).
  [117] Freund C, and Bolaky B, (2008), ‘Trade, Regulations, and Income’, Journal of Development Economics 87: 309-21
- World Bank Enterprise Surveys of 40,000 firms in over 100 (mostly developing) countries found that the business environment was the top constraint cited[118].
  [118] IFC Jobs Study ‘Assessing private sector contributions to job creation and poverty reduction’, p.41, January 2013, IFC
- 2014 research[119] using a database of some 25,000 firms from 78 developing countries concludes that the developmental impact of foreign direct investment is highly dependent on how good or bad a country’s general business environment is.
  [119] ‘The Role of Mediating Factors for FDI Spillovers in Developing Countries: Evidence from a Global Dataset’, T Farole, D Winkler, in ‘Making Foreign Direct Investment Work for Sub-Saharan Africa: Local Spillovers and Competitiveness in Global Value Chains’ January 2014, World Bank

Figure 9: Ease of Doing Business and Global Competitiveness

Ease of doing business is correlated with global competitiveness. Enabling growth and ensuring all people can participate in its benefits requires a strong regulatory and rules-based framework. Where regulations are onerous, levels of informality tend to be higher. Firms in the informal sector typically grow more slowly than their formal sector counterparts, employ fewer workers, and are also less likely to pay taxes[120].
[120] World Bank (2014), About Doing Business: Measuring for Impact
UK benefit
The five outcomes will contribute to greater market openness, market reforms, and adherence to domestic and international rules, which together create a better, more certain business environment and growing opportunities for UK businesses via trade and investment. In addition, relationships built through diplomacy under the programme will give UK businesses a competitive edge in accessing these opportunities while also placing the UK in a good position to benefit from international partnerships and Indian foreign direct investment. As a result new opportunities and mutually beneficial economic relationships will be developed in sectors of UK comparative advantage.

C2: Outputs to Outcomes
Does increased government capacity and the introduction of more efficient administrative systems lead to improved Ease of Doing Business?
Evidence: strong (Ease of Doing Business is strongly correlated with the willingness of the government to streamline administrative processes and actual measures taken to make relevant systems more efficient.)
1. Previous PF projects have demonstrated the value of government-to-government support in this area. Advocacy and support from the UK’s Regulatory Delivery Directorate (RDD) has led to states like Maharashtra planning a phased implementation of the RDD’s risk assessment framework across selected departments, covering regulation and inspection of businesses. This will help businesses by providing quicker registration, streamlining permits and licences, and improving services like electricity connection. Similarly, a team led by the Chief Technology Officer from the UK Government Digital Service met officials from India’s Department of Administrative Reforms & Public Grievances to share best practice on IT frameworks. This led to both departments agreeing to launch a pilot study on digital standards and design in India, based on UK frameworks.
2. While there is less evidence on the best delivery routes for regulatory reform, a number of conclusions can be drawn from how successful reform initiatives have been delivered globally:
- Successful reforms require significant government commitment. For example, Tanzania’s Business Enabling Environment Strengthening programme did not achieve its targets because it was unable to attract the right support from government or build consensus within the private sector to push for reforms. This speaks in favour of smaller scale reform initiatives that build the case for further reforms, and can be more tightly managed[121].
  [121] DFID (2014), Ghana Business Enabling Environment Programme
- Business enabling environment reforms are complex and require political will and incentives to improve exchanges and accountability dynamics between business, government and civil society. Reform actors and agencies will have to take an active role in defining and leading the reforms if the efforts are to be sustained. Therefore the management arrangements will have to flexible allowing technical assistance and support to be delivered in a timely and appropriate manner in response to stakeholders[122].
  [122] Ibid.
- Taking a results-based approach to delivering specific reforms rather than focusing on delivering the easy inputs (training) is important.

Do improvements in training capacity and the provision of enterprise support lead to a better skilled workforce and SME growth?
Evidence: medium to strong (there is strong evidence that targeted vocational skills training leads to development of a better skilled workforce and that higher competition among skills providers pushes up the quality of training which, in turn, reflects in higher productivity. However, the conclusions are sensitive to the nature of the skills being targeted).
1. There is some evidence of positive impacts of private sectors skills provision. An Inter-American Development Bank programme in Colombia found that training increased the likelihood of employment and an improvement in quality of jobs. Evaluations of this and other IADB job training programmes for young people from disadvantaged backgrounds in Latin America report that, in general, women and younger cohorts were most likely to benefit in terms of increased likelihood of employment[123].
  [123] DFID (2015), Skills for Jobs programme (https://devtracker.dfid.gov.uk/projects/GB-1-202865/documents)
2. Literature on skills programmes indicates that improved capacity of skill providers strengthens competition among them. In a competitive market skill providers are more conscious of the quality and market relevance of the training they provide. This in turn leads to better quality of skill providers for students and development programmes to choose from. It is therefore reasonable to assume that in a market where there is a significant undersupply of skills providers, increasing the supply of good quality providers can only improve output, particularly if those training providers can also play a role in employment facilitation. Evidence shows that increasing skills accreditation capacity also has benefits since students with internationally recognized certificates have higher job mobility and can compete better for jobs[124],[125].
  [124] Labour Market Policies Under a Youth Bulge. David Robalino and Yoonyoung Cho. World Bank Policy Papers series on Pakistan. Pk 14/12. 2012.
  [125] The Right Skills for the Jobs – Rethinking Training Policies for Workers. Rita Almeida, Jere Behrman, David Robalino, The World Bank, 2012.
3. Assuming that increasing the provision of quality vocational training leads to an increase in the size of the skilled workforce, focusing resources on increasing training capacity, rather than on direct skills training, represents better value for money as each pound spent supports the training of multiple students. Evidence also shows that vocational training represents equally good or better value for money when compared to more general skills. An analysis of data from eleven countries in Latin America in 1994 showed that half of these countries demonstrated a return for vocational secondary education that was higher than that for general secondary education[126].
  [126] International Growth Centre working paper 11/1017 (2012), Lessons for developing countries from experience of technical and vocational education and training
4. There is strong evidence indicating that training needs to be boosted with comprehensive complementary interventions if it is to lead to work. Though evaluations of technical assistance with baseline data are limited, there is evidence of year-on-year improvements in market outcomes due to technical assistance that helps build the institutional and technical capacity of training funds. Known elements that contribute to success are: participation of the private sector in the design, delivery and monitoring of training, monitoring and follow up of individual participants, job search and placement assistance, career guidance, and even going beyond the fund and building the capacity of the relevant ministry with a human resource/labour mandate[127],[128],[129],[130].
  [127] Rwanda Skills Development Fund, a component of the World Bank-funded Skills Development Project 2011 – 2016). Implementation Status & Results (ISR) report, October 2014.
  [128] Guinea Skills Fund (major component of the World Bank-funded Stepping Up Skills project).
  [129] Ghana: Financing of Skills & Technology Development Programs through the Skills Development Fund (the major component of the World Bank-funded Skills and Technology Development project.
  [130] http://www.youth-employment-inventory.org/inventory/view/162/
5. Collaborating on skills with the Government of India is a proven model for delivery of mutual benefit to India and the UK. A joint venture between two UK and Indian skills companies has secured subsidised loan funds from NSDC worth INR13m to support a diversified skills delivery portfolio comprising (i) certification services to third party skill development operators (ii) corporate up-skilling projects (iii) government projects, including both training and consulting assignments, and (iv) candidate training through own and franchised centres.
6. Similarly co-funding between the Government of Maharashtra and the previous PF delivered a Centre of Vocational Education in Pune. A UK organisation undertook the feasibility study and delivered the training and certification. As a result, the same organisation is now due to be engaged by an Indian engineering company on a commercial basis to provide international certification.

Does the promotion of international standards and access to expertise and enterprise support lead to financial reforms, increased capital flows and SME growth?
Evidence: medium (financial reforms and their translation into increased capital flows is a longer term and somewhat uncertain process. Although there is some evidence that technical assistance can spur financial reforms, this is contingent on political will and supporting political processes. Likewise, targeted enterprise development programmes impact SMEs positively, but this is sensitive to the nature of the enterprises being targeted)
Financial Services
1. Previous PF projects have demonstrated the role technical assistance can play in achieving financial reforms. An Insurance Laws Amendment bill that increased the foreign direct investment (FDI) limit to 49% had been pending in the Indian Parliament since 2008. A PF project laid out the benefits of the increase and used the project recommendations as an advocacy tool to engage with the Ministry of Finance to push the bill through. The bill was passed in 2015 resulting in foreign players, including UK re-insurers, being able to enter the market more easily. As a result two major UK insurance firms increased their stakes in the Indian market. It is estimated that revenues for UK insurers in India are likely to increase by up to £3bn by 2020. Similarly, IUKFP reports and recommendations have already led to legislative change in India – for example, announcements by the Reserve Bank of India to strengthen the corporate bond market. The PF will help support this work in future.
2. Financial sector development is a long-term process and requires longer term support in order to catalyse change. While the evidence base underpinning technical assistance programming in this area is limited, it reasonable to assume that a programme-focused option will have greater outcomes than a project focused approach[131]. Since success has already been demonstrated with the former and given that the programme will be focused on concrete, measurable targets linked to clear outputs, there is confidence of success. Nevertheless, recognising that there are some weaknesses in the evidence linking technical assistance interventions to financial sector reform, the programme will seek to build this evidence base through knowledge management and best practice related to its activities.
  [131] DFID (2013), Financial sector reform and strengthening initiative (FIRST): support for Phase III
Entrepreneurship
1. The enterprise support component of this intervention is based on the success of DIT’s Tech Rocketships project. £50k of annual funding has supported over 20 companies in three years, creating 25-30 jobs and helping four Indian companies enter and invest in the UK market.
2. However, the track record of government and donor provision of business development support is mixed. For example, independent evaluations of the Chilean government’s BDS provision showed that the programme has had little impact[132]. On the other hand, earlier widespread entrepreneurship development programmes introduced by the Government of India in the 1990s showed strong gains in sales and profitability with differences between the treatment and control group that were statistically valid[133]. An evaluation of large-scale BDS provision in Bangladesh found that when BDS was provided by private sector providers in combination with access to finance the performance of recipients was markedly better[134]. Access to finance and management training only make a difference if targeted at transformational enterprises[135].
  [132] Tang, H. (2009), Evaluating SME Support Programs in Chile Using Panel Firm Data. The World Bank, Policy Research Working Paper 5082
  [133] Awasthi, Dinesh, Approaches to Entrepreneurship Development: The Indian Experience, Journal of Global Entrepreneurship Research, Winter & Spring, 2011, Vol.1, No.1, pp.107-124
  [134] Sarder, et al. (1997), “The Importance of Support Services to Small Enterprises in Bangladesh”
  [135] World Bank WDR (2013), Can Entrepreneurship be fostered? Chapter 3

Does supporting policy reform and the energy ecosystem lead to more efficient energy markets and increased energy investment?
Evidence: strong (policy commitments, financial instruments for investment and structural adjustments are key components for supporting green energy growth in the power sector. Targeted policy mechanisms can lead to successful transition to green energy growth. Carefully designed policy reforms attract private finance and incentivise suppliers for investing in green capacity addition as well as energy efficient solutions).
1. Existing research underlines the impact of reforms on key economic variables in the Indian electricity sector, and the importance of further reforms[136]. Systematic analysis was undertaken of the impact of differing electricity market reform programmes on efficiency, price and investment flows in 19 states in India during 1991-2007. This study underlined the importance of sustained, long-term effort, the need to remain close to the politics, and that the real prize is tariff rationalisation (although this would need to be approached sensitively, over time)[137]. Evidence suggests that previous targets for reforms, including on access, distribution reforms etc. are often delayed, despite huge public sector investments being available[138]. DFID consultations highlighted that international technical expertise would be useful to maximise the impact of the available funding[139]. Evidence from DFID’s previous power sector reform programmes in five states suggests that capacity-building can lead to improvements in the regulatory and policy environment, improved performance and greater transparency[140]. A review by DFID (2015) highlighted the positive impact of targeted Technical Assistance on improving the policy and regulatory environment and leveraging additional public and private resources within the Indian power sector[141].
  [136] FICCI (2013), Power transmission: the real bottleneck
  [137] Sen, A. and Jamasb, T. EPRG Working Paper 1001, Cambridge Working Paper, The Economic Effects of Electricity Deregulation: An Empirical Analysis of Indian States (2010).
  [138] Planning Commission of India, 12th Five Year Plan (2012-17), Volume II, Chapter 14
  [139] DFID (2015), Supporting structural reforms in the Indian power sector
  [140] MP Power Sector Reforms: Support to Electricity Regulatory Commission, Project Completion Report 2002-2005; Andhra Pradesh Power Sector Reform Programme: Impact Assessment Study
  [141] DFID (2015), Lessons Learnt from DFID India’s support for Power Sector Reforms over 20 years
2. At the same time, current and previous PF projects demonstrate the value of targeted support to policy agencies/ private sector to create business opportunities in the energy sector. UK technical assistance has improved market access and increased commercial opportunities in the Indian gas sector for businesses, including UK companies, through reforms on commercially viable pricing, extending exploration contracts and streamlining processes. On the back of these reforms UK companies have signalled interest in increasing their investment. Similarly, a current PF project is supporting the GoI in launching an international call for bids for its first offshore wind projects. Recommendations on the potential bidding criteria and electricity tariffs that should be offered to attract international companies were shared with Government of India in October 2016. These recommendations developed in consultation with Indian stakeholders draw heavily from UK best practices, and are likely to shape and influence policies in the future. UK companies are expected to participate extensively in the international tender.

Does knowledge exchange and better planning lead to more and better urban infrastructure development?
Evidence: strong (Technical assistance is generally known to enhance the development of urban infrastructure. This is especially so where inadequate knowledge exchange is seen as a critical impediment to urban planning, and innovative financing can yield quick returns.)
1. There is evidence that the benefits of agglomeration can be offset by rising congestion, over-crowding, overloaded infrastructure, pressure on natural resources and ecosystems (such as water courses and air quality), and higher labour and property costs. These ‘agglomeration diseconomies’ increase as cities expand, especially if urbanisation is poorly managed and cities are deprived of essential public investment to maintain and expand infrastructure. The effects may be to increase business costs, reduce productivity, dampen private investment, and restrict economic growth[142].
  [142] DFID (2016), Future Cities Africa: developing action plans and tools for sustainable growth
2. There is broad consensus that support from the development community for well-planned and managed urbanisation is currently inadequate. Multilateral partners such as the World Bank have been undertaking various strands of work on cities, but beyond the 2009 World Development Report, there has not been a strong focus on the opportunities cities present for economic development collectively across donors and multilaterals[143].
  [143] DFID (2015), Infrastructure and cities for economic development
3. Nevertheless there is evidence that technical assistance programmes can be effective. DFID India’s Support Programme for Urban Reforms in Bihar has helped the state to almost double its self-generated revenue; amend legislation to enable cities to meet the requirements of the new urban national schemes and programmes like AMRUT and Smart Cities; and set up institutions for innovative financing[144].
  [144] DFID (2016), Support programme for urban reforms in Bihar: annual review summary sheet
4. Current PF projects have already begun to demonstrate the value of targeted assistance. For example, support given to the Special Purpose Vehicles set up by cities in Madhya Pradesh has helped them to develop an initial project pipeline of £100m, which is set to triple. In Pune, PF work has supported the delivery of an intelligent transport strategy for public buses. Both of these examples have subsequently resulted in commercial benefits for international and UK companies.

C3: Key assumptions
OUTCOME ASSUMPTIONS	JUSTIFICATION
Government initiatives/ commitment continues	The programme is focusing on areas where there is clear development need and cross-party consensus for continued government action.
Capacity and skills are used and retained after the programme ends	Stakeholders will be treated as clients, ensuring they play an active role in programme design. Flexible approach in order to tailor the necessary implementation support, which must be client-led.
Private sector responds to the opportunity	Continuous business engagement and past programmes provide evidence of private sector appetite in the focus sectors, as well as indicating what barriers the programme must address in order to improve this and translate into commercial benefits.
UK firms/ consortia/ joint ventures are competitive	Past performance demonstrates that under the right conditions UK firms are competitive. Driven by business engagement and DIT intelligence, the programme will focus on areas where this is most likely and will assist with coordination of India-UK commercial partnerships to enable UK firms to be competitive.
Scale-up beyond specific project benefits	Effective demonstrator projects in high demand sectors should result in both validated learning and a reduction in perceived risk.

OUTPUT ASSUMPTIONS
Buy-in from central and state government	The programme is focusing in areas where government initiatives are active and demand for assistance is high.
Buy-in from HMG partners continues	HMG partners have been engaged, enthused, and have participated in previous relevant work in these areas.
Availability of finance	Significant focus is given to increasing the availability of finance, not just within the Financial Services strand but also Energy and Urban strands. The programme also has links with sources of finance such as the UK-India sub-fund of the National Infrastructure Investment Fund, DFID’s start-up capital fund, and CDC.
Access to the right legislators, regulators and officials	The BHC and wider India network have good relationships with a wide range of key stakeholders in India, built up over many years. There is no reason this should change. India is a priority for the UK government and high level UK ministerial engagement will continue to facilitate access for UK officials.
Suitable private sectors partners can be found	The market is well developed and the potential commercial spin-offs from the work should make it an attractive proposition for suppliers.

Economic Appraisal
Having selected the most appropriate delivery option, the economic appraisal focuses on comparing the resulting recommended technical assistance programme with ‘doing nothing’ as the counterfactual, to ensure that the programme represents good value for money and remains so if risks materialise during implementation. This is analysed at the strand level, with a suitable counterfactual identified and described below given the context of the proposed strand intervention.
	‘Do nothing’ counterfactual	Intervention
Ease of Doing Business	Growth at 0.2% (expected baseline) related to ongoing business environment reforms.	Growth of 0.21% in the targeted states in the two years post intervention.
Skills	1m people receive skills training in relevant sectors over the next five years.	Same 1m people receive higher quality skills training in the next five years.
Financial services	Continued growth based on current trend increase in the size of the Indian bond market (estimated at 10%).	Additional 0.1% annual increase in the size of the Indian bond market.
Entrepreneurship	Continuation of 4.5% average annual growth rate for Indian SMEs.	Increased annual growth rate (5.5%) for supported firms in the second and third year post intervention.
Energy & Low Carbon	Continued baseline increase in energy capacity (and energy mix) in line with current expectations.	Approximately 5GW additional cleaner energy capacity by 2027.
Urban Development	Continued baseline increase in urban infrastructure investment plus approximately £0.5b in additional investment resulting from expected DFID intervention.	Almost £1bn in additional urban infrastructure investment resulting from a combination of both DFID and FCO interventions (min. £500m directly generated from PF programme).

In all cases the intention has been to estimate the additional benefits that will occur beyond the counterfactual case, and to assess how much of this is reasonably attributable to the PF intervention.

D1. Quantified costs and benefits
1. In-keeping with HMT guidance, a discount rate of 10% has been applied to primary benefits, and 3.5% to programme costs and secondary benefits. This appraisal period is 10 years from the start of the intervention (2017/18), with results given after both five and 10 years.
2. The costs of the programme are as profiled in the financial case below. An attempt has been made to quantify and value the following benefits under both the counterfactual and intervention scenarios:
	Quantified primary benefit	Quantified secondary benefit
Ease of Doing Business	Increase in India’s GDP resulting from business environment reforms in focus states.	Proportion of reform benefits that will additionally accrue to UK companies.
Skills	Increased income received by the 1m people receiving training as a result of this programme.	Increase in UK share of India’s advanced and specialist skills training market. / Productivity benefits to UK firms as a result of improved labour supply.
Financial Services	Increase in size of India’s corporate bond market.	Increase in the value of the UK’s financial services business in India.
Entrepreneurship	Increase in turnover of supported Indian SMEs. / Increased income to new hires as a result of jobs created in India.	Increase income to new hires as a result of jobs created in the UK.
Energy & Low Carbon	Increase in clean energy capacity as a result of programme leveraged investment.	Additional contracts for UK firms providing goods and services relating to the programme leveraged investments. / Increased business and fees for UK financial firms facilitating these investments.
Urban Development	Increased income to new hires as a result of jobs created by programme leveraged investments. / Welfare benefits of additional infrastructure investment.	Increase in UK share of India’s urban development market.

1. Full details of the methodology used and assumptions made are presented in Annex A, along with a breakdown of the annual results by programme strand. there is a large amount of uncertainty involved in this exercise due to information gaps and multiple factors at work. There are also risks and uncertainty on the potential success of the programme. Accordingly, we have attempted to use conservative assumptions wherever possible, based on whatever evidence is available. Nevertheless, caution is advised when interpreting these results.
2. Five and 10 year net present values for the programme as a whole are summarised in table 7 below for both the primary and secondary benefits. Lower, central and higher cases have been modelled in recognition of the large uncertainties involved, within the same conservative framework. Since the counterfactuals for each programme strand are not comparable, it is difference between the counterfactuals and the three intervention cases for each strand that have been combined and presented.

Table 7: Net Present Value and BCR summary
	NPV Primary (£m)		NPV Secondary (£m)
	5yrs	10yrs	5yrs	10yrs
Higher estimate	235	1,091	186	883
Conservative central estimate	151	741	97	574
Lower estimate	67	438	48	308
	BCR Primary		BCR Secondary
	5yrs	10yrs	5yrs	10yrs
Higher estimate	5	20	4	17
Conservative central estimate	3	14	2	11
Lower estimate	2	12	2	6

1. The net present value difference is positive in all cases. Even in the lowest case the intervention presents good value for money in the short term (5yrs) and excellent value for money in the medium term (10yrs).
2. secondary benefits are based on revenue figures. No attempt has been made to disaggregate profits, but neither has any attempt been made to account for supply chain benefits. It is reasonable to assume that many UK companies, whether operating at home or abroad, will have a significant UK presence within their supply chain and so secondary revenue benefits are likely to be underestimated.
3. In order to give figures in pounds sterling, exchange rates have had to be used. This appraisal has taken £1 as equal to $1.25 and INR85, which are reasonable at the time of writing.

D2. Unquantified benefits
1. In addition to UK supply chain benefits, there are a number of benefits that have not been monetised because of lack of data or otherwise. For all strands these include:
2. Induced income effect: This is the effect attributable to the ensuing change in compensation of employees and other incomes, which may cause further spending and hence further changes in final demand e.g. as a result of the direct and indirect effects the level of household income throughout the economy will increase as a result of increased employment. A proportion of this increased income will be re-spent on final goods and services. All of the strands that result in jobs being created will induce this effect but valuing this has not been attempted.
3. Carbon emissions reduced: Several strands, particularly Energy & Low Carbon and Urban, will result in a relative reduction in emissions, which is a social benefit. In the case of the energy and low carbon strand, it is assumed that in the short term the increased cleaner energy capacity is additional and therefore will actually increase total emissions. However, in the long term this capacity will substitute for dirtier forms of energy, resulting in an overall reduction. Modelling this has not been attempted, especially given the relatively short appraisal period.
4. Ease of Doing Business: Improvements in focus states are likely to spill over into other states via knowledge transfer and may also spur competition since the state ease of doing business rankings are a high profile metric by which states are judged.
5. Urban Development: UK investment in Indian urban infrastructure projects will also increase, both via the directly supported projects and indirectly as pilot projects increase demand by demonstrating commercial returns. However, the timescale of infrastructure projects means that the majority of returns are likely to materialise after the ten-year appraisal period and so these benefits have not been quantified.
6. Financial services: The appraisal only looks at capital market benefits as a proxy for all benefits resulting from the programme, but there are likely to be additional social benefits that will result from improvements in the pensions and insurance industries that have not been monetised.
7. Entrepreneurship: As well as UK supply chain benefits not being monetised for all strands, there will be benefits to the Indian supply chain via the entrepreneurship strand that have not been monetised due to lack of information.
8. Energy & Low Carbon: This appraisal has only monetised the benefits accruing from the additional energy capacity. It has not attempted to value the additional jobs that will be created as a result of that extra capacity in order to avoid any double counting with this or other interventions/inputs, in-keeping with the general principles of caution and conservatism.
9. Skills: Only 50% of those trained are assumed to find employment in the short term. However, in those additional skills may benefit even those who do not immediately find employment, if their prospects are improved in the long term.

D3. Ensuring value for money
1. Value for money will be measured on an on-going basis at the strand level, drawing on the logframes developed for each of the programme strands. These will be further revised and developed during the procurement process be agreed as a delivery of the design phase of each strand, and in collaboration with the teams appointed to undertake monitoring and evaluation.
2. From an economy perspective, the cost of procuring inputs for the programme will be considered. Given the nature of the programme, key indicators will include:
- Average consultancy fee rates across the components;
- Percentage of local consultants engaged out of total consultant pool;
- Unit costs of any training or related materials;
- Overheads as a percentage of total spend;
- Total unit costs of TA delivery (including overheads, delivery costs, expenses, etc.)
The efficiency with which inputs are converted into outputs is a second key value for money aspect. Indicators may include:
- The cost of new products developed (e.g. evidence products, delivery plans, bespoke toolkits, business/financial models);
- The volume of relevant stakeholder funds and resources leveraged, both public and private, for every pound of funding;
- Productivity gains realised in supported firms for every pound of funding.
The extent to which the programme delivers value for money for effectiveness will be measured by the extent to which programme outputs translate into high-level outcomes. Capturing and measuring these outputs will not be trivial. They may include:
- Policy recommendations adopted;
- Jobs created/incomes raised linked to the intervention;
- Infrastructure investment/projects linked to the intervention;
- Energy capacity linked to the intervention;
- Improvements in Ease of Doing Business rankings linked to the intervention;
- UK commercial wins linked to the intervention.
1. Similarly, cost-effectiveness will be measured by estimating the cost per outcome, i.e. high-level outcomes divided by input costs.
2. Input costs will be measured to ensure that input costs do not exceed market rates. This will be achieved by comparing costs to those of similar programmes in India, especially those of other donors. They are not generally expected to decline during the life of the programme, but rather are likely to increase in line with wage growth. Each programme strand will continually appraise which activities are working most effectively, using the sort of metrics set out above, and adapt accordingly, while also taking into account the expectation that benefit trajectories will differ depending on the type of intervention. The above indicators above will also be disaggregated by gender to allow some assessment of equity.
3. Baselining will be undertaken during programme design phases as part of the approach to monitoring and evaluation. The benchmarks denoting poor value for money for each programme strand will also be developed during the design phases. In the event of these occurring, the FCO will consider significant modification to the programme course, strategies and partnerships, including the option of stopping funding for the relevant initiative.

Sustainability and Gender Equality
E1. Sustainability
The programme will maximise the likelihood of sustainability by focusing on removing economic roadblocks, rather than powering the economic vehicle itself. Successful programme activities should therefore result in a medium to long-term change that is less subject to reversal, thus removing the need for continuous support. The key to this is the translation of outputs to outcomes by stakeholders that are incentivised and empowered to do so. This means:
- Training and capacity building tools and resources will only improve capacity in the long-term if senior managers and their subordinates see the continued benefits of implementing them;
- Policy reforms will only be adopted and followed if they are aligned with interests of key stakeholder, including the politicians and officials tasked with implementation;
- Market development will only be sustained if support projects are replicable and scalable and investor returns are demonstrated under market conditions;
- Commercial partnerships will only be maintained if they prove more profitable for all parties than alternative options.
The programme will promote these sustainable outcomes by adhering to a number of fundamental principles:
1. Focusing on sectors/ themes of high primary demand (i.e. supporting key Government of India policy initiatives) and high secondary supply (i.e. where the UK has expertise to offer);
2. Developing the programme in partnerships with a full range of stakeholders, including at both federal and state level, to ensure optimal design and a broad base of support;
3. Focusing on progressive states that are open to reform and seek our assistance;
4. Embedding the programme within the British High Commission’s continuous work on policy engagement;
5. Promoting private sector solutions wherever possible in order to support commercial sustainability;
6. Emphasising the importance of research and evidence building to both capture learnings and also demonstrate the benefits of sustained change

E2. Poverty Impact
Despite its positive economic growth story, India still faces enormous development challenges:
- India is home to one third of the world’s extreme poor (circa 300m people)[145];
  [145] UN (2015), India and the MDGs: Completing the Task
- India ranks 131th on the UNDPs Human Development Index[146];
  [146] UNDP (2015), Human Development Report
- India ranks 100th on the Global Hunger Index out of 119 (in the ‘Serious’ category)[147];
  [147] International Food Policy Research Institute (2017), Global Hunger Index
- 240m Indians have no access to electricity[148];
  [148] International Energy Agency (2016), World Energy Outlook 2016
- India is the third largest carbon emitter and is set to double emissions by 2030[149];
  [149] World Resources Institute (2015), CAIT climate data explorer
- Inequality is high and increasing. India’s Gini coefficient of inequality is 51, up from 45 in 1990, and amongst the highest in Asia[150].
  [150] IMF Working Paper (2015), Sharing the growth dividend: analysis of inequality in Asia
1. The primary purpose of the programme is to contribute to inclusive economic growth and poverty eradication India. The five focal areas of this programme reflect those sectors, which are assessed as being most critical for unlocking barriers to economic growth, which will translate through into poverty eradication at the city, state and national level.
2. The correlation between economic growth and poverty in India is evidenced by the below.

Source: McKinsey Global Institute analysis
At the strand level the following poverty benefits are expected to result from the interventions of this programmes:
- Financial services: As of 2014, almost half of all Indian adults did not have access to banking and financial services and only 14% of Indians had any formal savings[151]. Improving financial services translates into poverty impacts by increasing the ability of poor people to receive financial benefits, to access credit for income generation purposes e.g. micro-finance for SME development and to build their resilience to and mitigate risks – including by providing a financial safety net.
  [151] World Bank (2014), Financial Inclusion Data / Global Findex
- Ease of Doing Business: There is strong correlation between a country’s ease of doing business ranking and the size of its informal economy. Improving India’s ranking from 100 to 50 – as per Modi’s ambition – would unblock much needed investment and imply an addition of approx. £200bn to official GDP (World Bank 2015). This would significantly increase India’s tax base and unburden small businesses to enable their growth, resulting in job creation and increased social welfare spending. It will also bring more poor and marginalised citizens, especially women, into the formal economy.
- Energy & Low Carbon: 300m Indians lack access to electricity, which acts as a critical barrier to moving out of poverty (economic time spent collecting fuel wood, impact on education, health impacts from indoor air pollution, restriction on energy dependant income generating activities etc.). The Government of India estimates that for the GDP to grow at 9.0 per cent per annum, commercial energy supplies will have to grow at a rate between 6.5-7.0% per year[152]. However, GDP growth will only be sustainable if expanding energy supply is low carbon and avoids dangerous climate change. There is substantial evidence that lower carbon transition in many green sectors, including energy, provide significant opportunities for investment, growth and jobs – all critical enablers for poverty alleviation.
  [152] Government of India (2011), Faster, Sustainable and More Inclusive Growth, An Approach to the Twelfth Five Year Plan
- Urban: As a result the provision of basic urban services is also poor. India’s urban population has increased from 222m (26% of the population) in 1990 to 410 million (32%) in 2014 and is expected to reach 814m (50%) by 2050. Total investments of at least $640.2 billion are needed for urban infrastructure and services until 2031 to meet the needs of the growing urban population and improve the standard of living of the existing urban population[153]. Investment in urban infrastructure directly translates into poverty reduction through job creation, improving access to services such as health care and education, improving access to markets and improving communication and transport infrastructure.
  [153] World Economic Forum (2015), The future of urban development and services: urban development recommendations for the government of India
- Skills: The National Policy on Skill Development and Entrepreneurship 2015 estimates an incremental requirement of about 110m skilled personnel in 24 key sectors by 2022. Tackling this skill shortage is vital for economic growth and for poverty reduction, particularly amongst women whose labour force participation is only 29%, compared with 80% for men[154]. An example of evidence on the links between better skills training leading to jobs and poverty reduction is: Nepal, graduates of the Employment Fund reported a 2.6 times increase in income with contributions to household income increasing by up to 67%[155].
  [154] ILO (2013), India: why is women’s labour force participation rate dropping
  [155] Review of Employment Fund Project Nepal. May 2013.

E3. Gender Equality
Women’s rights remain an issue with India ranking 130th on the Gender Inequality Index[156]. India’s female work force participation, at 29%[157], is one of the lowest in the world and women constitute only 10% of entrepreneurs[158]. According to a McKinsey report, India could add $700 billion of additional GDP by 2025 – upping the country’s annual GDP growth by 1.4 percentage points – by ensuring gender equality alone[159]. In order to achieve the highest level of growth and development for India, this programme will identify opportunities to improve the lives of women and girls and will actively seek out opportunities to achieve gender equality. Gender cross cutting theme through each of the five strands, which explicitly set out how they will individually improve the lives of women and girls. Examples of this include:
[156] UNDP (2015), Human Development Report
[157] World Bank (2016) – Women, Business and Law.
[158] M. Balaji et all: Women Entrepreneurship - Opportunities and Challenges in South Asia; IJEMLS, 2016.
[159] McKinsey (2015), The Power of Parity: Advancing Women’s Equality in India
  1. Energy & Low Carbon: Electrification and the use of renewable energy can particularly benefit women and girls in emerging economies. Access to energy services significantly improves women’s lives by freeing time that was previously spent gathering fuel and cooking with inefficient stoves, by alleviating health problems caused by burning wood and dung, and by increasing access to information services such as television, radio and the Internet[160]. This provides the opportunity for women to assume less traditional roles and generate income, and ultimately leads to higher gender equality[161].
    [160] UNDP Policy Brief 4 – Gender and Climate Change, Asia and the Pacific
    [161] Kanagawa, M. and T. Nakata, Tohoku University, Sendai, Analysis of the Energy Access Improvement and Its Socio-Economic Impacts in Rural Areas of Developing Countries (2005)
  2. Urban: Analysis by the National Bureau of Economic Research has established a clear relationship between better quality infrastructure and increased women’s entrepreneurship and economic participation into industry/enterprise. Benefits include safety, time savings and access to public services and markets[162].
    [162] Ghani, Kerr and O’Connell (2011) ‘Local Industrial Structures and Female Entrepreneurship in India’. National Bureau of Economic Research
  3. Ease of Doing Business: By reducing the regulatory burden of entering the formal economy, more citizens will be able to enjoy the benefits of public services and welfare support. Women comprise only 15% of the formal economy currently, so reducing the informal economy will disproportionally benefit women (ILO 2011).
  4. Financial Services: The programme will develop the potential of FinTech to increase access to financial services and welfare support, providing greater security and opportunity to citizens, particularly women, with more than 30% of women likely to borrow informally as access to finance through formal sources still poses a challenge (World Bank 2017)
  5. Skills: Tackling India’s skill shortage is vital not just for poverty reduction but also for achieving a skills labour force and supporting entrepreneurship.
Each India PF strand programme lead will ensure that gender issues and opportunities are addressed in delivery and monitoring to ensure compliance with the Gender Equality Act through the following measures:
- Bidders (at the tender stage) will be required to submit a preliminary gender equality assessment (including consultations with women or women’s groups) outlining how they propose to address gender issues in the programme design. All contracted delivery partners will be contractually required to address gender equality.
- Each programme will report on sex-disaggregated data and include specific indicators on women and girls within their logframes.
- Each supplier will be required to submit an assessment of the impact of their work on gender equality as part of their annual reports, including but not limited to the logframe.
- A gender expert will be involved at appropriate stages to ensure the programme continue to maximise the opportunities to deliver gender equality.

Summary Value for Money Statement
The economic appraisal shows a high return for the programme both on a primary and secondary benefits basis. This conclusion is based on conservative assumptions and evidence of the impacts of other similar programmes. Value for Money in delivery will be ensured through competitive procurement of implementing partners and working closely with other agencies to mobilise resources and jointly deliver greater impact. As a result the India PF Programme represents a good use of UK taxpayers’ money to enable India’s continued inclusive growth and poverty reduction and to enable international and UK companies to benefit from the resulting commercial opportunities.

COMMERCIAL CASE

Overall Commercial Approach
Each strand is separated into two tranches. Tranche 1 constitutes up to 90% of the budget and is committed to Primary Service Delivery Providers (PSDPs) to design and deliver the majority of outcomes and activities. Tranche 2, generally up to 10%, is for smaller, shorter, projects with a variety of delivery mechanisms. The Commercial Case outlines the tranches and commercial approach to meet the PF India objectives.

Route to Market – Direct Procurement of Primary Service Delivery Provider (PSDPs)
Following assessment of the options, direct procurement was identified as the recommended route to market for each strand, as follows:
- Urban Development - £12.4m
- Energy and Low Carbon - £7.7m
- Financial Services - £6.55m
- Ease of Doing Business - £8.2m
- Skills - £4.7m
1. The Energy & Low Carbon strand will be divided into a main Tranche 1s, and a number of Tranche 2 programmes. The rationale is that formal approval on Tranche 1 delayed engaging a vendor for a single large programme and it is considered that value for money and effectiveness can be enhanced by complementary, smaller and more agile projects with multiple delivery partners rather than engaging with one PSDP.
2. The Ease of Doing Business strand will use multiple delivery partners to achieve the outcomes (as per the Appraisal Case); International Finance Corporation (IFC), a Primary Service Delivery Partner, and HMG Departments.
3. DFID India will lead and manage the Skills strand (as set out in the Appraisal Case). DFID will combine the PF funding allocation with its own funding in a single programme and will take on full accountability and responsibility for delivery of the India PF Skills strand. DFID India is well established and has good experience in skills development and good relationships with relevant government stakeholders. DFID will lead a common contracting process, which offers greatest value for money for HMG. The funding will be transferred to DFID and the strand will follow DFID’s assurance process and timetable. Existing governance and joint working arrangements at Post will ensure continued coherence of the overall PF India Portfolio. DFID India will involve FCO in delivery, but it will be DFID that provides assurance. For reporting purposes the PF India team will continue to report against the full portfolio where necessary (except for financial reporting, which will be made through DFID to avoid double-counting). A full note on this is at Annex E.
4. The following options have been considered to procure the Primary Service Delivery Partners for each strand:
    1. PF Framework Agreement. As part of the overall procurement strategy for the PF, the FCO completed a competitive tender exercise, following the OJEU process, to put in place a PF Framework Agreement. This multi-supplier approach provides a cost effective and legally compliant framework to provide HMG with timely access to a wide range of high quality strategic, advisory, delivery and management technical assistance services. The suppliers on the Framework have the capability and eligibility to work in diverse countries, sectors, and themes. Each of the suppliers demonstrated that they possess the capabilities HMG needs to meet PF objectives and deliver value for money. The Framework includes maximum day rates for a number of roles, which suppliers cannot exceed.
    2. Full open competition, following the OJEU process. This would involve a full open procurement process for each strand, following the OJEU procedure. Suppliers would be evaluated against commercial and technical criteria and suppliers who have been un successful in selection for the PF Framework would be able to submit tenders.

Option	Advantages	Disadvantages
PF Framework Agreement	Shortened timescale. / Pre-qualified suppliers. / Key element of the overall PF procurement strategy. / Maximum day rates agreed.	New framework – India likely to be the first PF programme to test the framework capabilities.
Open Competition – OJEU	Does not limit participation in procurement to framework suppliers.	Longer timescale. / Market already engaged and been through tender process for the Framework – appetite for full procurement process could be low. / Likely to attract suppliers already awarded to the Framework and therefore would require some duplication of effort.

Selected Procurement Option – PF Framework. Use of the Framework Agreement as the key sourcing route offers a number of advantages:
- Due diligence will have been carried out on each supplier centrally and procurement timescales are significantly reduced (by 4-8 weeks).
- There will be improved VfM on rates and costs because the bidders’ maximum rates are likely to be significantly reduced from the day rates submitted when joining the Framework.
- Suppliers have not been required to identify their consortium or sub-contractors to bid for a place on the Framework Agreement. Flexibility is therefore retained for suppliers to identify supply chains to meet specific local requirements.
- The Framework Agreement set out key contractual terms which suppliers are required to adhere to when delivering. The Framework Agreement will be managed robustly by FCO’s Central Procurement Group which will provide backup to local contract managers. Poor performancing suppliers may affect their prospects on receiving work elsewhere thereby incentivising good performance. Call-offs from the PF Framework is assessed as the most appropriate option for the procurement of PSDPs. The Framework forms the basis of the overall procurement strategy and successful suppliers have been assessed as having the capability and capacity to deliver. Further call-down competitions will provide further opportunity to drive VfM.
Call-offs will be undertaken across the four strands managed by the FCO: Energy & Low Carbon, Financial Services, Urban, and EoDB The proposed lotting structure for the procurement of each strand is set out below. It was originally intended to use one lot for EoDB. However, it was later deemed more effective to use lots A1, A2 and A3 to achieve greatest market outreach. It was intended that we will use two lots for Financial Services and Urban Development. The rationales for this are given below, but stem from the fact that both of these strands require expertise which could be delivered across multiple lots. Going out to multiple lots maximises our ability to procure the most competent delivery partners for these strands.

Strand	Lot	Rationale
Ease of Doing Business	A1 – Business Environment / A2 – Finance Trade / A3 - Trade	To improve the business environment in India.
Financial Services	A2 – Finance Trade	To increase trade in financial services in India.
Urban Development	B1 – Infrastructure	To leverage investment and commercial wins in infrastructure.
Energy and Low Carbon	B3 – Energy	To increase investment in renewable energy and smart power in India
Financial Services	B4 – Digital	Improving access to finance, including through FinTech.

Commercial Overview – Primary Service Delivery Partners (PSDPs)
1. The FCO will appoint a minimum of six PSDPs to deliver the services against the four FCO-led strands. Contracts will end on 31 March 2023 with an option to extend for up to 3-5 years. There will be a maximum uplift value of up to 50% to provide some flexibility.
2. The initial contracts procured through the PF Framework Agreement will be for the duration of the programme, but will consist of two key phases. Design Phase will involve detailed scoping and design of programme methodology, the delivery and finalisation of logframes, MREL and detailed action plans and budget. Implementation Phase only be entered into on the completion of a successful Design Phase.
3. Full Statements of Requirements (SoRs) are being developed by the programme and PF procurement teams. These will clearly define expected deliverables (primary purpose and secondary benefits) focusing on the outputs required. However, they will not prescribe a methodology or approach to encourage suppliers to propose innovative and workable solutions and improve the ability to assess bids based on their technical strength and value for money. The PSDPs will be responsible for:
1. Designing, developing and implementing a programme-level approach to delivering strand level outcomes (primary and secondary);
2. Undertaking and/or overseeing activities set out in their programme document, which deliver strand level outcomes – including capacity-building, technical assistance, research and stakeholder engagement;
3. Conducting project level due diligence/ independent assessments for FCO where appropriate;
4. Building partner capacity at the institutional and project level; and
5. Developing and implementing an MREL system to dovetail with FCO MREL processes.
1. As a key deliverable of the Design Phase, PSDPs will be required to identify and detail the approach, methodology and activities to be followed in the Implementation Phase, these will be agreed as part of the approval and sign off process.
2. The initial contract value of PSDP’s call-down contracts will be a maximum of 90% of the total budget allocation for each strand. This is to reduce risks associated with having all spend delivered by a single delivery partner. It ensures a level of flexibility in the programme and provides the opportunity to keep some budget back to act as an incentive to drive strong delivery i.e. uplift could be given in accordance with consistent high performance and identification for further delivery.
3. EoDB programme will use multiple delivery partners to deliver >90% of the strand budget; IFC, PSDP (contracted through the PF Framework Agreement), and MoUs with UK government departments. This delivery option offers best value for money and increases speed, outreach and level of impact.
4. The above approach offers the most effective and efficient mechanisms for achieving primary and secondary benefits of the PF by reducing transaction costs whilst drawing on market best practice, skills and capacity. It is consistent with the purpose of the PF Framework Agreement.
5. This method of dividing programmes funds with a significant proportion being allocated to a PSDP, whilst retaining a small percentage for more flexible programming is standard practice used by DFID and others. Allocating a significant proportion to service providers attracts high quality providers, enables the fund’s results and activities to be effectively programmed across the programme timeframe and is an efficient means to manage funds with low transaction costs to the FCO.

Procurement of ad-hoc contracts and non-primary service delivery partners – 10% of each strand value
This second tranche of up to 10% will be committed for the following:
1. Rapid delivery approaches in the form of small and distinct areas work which can deliver quick wins and achieve early results during the procurement, design and early implementation phases of the primary delivery partners.
2. Ability to engage on smaller projects to respond to changing circumstances or emerging priorities (mutually agreed by the FCO and GoI).
3. Where a distinct or new area or piece of work is required which sits outside the mandate or capacity of the PSDP (e.g. research).
4. To respond to organisations which make unsolicited approaches to the India network but only where they have an excellent proposal, which delivers over and above what is achievable by the Primary Service Delivery Partners.
5. Potential to amend the PSDPs’ contracts, in accordance with the call-off contracts, where a component of a strand is delivering significant results or has the potential to do so, but requires additional support to unlock this potential.
1. Retaining a small proportion back from PSDPs enables a level of flexibility to programme delivery and reducing the programme’s financial exposure risk by not committing all funds to a single service provider. A 75% limit of funds being allocated to PSDPs was considered, however this was not considered viable as a lower overall budget would be less likely to attract stronger partners, not committing the full budget to the PSDPs in the first instance does not enable them to develop a full workplan to deliver the full set of results, going out to the market though alternative procurement routes for 25% of the programme budget would be inefficient and transaction cost heavy for the PF team in Delhi.
2. The following will be considered in order to engage partners to provide emerging requirements throughout the life of the programmes:
  1. Accountable Grants will be used to engage not for profit partners that approach the India network with excellent ideas, which are assessed as being highly relevant to delivery of the PF objectives.
  2. Competitive tender (local, regional, or international) process will be used for all private sector contracts. An appropriate procurement route will be agreed with the FCO Procurement Team and could include the use of PF Framework Agreement or OJEU (threshold of £118,133). Any OJEU process would be undertaken by the FCO procurement team in London.
  3. MoUs will be used in instances of multilateral organisations (e.g. World Bank, UN). being identified as the most appropriate delivery partner.
  4. A ‘calls for bids’ mechanism will only be used in exceptional circumstances. Full details on this area set out in ‘Alternative Approaches’ in Section C.
1. The mechanism by which this spend is made will be assessed on a case by case basis to meet specific requirements. SoRs, evaluation criteria and pricing structures will be developed in accordance with FCO procurement rules and in consultation with the Corporate Procurement Group. Pre-market engagement will be held where necessary and all documents will be publically available. It is envisaged that the contracting will be for distinct pieces of work, which cannot be delivered by the PSDPs e.g. more agile programming which is better able to respond to new or additional requests, or opportunities where we see real value in investing, but where our contract with our PSDP does not allow. It could also be used for rapid work to be delivered in the first year of programme implementation. An evaluation panel chaired by the Strand Lead will be convened, consisting of at least three members including from one other government department. Contracts will be signed and awarded by the India SRO in consultation with the Corporate Procurement Group. There will be no payment in advance of need.
2. Grant contracts will be used to commission work by not for profit entities and will be awarded on the basis of an organisation approaching the PF India team with a proposal which is of exceptional quality and offers the ability to deliver outcomes, which cannot be achieved by the PSDPs. Funding will be in the form of non-returnable grants and payments will be made on the achievement of results.

Market Analysis
1. The suppliers who were successfully awarded onto the Framework were assessed as having the relevant capability and capacity to meet the PF’s needs. There was a strong market response from the Framework suppliers to the call-off procurements, not least because India is one of the first PF programmes to launch tenders through the Framework Agreement. The FCO is an attractive buyer and the PF is a high profile cross government fund which attracted a high level of interest during the procurement of the Framework. Suppliers were able to demonstrate their capabilities during early call-downs to provide confidence that they had the ability to meet FCO programme requirements. Strong interest from the local market in India was expressed and interest from the domestic market in DFID India’s technical assistance component of the NIIF was an indication of the likely strength of the market response.
2. Early market engagement: There was a strong interest across all strands. Four early market engagement events took place in Delhi between June and November 2017 to test the concept notes for the programme with the market.
3. After the Prosperity Framework was awarded, the draft SoRs were shared with Framework suppiers through the FCO procurement portal. This was an opportunity for the market to identify gaps, test any assumptions, and provide overall comment to inform the final SoRs. In addition, there was a commitment to undertake a formal pre-procurement launch event to fully present the ITT documentation and ensure Framework providers fully understood the requirements of the SoRs, call-off, and evaluation process.
4. For non-PSDP work, there may be cases where the implementer may be a government partner or a multilateral/ non-government organisation (NGO). These relationships are already well established. The Ease of Doing Business strand has already run several projects with the proposed UK government partners and has Memoranda of Understanding in place with the Regulatory Delivery Directorate. The India network also has an ongoing dialogue with multilaterals operating in South Asia.

Key Cost Drivers
1. The PF is a technical assistance programme, which is relatively personnel heavy. The main cost drivers for this technical assistance are individual fee rates of technical experts as well as the management fees of suppliers. Key cost drivers are service provider management fees, personnel (day-rates), hosting of events, travel and training provision, and prices of related goods such as travel and transport.
2. As these are first call-offs from the PF Framework Agreement, the fee rates submitted inform the benchmark for future programmes. There is an expectation that, through further competition, the maximum rates submitted at Framework level will be reduced. Rates were be benchmarked at evaluation against known comparators, i.e. CSSF and DFID, to ensure VfM.

Evaluation of Invitation to Tenders – PSDPs
The PSDP procurement was structured as a design and implement contract. Full evaluation criteria were produced as part of the call-off procedure. The PF Framework overall call-down evaluation criteria:
Technical - 60-80% weighting
Sub-criteria:
- Methodology
- Resourcing – Skills and experience of team
- Delivery approach:
  - Project plan
  - Stakeholder management
  - Contract management approach
Price/ Commercial 20-40% weighting
Draft evaluation criteria have been developed, in line with the overall Framework call-down evaluation criteria above:

		Overall Weighting
Technical Criteria	Indicative Technical Sub-criteria	70%
Methodology	Demonstrates a clear knowledge and understanding of the sector and of India. Outlines a proposed methodology to deliver programme in their bid and this should then be refined during the Design Phase and further detailed as an output in the design report.
Resourcing / Delivery Team	Clear explanation of the proposed resourcing structure/ delivery team showing all key personnel. Demonstrates coverage across all sub-sectors. CVs for proposed team to demonstrate skills coverage and capability.
Delivery Approach	Demonstrable Project Plan, with programme timelines, Stakeholder management plan, Communication plan.
Commercial Criteria	Indicative Commercial Sub-criteria	30%
Design Phase	Total Fixed Price for delivery of Design/Inception phase.
Implementation	Day-rates for Implementation Phase (the rates submitted at ITT will be used for the pricing of the Implementation Phase and will not be amended following submission of the final implementation design).
Forecasting	Prepare a realistic forecast for monthly expenditures for the first year, and quarterly expenditures for the following years and establish guidelines for monitoring project expenditure, including output based budgeting and verification procedures.
TOTAL		100%

Bidders are also expected to submit tenders, which include the following:
- Design Phase – Fully costed breakdown of input resource (time, resource and materials) to deliver the Implementation Phase. This will involve evaluation of the rates which will be used for implementation
- strong value for money against the three E’s (Efficiency, Effectiveness and Economy).
- a robust and evidence-based methodology demonstrating innovation and best practice approaches to deliver high quality results and sustainable impact.
- how they will achieve a balance between primary and secondary benefits.
- a clear timeline for the delivery of the design phase, implementation results and spend.
- a theory of change and a provisional logframe (including sex-disaggregated data).
- a provisional gender equality assessment.
- detailed governance arrangements including financial and results reporting.
- a detailed risk management matrix, including how risks will be managed and escalated. Demonstrate a zero tolerance to fraud and corruption.
- outline team structure with associated skills and roles and fee structure. The SoR set out ‘fee bands’ for staffing levels (e.g. lead consultant, programme support etc.).
- relevant/ requested due-diligence documents e.g. audited financial reports for the last two years.
An Evaluation Panel, moderated by a D6 PF Commercial Portfolio Lead was convened. The panel agrees the technical moderated scores for each tender received. As per FCO procurement rules, the panel was not to be privy to the commercial submission, which was assessed by the FCO PF procurement team.

Management of costs to achieve value for money (VfM)
1. The FCO ensures best value for money by assessing costs as part of the commercial evaluation, ensuring that they are commensurate to the delivery of the outcomes and associated activities. All day-rates require robust justification and are scrutinised prior to any contract award.
2. All costs and invoices are scrutinised at invoicing and receipting stage prior to payments being made. All payments are made in arrears subject to satisfactory performance/ delivery of services.
3. Governance arrangements set out in the Management Case ensures costs are carefully managed including ensuring FCO resources are not exposed to unmanageable levels of commercial risk.
4. All call-off procurements are subject to an internal Peer Review Panel prior to issue of the ITT documentation to ensure consistency of approach and best practice has been applied.
5. All implementing partner contracts and agreements are signed in accordance with internal delegated authority limits.
6. All contracts are signed and held by the Corporate Procurement Group. Commercial compliance and contract management is overseen at post (at both Strand level and by the India PF Portfolio Team), with dedicated commercial advisory support from the Corporate Procurement Group in London who ‘owns’ any variations in the contract which are identified and driven by post.
7. All responsibility for the delivery of the contracts at post lies with the Strand leads, the India PF Portfolio Team and ultimately the India PF SRO.

Contract and Performance Management
1. This section should be read in conjunction with the Management Case (below), which sets out the governance arrangements for implementing partners and the India PF in greater detail.
2. Design Phase: Subsequent to the awarding and signing of the contract a Design & Inception phase will begin. During the Design Phase, a full final Design Report is developed by the delivery partner in close collaboration with the Strand. A draft report is provided at two months to provide sufficient time for approval by the India PF team ahead of the end of Design Phase. This reduces the risk of a hiatus of activity at the end of Design Phase. The report is presented to the India PF Board and approved by the PF India SRO. The report includes:
    1. Programme methodology and approach.
    2. Staffing structure and governance arrangements.
    3. Budget – including detailed breakdown for their FY1 (equivalent to India PF FY3).
    4. Payment milestones linked to deliverables and results.
    5. Programme document including logframe and risk matrix.
    6. Reporting structure including monitoring and evaluation and financial reporting.
    7. KPIs.
    8. Work plan necessary to achieve the KPIs.
1. During Design Phase particular attention is paid to any changes in overhead costs to ensure that they are commensurate with the quality of delivery, and to ensure that there are no costs hidden within the programme (e.g. additional contractor staff or travel expenses built into monitoring & evaluation activities).
2. Transition from the Design Phase to Implementation is subject to FCO approval of the Design Report, excellent performance of the supplier, positive feedback from stakeholders and agreement of a detailed work plan, monitoring and evaluation framework and a realistic forecast for monthly expenditure.
3. If the FCO decides not to proceed to the Implementation Phase, the contract is terminated at no further cost to the FCO. If the FCO decides to proceed to the Implementation Phase, a contract amendment is issued to include details of the services to be provided in the form of updated terms of reference and detailed costs.
4. Implementation Phase: Once in implementation the following are used to ensure strong delivery and effective management of the delivery partners:
    1. Detailed logframe, including annual and end of programme targets for both primary and secondary benefits. This is agreed during design phases and is signed off by the strand leads in the India PF Team and the PF India SRO.
    2. Detailed budget including monthly and quarterly forecasts for Y3 as well as results based payment milestones. Spend is not loaded in Q4 to avoid risks in underspend.
Four main documents provide the basis for the management of implementing partners and are used to hold them to account on delivery of quality results and spend:
  1. The Full Business Case.
  2. SoR and supporting procurement documents.
  3. Their own tender documents.
  4. Design Report including a detailed work plan, budget, logframe and risk matrix.
Management of the relationship with implementing partners is primarily the responsibility of the Strand at post with support from the India PF Portfolio Team, the Deputy Director, Prosperity Programmes and ultimately the PF India SRO. The Strand receives sufficient commercial and programme management training to ensure they have the right skills and tools to effectively manage contract and implementing partners.

Payment Profile and Performance Requirements
1. The Design Phase is based on an output based payment mechanism with payment linked to agreement of the draft and final design reports. It is expected that a contract amendment will take place following the design phase to a) include the final KPIs and b) revised budget, work-plan and logframes.
2. During Implementation it is expected that the PSDP will be engaged on an open book time and materials basis with a percentage of payment linked to key performance indicators – however we will endeavour to agree output based pricing where possible, following the design report. Indicative KPIs, have been drafted below, and will be refined and agreed as a key output of the design phase:

Indicative KPIs:
Working effectively in the geographical regions and various institutions.	Risk Management / PSDP has delivered new ideas to the benefit of the programme / Team builds effective relationships with stakeholders to achieve results. / Team receives positive feedback from stakeholders and responds to constructive feedback.
Supplier monitoring and managing performance	Performance of team leader / Performance of the overall team / Managing underperformance / Provider has sought to improve on the last reporting periods performance / Ability to deliver in line with agreed budget
Delivery to time	Quality deliverables are on time / Key programme results are on track according to programme logframe
Regularity of communication and coordination with FCO and other stakeholders	Responsiveness of PSDP to stakeholders / Impact of external communications / Regular communication with FCO and delivery of weekly meeting action points
Quality and timeliness of reporting/ forecasting	Quality of monitoring, evaluation and reporting / Lessons learned captured and shared / Attention to FCO and PF policies

Programme Delivery and Management:
1. All contractors are required to assign a key point contact, responsible for interfacing with the Strand. Meetings take place between the Strand and the delivery partner on a regular basis through a strand level working group (see Management Case). The frequency of these meetings is likely to change during the programme but should not go beyond monthly. Additional team members from both the PF and delivery partner are involved in these meetings as appropriate i.e. programme managers, M&E experts etc. The purpose of these meetings is to review progress against agreed work plans, identify any upcoming challenges/ risks/ opportunities and ensure programme delivery is on track. Financial forecasts and risk matrix will be reviewed monthly.
2. Implementers are expected to submit reports on a quarterly basis providing summaries of progress against the work plan deliverables and logframe outputs. Any reports raising issues of concern or risk are escalated to the SRO; Director of Prosperity Delivery.
3. Post-procurement reviews are also undertaken on a sample of any sub-contracts let in the case of a Management Agency. Partner Government Ministries at national and state level would also be engaged in the review process.
4. Where changing circumstances mean that in the FCO’s view the agreed work plan under a contract is no longer appropriate, contracts provide for renegotiation between the parties with the FCO ultimately having the right to terminate the contract. Where significant change is required the formal change management process is followed.
5. As set out in the Management Case, annual Strand Level Steering Committees are organised by the PSDP and chaired by the India PF Strand lead. These have oversight of programme delivery, annual work plans and budgets and receive and make recommendations for any changes to the delivery of the programme (all changes that go beyond the PF tolerance level are escalated into the formal change management process).

Risk Management
1. Delay in spend and delivery during the procurement process is mitigated by keeping back at least 10% of the programme budget to spend on small contracts to deliver work in the ‘transition period’, prior to the PSDPs being ready and able to spend in full swing.
2. Delivery partners are required to provide a detailed FY3 (their spending FY1) budget, including monthly and quarterly forecasts. This will be finalised and agreed at design and will be reviewed at quarterly meetings between the India PF team (strand lead or programme manager) and the implementing partner.
3. A tolerance in variance between forecasting and actual spend is built into the contracts, grant contracts or MoUs and are used as an early indicator in any underperformance. Any significant variance in spend will be raised with the Deputy Director, Prosperity Programmes immediately for discussion with the SRO. Any unmanageable variation which goes beyond PF tolerance will be raised with London and the formal change process instigated if required.
4. In keeping with FCO reporting requirements, implementing partners are required to provide quarterly financial reports as well as audited financial reports at the end of each financial year.
5. FCO carries out an annual audit of the delivery to ensure financial compliance and Value for Money, and to establish costs and outputs for future years based on satisfactory delivery of previous years’ outputs.

Commercial Risk Analysis
The following commercial/ procurement and programme management risks have been identified and mitigated to address the impact and likelihood.
Risk	Impact (1-5)	Likelihood (1-5)	Risk Score	Mitigation
Delay in finalisation of the PF Framework Agreement	3	2	6	Framework procurement has all approvals in place to award. / Audits on the procurement process have been undertaken. / Possible use of OJEU process as an alternative.
No bids or low number of bids received	5	3	8	Extensive market engagement. / Further market engagement planned to test SoRs and to warm up market to bid. Likely that an ITT launch even will be held in Delhi to reduce risk of market failure.
PF funds used for fraud or corruption.	5	2	7	Due diligence undertaken on PF Framework Agreement Partners. / Due diligence is undertaken on suppliers outside the PF Framework Agreement. / No payment in advance of need will be made. All funds released on achievement of delivery milestones. / Accounts audited annually and financial reports required every 3 months. / Any risk of fraud or corruption will be raised within 24 hours and will be taken to the Financial Compliance Unit.
Poor performance of selected supplier.	4	2	8	Close reporting and contract management. / Use of KPIs to monitor performance. / Application of contract terms for termination / Annual Reviews and Evaluations / Framework providers have been pre-qualified. / Framework level contract management and SRM
Call-off contract changes/amendments – increase in costs.	4	3	12	Maximum day rates agreed as part of framework. / Full breakdown of costs for implementation phase, with budget forecasts. / All amendments to follow formal amendment process, including scrutiny of cost proposals. / Effective contract management. / Clear scope in SoRs / Open Book / Profit caps

1. Strand leads are responsible for implementing a consistent and robust approach to risk management with delivery partners. This is overseen by the Deputy Director, Prosperity Programmes with ultimate responsibility of the India PF SRO.
2. Each strand has a clear risk management matrix which addresses the seven risk categories; external, safeguard, operational, delivery, fiduciary, reputational, and strategic.
3. The India PF Prosperity Portfolio Team maintains a portfolio level risk matrix and register – including those risks associated with our delivery partners.
4. Delivery partners are required to present and maintain a clear risk matrix and risk management process which are revisited on a monthly basis between strand leads and the delivery partner.

Commercial Case – Financial Services (updated 5th December 2018)
The Financial Services Strand is being delivered through:
Tranche 1 – a Primary Service Delivery Partner procured through the PF Framework Agreement, and
Tranche 2 –flexible funding mechanisms including; support to Chevening Fellowship Programme, Accountable Grants with Not for Profit Organisations, smaller contracts awarded through open market, limited market and single source tenders. Other funding mechanisms may be explored as the programme develops.
Tranche 1 Supplier Procurement
1. Approval to procure, via the PF Framework, was given by the IIOC Board on 1st November 2017. Following a competitive procurement process against the PF Framework Finances Service Lot, the total contract value over the contract duration (January 2019 – March 2023, with review points at the end of inception and in March 2021 to coincide with the Spending Review) will be around £6.5m.
2. Timeline The table below sets out the indicative timetable for contracting, implementation and delivery
Issue ITT	30th July 2018
ITT Returns	1st October 2018
Evaluation	3rd – 31st October 2018
Moderation	13th November 2018
Interviews	14th November 2018
Draft recommendation to award report	22nd November 2018
Contract Award	December 2018 (Following approvals process).

Market engagement: Following the 2018 launch of the tender, a ‘Direction of Travel’ meeting was held on 22 August. The event was attend by five potential framework bidders and consortia partners. The event allowed post tender clarifications to be made and answered. A report of the meeting was made available.
Statement of Requirements (SORs)
1. The scope of activity to be undertaken was defined in a detailed Statement of Requirements (SOR). On 30th July 2018 the Invitation to Tender (ITT) PF18 006 was published, setting out clear deliverables (expected outcomes and impacts and any minimum outputs) and indicative activities to achieve them.
2. The ITT also made clear that there was scope for implementers to input their own ideas as to how best to deliver the required outputs and outcomes, thus benefitting from their expertise and innovative outlook. The appointed suppliers will be expected to implement and manage the programme, working to the Financial Services Strand Lead and Programme Manager who will manage and monitor the programme and ensure alignment with HMG priorities.
3. The SoRs included an explicit section on ODA, IDA and the Gender Act Compliance requirements.
4. As per the Commercial Case, the SoR set out two clear phases, noting a go/no-go clause at the end of Inception Phase;
  1. Inception Phase (3 months)
  2. Implementation Phase (until end March 2023)
1. The full cost of the programme was assessed as well as day-rates. The ITTs explicitly stated that day rates which offered value for money and were in keeping with market rates were expected.
2. The contract for the Tranche 1 Financial Services programme was procured via the Cross-Whitehall PF Agreement, awarded by the FCO to 27 suppliers across 11 Lots. The Framework has been designed specifically for the PF Programme and is available to Other Government Departments to access. This contract was competed via a call for further competition from suppliers selected based on evaluation of technical and commercial offerings and all will be invited to tender for this requirement. Five suppliers bid.
3. Evaluation The evaluation panel consisted of the Deputy Director Prosperity FCO India, Strand Lead, DIT Head of Trade, and Head of MREL PF India. The process was moderated by CPG London. All evaluators confirmed that they had no conflict of interests. The evaluation model used was the Most Economically Advantageous Tender (MEAT). The bidder with the highest score was Ernst & Young LLP. To ensure VfM, the right balance of quality vs price, and that priorities in terms of service capability and capacity were addressed, there was a defended quality threshold for bidders to meet in order for commercials to be evaluated.
4. The Commercial Case includes some relatively high day rates but still within the cap, which has been placed on DFID PF procurements (subsequent to the launch of this tender).
5. The preferred supplier demonstrated:
- Excellent understanding of the Financial Services agenda including key challenges and barriers to growth in India as well as opportunities for international and UK business;
- Ability to draw in and work with the strong partners;
- Innovative ideas and methodology which went beyond activities set out in the SORs;
- A proven track record of delivering in India and delivering impact in Financial Services.
Subject to IIOC approval, the contract winner will be announced in late December 2018 followed by a 10-day standstill period. A contract award will be made in early January 2019. The Inception Phase will start as soon as the contract is awarded and will last until the end of March when full implementation will commence assuming a successful Inception Phase.

Commercial Case –Ease of Doing Business Strand (updated 03/07/2019)
The Ease of Doing Business (EoDB) strand is being delivered through:
- Tranche 1 – a Primary Service Delivery Partner procured through the PF Framework Agreement.
- Tranche 1 (Alternate Delivery Mechanism) – a Single Donor Trust Fund with International Finance Corporation (IFC) agreed via an MoU (or Administrative Agreement).
- Tranche 2 – bilateral MoUs signed between FCO India and Other Government Departments (OGDs) under HMG to facilitate government-to-government knowledge exchange.
Tranche 1 Supplier Procurement
1. Approval to procure via the PF Framework, was given by the IIOC Board on 1st November 2017. Following a competitive procurement process against the PF Framework,nvitations for this tender opportunity were issued to all 23 Suppliers on the A1 Business Environment/ A2 Finance Trade/ A3 Trade Lots.
2. The total contract value over the contract duration (December 2019 – July 2022, with review points at the end of inception and in March 2021 to coincide with a Spending Review) will be £4.5m. Based on the budget and proposed Contract value, a cost avoidance saving of £0.5m is identified.
3. The table below sets out the indicative timetable for contracting, implementation and delivery of the Urban Development Strand
Proposed Procurement Timetable
ITT documentation issued on the e-procurement system, Jaggaer	8th April 2019
Deadline to submit requests for clarification via the e-procurement system, Jaggaer	3rd May 2019
Deadline for Tender Responses	3rd June 2019
Evaluation	5th June to 17th June 2019
Moderation	20th June 2019
End of 10-Day Standstill period	2nd August 2019
Contract Signature	3rd October 2019
Contract Commencement	3rd October 2019

Following the launch of the tender, a Market Engagement meeting was held in New Delhi on 30th April 2019. The event was attended by 25 potential framework bidders and consortia partners. The event allowed post tender clarifications to be made and answered..
Statement of Requirements (SORs)
1. The scope of activity to be undertaken was defined in detailed Statement of Requirements (SORs). On the 8th April 2019 the Invitation to Tender (ITT) PF18 005 was published and set out clear deliverables (expected outcomes and impacts and any minimum outputs) and indicative activities to achieve these deliverables.
2. The ITT also made clear that there was scope for the implementers to input their own ideas as to how best to deliver the required outputs and outcomes, thus benefitting from their expertise and innovative outlook. The appointed suppliers will be expected to implement and manage the programme, working to the Ease of Doing Business Strand Lead and Programme Manager who will manage and monitor the programme and ensure alignment with HMG priorities. The SoRs included an explicit section on ODA, IDA and the Gender Act Compliance requirements.
3. As per the Commercial Case, the SoR set out two clear phases, noting a go/no-go clause at the end of Inception Phase;
  1. Inception Phase (3 months).
  2. Implementation Phase (until March 2023)
1. The full cost of the programme was assessed as well as day rates. The commercial case set out all potential staff costs, operational cost, design phase cost and implementation costs to support the team manage value for money and identify any key cost drivers. Average day rates were set at £900, in line with Global PF procurement rules. The ITTs explicitly stated that day rates which offered value for money and were in keeping with market rates were expected.
2. The contract for the Tranche 1 Ease of Doing Business programme was procured via the Cross-Whitehall PF Agreement, awarded by the FCO to 27 suppliers across 11 Lots. This contract was competed via a call for further competition from suppliers that have been selected based on evaluation of technical and commercial offerings and all will be invited to tender for this requirement. Three suppliers submitted bids: Ernst & Young LLP, Oxford Policy Management, and PricewaterhouseCoopers LLP.
3. Evaluation. The evaluation panel consisted of the Head of Ease of Doing Business Programme, FCO India; Head of Economics & Finance, FCO India; Senior Trade Policy Advisor, FCO India, and Senior Economic Advisor, DFID India. FCO Commercial held a training session for the Panel members, which covered guidance and rules for evaluating tenders and advice about the moderation.The evaluation model used was the Most Economically Advantageous Tender (MEAT).
4. The bidder with the highest score was PricewaterhouseCoopers LLP. To ensure VfM, the right balance of quality vs price, and that priorities in terms of service capability and capacity is addressed, there was a defended quality threshold for bidders to meet in order for commercials to be evaluated.
5. The SOR specifically indicated a capped average day rate at a reasonable level. In addition, bidders were asked to separate out staff costs vs operational costs to ensure VfM was being achieved.
  1. Value for Money: Based on the initial budget of £5,000,000 and the contract value of £4.5m (approx.) a cost avoidance saving of £0.5m is identified. This will be used to support flexible programme either through Tranche 2 programmes, or through a potential contract uplift should the chosen supplier demonstrate ability to spend more on quality outcomes.
The preferred supplier, PricewaterhouseCoopers LLP, demonstrated:
- Excellent understanding of the Ease of Doing Business agenda including key challenges and barriers to growth in India as well as opportunities for international and UK business.
- Ability to draw in and work with a strong consortium which brings in the right practical skills and experience needed to work on this programme in India. Furthermore, the spread of activities across chosen consortium partners was well laid out.
- Innovative ideas and methodology which went beyond the activities set out in the SORs, alongside a constructive assessment of the indicative logframe provided.
- Proven track record of delivering high impact programmes in India and in the field of Ease of Doing Business, not just alone but through consortium partners as well.
Subject to IIOC approval, the contract winner will be announced in July 2019 followed by a 10- day standstill period, and a contract award will be made in August 2019. The inception phase will start as soon as the contract is awarded and will last three months when full implementation will commence assuming a successful inception phase.
Tranche 1 (Alternate Delivery Mechanism)
1. As set out above, a single donor trust fund has been set up with International Finance Corporation via an Administrative agreement in February 2019. The value of the fund is £2,598,312 and the agreement is valid until March 2023. It will be used for capacity-building of the newly formed Reforms Secretariat and sustaining India’s response to the World Bank’s Doing Business Reporting.
2. The agreement was developed based on the Global Business Environment programme run via IFC and the arrangement was overseen by the Commercial Procurement Group.

Commercial Case – Urban Development Strand (updated 13/03/2019)
The Urban Development strand is being delivered through two ‘tranches’:
- Tranche 1 - a Primary Service Delivery Partner procured through the PF Framework Agreement
- Tranche 2 – flexible funding mechanisms including Accountable Grants with not-for-profit organisations, smaller contracts awarded through open market, limited market and single source tenders. Other funding mechanisms will be explored as the programme develops.
Tranche 1 Supplier Procurement
1. Summary: Approval to procure was given by the IIOC Board on 1st November 2017. Following a competitive procurement process against the PF Framework, invitations for were issued to the 24 Suppliers on the Infrastructure Lot B1 and Future Cities Lot B2.
2. The total contract value over the contract duration (May 2019 – March 2023, with review points at the end of inception and in March 2021 to coincide with the Spending Review) will be upto £10m.
3. Timeline. The table below sets out the indicative timetable for contracting, implementation and delivery.
ITT documentation issued on the Bravosolution Portal.	9th November 2018
Deadline to submit requests for clarification via the Bravosolution Portal discussion facility.	10th December 2018
Deadline for Tender Responses.	23rd January 2019
Commencement of Tender Evaluation Period (including Post-Tender Clarification).	28th January 2019
Moderation	4th -5th March 2019
Interviews	7th March 2019
Successful bidder announced, subject to IIOC approval	April 2019
10-Day Standstill period.	April 2019
Contract signing	June 17th 2019

Market engagement. Following the launch of the tender, a ‘Direction of Travel’ meeting was held. The event was attended by 23 potential framework bidders and consortia partners. The event allowed post tender clarifications to be made and answered. A report of the meeting was made available.
The Statement of Requirements (SORs)
1. The scope of activity to be undertaken was defined in detailed Statement of Requirements (SoRs). On 9th November 2018 the Invitation to Tender (ITT) PF18 003 was published and set out clear deliverables (expected outcomes and impacts and any minimum outputs) and indicative activities to achieve these deliverables.
2. The ITT made clear that there was scope for the implementers to input their own ideas as to how best to deliver the required outputs and outcomes, thus benefitting from their expertise and innovative outlook. The appointed suppliers will be expected to implement and manage the programme, working to the Urban Development Strand Lead and Programme Manager who will manage and monitor the programme and ensure alignment with HMG priorities. The SoRs included an explicit section on ODA, IDA and the Gender Act Compliance requirements.
3. As per the above Commercial Case, the SOR set out two clear phases, noting a go-no-go clause at the end of Inception Phase;
  1. Inception Phase (6 months).
  2. Implementation Phase (until end March 2023)
1. The full cost of the programme was assessed as well as day rates. The commercial case set out both implementation costs and programme management costs to support the team manage VfM and identify any key cost drivers. Average day rates were set at a reasonable amount and justification was asked if quoted day rates were substantially higher than set levels. The ITTs explicitly stated that day rates which offered value for money and were in keeping with market rates were expected.
2. The contract for the Tranche 1 Urban Development programme was procured via the Cross-Whitehall PF Agreement, awarded by the FCO to 27 suppliers across 11 Lots. This contract was competed via a call for further competition from suppliers that have been selected based on evaluation of technical and commercial offerings and all will be invited to tender for this requirement. Seven suppliers submitted bids under the programme.
3. Evaluation. The evaluation panel consisted of Deputy Director Prosperity FCO India, Strand Lead and Programme Manager for the Urban Development programme, DIT Head of Trade, and DFID’s Senior Programme Manager for Urban. The process was moderated by CPG London. All evaluators confirmed that they had no conflict of interests. The evaluation model used was the Most Economically Advantageous Tender (MEAT).
4. The bidder with the highest score was Mott MacDonald Ltd. To ensure VfM, the right balance of quality vs price, and that priorities in terms of service capability and capacity is addressed, there was a defended quality threshold for bidders to meet in order for commercials to be evaluated.
5. The SOR specifically indicated a capped average day rate which was set at a reasonable amount and justification was asked if quoted day rates were substantially higher than set levels.. In addition, bidders were asked to separate out programme management vs programme delivery costs to provide assurance that the programme offered VfM and that the FCO were not paying over and above market rates for the management of the programme.
6. The preferred supplier demonstrated:
1. Excellent understanding of the Urban Development agenda including key challenges and barriers to growth in India as well as opportunities for international and UK business;
2. Ability to draw in and work with the strong partners with a consortium which brings in the practical level of skills and experience needed to work on urban infrastructure programmes in India;
3. Innovative ideas and methodology which went beyond the activities set out in the SORs;
4. Proven track record of delivering in India and delivering high impact in the field of Urban Development.
After receiving IIOC approval, the contract winner was announced in March 2019 followed by a 10-day standstill and a contract award made in April 2019. The inception phase started as soon as the contract was awarded and lasted six months when full implementation commenced following the inception phase. A six-month inception phase was chosen as this will include complex identification and selection of commercially viable programmes to be taken forward at implementation.

Commercial Case – Energy & Low Carbon Strand (updated 06/08/2021)
The Energy & Low Carbon strand is being delivered through two ‘tranches’:
- Tranche 1 - a Primary Service Delivery Partner procured through the PF Framework Agreement
- Tranche 2 – flexible funding mechanisms including smaller contracts awarded through open market, limited market and single source tenders. Other funding mechanisms will be explored as the programme develops.
Tranche 1 Supplier Procurement
Approval (through OBC) to procure the India Programmes via the PF Framework was agreed by the IIOC board on 1st November 2017, followed by Ministerial approval on 20th February 2018.
CAB agreed the submission on 21st Nov 2019. The value of the programme was adjusted from £14 Million to less than £8 Million. Head of PF Commercial approved the adjusted value prior to market release. CAB Secretary advised that the opportunity did not need to return to CAB as the value had reduced.
The changes between the intial requirement and the one taken to market are:
- Value decrease from £14 Million to £8 Million
- Change in Contract Length from 3 to 2 Years.
- Push back of Tender release date and award date
- Additional market engagement took place to re-inform suppliers of changes made.

There was no necessity to go back to CAB prior to market release because the value had reduced.

Following the evaluation process the programme was taken back to Mini-CAB on 20/1/2021. Head of Procurement – Prosperity Fund approved the award.

The PF Framework went live on 9th March 2018 (2018/S 052-115615) and has 11 Lots as detailed below;

A1 Business Environment	A2 Finance Trade	A3 Trade
A4 Managed Service	B1 Infrastructure	B2 Future Cities
B3 Energy	B4 Digital	B5 Health
B6 Education	B7 Managed Service

## Invitations for this tender opportunity were issued to 23 Suppliers on the Lot B3 Energy.

1. The total contract value over the contract duration (August 2021 – March 2023, with review points at the end of inception and in March 2021 to coincide with the Spending Review) will be up to £8m (inclusive of taxes).
2. Timeline The table below sets out the indicative timetable for contracting, implementation and delivery of the Energy & Low Carbon Strand
Issue ITT	5th October 2020
Last date for Supplier clarifications	20th November 2020
ITT Submissions	30th November 2020
Evaluation / Moderation	1st December – 31st December 2020
Award Notification	23rd September 2021
10 Day Standstill Period	23rd September – 3rd October 2021
Contract Award/Signature	4th November 2021
Contract Commencement Date	29th October 2023

Market engagement.
Several market engagement events were held to provide advance information on the procurement and the approach, to provide opportunity to refine the requirements, to encourage uptake and understand market appetite (restricted to framework market) before formally publishing the tender documents. The events took place as follows;

Market Engagement: May 2018
Prosperity Fund Framework - Launch Event

Market Consultation: Dec 2018
PF Framework suppliers were engaged to discuss the project design, after the Energy Dialogue, in terms of cost sharing, priority interventions, budget allocations and timelines. These meetings took place on a 1-1 basis.

RFI to PF Framework Suppliers for Market consultation to all PF Framework suppliers’ further shape the design of the business case, to elicit market views on the feasibility of various delivery options and to discuss challenges and opportunities related to the Programme.

Market Engagement: Feb 2020
All Suppliers in Lot B3 Energy were invited to Formal Market engagement at the British Embassy in Delhi. The aim was to present the tender documents to the Suppliers but they were not approved for release. Instead the Programme team outlined the objectives, outcomes and intermediate outcomes to the Suppliers. The Commerical team lead and delivered a presentation on the tender process.

Market Engagements: October 2020
Prior to ITT release to market a virtual session was held to update the Suppliers on amendments to the procurement. Including the reduction in contract budget and scope.

Confirmation of Tender Validity Spring/ August 2021
Messages have been sent to the bidding suppliers on:
  - 07/04/2021
  - 04/05/2021
  - 02/08/2021
All suppliers have replied confirming their tender responses remain valid.

The Statement of Requirements (SORs)
1. The scope of activity to be undertaken was defined in detailed Statement of Requirements (SoRs). On 5th October 2020 the Invitation to Tender (ITT) PF19 011 was published and set out clear deliverables (expected outcomes and impacts and any minimum outputs) and indicative activities to achieve these deliverables.
2. The ITT made clear that there was scope for the implementers to input their own ideas as to how best to deliver the required outputs and outcomes, thus benefitting from their expertise and innovative outlook. The appointed suppliers will be expected to implement and manage the programme, working to the Energy & Low Carbon Strand Lead and Programme Manager who will manage and monitor the programme and ensure alignment with HMG priorities.
3. The SoRs included an explicit section on ODA, IDA and the Gender Act Compliance requirements.
4. As per the above Commercial Case, the SOR set out two clear phases;
  1. Inception Phase (4 months).
  2. Implementation Phase (until end March 2023)
1. The full cost of the programme was assessed as well as day-rates. The commercial case set out both implementation costs and programme management costs to support the team manage value for money and identify any key cost drivers. Average day rates were set at a reasonable levelto ensure value for money and reflect market rates .
2. The contract for the Tranche 1 Urban Development programme was procured via the Cross-Whitehall PF Agreement, awarded by the FCO to 27 suppliers across 11 Lots. This contract was competed via a call for further competition from suppliers that have been selected based on evaluation of technical and commercial offerings and all will be invited to tender for this requirement. Five suppliers submitted bids under the programme.
Summary of procurement route
The Evaluation Panel:
The programme team identified suitable candidates for the Evaluation Panel (“Panel”). The Commercial team sought and reviewed the Panel’s credentials to provide assurance of the candidate’s suitability and identify any gaps. The information requested identified current or previous experience in:

- The Prosperity Fund
- Programme Methodology and Team Expertise
- The geographies covered by the programme,
- The primary purpose, financial services and economic development, and secondary benefits of the programme
- Gender and Inclusion
- Monitoring reporting and Learning
- Programme management
- Smart Power and Renewable Energy

The Commercial team made recommendations to the Programme team, based on the information supplied by the selected candidates, and the following Panel was agreed;

UK PACT Green Recovery Challenge Fund Programme Manager (BEIS)
Programme Manager for the 2050 Calculator Extension Programme (BEIS)
Team Leader Energy and Low Carbon Growth
Low Carbon Energy Programme and Policy Lead-UK Trade Economics and Prosperity
Energy Advisor, DFID
Senior Advisor, Energy Security (Smart Power Specialist)
Senior Advisor, Energy Security (Renewable Energy Specialist)
FCO PF Social Development Adviser
Programme Monitoring & Evaluation Manager

The selected Panel members attended training sessions held by the Commercial team 27th Nov 2020 which covered guidance and rules for evaluating tenders. Social Development Adviser presented information on how to evaluate whilst prioritising G&I.
Guidance documentation was shared with evalutors to be used independently throughout the evaluation period.

The Panel signed and completed a Confidentiality Undertaking and Conflict of Interest form via the Jaggaer portal (collaborations) prior to accessing tender submissions and conducting their independent evaluations.
The evaluation model used was the Most Economically Advantageous Tender (MEAT).
1. The bidder with the highest score was KPMG. To ensure VfM, the right balance of quality vs price, and that priorities in terms of service capability and capacity is addressed, there was a defended quality threshold for bidders to meet in order for commercials to be evaluated.
2. The SOR specifically indicated a reasonable capped average day rate. In addition, bidders were asked to separate out programme management vs programme delivery costs to provide assurance that the programme offered Value for Money and that the FCO were not paying over and above market rates for the management of the programme.
  2. None of the Supplier’s bids included £200,000 of the total contract value which has been set aside for achievement of Intermediate outcomes which must be achieved by the end of the Programme’s implementation phase (Dec 2020). This value has been added to the contract value proposed by KPMG in their commercial submission.

The preferred supplier, KPMG. demonstrated:
1. Excellent understanding of the Energy & Low Carbon agenda including key challenges and barriers to growth in India as well as opportunities for international and UK business;
2. Sound understanding of gender aspects across all sub-themes of the Smart Power and Renewables and Storage Projects illustrated with specific examples, identified early wins, strong linkages with climate/COP 26 agenda; strong understanding of the log-frame wih robust indicators and assumptions, provided detailed scope of activities for each Project theme Scope of the activities with lcear rationale, mapped to relevant UK expertise.
After receiving CAB approval on 21st Jan 2021, the contract winner was announced in October 2021 followed by a 10-day standstill and a contract award made in November 2021. The inception phase started as soon as the contract was awarded and lasted four months when full implementation commenced following the inception phase. A four month inception phase was chosen as this will include complex identification and selection of commercially viable programmes to be taken forward at implementation.

Managing Implementers during delivery (Applicable to all strands)
1. Contract forms and duration. The FCO is the Contracting Authority. For Tranche 1, contracts are awarded on the basis of the Framework Agreement ‘Terms & Conditions of Contract’. For Tranche 2, the FCO Procurement Hub at post is responsible for undertaking procurement and issuing contracts, which are signed by a member of staff with sufficient delegated authority. Accountable Grants are also managed at post. All spend is only undertaken following thorough due-diligence checks. Safeguarding policies are included.
2. The PF will close on 31st March 2023 and commercial contracts will have that end date, with scope to extend by contract amendment for an additional 50% of value or an additional five years duration to retain flexibility. No material change will be permitted and should the initial requirement significantly change, the contract will be terminated and a new competition to award the revised scope initiated via the PF Framework or a new agreement made with a multilateral organisation.
3. Ongoing Design Work. While the pipeline of priority interventions will be set out at the implementation stage, this may need to be updated during the lifetime of the programme in line with changing external and internal demands. Delivery partners may also recommend changes as a result of experience on particular projects. Such changes will be kept to a minimum and will be carefully handled and coordinated by Post, the India PF Board, the supplier and the Programme Managers and in accordance with the Variation process and Contract Management plan (to be developed at post).

Terms and Conditions
The Framework Terms and Conditions reflect the Government Model Contract Terms for Services and have been developed to reflect the specifics of the PF, ODA and IDA requirements. Key terms include:
1. Data Protections
2. Intellectual Property Rights
3. Transparency
4. Tax Compliance, Termination rights
5. Environment, Health & safety, Equality & Diversity, and Anti-Terrorism clauses
Call-off terms provided for a roll down to a more detailed level to be adapted in line with the requirements and the environment in which the services will be delivered. Additional clauses in Service Levels & Credits, Performance Management, Business Continuity and Exit arrangements were included and as relevant to the requirement.

Tranche 2 procurement
1. As set out above, a flexible approach will be required to respond to new and emerging areas of work which sit outside of the scope of the Framework Supplier. The programme team alongside DIT, DFID and Prosperity Advisors in India will be responsible for scoping areas of work, which drive impact, spend in those areas which are of mutual benefit to the UK and India.
2. In keeping with the responsive nature of the PF, a small distinct amount of funding will be used to secure technical experts from HMG based on the areas identified either by PSDP, IFC, or Government of India to respond to niche areas. To ensure availability of experts, bilateral MoUs will be signed between FCO India and the international arms of relevant Other Government Departments (OGDs). All funding mechanisms will be aligned to FCO policy and regulation and will ensure VfM, ODA, IDA, Gender Equality, Due Diligence and Safeguarding compliance.
3. Procurements for commercial contracts will be run by the Procurement Hub at post. Accountable Grants, MOUs etc. will also be overseen at post.

# FINANCIAL CASE
## A. Programme Budget
1. The programme was originally designed to provide support of £60m from PF resources over five years (2017– March 31, 2023). However, £10.5m was later cut from the Energy & Low Carbon programme which was followed by a further cut of £1.65m on account of ODA prioritisation which was contributed by Financial Services strand. The summary budget at Table 9 below shows the indicative break-up of envisaged programme costs. Based on experience for delivering this type of programme, the expenditure is purposefully high to allow for the underspend that strands may have especially towards the outer years.
2. Activity-Based Budgets, which link spend to defined outcomes, are developed during the Design Phase of each programme. However, workplans and associated budgets retain a degree of flexibility as the Government of India is a key stakeholder in all programme strands and it is not possible to accurately predict the pace and scope of policy reforms and wider delivery over the medium term. Value for money assessment may be done at any stage where a significant change in budget or results is being proposed.
Table 9:Indicative programme costs for future years[163]:
[163] The figures include a projected overspend of 20%
	Allocation	FY / 17-18	FY / 18-19	FY / 19-20	FY / 20-21	FY / 21-22	FY / 22-23	Total
Admin	5,206,000	263,858	680,434	687,413	770,636	831,202	917,875	4,151,418
EoDB	8,200,000	92,950	313,989	394,523	1,470,014	3,358,330	2,358,332	7,988,138
FS	6,550,000	108,322	500,904	1,538,265	1,182,819	2,221,698	1.538,145	7,090,152
Energy	10,000,000	285,186	146,518	652,037	1,013,039	5,627,500	5,142,057	12,866,337
Urban	12,400,000	-	17,808	1,927,724	1,541,889	4,160,000	3,763,713	11,411,134
Skills	4,700,000	-	200,000	1,100,000	1,200,000	1,200,000	1,000,000	4,700,000
Total	47,850,000	750,316	1,859,653	6,299,963	7,178,397	18,795,730	16,817,121	48,207,179

Administration costs including staffing are included in the figures above. Staffing costs are primarily driven by the need for UK officers in key D-band posts to ensure sufficient strategic oversight and to drive delivery particularly in the early years where systems and processes are still evolving and we need to embed a strong secondary benefits approach. (Staffing costs are based on full economic costs including salaries, accommodation, allowances, etc.).

A1. How will this be funded?
1. The full £47.85m programme allocation will come from the £1.3bn PF announced by the UK Government in November 2015.
2. Any capital assets procured under this programme will be treated in accordance with FCO procedures and declared on an annual basis. Should assets remain at the end of the programme; an exit strategy will be agreed with FCO.
3. The programme consists solely of technical assistance and is largely being delivered through external implementers. The nature of the services they are providing means that a majority of their costs is personnel time costs. Programme implementation also involves relevant reimbursable costs such as project related travel and accommodation, events organising and other delivery related costs as well as monitoring. Funding is also required for HMG staff as well as overheads, training and development and other admin costs.
4. Built on experience within HMG (particularly DFID) there is a strong administrative and technical team in India overseeing the delivery of the India PF. Whilst PSDPs are in place it has been demonstrated that a high level of both technical and programme management oversight is required to mitigate potential risks of under-performance or non-delivery and to ensure that the programme is delivered in a way which maximises benefits.

A2. How will funds be paid out?
1. PSDPs for each of the strands managed by FCO will be procured and contracted through the PF Framework Agreement. The PSDPs will be responsible for all activities set out in the Commercial Case.
2. For ad-hoc or smaller contacts alternative procurement arrangements are used including: MoUs, grant contracts, open market tender.
3. For all contracts and financial agreements, SMART performance matrices are used to link payments to specific activities. Payment is made in arrears and FCO reimburses the service provider on the delivery of results and satisfactory achievement of milestones.
4. Funding tranches are agreed with the service provider based on the SoR for implementation Y1 (programme Y3) and from there on is based on the approach and activities agreed at design phase.
5. No payment in advance of need is envisaged except for IFC under Ease of Doing Business strand – any legitimate request for an advance of need either by a direct service provider or a third party contracted by a primary services provider will be raised with HMT for approval. For IFC, all the necessary approvals were obtained before advancing money from FCO.

A3. Management of Risks:
1. The financial risk of this programme is assessed to be low-medium on the basis that TA programmes are not highly susceptible to fraud and corruption and that the Primary Service Delivery Providers will have been through the full FCO due-diligence process during the PF Framework Agreement Procurement Exercise.
2. Risks we anticipate based on past programme experience of FCO and DFID include delays in Government of India approvals for scope, procurement bottlenecks when tendering multiple contracts simultaneously, and visa delays which affect those strands that assume movement of officials between countries. These are being managed by building in time to complete procurement processes, effective contracting and working with implementers and the Government of India to overcome external delivery roadblocks.
3. Should unforeseen problems arise in the programme, our maximum financial exposure will be dependent upon the timing. Experience from other similar programmes indicates that the highest risk point is at the end of implementation phase where funds will have been spent without any primary or secondary benefits having been achieved. The amount of funds committed at design phase will vary between each strand. Thereafter, spend will be linked to the achievement of impact so exposure will be low.
4. The India PF Portfolio Team will work with strand leads and programme managers to ensure any financial risks associated with under or overspend are tracked and raised immediately with the Head of PF Programmes and Strategy and the PF India SRO.
5. A full risk register is included in the management case below and a detailed risk register will be developed at the strand level during design phase of each programme. This will kept under tight review with a particular focus on financial risk and exposure.

Financial Management
B1. Budget Responsibility:
1. The programme budget for all strands except Skills is held by the FCO in Delhi. Responsibility for financial management and reporting at strand level sits with each programme strand lead. FCO maintains responsibility for reporting on the £47.85m of the India PF which is delivered by the FCO. The Skills strand will be managed and reported on by DFID. Each strand lead is supported and overseen by the India Prosperity Portfolio Team (PPT) at post, which is responsible for financial management at the programme level under the PF India SRO (Director of Prosperity Delivery). Programme level reporting is fed into the Prosperity Fund Delivery Unit (PFDU) in London for all FCO programmes. Responsibilities at post are set out in more detail in the management case below.
2. Skills: DFID India takes on responsibility and accountability for the delivery of the India PF Skill strand. The funding is transferred to DFID and the strand follows DFID’s assurance process and timetable. For reporting purposes, the PF India team continues to report against the full £47.85m programme where necessary (except for financial reporting which is made through DFID to avoid double counting).

B2. Budget Allocation and Financial Reporting:
1. The reporting requirements for implementers is set out in the contracts agreed with the winning bidders which specifies the need for compliance with PFDU requirements and, as appropriate, DFID Smart Rules and guidance (such as that payments will not be made in advance of need).
2. Forward-looking budgets, delivery plans, and milestones are agreed following submission of the design and inception report under each contract, and annually thereafter. Obligations for meeting spend forecasts are built into the contracts to ensure effective costs and spend management. Spend is reviewed at quarterly meetings between the programme lead and contractors and any concerns on ability to meet forecasts is raised immediately.
3. Budgets and delivery plans are produced alongside retrospective analysis of performance in the preceding year. These annual reports are supplemented by quarterly reports, which include a record of activity over the previous quarter, progress against the work plan and logframe outputs, a risk register, and any expected deviations from the agreed forward-looking budgets and delivery plans. Invoices are delivered along with these quarterly reports, with payment made in arrear against satisfactory completion of activity set out in the agreed work plan.
4. For internal reporting, each strand team provides monthly updates and a more detailed financial and management report (including risks) on a quarterly basis to PPT at post. The PPT compiles a Monthly Report for the India SRO (Director, Prosperity Delivery) and more detailed financial report and risk register on a quarterly basis that covers all of the India network’s PF programming, and takes responsibility for assuring accuracy of data on Hyperion and Oracle Business Intelligence Enterprise Edition (OBIEE). Quarterly reports are submitted to PFDU.
5. Implementers submit a quarterly progress report along with an invoice for fees and expenditure. Rigorous monitoring of invoices and activities is undertaken throughout the duration of the programme.

Scaling the Programme Up or Down
Given the finite nature of the programme funding available, it is expected that the majority of funding will be dispersed in focus states, with the remaining funding used to capitalise on high value opportunities that arise elsewhere. In the event that the amount of money made available to the programme is increased or reduced, the overall programme can be scaled up or down by either:
- Increasing or reducing the number of focus states;
- Increasing or reducing the amount of money made available for high value opportunities in non-focus states.
The former is more suited to a significant change in the scale of funding, while the latter allows flexibility on a more moderate level.
The following flexibilities have been built in the programme design and contracting approach to protect the FCO and maximise the effectiveness over the life of the contract as it matures and as requirements evolve:
  1. Contracts will be set up in such a way that they can be terminated should there be under performance or a significant change in priorities, which results in the focal strand no longer offering value for money in terms of delivering both primary and secondary benefits.
  2. 10%/ 90% split in funding between the PSDPs and ad hoc programmes and/or uplift allowing a proportion of the budget to be used as both an incentive for strong performance and/or to spend on opportunities to deliver results which fall outside of the mandate of the PSDPs.
  3. Contingency retained at the portfolio level, which can be used to uplift strands which demonstrate high performance and absorptive capacity to deliver more.
  4. It is stipulated in the contract that Annual reviews and Mid-term Evaluations are the point at which changes to the programme (logframe, activities to deliver results etc.) are recommended and made. A formal change management process is triggered should the changes be outside of the programme tolerance for sign off at SRO level.

# MANAGEMENT CASE
      1. Governance
A1. Whitehall architecture
Multiple government departments share an interest in the UK’s relationship with India and several have staff based in India including BEIS, DFID, DIT, FCO and HO. The India Strategy Board (ISB) provides a Whitehall-led forum for senior officials to coordinate efforts in order to deliver the NSC’s ambitions in India. The ISB meets quarterly and is chaired by FCO’s Director, South Asia and Afghanistan. Senior officials from across Whitehall and at Post attend, including the High Commissioner, DFID, Tech Partnership SRO, and the PF SRO. The ISB feeds in to Ministerial decision-making forums as required. The ISB does not have a formal governance role for the PF but it routinely receives (and requests) updates on prosperity issues including the PF which helps to integrate the PF into the cross-Whitehall picture ensuring it remains relevant and targeted on Ministerial priorities.

A2. British High Commission wider governance structures
1. The British High Commission in India is a large mission, encompassing several partners across government including BEIS, DFID, DIT, FCO and HO. cross-government governance structures exist to support a coordinated, coherent approach to UK engagement in India. Two in particular are relevant to the PF: the Board of Management and the Delivery Board. They are chaired by the High Commissioner and the PF SRO attends both.
2. The quarterly Board of Management is attended by all HMG partners at Post and by the Deputy High Commissioners from around the India network. Its remit covers corporate services, policy and delivery issues. The Board’s membership makes it a useful forum through which the PF team can communicate with internal stakeholders and receive feedback, as well as maintain awareness of relevant activity underway by others.
3. The Delivery Board was created by the High Commissioner to drive activity in priority areas to support delivery of the NSC Strategy. Senior managers sit on the Delivery Board and review delivery progress on a quarterly basis. Priority areas include the thematic areas under the PF programme. For each area there is a cross-HMG Delivery Plan that sets out Post’s ambition and how a cross-HMG approach is being used to support delivery. This approach to delivery is helping to foster closer working between HMG departments and keep minds focused on delivering with impact. The PF is recognised as one of the key programme tools to support delivery alongside programmes funded by DFID, UKRI and others.

A3. Prosperity Fund India: financial accountability and governance structure
1. Responsibility for India PF Programme budget will be delegated to the PF India SRO via the following route: Cabinet Office > PUS of the FCO > DG Global Britain > Director, South Asia and Afghanistan (SAAD) > High Commissioner to India > PF India SRO. The PF India senior responsible officer (SRO) with operational responsibility and financial accountability for the India PF Programme will be the Director, Prosperity Delivery (SMS1). The SRO will have full oversight and will be ultimately accountable for the India PF. The PF India SRO will deliver through a team at Post comprising PF and non-PF staff, through direct and indirect (matrix) arrangements.
2. The PF India SRO and PF India team will report through the FCO’s Prosperity Fund Delivery Unit (PFDU) which has overall responsibility for FCO PF Programming, on behalf of DG Global Britain. The PF India SRO will also maintain regular contact with the High Commissioner and the Director SAAD so that they are well sighted on delivery, issues and risks. This will be important given the High Commissioner’s responsibility for overall HMG activity in India. A key element of governance arrangements at Post is the India PF Board that meets quarterly. Membership and function of the Board is well defined. Boards are chaired by the SRO with representation from PFDU, senior HMG representatives from FCO, DFID and DIT, Deputy High Commissioner from regional network, Tech Partnership, strand leads of the five programmes, Finance and MREL. Membership will be reviewed annually and adjusted if required to ensure relevant stakeholders are represented.
3. Day-to-day management of the PF India portfolio will be delegated by the SRO to the Deputy Director, Prosperity Programmes (D7). The Deputy Director, Prosperity Programmes will run the India Prosperity Portfolio Team (PPT) and will provide oversight of the programme strands, working closely with Strand Leads. The PPT will support delivery of the programme (financial management and reporting, MREL, risk management, procurement and contractual management etc.). The PPT will interface with PFDU and PFMO as required. The PPT will act as secretariat to the PF India Board. It will consist of a dedicated D6 Head of PPF, supported by two C-band level programme managers and several B-band and A-band officers.
4. At a strategic level, the D7 Deputy Director, Prosperity Programmes as well as the SRO; Director of Prosperity Delivery will be responsible for ensuring coherent portfolio level delivery providing advice, guidance and challenge to the strands as well as to PFDU and PFMO. A Portfolio Working Group, chaired by the D7 Deputy Director, Prosperity Programmes will be convened at least once a month (likely more frequently in the initial stages) to oversee portfolio level delivery. This will be made up of strand leads and programme managers, the PPT and SRO when required.
5. At programme level, the four programme strands will be delivered by D-band officers within relevant policy teams supported by embedded C-band programme managers (for more detail see strand level management and staffing sections below). Some of the D-band officers are PF posts, some are FCO policy posts that will combine PF and BAU activity. All C-band programme managers are PF posts. Line management of the Strand leads will continue to be through their respective work stream line managers (DIT, FCO etc.) but they will be expected to report (in a matrix arrangement) to the PF at different levels and for different purposes.
6. Strand leads will report to the PF India Board on a quarterly basis to enable the Board to discharge its function. They will report to the D7 Deputy Director, Prosperity Programmes allowing the D7 to provide strategic oversight at portfolio level (and by strand where appropriate) and they will provide reporting (financial, delivery) through the Prosperity Portfolio Team. The governance arrangements for the India PF Programme are summarised below:
Roles and Responsibilities:
FUNCTION	PERSONNEL	RESPONSIBILITIES
SRO	Director of Prosperity Delivery (SMS1) reporting to the High Commissioner	Overall accountability for India PF Programme
India PF Board	Chaired by the SRO (Director of Prosperity Delivery) (SMS). Director of Economics & Trade (SMS) as Co-Char. with senior level representatives including from PFDU, PFMO, SAAD, DFID and BHCs in India	Review fund progress, provide challenge and advise on strategic priorities.
Management	Deputy Director, Prosperity Programmes (D7) supported by D6 Head of Prosperity Portfolio Team and the Prosperity Portfolio Team (PPT)	Managing India PF Programme at Portfolio Level and Prosperity Portfolio Team.
Delivery	Prosperity Portfolio Team, led by the D6 / Strand Leads and supporting Programme Managers (as well as Delivery Partners)	Programme management including finance, procurement, monitoring and evaluation.

A4. India PF Management of Strand Delivery:
All Strands other than Skills will be delivered and managed by the FCO in India. The skills strand will be managed by DFID, who will have responsibility for both financial and results management. A member of the India PF will act as the liaison point with DFID to ensure a coherence across the PF portfolio and that the skills component remains a strategic fit with the PF. A full explanation of how the Skills strand will be managed is at Annex E.

A5. Strand Level Delivery – Management by India PF Strand Leads
1. Each of the four FCO-managed strands will be led by a D-band Strand Lead responsible for delivery at Strand level – in effect strand-level SROs. They will be responsible for overseeing programme delivery including financial reporting and forecasting, risk management, and MREL. They will ensure that the allocation of programme funds by the PSDP as well as other delivery partners maximises the achievement of primary and secondary benefits, demonstrates additionality, maximises VfM, and mainstreams gender and social inclusion.
2. It will be the Strand Leads’ responsibility to allocate strand level funds e.g. for ad-hoc or smaller contracts outside of the PSDP. Significant decisions such as changes to funding or scope may only be done in consultation with the D7 Deputy Director, Prosperity Programmes, and where appropriate, the PF India SRO. Where changes exceed FCO tolerances, these will be escalated.
3. As set out earlier, oversight of the Strands will be provided in several ways. Strand Leads will report to the quarterly India PF Board. The D7 Deputy Director, Prosperity Delivery will provide day-to-day strategic oversight, while reporting (financial, MREL etc.) will be done through the PPT headed by the D6 Head of Prosperity Portfolio Team (PPT). Their direct line management will lie under the management chains of either the Director of Prosperity Delivery (also PF India SRO).
4. Strand Leads will be supported by embedded C-band programme managers in their teams, prosperity advisors, the Prosperity Programmes Team (PPT) and, where appropriate, other FCO prosperity (non-PF) staff working in the PF thematic areas.

A6. Strand Level Delivery – Management by Primary Service Delivery Partners (PSDPs)
At the strand level, PSDPs will be responsible for managing the operational delivery of their respective strands. Activities will include:
  1. Detailed design (inception phase) and implementation of programme delivery approach, which achieves primary and secondary benefits and ensures additionality, VfM, and mainstreams of gender and social inclusion
  2. Fund management, which may include procurement at the project level and for distinct areas of work.
  3. MREL.
  4. Financial and risk management and reporting.
  5. Relationship management with key stakeholders and the market.
1. A contract will be signed between Corporate Procurement Group and the PSDPs. The contract will be the legally binding document that sets out the detailed legal and financial terms of the partnership, defines roles, responsibilities, obligations and relative legal positions for each entity with clear accountabilities.
2. Each PSDP will have a designated senior representative who will be the point contact with the PF strand lead. They will be fully accountable to the FCO (via the strand leads) for the delivery of the strand outcomes, financial and risk management etc. They will represent the strand to the PF India Board if required.
3. It is anticipated that PSDPs will at a minimum have the following skills represented:
  1. Programme management including risk, budget and forecasting.
  2. Development within the South Asia context.
  3. Private sector, trade and investment.
  4. Fund and investment management
  5. MREL including financial reporting
A strand level Steering Committee will be established which meets at least biannually with responsibility for:
  1. Providing strategic oversight to the delivery of the strand.
  2. Taking decisions on budget allocation, programme documents – including annual work plans etc.
  3. Steering Group will be chaired by the Strand Lead with a PSDP providing a secretariat function. It will have a membership of the strand lead, the D7 Deputy Director, Prosperity Programmes, at least one other representative of HMG as well as senior representation by the PSDPs and relevant PSDPs team members.
A Strand Working Group will be established which meets at least once a month (more frequently in the initial stages). It will constitute at a minimum the PF strand lead and programme manager and relevant team members from the PSDPs. It will be responsible for:
  1. Day-to-day oversight and management of programme delivery - including standing items of spend and forecasts as well as risk management.
  2. Technical level discussions on programme development and delivery – including potential areas of investment and stakeholder engagement.
1. We anticipate two main approaches to PSDPs bids during procurement. In the first, the PSDPs bids as a consortium (main partner and sub-contractors) and sets out in the tender which consortium partners will lead which package of work and for what price. In the second, the PSDP bids as a single provider or as a limited consortium and procures individual projects and work areas after being appointed. In the event of the latter, an Investment Committee will be established, constituting at a minimum the PF strand lead and relevant team members from the PSDP. The PF strand lead will have veto rights on any spend and will be the strand mechanism for influencing and retaining control and oversight of investment decisions. The Investment Committee will be chaired and managed by the PSDP. In keeping with legal advice, the contract for third party procurement will be held by the PSDP and will comply with all Public Financial Management rules and procedures.
2. Figure 10 below illustrates how this will work for an example strand:

D7
Deputy Director Prosperity Programmes

Strand Steering Committee
(Chaired by Strand Lead)
Annual/ biannually

Portfolio Delivery Group
(Chaired by D7)
Monthly

PSDPs Senior Representative
Strand Lead

Strand Investment Committee
(Chaired by Strand Lead)
As required
Strand Working Group
2-4 weekly

PSDPs
Programme Team

      1. Reporting
The following reporting will be undertaken:
  1. Financial reporting
  2. Activities and delivery reporting
  3. Results and impact reporting.
B1. Generic progress reports
The contracted lead delivery partner for each strand will provide monthly reports to the Strand Steering Group (chaired by the D-band programme strand lead). The strand lead, supported by their C-band programme manager, will then report quarterly into the India Prosperity Portfolio Team (PPT), led by the D6 Head of Prosperity Portfolio Team (PPT). The PPT will collate these into a programme level report covering the status of the five strands and the programme as a whole. This will be submitted to the SRO and PFDU on a quarterly basis. Reporting to the PF India Board will be also on a quarterly basis to suit the meeting cycle. Generic Reporting routes will be as below:

Contracted delivery partner/s
India PF Prosperity Portfolio Team (PPT)
(via D7 and SRO as needed)
Strand Level Working group
Prosperity Fund Delivery Unit
(and PFMO where required)
Strand Level Steering group

B2. Financial Reporting – including spend and forecasts accuracy:
1. All financial reports will be structured in a way which meets FCO, HMT and Cabinet Office requirements.
2. Budgets and delivery plans will be produced alongside retrospective analysis of performance in the preceding year. These annual reports will be supplemented by quarterly reports, which will include a record of activity over the previous quarter, progress against the work plan and logframe outputs, a risk register, and any expected deviations from the agreed forward-looking budgets and delivery plans. Invoices will be delivered along with these quarterly reports, with payment made in arrear against satisfactory completion of activity set out in the agreed work plan.
3. For internal reporting, each strand team will provide monthly updates and a more detailed financial and management report (including risks) on a quarterly basis to PPT at post. The PPT will compile a Monthly Report for the India SRO (Director, Prosperity Delivery) and more detailed financial report and risk register on a quarterly basis that covers all of the India network’s PF programming, and will take responsibility for assuring accuracy of data on Hyperion and Oracle Business Intelligence Enterprise Edition (OBIEE). Quarterly reports will be submitted to the PFDU.
4. Monthly financial data will be collected and used for early identification of any discrepancies in spend and potential under performance. Strand Leads / Programme Managers with support from the Prosperity Portfolio Team will be responsible for ensuring Prism is kept up to date. The Deputy Director, Prosperity Programmes and the Head of the PPT will utilise the OBIEE Dashboard to undertake in-month and Outturn Analysis.
5. Implementers will submit a quarterly progress report along with an invoice for fees and expenditure. Rigorous monitoring of invoices and activities will be undertaken throughout the duration of the programme. Funding will not be disbursed if we have concerns about an organisation’s track record.
6. Full financial reports and audited accounts will be required on an Annual Basis. Qualified Accounts will be required before any implementing partner is approved to move forwards to the next implementation year.
Programme reporting for SRO and SBH
Frequency	Artefact(s)	Input	Author(s)	Audience
Weekly	Prosperity Fund Delivery Unit update	Verbal updates	Head of PFDU	Geographic and Thematic Leads
Monthly	Highlight Report (covering: summary; individual Programme achievements / next steps; key risks and issues and; areas requiring escalation.	PFDU commissioning e-mail to all Programme Leads / PFDU Heads / Director	Overall: PFDU – Corporate Scrutiny & Assurance Manager / Programme Leads	Director, Economic Diplomacy / DG Global Britain / Lodged on Sharepoint for wider information.
Monthly	Input into PFMO Dashboard	PFDU	PFDU – Corporate Scrutiny & Assurance Manager / Programme Leads	Portfolio Board members
Quarterly	Quarterly Progress/ Monitoring Reports	Implementers/ Posts/ Programme Teams/PPT	Programme Leads & SRO	DG Global Britain / Director, Economic Diplomacy / Head PFDU
Yearly	Annual Review / One annual DipTel, summarising key achievements, lessons learned and how UK interests have been advanced.	Posts / Programme teams Posts, PPT / Post	Review Panel (formed every year), SRO & SBH (with Programme Lead input) / SRO & SBH	Director, Economic Diplomacy / DG Global Britain / Head PFDU / PFMO
Programme Completion Report (PCR)	Programme Completion Report (PCR)	Programme Team	Programme SRO and SBH	All stakeholders (specifically: PFDU/ PFMO/ Ministers/ Portfolio Board)

B3. Annual Review
1. Annual Reviews will be used as a continuous process of review and improvement throughout the delivery of the India PF. The approach set out below is based on DFID’s SMART rules. The Review Panel will lead the Annual Review. Panel members will be selected every year consisting of representation from both India PF team and JFU/PFDU.
2. In undertaking a formal review of progress achieved since design or the last annual review, including an assessment of the quality of progress, the Annual Review will:
- Be proportionate to the budget, risk, and level of complexity of the programme;
- Make evidence-based judgements on whether the programme is delivering the outputs expected by this point in the programme’s cycle, as set out in the results framework; consider whether the targets are still realistic yet ambitious and draw conclusions as to the likelihood of a programme achieving its stated outcomes;
- Consider significant changes to the assumptions made in the Business Case (i.e. context, risk, value for money, operating or political environment), as set out in the Theory of Change;
- Make judgements on whether the programme is managing risk well and represents good value for money (VfM) including by flexing and adapting to change;
- Consider the quality of financial and results reporting and provide assurance that funds are being managed well;
- Consider risks identified in the Due Diligence Assessment, Fiduciary Risk Assessment or contracting process and consider how these have been addressed;
- Judge whether gender, inclusion, conflict sensitivity and human rights are being effectively taken into account and managed in programme design and implementation, for ensuring alignment with the International Development (Gender Equality) Act (2014) and PF Gender and Inclusion Policy, and progress against the PF Gender and Inclusion framework;
- Consider the effectiveness of partnerships, including through the government’s viewpoint and beneficiary feedback, the suppliers’ performance and contract implementation;
- Be informed by discussions with a wide range of stakeholders, including as necessary beneficiaries (including the views of men and women from different poor and excluded groups), government, civil society (including relevant organisations representing women and excluded groups), SMEs and other donors, and not just by reporting and meetings with implementing partners. They may also incorporate other sources of evidence that support a greater understanding of progress towards targets;
- Provide specific, time-bound recommendations for action that are consistent with the key findings;
1. The Annual Review will be delivered through a combination of desk-based work utilising existing M&E data as well as external interviews with delivery partners, beneficiaries, the GoI and other relevant stakeholders. It will in the first instance be quality assured by the Deputy Director, Prosperity Programmes and Economics unit before being presented to the PF India SRO; Director of Prosperity Delivery.
2. Any programme performing scoring a B or a C will need to build improvement measures into the Delivery Plan. JFU will provide assurance of the improvement measures and advise the Portfolio Board on the effectiveness and whether early closure or restructuring of the programme should be recommended.
3. The information from the Annual Review will be used to:
  - Update delivery plans in accordance with key recommendations.
  - Reflect shifting strategic priorities
  - Move funds from poorly performing to highly performing programmes
  - Address change requests submitted by programmes
  - Manage underspend/overspend across the portfolio
  - Update and revise existing activities, timelines and resources.
  - Amend the results framework below outcome level (above which would trigger the formal change process).
  - Update risk management plans.
1. An Annual Review recommendations tracker will be developed to ensure recommendations are being effectively responded to throughout programme delivery. This response will be reported on in the subsequent years Annual Review.
2. The Annual Review process will act as the formal mechanism for ensuring effective management and delivery by the contracted partners from point of contract through to programme close. This will be supplemented by regular contract management meetings throughout the year, which will enable any problems or risks to effective delivery to be caught and addressed early on.

Staffing
1. Most day-to-day delivery will be outsourced to service providers but it is essential that the in-house team is equipped to manage larger scale procurement and contracts, to act as ‘intelligent customers’, and to ensure secondary benefit is derived alongside primary benefit. Trainings are scheduled on regular basis depending on the need assessment along with orientation in London for PF core team. The India PF team will continue to work closely with London to draw down on capabilities as required and will work with DFID, DIT and others to ensure sufficient skills and capabilities exist at post.
2. Figure 11 details the staff structure that will deliver the India PF programme. Existing FCO staff at Post (non-PF) will also support delivery in Delhi and regionally. We will also ensure close working with other teams at Post including FCO, DFID and DIT.
3. C-band programme managers supporting D-band strand leads will be embedded within strands ensuring good programme management practice is adopted for day-to-day delivery. We will also have a strengthened PPT to manage larger financial flows, larger scale procurement / contracts, reporting and monitoring and evaluation.
Figure 11: Staffing structure

DFID
Deputy Director
Prosperity Programmes
(D7)
Head of Prosperity Portfolio Team (D6)
Programme Manager
(LE C4)
Programme Manager
(LE C4)
Programme Manager
(LE C4)
Financial Services lead
(D Band)
Skills DFID
Finance Manager
(LE C4)
Urban Lead
(D Band)
Ease of Doing Business Lead
(D Band)
Energy & Low Carbon Lead
(D Band)
A2: Programme Administrators
B3: Programme Management Support
Prog. M&E Manager
(LE C4)

Staffing will be kept under review and adapted if necessary throughout the duration of the programme, particularly once implementer contracts are in place and design phases completed.

Monitoring and Evaluation
1. The below sets out the expected monitoring and evaluation strategy as advised by the PFMO. The India PF will feedback lessons learned in M&E to ensure a best practice approach is achieved.
2. Results framework. The monitoring, reporting, evaluation and learning (MREL) for the programme will be consistent with the overall PF approach to MREL. The team in India will work with the central Fund MREL contractors and PSDP to develop critical indicators for Fund and programme level reporting, identifying indicators for regular reporting and management indicators to allow programme managers to assess progress and impacts. The programme MREL will be consistent with the programme theory of change and the logframe analysis that flows from this. Expenditure will be reported monthly and impacts (results) quarterly, in line with Fund reporting rhythms. Where possible, reporting will be disaggregated by gender, disability, age, etc.
3. Reporting frequency and costs. Programme implementing partners will develop a quarterly results reporting system and will work with the MREL manager at FCO and central Fund Monitoring & Reporting contractor to ensure consistency with Fund processes and systems – particularly around data quality and consistency. Programme data capture and baselining will be the responsibility of the programme and its implementers but, as instructed, the costs of this will be charged to the central MREL budget. This element of the programme is capped at 1% of programme allocation.
4. Evaluation & Learning. If the programme is selected as one of the sample for fund level evaluation, the MREL manager in tandem with strands will work with the Fund evaluation and learning contractor to develop strategic questions that will be required for both the fund evaluation and to provide feedback to programme managers on routes to impact. The overarching evaluation methodology will be decided by the fund level evaluators and we will work to deliver the required coordination between the various contractors at programme level. If the programme is not selected for Fund level evaluation we will work with the programme level evaluation and learning contractor to develop an approach paper including a set of strategic questions that we will want to answer through the process. These questions may include fund level questions if appropriate. Evaluation will be conducted once the programme is into at least six months of implementation. In the absence of evaluation due to extended design phases, readiness review will be conducted by evaluation and learning contractor to assess the progress of the programme.
5. Monitoring and Reporting. Responsibility for data capture, baselining and reporting sits with programme managers and their implementers. Indicators will be agreed with the fund level monitoring and reporting contractor, the evaluators and the programme implementers. The monitoring and reporting contractor will identify the data requirements in terms of format and quality. We will work with our stakeholders to ensure that reporting is done in a timely and useful manner.
6. Logframes. Indicative logframes for each of the five strands can be found in Annex B. These were further developed during the design phase and will be reviewed and updated on an ongoing basis.
Adaptive and Flexible Programming
Adaptive programming is an approach being taken forward by DFID (new guidance developed with ODI has been released by DFID). This programme will adopt adaptive programming to ensure flexibility by building this into the structure of the main implementer contracts. Funds will not be deployed all at once but rather act as a facility over the period of the programme, allowing room for the programme adapt to changes in risk, context and priority. Contracts and implementer agreements will also be structured such that work can be scaled if necessary and is dependent on performance. The budgets for each strand are indicative and can be adjusted if necessary within the overall budget envelope in response to learnings and changing circumstances. A change management process will follow FCO change management process for the PF.

Risk Register
#	Risk description	Prob.	Impact	Mitigation strategy
1	Lack of correct GoI approvals for bigger programme could delay delivery and/or change scope	H	H	We are reviewing our approach and identifying ways internally to ensure we operate with right levels of Government of India approval.
2	Change in government or government policy post UK election could adversely impact the direction of the PF in India (e.g. new approach to India, to PF, to trade and investment).	L	H	Areas covered by the India PF reflect UK strengths and commercial opportunities, and are some of the key Indian asks of the UK. In a post-EU world, emerging economies like India will continue to remain important. We are in regular contact with SAAD, PFMO and PFDU so well-placed to respond to incoming government requests for information.
3	Timeframe for delivery compromises quality of delivery	M	M	Discussions underway in London for no-cost extension to the PF to cross into the next Spending Review year.
4	Strong consortia fail to form to deliver India PF programme strands	L	M	Early Market Engagement events have built a good level of interest with potential international and Indian delivery partners.
5	Corruption of third parties leads to misuse of public funds could affect reputation.	L	H	All funding to be channelled through trusted partners with sufficient financial capabilities. Appropriate due diligence will be undertaken for all partners. Rigorous monitoring of invoices and activities will occur throughout the programme duration. Funding will not be disbursed if there are any concerns about an organisation’s track record.
6	Legal and compliance issues around Official Development Assistance and International Development Act requirements could cause reputational damage and limited impact.	L	H	Testing ODA/ IDA compliance will be an explicit part of the annual review process, alongside ongoing challenge from the Advisory Board.
7	Lack of cooperation from state governments due to political or capacity constraints leads to reforms not being implemented and change being un-sustained	L	H	Programme and policy teams are continuously engaging with state agencies to ensure buy-in and will only work with States that respond positively and are prepared to commit their own resources where necessary. We are also working with DHCs on the role they can play and how they can support at local level.
8	Difficulties of Monitoring & Evaluation mean that outputs, outcomes and impacts are not adequately captured or tracked, leading to poor reporting, an inadequate feedback loop and reputational damage.	L	H	Rigorous implementation of the PF monitoring and evaluation framework, with a dedicated resource within the Prosperity Portfolio Team at Post.
9	Poor internal delivery and programme management leads to delays and ineffective programming	L	H	Mitigation by ensuring adequate resourcing and capacity building - strengthening an already experienced programme team. Follow on finance training for programme staff planned for May 2017. Ensuring senior managers prioritise PF work.
10	Post the UK's EU referendum, high ministerial expectations around secondary benefit could fall short due to a weak response from the private sector and investors, could result in reduced secondary benefits. / A programme-level approach to quantification of secondary benefits and attribution of impacts to the PF could become difficult.	M	M	There is greater collaboration across the India network and between departments to ensure the India programme delivers secondary benefits. A new cross-Mission approach to delivery is also driving more coordination and we are ensuring the PF is strongly aligned with commercial priorities/opportunities. Past PF projects continue to delivery commercial wins, and commercial contracts have already been secured through Yr. 1 projects. Continuous engagement with businesses and flexible design will allow us to adapt the programme if necessary. Working across a portfolio of sectors spreads the risk, reducing the impact in any one sector.
11	Changes in relevant Government of India priorities leads to reduced engagement and benefits of PF intervention not fully realised.	L	M	The likelihood of this is reduced by targeting sectors of high demand where there is cross-party consensus that reform is needed and also by building on previous work where political buy-in has already been secured. Programmes are being developed in close consultation with the relevant Ministries, ensuring that even if there are policy changes the interventions will still remain useful and valuable.
12	Complementary funding arriving late or not at all leads to delays and reduction in scope	L	M	Designing flexible programmes that can respond to changes in wider resources while maintaining impact. The new cross- Mission approach will ensure any changes are picked up and mitigated against early.
13	Limited interaction between the strands could lead to teams not spotting and exploiting some potential synergies	L	M	Encouraging and ensuring cross team working across the India network to deliver maximum benefits.

Communication Plan
The India PF Programme is a key element in delivering HMG objectives in India, in conjunction with other tools and resources at the India network’s disposal. Those objectives and specific outputs relating to them may be communicated as and when they are announced and realised. However, communications will generally refer to “UK government funding” rather than disaggregating between specific departments or funding vehicles. The OASIS framework will be followed when developing future communication and communication campaigns.
# Annex A: Economic Appraisal Details

Net Present Value summary table – central estimates
Primary benefits are discounted at 10%, while secondary benefits and costs are discounted at 3.5%.
NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total*
Primary (£m)	-1	-5.2	2.9	61	93	138	112	126	111	103	741
Secondary (£m)	-1	1.1	0.2	26	70	92	99	93	97	97	574

*Throughout the analysis stream of benefits might not sum to the total given due to rounding.
All benefits are expressed as expected benefits taking into account the probability of success as set out below. It should be noted that the probably of success would be significantly increased (with the exception of skills) by approximately 20% if the PF was extended to 2022.
Strand	Probability of success	Rationale
Ease of Doing Business	65%	A highly conservative probability of success is given to reflect the risk and challenges associated with achieving the scope, outcomes and spend of the programme within the current time-frame of the PF (March 2021).
Skills	70%	A highly conservative probability of success is given to reflect the risk and challenges associated with achieving the scope, outcomes and spend of the programme within the current time-frame of the PF (March 2021). However – this is slightly higher than other programmes given the Skills component represents a relatively small amount of the overall PF budget. This will be combined with DFID funding, which does not have the same time constraints as the PF and therefore we can stipulate that PF funding is front-loaded in the programme spend. In addition, DFID are delivering the Skills component, building on a pre-existing presence in the skills area.
Financial Services	65%	A highly conservative probability of success is given to reflect the risk and challenges associated with achieving the scope, outcomes and spend of the programme within the current time-frame of the PF (March 2023).
Entrepreneur-ship	65%	A highly conservative probability of success is given to reflect the risk and challenges associated with achieving the scope, outcomes and spend of the programme within the current time-frame of the PF (March 2021).
Energy	70%	A highly conservative probability of success is given to reflect the risk and challenges associated with achieving the scope, outcomes and spend of the programme within the current time-frame of the PF (March 2021. However – this is slightly higher than other programmes given the strong base from which the energy strand will be starting.
Urban	65%	A highly conservative probability of success is given to reflect the risk and challenges associated with achieving the scope, outcomes and spend of the programme within the current time-frame of the PF (March 2021).

Ease of Doing Business
The costs of the Ease of Doing Business programme are £9.2m, profiled over four years as outlined in the financial case above, plus a pro-rata element of the administrative costs and contingency of the overall programme. Taken together this gives a total discounted cost of £8.6m.
The benefits are calculated based on Eifert’s finding that countries which are relatively poor and relatively well governed (such as India) grow between 0.4 and 0.2 percentage points faster in the year immediately following business environment reforms[164]. Since Ease of Doing Business is a priority for the Government of India and the World Bank and other donors are active in this area, it is assumed that in the counterfactual case reform is ongoing and that incremental growth is 0.2% in the absence of PF activity, i.e. the lower bound of Eifert’s estimate. In the event of PF intervention, growth of 0.21 (i.e. additional growth of only 0.01%) is presumed in 2020/21 – 2022/23, which is the period when related reforms are likely to be enacted. A tapering increase of 0.005% is applied in the years either side of this period, to take account of both the previous work in this area that the intervention will leverage and also the likely persistence of intervention effects. Previous DFID programmes have used much larger additional growth estimates of 0.1%-0.3% under intervention scenarios[165] [166]. The rationale for using the much smaller figure of 0.01% in this case is that in the absence of clear evidence, a very conservative estimate is the safest bet.
[164] Eifert (2009), Do Regulatory Reforms Stimulate Investment and Growth? Evidence from the Doing Business Data, 2003-7
[165] DFID (2015), Business enabling environment programme, Ghana
[166] DFID (2012), Private sector development programme, Malawi
The Ease of Doing Business strand will operate in all the programme’s focus states, which together are likely to account for approximately 40% of India’s GDP. (This appraisal does not attempt to separately monetise the benefits from central reforms). However, despite Eifert’s findings, we have conservatively assumed that business environment benefits will only impact on half of this value i.e. 20%. Using the World Economic Outlook figures for October 2016 as a basis for India’s growth over the next ten years and applying the above methodology yields a primary expected benefit of £13.7bn over ten years in the counterfactual scenario and £14.0bn in the intervention scenario. After discounting, this leaves a difference of £170m and £110m after applying the probability of success, which is the additional discounted expected primary benefit in comparison with the counterfactual.
Research by IMRB estimates that UK companies have a combined revenue of over $54bn in India, equivalent to approximately 2% of India’s GDP[167]. Since the intervention will be focused in states where the UK has significant business interests, it is assumed that at least 2% of all business environment benefits will accrue to UK companies even in the counterfactual case. This proportion is assumed to be larger in the intervention case given that the programme will focus on constraints that affect UK businesses and will promote UK models of public administration. Consequently, the UK’s share of business environment reform benefits is assumed to increase to 3% in the three reform years (2020/21 – 2022/23) due to the increased UK influence over the relevant states’ Ease of Doing Business reforms. Furthermore, in recognition of the pro-UK agenda setting role of the programme, UK share of benefits is assumed to be 2.5% in the subsequent four years (2023/24 – 2026/27) and also in the year immediately before (2019/20), i.e. an increase of 0.5% in comparison with the counterfactual. This corresponds to a secondary benefit of £360m over ten years in the counterfactual scenario and £275m in the intervention scenario. After discounting, this leaves a difference of approximately £70m and £46m after applying the probability of success, which is the additional discounted expected secondary benefit in comparison with the counterfactual.
[167] CBI (2015), Sterling Assets India: UK investment creating jobs in India
The secondary benefits accrue both from the increase in the overall size of the pie (i.e. share of the additional primary benefits) and also from an increase in the UK share of that pie (i.e. greater UK share of overall primary benefits because UK interests are better reflected in overall business environment reforms). One way to sense check this figure is to compare it against UK exports to India, which are in the region of £10bn per year – approximately £100bn over ten years. An expected secondary benefit of just £46m over ten years therefore equates to just a 0.05% increase, which seems very plausible given the emphasis placed by international companies on India’s difficult business environment.
Primary sensitivity analysis: Vary proportion of economy affected by state reforms from a minimum of 10% to a maximum of 30%.
Secondary sensitivity analysis: As above as primary benefits feed directly through to secondary.
As with all such appraisals, there are uncertainties around the assumptions, which have been mitigated by taking conservative estimates and sense checking for plausibility. These reflect the most likely expected outcome, given programme risks and information uncertainties. The Ease of Doing Business programme is perhaps less risky than some others given the huge space and demand for support in this area from both the public and private sectors and the direct link from primary to secondary benefits. The most fundamental uncertainty centres around the extent to which the programme will result in growth promoting reforms. Sensitivity analysis has therefore been applied around the proportion of the Indian economy that will be affected, introducing a variance of 10% either side of the central 20% estimate.
The resulting net present values - i.e. discounted benefits minus discounted costs – are presented below.
Primary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.25	-1.1	18	40	41	42	21	0	0	0	160
Medium (£m)	-0.25	-1.1	11	26	28	28	14	0	0	0	105
Low (£m)	-0.25	-1.1	4	12	14	14	7	0	0	0	50

Secondary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.25	-1.1	3	10	12	13	7	6	7	7	64
Medium (£m)	-0.25	-1.1	0.86	6	8	9	5	4	5	5	41
Low (£m)	-0.25	-1.1	-0.88	2	4	4	2	2	2	3	18

Skills
The Skills strand will be delivered by DFID and the DFID Business Case should be used as the reference document for the skills component.
The costs of the Skills programme are £5.1m, profiled over four years as outlined in the financial case above, plus a pro-rata element of the administrative costs and contingency of the overall programme. Taken together this gives a total discounted cost of £4.7m.
The primary benefits of the skills programme are calculated based on the wage differential between skilled and non-skilled labour and the resulting additional income received by those benefiting from training as a direct result of the intervention. No attempt is made to quantify the induced multiplier resulting from this income effect, but it is reasonable to assume that this would also be positive. The intervention will be jointly funded by DFID (£8m) and the FCO (£5m), but as the case for each funding stream is partially contingent on the other, the counterfactual case is the absence of all funding.
By increasing training and accreditation capacity, the programme aims to improve the training outcomes for approximately 1m people over the next five years in specific sectors. (This figure is derived from estimating the number of additional trainers and assessors likely to be upskilled and therefore the number of learners likely to be immediately impacted). The counterfactual case assumes that the same 1m people would still be trained, but that the quality will be reduced in comparison with the counterfactual. This manifests itself in higher wages under the intervention case.
Wage differentials are estimated by using the National Rural Employment Guarantee Act wage rate in 2016 as a base, with conservative and premium work placement wages calculated respectively based on the average wage for skilled and semi-skilled labour in India[168] and the average manufacturing wage rate in India in 2014[169]. Inflation is applied at 5%. It is assumed that those successfully benefiting from the intervention will receive the premium wage if they find employment (starting at INR 364 per day), while in the counterfactual case those same learners will receive a lower wage lying midway between the conservative and premium rates (starting at INR 324 per day). We conservatively assume that only 50% of trainees find employment, even though the Government of India target is 70%. Each job is expected to last for five years. The average cost to the government or private sector of delivering advanced skills training is assumed to be 10,000INR per person in 2017/18, based on research undertaken for the British High Commission. Using the above methodology, it is estimated that primary benefits in the counterfactual case amount to approximately £930m, while in the intervention case they equate to approximately £1.26bn. The difference of approximately £330m is attributable to the whole intervention (DFID + FCO). After discounting, the PF portion of the jointly funded programme (5/13ths) accounts for a difference of £80m and £56m after applying the probability of success, which is the additional discounted expected primary benefit over the ten years in comparison to the counterfactual.
[168] http://www.simpliance.in/dashboard/minimum_wages
[169] www.tradingeconomics.com/india/wages-in-manufacturing
Secondary benefits are estimated by combining the following two benefit streams: i) UK institutions and training providers’ additional share of the skills market in India, and ii) the cost savings/productivity gains to UK firms operating in India resulting from an improved labour supply.
The available evidence, including research undertaken for the British High Commission, suggests that the UK’s current share of India’s skills market is negligible, but that in the short to medium term 1 - 1.5% is a reasonable target to aim for in the relevant sub-sectors. The same research suggests that the size of relevant skills market in the top ten UK focus sectors is approximately £9bn over the next five years. In the counterfactual case a 0.1% UK market share is assumed at the start of the period (equivalent to ‘negligible’) rising to 0.3% over ten years given the emphasis on skills that will continue even in the absence of the intervention, e.g. through work by UKIERI and the British Council. This equates to approximately £40m of secondary benefits in the counterfactual scenario. In the intervention scenario it is assumed that a 1.0% share is achieved after 5 years (2022/23) and that the 1.5% target is reached by the end of the appraisal period (2026/27). This results in a total of £140m commercial opportunities over ten years, £100m more than in the counterfactual case.
At the same time, UK companies are estimated to have approximately 691,000 employees in India[170] and account for 1 in 20 Indian jobs in the organised private sector[171]. It is therefore reasonable to assume that 5% of those people trained and employed directly as a result of the intervention will be employed by UK companies, given that the sectors and geographies will be targeted at UK demand. (This equates to 25,000 workers i.e. 5% of the 500,000 trainees that are expected to achieve employment). This is higher than the 3% that are assumed to be hired by UK firms in the counterfactual case, when sectors and geographies are less UK targeted. The productivity benefits of this improved labour supply can be estimated based on the fact that 67% of firms in India struggle to find workers that meet their requirements[172] and that the Society for Human Resources Management estimates that the cost of a bad hire to a firm is five times their annual salary, although this appraisal reduces this via a 30% deadweight factor in acknowledgement of the fact the UK firms are likely to be relatively sophisticated hirers. Using the above assumptions the counterfactual case yields a secondary benefit of approximately £37m, while the intervention case results in £68m, a difference of circa £30m over ten years.
[170] CBI (2015), Sterling Assets India: UK investment creating jobs in India
[171] Department for International Trade (2016), UK still Europe’s top investment destination, with help from India
[172] ICEF Monitor (2013), To upskill 500 million workers, India goes international
The combined difference across the two benefits streams of approximately £130m is attributable to the whole intervention (DFID + FCO). After discounting, the PF portion of the jointly funded programme (5/13ths) accounts for a difference of over £40m and £30m after applying the probability of success, which is the additional discounted expected secondary benefit over the ten years in comparison to the counterfactual.
Primary sensitivity analysis: Adjusting the number of learners affected from a minimum of 0.5m to a maximum of 1.5m.
Secondary sensitivity analysis: Adjusting the UK market share achieved by the end of the period to between 1.0% - 2.0%.
As with all such appraisals, there are uncertainties around the assumptions, which have been mitigated by using conservative estimates. These reflect the most likely expected outcome, given programme risks and information uncertainties. The most fundamental uncertainties centre around the number of people likely to be affected by the intervention and the market share that can be achieved by the UK by the end of the appraisal period. Sensitivity analysis has therefore been applied around the number of learners affected (between 0.5–1.5m people) and the UK’s market share (between 1 – 2%).
The resulting net present values - i.e. discounted benefits minus discounted costs – are presented below.
Primary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	0	2	4	9	17	17	14	11	6	0	80
Medium (£m)	0	1	2	6	12	11	10	7	4	0	52
Low (£m)	0	0.5	0.5	2	6	6	5	4	2	0	24

Secondary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	0	0.13	-0.6	0.6	4	5	6	6	7	7	35
Medium (£m)	0	0.11	-0.8	0.2	3	4	5	5	5	5	26
Low (£m)	0	0.09	-1	-0.5	2	2	2	2	3	3	12

Financial Services
The costs of the Finance programme (excluding the Entrepreneurship component) are £8m, profiled over six years as outlined in the financial case above, plus a pro-rata element of the administrative costs and contingency of the overall programme. Taken together this gives a total discounted cost of £7.5m.
A central objective of the finance programme is increasing the size of India’s capital markets, specifically the bond market, through both market reforms and supporting the raising of infrastructure investment. India’s corporate bond market is currently worth approximately $330bn, up from approximately $100bn six years ago[173]. This strong growth is expected to continue; we have taken 10% as a conservative baseline. It is assumed that the intervention will result in an additional increase of 0.1% in each year immediately following the three main intervention years (i.e. 2019/20, 2020/21 and 2021/22). This figure is used on the basis that, in the absence of additional information, 0.1% is conservative and plausible. However, since deploying the capital in India means it cannot be used elsewhere, a large displacement factor of 80% is applied.
[173] http://www.sebi.gov.in/cms/sebi_data/statistics/corporate_bonds/outstandingcorpdata.html
There is a small but growing body of literature linking economic growth to bond market development[174]. Most find a significant positive relationship, but few venture to quantify it. We have cautiously assumed a ratio of 1:1, even though the incremental capital-output ratio of most countries (including India) is greater than unity. A lag of one year has been applied for the effect on output. Based on these assumptions, the counterfactual case yields a primary benefit of £4.2075 trillion over ten years in the counterfactual case, compared with £4.2077 trillion in the intervention case. After discounting, this leaves a difference of £144m and £94m after applying the probability of success, which is the additional discounted expected primary benefit in comparison with the counterfactual.
[174] Kapingura & Makhetha-Kosi (2014), The causal relationship between the bond market development and the economic growth in Africa: a case study of South Africa
In terms of secondary benefit, again only macro level analysis has been attempted. This is not unreasonable, given that the industry is centrally regulated and the very high concentration of the industry within Mumbai, the financial capital. As noted above, it is estimated that UK companies have a combined revenue of over $54bn in India, which equates to approximately £43bn based on current exchange rates[175]. Since financial services accounts for approximately % of the Indian economy, in the absence of further information this appraisal conservatively assumes that financial services also account for 8% of UK business in India, i.e. £3.4bn[176]. This is in keeping with UKIBC’s estimate that financial and professional services together account for 26% of UK business in India[177]. Given the UK’s competitive advantage in this sector, it is assumed that the value of UK financial services business will increase in size by 1% over the appraisal period even in the counterfactual case, and by 2% in the intervention case. (An additional 1% increase seems reasonable, particularly given UK strength in this area). This results in a secondary benefit of £34.59bn over ten years in the counterfactual case, compared with £34.76bn in the intervention case. After discounting, this leaves a difference of £140m and £91m after applying the probability of success, which is the additional discounted expected secondary benefit in comparison with the counterfactual. By way of a sense check, DIT is targeting over £400m of financial services export wins in India over the next five years. Extrapolated over ten years this amounts to approximately £1bn. £91m is a significant (9%) but not implausible increase on this baseline, which covers only exports. Therefore, considering the increase actually covers both trade and investment, the scale is not unreasonable.
[175] CBI (2015), Sterling Assets India: UK investment creating jobs in India
[176] http://www.financialexpress.com/economy/how-to-make-india-a-financial-services-hub-stop-huge-amounts-flowing-as-fees-to-foreign-amcs/612540/
[177] UKIBC (2015), Report on British Business in India
Primary sensitivity analysis: Adjusting the displacement factor to a maximum of 90% and a minimum of 70%.
Secondary sensitivity analysis: Adjusting the additional growth in the value of the UK financial services market in India between 0.5% - 1.5%.
As with all such appraisals, there are uncertainties around the assumptions, which have been mitigated by adopting a conservative approach. The assumptions reflect our best estimate of the most likely expected outcome, given programme risks and information uncertainties. The Financial Services programme does not present a huge risk given the huge importance attached to the sector in India and the UK’s acknowledged competitive advantage. The most fundamental uncertainties centre on the extent to which the programme will boost financial market reform and the growth in capital markets and also the level of additional UK business that will result. Sensitivity analysis has therefore been applied around the displacement factor used to calculate the primary benefit (introducing a variance of 10% either side of the central 80% estimate) and around the additional UK financial services business growth (introducing a variance of 0.5% either side of the central 1% estimate).
The resulting net present values - i.e. discounted benefits minus discounted costs – are presented below.

Primary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.22	-1	-2	45	47	47	0	0	0	0	136
Medium (£m)	-0.22	-1	-2	30	31	31	0	0	0	0	89
Low (£m)	-0.22	-1	-2	14	16	16	0	0	0	0	42

Secondary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.22	1	4	8	14	17	20	23	24	25	135
Medium (£m)	-0.22	-1	2	5	10	11	13	14	15	16	86
Low (£m)	-0.22	-1	-0.2	2	6	8	9	9	8	8	49

Entrepreneurship as a component of the Financial Services Strand
The costs of the Entrepreneurship programme are £1.1m, profiled over four years as outlined in the financial case above, plus a pro-rata element of the administrative costs and contingency of the overall programme. Taken together this gives a total discounted cost of £1m.
The primary benefits of the entrepreneurship programme are calculated based on the additional growth expected to occur within SMEs that are supported versus those that are not. This is proxied by the expected outperformance of private equity funds versus public indexes, since companies that receive PE funding also tend to receive managed support. This outperformance is estimated at 6% in the near term, however PE companies will receive a much more comprehensive level of support than this intervention is able to offer[178]. Consequently, this appraisal uses a much more conservative 1% figure for the expected additional growth rate.
[178] International Finance Corporation (2013), The case for emerging market private equity
The support provided to each firm is expected to cost an average of £5000. This is double the cost of the current entrepreneurship programme run by DIT. £1.1m of support therefore corresponds to approximately 400 firms supported over the lifetime of the programme. The benefits of enterprise support are not instant and so it is assumed that the additional growth will not occur until two years after the support is received, and will last for two years. Since India SMEs have on average grown at a stable pace of 4.5% over the last five years, this is assumed to be the default while the growth rate in the intervention affected years is assumed to be 5.5%[179]. The starting turnover of each SME is assumed to be £62,500m. This is estimated using the approximate mid-point for the value of fixed assets according to the Indian definition of a small company (£250k) and applying India’s approximate prevailing capital-output ratio of 4[180]. To further justify the use of this ratio, according to the 2016/17 Annual Report of the Ministry of Micro, Small and Medium Enterprises[181] MSMEs accounted for 31% of India’s GDP in 2014/15 and in that year there were 51m MSMEs, which gives an approximate output per MSME of US$13000. In the same report the assets per enterprise can be estimated at US$4400 in that year, which gives a capital-output ratio of about 3. This means that the ratio used in these calculations is somewhat conservative. An additional 200 jobs are also expected to be created in India, based on conservative estimates of the number of jobs created by enterprise funding[182]. Based on the above methodology a primary benefit of £76m is expected in the counterfactual scenario, compared with £78m in the case of the intervention. After discounting, this leaves a difference of £1.5m and £0.94m after applying the probability of success, which is the additional discounted expected primary benefit in comparison with the counterfactual.
[179] Firstbiz (2014), The Indian SME Survey: Analysing Indian SME Perceptions Around Union Budget 2014-15
[180] IMF working paper (2015), Pressing the Indian growth accelerator: policy imperatives
[181] http://msme.gov.in/sites/default/files/MSME%20ANNUAL%20REPORT%202016-17%20ENGLISH.pdf
[182] Ministry of MSME, Govt. of India, Fourth All India Census of MSME 2006-2007
Based on past performance of DIT’s current entrepreneurship programme (Tech Rocketships), it is expected that one fifth of the firms supported will enter the UK market. Using the current UK Global Entrepreneur Programme as a benchmark, we expect each firm to create an average of one job per year upon entering the market in the short term[183]. The value of these jobs is assumed to be comparable to the UK average wage. However, some of these SMEs may have entered the UK anyway even without PF support and so it is assumed that 30% of the secondary benefit is deadweight and will occur anyway under the counterfactual scenario. This is equal to approximately £5m secondary benefit over ten years in the counterfactual case, in comparison with £18m in the intervention case. After discounting, this leaves a difference of approximately £11m and £7m after applying the probability of success, which is the additional discounted expected secondary benefit in comparison with the counterfactual. (The above assumptions mean that the job creation rate is much higher in the UK than it is in India. This is not unreasonable, because the firms that do successfully enter the UK market will by definition be the most successful of the firms supported.)
[183] https://www.gov.uk/government/publications/entrepreneurs-setting-up-in-the-uk/entrepreneurs-setting-up-in-the-uk
Primary sensitivity analysis: Varying the additional growth experienced by supported SMEs from 0.5-1.5%
Secondary sensitivity analysis: Vary the proportion of supported SMEs that enter the UK market from 5 – 35%.
As with all such appraisals, there are uncertainties around the assumptions, which have been mitigated by using conservative estimates. These reflect the most likely expected outcome, given programme risks and information uncertainties. The most fundamental uncertainties centre around the level of additional firm growth the will result from intervention support and the number of supported firms that will succeed in entering the UK market. Sensitivity analysis has therefore been applied around the expected additional growth rate (between 0.5 – 1.5%) and the proportion of firms entering the UK (between 5 – 35%). The latter in particular is difficult to quantify since entrepreneurship is by definition a high risk business and so a relatively larger range has been applied to this variable to reflect this extra uncertainty.
The resulting net present values - i.e. discounted benefits minus discounted costs – are presented below.
Primary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.03	-0.09	-0.30	-0.16	3	5	5	5	5	4	27
Medium (£m)	-0.03	-0.09	-0.30	-0.17	2	3	4	3	3	3	18
Low (£m)	-0.03	-0.09	-0.30	-0.18	1	2	2	2	2	2	9

Secondary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.03	-0.09	-0.24	0.07	0.7	1.2	1.7	2.2	2.7	3.2	11.5
Medium (£m)	-0.03	-0.09	-0.28	-0.06	0.4	0.7	1	1.3	1.6	1.8	6.3
Low (£m)	-0.03	-0.09	-0.31	-0.19	0.1	0.17	0.25	0.32	0.39	0.45	1.1

Energy & Low Carbon
The costs of the Energy & Low Carbon programme are £23m, profiled over four years as outlined in the financial case above, plus a pro-rata element of the administrative costs and contingency of the overall programme. Taken together this gives a total discounted cost of £21.3m.
The primary benefits are calculated based on monetising the benefits of the additional energy capacity that is expected to be installed in India as a result of the intervention. This is done by quantifying the additional energy produced and valuing it via the market price, using the current average domestic rate of INR 3.80 per kWh, since this rate is less affected by subsidies or taxes than the corresponding agricultural, industrial or commercial rates[184]. Inflation is not applied since all these tariffs are controlled.
[184] http://1.bp.blogspot.com/-8jVLyM9sfHA/VZPgXy3bmoI/AAAAAAAADfU/r4Dm_QQ1fD4/s1600/Electricity%2BTariffs%2BStatewise%2Bcomparison.png
It is assumed that every pound of technical assistance directly leverages approximately twenty-five pounds of additional energy infrastructure investment, as opposed to fifteen pounds in the case of urban infrastructure (for which we have some evidence – see urban section below). A higher leverage factor is assumed in the case of energy because the market is more developed and DFID India has found leveraging investment easier in practice. A further scaling factor of five is then applied to take account of indirect leveraging – the additional increase in wider energy investment associated with the improvement in the commercial environment and increased investor confidence resulting from the directly supported projects. A 1yr lag is assumed for direct leverage and a 3yr lag for indirect, meaning that the additional investment is spread over the first seven years.
The cost of an extra GW of installed capacity is assumed to be a standard £0.5bn for renewables. A two year lag is assumed for renewables investment to come on stream. This is based on reforms needed, 4 months of tendering process and 18 months of project commissioning timeline, as per standard clauses in the contracts offered by the Indian renewables development agencies.
An average 20% capacity factor is applied to renewables when calculating the energy produced, which is reasonable for India[185] (this assumption has been taken from the data used by the Government of India’s NITI Aayog in developing the India Energy Security Scenarios)[186]
[185] Central Electricity Regulatory Commission (2016), Petition No. SM/03/2016 (Suo-Motu) http://cercind.gov.in/2016/orders/sm_3.pdf
[186] http://indiaenergy.gov.in/iess/docs/Thermal-power-generation-documentation.pdf
A combined deadweight and displacement factor of 50% has been applied to take account of the reduced capital and labour that will be available as a result of the investments leveraged and any overestimate of the scale of additional investment, which increases to 70% towards the end of the period as the effect of the intervention starts to wane. The rationale for this is that the capital could be productively employed elsewhere in the economy, and on the second, making clear that it is the deadweight element that rises for the reason highlighted in yellow below would help avoid others having the same misreading that I did. The logic behind a rising deadweight is that the further you move beyond the actual intervention (e.g. ten years after as opposed to five years after) the more time and potential there is for other factors to contribute to the intended change. So attributing that change to the PF becomes less and less clear and almost certainly weaker. Altogether this yields an additional primary benefit of approximately £950m over ten years attributable to the intervention, which after discounting and applying the probability of success leaves an additional discounted expected primary benefit of £340m in comparison with no intervention.
Secondary benefit are calculated by triangulating i) estimates of the proportion of the additional investment that commercially benefits UK firms via operating revenues and financial investment returns (bottom up) and ii) estimates of overall improvement in overall UK market share (top down).
Research commissioned by the British High Commission has indicated that a 5% share is achievable for the UK within India’s clean energy market. Accordingly 5% of the additional investment equates to almost £150m. Comfortingly, this is almost identical to the findings of separate FCO research into the UK commercial (goods and services) gains achievable in a number of countries as a result of PF intervention in the low carbon sector. At the same time it is expected that £1bn of the additional investment will flow from UK based financial investors, given the UK’s expertise in green finance. This assumption has been made in view of the strong momentum currently in India on developing energy infrastructure and evidence from our past work through the PF.
- India has plans for over a trillion $ investment in energy infrastructure till 2030, out of which $200 bn is till the year 2022. The PF focus states account for over half of this planned investment. Our hope is that with targeted technical assistance, we will be able to trigger and accelerate this investment.
- The evidence on leverage achieved from technical assistance through PF has been mixed. Illustrative technical assistance projects focusing on policy reform (yielding indirect investments) and project development (resulting in direct investments) are below:
  - An investment of around £0.35m over 4 years through technical assistance for design and implementation of India’s Perform, Achieve and Trade scheme ( energy efficiency and trading policy) has resulted in direct investment by the industry of INR 140 crores ( £16 mn) and indirect investment of £2884m in PAT Cycle I. This is a direct investment multiplier of 45 and indirect investment multiplier of 8242.
  - A Technical Assistance project worth £0.1m to design a 1600 MW solar park in Indian state of Karnataka led to an investment of £750m for the solar projects. This is a multiplier of 7500.
Since 2016, a previous PF supported project, jointly with active lobbying by the UK Government, has already catalysed issuance of $1.2 bn worth Green/Masala Bonds at the London Stock exchange by Indian energy companies. This provides a strong basis to assume that £1 bn investment from the UK may be achievable. The programme has a strong focus on making it happen – through a dedicated output in the energy and low carbon strand on development of pipelines of investment opportunities by UK financial investors, and a complementary output focusing on match-making the investors and the investees. At the same time, we also recognise that the low hanging opportunities may be getting exhausted, so, a rather conservative figure of a £1 bn investment over 3 years has been assumed.
This increased in investment flows will result in increased fees and business for UK financial services firms involved in raising this capital, e.g. green bonds issued in London such as the National Thermal Power Corporation bond[187]. Evidence quantifying these benefits is slightly dated, but suggests that they will be driven by underwriting fees (3-4%) and professional and other direct fees (3-6%)[188]. This appraisal takes the midpoint, which is a combined total of 8%. (These figures do not account for jobs created in the UK as a result of this additional activity and any associated multiplier effects). This corresponds to additional benefits of approximately £100m. Taken together the bottom up estimate of additional goods and services benefits and UK financial/professional sector benefits comes to almost £250m over the seven year period of additional leveraged investment.
[187] http://www.lseg.com/sites/default/files/content/documents/20170105%20Masala%20Bonds%20Presentation_1.pdf
[188] Oxera (2006), The cost of raising capital: an international comparison. http://ec.europa.eu/economy_finance/events/2006/workshop271106/p6_luis_correia_da_silva_workshop_presentation_271106.pdf
From a macro perspective, research commissioned by the British High Commission estimates that the UK market share of India’s total energy and low carbon market could be worth between £15-30bn by 2022. Taking the lower figure as the baseline and extrapolating over ten years gives a counterfactual scenario of £31bn commercial benefits to the UK in the absence of any intervention. Adding the additional bottom up benefits to this baseline equates to an increase in value of between 0 – 2.5%, depending on the year, which is very plausible. By following this additional benefits envelope and extrapolating over the ten year period (peaking at an additional 2.5% in 2023/24 before reducing to 2%), secondary benefits in the intervention scenario are estimated at £31.5bn. After discounting and applying the probability of success leaves a difference of over £290m, which is the additional discounted expected secondary benefit in comparison with the counterfactual.
By way of a sense check, DIT is targeting almost £2bn in energy export wins in India over the next five years. Extrapolated over ten years this amounts to approximately £4bn. £290m is a significant (circa 7.25%) but not implausible increase on this baseline, which covers only exports. Therefore, considering the increase covers both trade and investment, the scale is not unreasonable.
Primary sensitivity analysis: Adjust the increase in deadweight/displacement applied over the appraisal period, from a minimum of 50% (i.e. no increase across the period) and a maximum of 90% (i.e. an increase of 40% across the period)
Secondary sensitivity analysis: Vary the peak additional increase in the value of the UK’s market share between 1.5-3.5%.
As with all such appraisals, there are uncertainties around the assumptions, which have been mitigated by adopting a conservative approach, triangulating both bottom up and macro approaches and sense checking for plausibility. The resulting assumptions reflect our best estimate of the most likely expected outcome, given programme risks and information uncertainties. The most fundamental uncertainties centre on the extent to which the programme will result in additional energy generated, and also the extent to which the value of the UK’s market share will increase as a result of the intervention. Sensitivity analysis has therefore been applied around the combined deadweight/displacement figure used to calculate the primary benefit (introducing a variance of 20% either side of the central 70% peak) and around the additional increase in the value of the UK’s market share (introducing a variance of 1% either side of the central 2.5% peak).
The resulting net present values - i.e. discounted benefits minus discounted costs – are presented below.
Primary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.5	-3.3	-4.8	-0.41	15	38	67	101	119	128	458
Medium (£m)	-0.5	-3.3	-4.8	-0.41	15	38	53	81	71	77	325
Low (£m)	-0.5	-3.3	-4.8	-0.41	15	38	53	60	48	26	230

Secondary NPV	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.5	4.3	11	29	46	57	70	62	64	62	404
Medium (£m)	-0.5	4.3	3	12	37	48	50	41	43	41	277
Low (£m)	-0.5	-3.3	3	12	18	29	30	21	21	21	150

Urban Development
The costs of the Urban Development programme are £13.7m, profiled over six years as outlined in the financial case above, plus a pro-rata element of the administrative costs and contingency of the overall programme. Taken together this gives a total discounted cost of £12.3m.
The primary benefits are calculated based on separately monetising the economic output and welfare benefits of additional infrastructure investment in India as a result of the intervention. Increased output is proxied by jobs created, which is calculated using a figure of 75 jobs per $1m of additional investment. (This is the midpoint of estimates in the literature which range from 40[189] to 110[190] jobs per $1m.) Welfare benefits are calculated using the IMF’s estimate for the welfare multiplier for public infrastructure of 0.8[191]. As the intervention will be jointly funded by DFID (£10m) and the FCO (£12.4m), it is assumed that the counterfactual case is a slightly smaller scale programme funded by DFID alone.
[189] DFID (2016): Sustainable urban economic development programme
[190] Paul Starkey, John Hine (2014), Poverty and sustainable transport: How transport affects poor people with policy implications for poverty reduction
[191] IMF working paper (2016): The welfare multiplier of public infrastructure investment
Review of current and previous DFID India urban interventions suggests that on average every pound of technical assistance directly leverages approximately fifteen pounds of infrastructure investment. It is assumed that for each year of technical assistance the related investment is spread over five years with a two year lag[192]. It is also assumed that the corresponding improvement in the commercial environment and increased investor confidence resulting from these directly supported projects will contribute to an indirect increase in the realisation of additional wider urban infrastructure. At least £200bn - £1trillion is expected to be spent over the next twenty years[193]. This appraisal takes £500bn as the most likely case and on that basis assumes that approximately £200bn will be spent over the ten year appraisal period. It is anticipated that this will follow a linear growth curve with investments starting relatively slowly, but significantly increasing from year 3 onwards. It is assumed that the full intervention (DFID+FCO) will indirectly support 0.5% of that investment over the next ten years, while the counterfactual intervention (DFID only) will support only 0.2%, both with a lag of 2 years. Together this corresponds to total (direct and indirect) supported investment of almost £1bn in the intervention scenario, as opposed to nearly £0.5bn under the counterfactual case. (In both cases, this represents a scaling factor of around 50, which is comparable with similar interventions).
[192] This is consistent with ADB estimates for the average project lifecycle (6 years), given that projects are likely to be supported for more than just one year.
[193] Ministry of Urban Development have estimated $250bn must be spent on just basic urban infrastructure over the next 20 years, while McKinsey estimated $1.2tr back in 2010 [McKinsey Global Institute (2010), India’s urban awakening: building inclusive cities, sustaining economic growth]
Using the methodology and assumptions above, the jobs expected to be created over the next ten years in the intervention scenario are assumed to last five years and are monetised via the conservative placement wage assumptions detailed in the skills economic appraisal above (starting at INR 285 per day with inflation at 5% per annum). Combined with the welfare benefits, for which an additional two year lag is assumed, it is estimated that the full intervention yields additional primary benefits of approximately £830m, in comparison with approximately £386m in the counterfactual case. After discounting, this leaves a difference of around £227m and £147m after applying the probability of success, which is the additional discounted expected primary benefit over ten years in comparison with the counterfactual.
Secondary benefits are calculated based on the likely UK commercial share of both the directly supported projects and the wider projected urban development market. Since the former will be chosen and structured to promote UK capability, it is assumed that 10% of the direct project opportunities will be captured by UK firms, as opposed to 5% in the counterfactual case of purely DFID funding. In the wider Indian urban market (assumed, as above, to equal approximately £200bn over the next ten years), UK penetration is currently low and is assumed to be just 1%. Given the focus on the urban sector, it is assumed that this will increase to 1.3% by 2023 even in the counterfactual case. PF intervention is assumed to further increase this to 1.5% by the end of the appraisal period (i.e. additional market share of 0.2%). This equates to around £2.5bn of secondary benefits over ten years in the intervention case, as compared to approximately £2.3bn in the counterfactual. After discounting, this leaves a difference of over £155m and £100m after applying the probability of success, which is the additional discounted expected secondary benefit in comparison with the counterfactual.
To sense check this, compare this figure against DIT’s export targets (which is nearly £1bn for infrastructure exports over the next five years). Extrapolating over ten years equates to approximately £2bn over ten years. £100m is a significant (circa 5%) but not implausible increase on this baseline, which covers only exports. Therefore, considering the increase covers both trade and investment, the scale is not unreasonable indeed £100m of additional value from a £12.4m investment over ten years seems quite conservative.
Primary sensitivity analysis: Varying the indirect leverage in the intervention case between 0.3% - 0.7%, i.e. additional indirect leverage of between 0.1% - 0.5% over the counterfactual.
Secondary sensitivity analysis: Varying the UK market share achieved by the intervention to between 1.4% - 1.6%, i.e. additional UK market share of between 0.1% - 0.3%.
As with all such appraisals, there are uncertainties around the assumptions, which have been mitigated by adopting a conservative approach and sense checking for plausibility. The resulting assumptions reflect our best estimate of the most likely expected outcome, given programme risks and information uncertainties. The most fundamental uncertainties centre on the extent to which the intervention will contribute to additional infrastructure investment and also the extent to which the value of the UK’s market share will increase as a result of the intervention. Sensitivity analysis has therefore been applied around the additional indirect leverage figure (between 0.1% - 0.5%) and the additional increase in the UK’s market share (between 0.1% – 0.3%).
The resulting net present values - i.e. discounted benefits minus discounted costs – are presented below.
Primary NPV	2017/18	2018/19		2019/20		2020/21		2021/22		2022/23		2023/24	2024/25	2025/26	2026/27	Total
High (£m)	-0.07	-0.4		-2.1		0.05		3.3		34		42	48	50	43	219
Medium (£m)	-0.07	-0.4		-2.1		-1		1.2		21		27	32	34	27	139
Low (£m)	-0.07	-0.4		-2.1		-2		-0.8		8		13	17	19	19	70

Secondary NPV	2017/18	2018/19	2019/20		2020/21		2021/22		2022/23		2023/24		2024/25	2025/26	2026/27	Total
High (£m)	-0.07	-0.4	-2.1		2.4		9		17		25		38	40	41	168
Medium (£m)	-0.07	-0.4	-2.1		-2.3		-1.5		6		13		25	26	27	93
Low (£m)	-0.07	-0.4	-2.1		-2.3		-1.5		6		7		14	14	14	48

Addendum:
A summary of the changes made to the central case of the economic appraisal in progressing from OBC to FBC is shown in the table below.
Summary of the March 2019 Changes to the Central Economic Appraisal	Budget	No. of years	10yr. NPV / Primary Benefits	10yr. NPV / Secondary Benefits	Benefits Cost Ratio / Primary Benefits	Benefits Cost Ratio / Secondary Benefits
OBC	£12.2m	4	£154m	£129m	13	11
FBC	£12.4m	6	£139m	£93m	12	8
% Change / (+ve = decrease; -ve = increase)	-2%	-50%	10%	29%	7%	25%

The main reason for the reduction in the primary benefits is the reprofiling of the programme, extending it from four to six years to accommodate a two year delay to the start of the FCO intervention. This delay results in a later than anticipated realisation of benefits which means that some of the benefits fall outside of the 10 year assessment period and are therefore not captured in the calculations. However, as the Primary Benefits NPV is still overwhelmingly positive, and the programme has not fundamentally changed, we have not redone the calculations to include an extended assessment period.
The secondary benefits are similarly delayed as it is assumed that the increase in UK market share of the investment is delayed to correspond with the delayed start to the intervention. This results in the realisation of some of the Secondary Benefits falling outside of the 10 year assessment period. However, as the Secondary Benefits NPV is still overwhelmingly positive, and the programme has not fundamentally changed, we have not redone the calculations to include an extended assessment period.
# Annex B: Indicative Logframes

Annex B1: Ease of Doing Business
Objectives	Success measures	Verification	Assumptions
IMPACT: / Inclusive economic growth and poverty reduction / Increased UK-India trade and investment	TBC	Government/multilateral data / Analyst reports
OUTCOMES: / Increased investment / Improved ease of doing business / Strengthened Policy and Regulatory Capacity / Economic, Trade and Financial reforms / UK firms see India as a better place to do business / UK and Indian firms find it easier to trade and invest bilaterally / UK consortia compete for more Indian business	Improvement in EoDB ranking. / Improvement in e-governance ranking / State level business environment indicator / Increase in number of UK firms and size of their operations in India / Improved UK plc perception of Indian business environment	Government/multilateral data / Analyst reports / DIT/UKIBC survey of UK business groups	Improvements in trade and business environment support private sector growth / Private sector, including UK firms, respond to opportunity / UK firms/consortia/joint ventures are competitive
OUTPUTS: / Better understanding of reforms required / Roadmap for a more streamlined tax system / Demonstration of improved public administration and e-governance systems / Specific policies and regulations improved / Regulators are more business friendly	GoI adopts UK best practice models / Reduction in dispute cases	Data gathering by implementer / DIT/UKIBC survey of UK business groups / Newspaper reports	Sustained focus on Ease of Doing Business agenda by Government of India / Successful centre-state coordination / Health dialogue between government and business
ACTIVITIES: / Regulation|Tax|Trade|e-governance / Consultation, advisory and planning services / Resource and toolkit provision / Training and capacity building / Delivery and implementation support	INPUTS:	COSTS:	Buy-in from central and state governments / Buy-in from HMG departments / Successful coordination and delivery of intervention

Annex B2: Skills
Objectives	Success measures	Verification	Assumptions
IMPACT: / Inclusive economic growth and poverty reduction / Increased UK-India trade and investment	% of GDP created by targeted sectors? / Increased productivity? / Increased UK-India trade and investment?	National statistics
OUTCOMES: / Increased investment in human capital / Greater innovation and knowledge transfer / Improved ease of doing business / UK firms see India as a better place to do business / UK and Indian firms find it easier to trade and invest bilaterally / UK consortia compete for more Indian business	1m people receiving improved training/assessment in target sectors / 250 SMEs supported to scale / £30m skills contracts opened up to British firms by 2022	Project management information / System, monitoring and evaluation framework / National Labour market information system (LMIS) / Trade association data	Innovation and knowledge transfer drive productivity and sustainability / Private sector, including UK firms, respond to opportunity / UK firms/consortia/joint ventures are competitive
OUTPUTS: / Increased skills training capacity / Promotion of international accreditation standards / Establishment of skills networks	Increase in vocational training capacity (4000 trainers?) / Number of UK accreditation /certification standards adopted (target!) / Number of UK-India skills partnerships	Project management information / System, monitoring and evaluation framework	Government commitment to Skilling India continues / Formal qualifications are valued in the market and therefore by the workforce / Support from relevant (UK) employers in India
ACTIVITIES: / Training of trainers and assessors / Curriculum development / Accreditation and skills delivery mechanisms / Brokering new UK-India joint ventures	INPUT:	COSTS:	Buy-in from central and state governments / Private sector, including UK firms, responds to opportunity / Demand from high potential Indian companies for UK enterprise support

Annex B3: Financial Services
Objectives	Success measures	Verification	Assumptions
IMPACT: / Inclusive economic growth through expanded and deepened financial sector that protects financial stability and consumer interest by developing suitable regulatory framework whilst unlocking new financing opportunities	Indian financial sector contribution to GDP increases from 5.7% in 2017 to 7% in 2023.	Government of India data. / International financial institution data (e.g. World Bank or IMF). / Private sector data (e.g. bank reports).	India continues its reform process thereby boosting growth. / Improvements in trade and business environment supports private sector growth. / Private sector, including UK firms, respond to opportunity
OUTCOMES: / Improved capacity and capability in the Indian financial services sector leading to, more efficient, effective and inclusive financial markets and products in India / Increased access and cheaper finance for Indian organisations to invest in infrastructure for sustainable and inclusive growth. / Increase in Indian and UK FinTech entrepreneurship partnerships, including collaboration to provide more and better jobs for women and disadvantaged communities within the sector. / Improved business environment in India for international firms, including UK firms and investors. / Additional trade and investment opportunities for international, including UK business and industry	The size of Indian capital markets – bond market to increase from £330bn to £500bn by 2023. / Support development of universal health care system in India and improve insurance coverage from 4% to 9% to 2023. / Increase the National Pension Scheme subscriber coverage from present 21-26m by 2023. / India moves up the World Bank Ease of Doing Business ‘Resolving Insolvency’ Rankings from 108 in 2019 to below 60 in 2020. / Support state and municipal bodies to raise over £500m from international capital markets. / Indian financial regulators adopt a regulatory sandbox to promote innovative businesses setting up in India, including international firms.	Indian, UK and World Bank statistics / Financial accounts of state infrastructure funds	GoI and financial regulator ambitions continue to be aligned with the UK offer. / UK continues to be world’s leading financial centre. / Sustained focus on Fintech by Government of India and regulators. / Dialogue between the UK Government, GOI and businesses. / UK continues to be the leading global FinTech centre. / UK continues to be world’s leading financial centre
OUTPUTS: / A programme strand that supports the development of India’s financial markets, drawing on International best practice, particularly from the UK. / A programme strand that supports Indian organisations, in raising finance for infrastructure. / A programme strand that supports the development of FinTech policy and entrepreneurship in India, including through the new UK-India FinTech Dialogue and FinTech Rocketship Awards.	Create a pipeline of over 100 Indian organisations, which could potentially raise international capital for infrastructure investment. / RBI introduces a regulatory sandbox that permits innovative international firms to test new products and services in India. / A new FinTech industry body is set up to promote the development of new innovations that support growth and jobs. / Support at least 15 Indian organisations, to develop finance plans, with a view to raising international capital for infrastructure investment	Government of India data. / Financial regulator and Government of India publications. / Data gathering by Service Delivery Partner	Political and economic conditions are favourable to investment / Capacity strengthening translates into enhanced action and leadership
ACTIVITIES: / Capacity Building of government, institutions and labour market. / Policy Reform of market regulations, frameworks and standards. / Market Development via demonstrating new technologies / commercial models and project / investor pipeline development; and / Partnership Coordination including commercial ventures.	INPUT:	COSTS:	Buy-in from central and state governments / Private sector, including UK firms, responds to opportunity / UK firms are able to offer products and services that meet the needs of the Indian market / Demand from high potential Indian FinTech SMEs for UK enterprise support

Annex B4: Energy & Low Carbon
Objectives	Success measures	Verification	Assumptions
IMPACT: / Primary: Energy supporting economic growth and poverty reduction in India / Secondary: Increased UK-India energy and low carbon trade and investment	Energy demand met through increased investment in cleaner energy supply in India (Absolute and % of cleaner energy in supply mix). / Increase in UK share of India’s energy and low carbon markets
OUTCOMES: / Primary / Energy market policy and regulatory reforms / Increased investment in energy infrastructure / improve investment environment / Secondary / UK firms see India as a better place to do business / UK and Indian firms find it easier to trade and invest bilaterally in the energy sector / UK businesses compete for more Indian business	Increased private investment in cleaner energy (£400-600m all sources) / Additional cleaner energy capacity related to PF support (0.8 GW) / Value of investments and trade contracts won by UK companies on energy and low carbon related to PF support (£80mn) / Number and value of UK investors and firms operating in Indian energy and low carbon sectors. (50% increase) / Greater low carbon ambition in India’s next INDC in 2020 (30% increase in renewables and reduction in carbon intensity)	Government/multilateral data / Analyst reports / DIT/UKIBC survey of UK business groups	Improvements in infrastructure support private sector growth / Innovation and knowledge transfer drive productivity and sustainability / Private sector, including UK firms, respond to opportunity / UK firms/consortia/joint ventures are competitive
OUTPUTS: / Catalysing Leadership and Policy Reforms / Evidence and roadmaps for energy policies that provide incentives for investment and deployment / Increased GoI appetite and institutional capacity for cleaner energy and low carbon policies / Piloting and incubation of cleaner and low carbon innovations/reforms to demonstrate viability / Development of Project pipelines and Partnerships / Development of improved business models and technologies to underpinning policies / Advocacy and engagement with business community to ensure viability / Pipeline of investible clean energy project / New partnerships between UK and Indian business / Incubations support / Proof-of-concept pilots for demonstrating viability / Green finance mobilisation / Developing eco-system for green finance market in India / Mobilising market players and green finance deals / Leveraging strengths of City of London for financing transactions	Number and scale of the policies intentionally transformed by PF support / Public and Private Green Leadership evident / Size and number of business opportunities created / No. and size of deals won by UK companies / Number of new India-UK business links attributable to the programme [10]	Project management information / System, monitoring and evaluation framework	Political and economic conditions are favourable to investment / Political will in India remains favourable to scaling up gas exploration and clean energy; / Capacity strengthening translates into enhanced political drive and leadership / Market reforms improve investment climate
ACTIVITIES: / Policy and regulatory advocacy and assistance / Promoting and developing green finance instruments / Technology support, incubation and piloting / Project development facility / Coordinating UK-India partnerships and JVs / Capacity development in key areas for reform and policy development / Low carbon policy leadership / G2G support for deals, building consortia and exposure of UK offer	INPUT: / UK: / knowledge / international network / convening power / brokering ability / relationships / technical assistance / - blended with inputs from partners matched to their expertise.	COSTS: £22m overall, sub-divided into: / Catalysing Leadership and Policy Reform – £8m / Projects and Partnerships Development Support - £12m / Green Finance Market mobilisation - £2m / Staff and admin	Central and state agencies are receptive and act on advice and support; / Private sector, including UK firms, responds to opportunity / UK firms are able to offer products and services that meet the needs of the Indian market

Annex B5: Urban Development
	Detail	Indicator	Source	Assumptions
India PF Overall Programme Objectives	Objective 1; Promote inclusive economic growth in India / Objective 2; Support poverty reduction including promoting the inclusion of women and disadvantaged communities. / Objective 3; Increased prosperity for both India and the UK.
Impact	Primary benefit: Improved urban infrastructure leads to reduction in urban poverty, inclusive economic growth and widely-shared prosperity. / Secondary benefit: Improved business environment leads to UK companies more willing to engage in Indian urban sector. / Greater pipeline of investible projects results in increased potential for UK exports to India	Quality of overall infrastructure. / Gender Equality Gap Index / Engagement levels of UK (and international) companies in India’s urban sector. / UK (and international) exports to India’s urban sector. / UK (and international) investment in India’s urban sector.	World Economic Forum / GoI/States/Cities / Primary Service Delivery Partner / DIT/UKIBC survey of UK business groups	Inclusive economic growth leads to poverty reduction. / If business environment improves, UK companies will be more willing (or have the capacity) to engage with Indian urban sector.
Outcome	Outcome 1: States where TA is being delivered undergo a transformational change in the way in which they plan, develop and deliver urban infrastructure which supports inclusive growth and poverty reduction, acting as exemplars for other states in India.	1. In each state receiving TA, the number of policy reforms that are adopted and implemented to recognised international standards before 2023, overcoming barriers to high-quality urban interventions, such as in the fields of procurement, financing, project design, contract management etc. / 2. The number of times reforms achieved (see indicator 1 above) are recognised, replicated and used on high-value projects (c. £100m) before 2023 outside the footprint of this programme, anywhere in India.	GoI/States/Cities / Primary Service Delivery Partner / Programme Steering Board	GOI/State/City/ULB Buy in / Sufficient barriers are identified and overcome / Stable political and economic conditions
	Outcome 2: Relevant Indian Urban Stakeholders are better skilled in the delivery of urban interventions to international standards that promote quality infrastructure interventions, inclusivity, sustainability and widely-shared prosperity.	1. Number of relevant urban stakeholders indirectly upskilled before 2023 through a train-the-trainer programme in order to addresses capacity gaps that prevent the delivery of high quality urban interventions. / 2. Of those officers directly trained (including as trainers) by this programme, in March 2023 the percentage still using their new skills/knowledge in relevant public sector urban development roles. / 3. Before March 2023, the number of high-value (c. £100m) urban development projects (outside the footprint of this programme) that directly benefit from the newly-acquired expertise of those officers both directly and indirectly trained though this TA.	GoI/ States/ Cities / Officials identified for training / Primary Service Delivery Partner / Programme Steering Board	GOI/ State/ City/ ULB buy in / Gap in key skills can be readily identified. / Officials can be released for training / Individuals are willing to be trained. / Mechanisms to retain skilled staff in relevant roles can be identified and implemented.
	Outcome 3: India demonstrates improved collaboration between urban actors; adopts new long-term tools for learning lessons (both domestic and international) in inclusive and sustainable urbanisation; and adopts new innovative solutions to urban challenges.	1. The number of innovation interventions implemented (e.g. national innovation network, research partnerships, economic partnerships; city-city partnerships; innovation hub/spokes etc.) To respond to GoI demand and blend seamlessly with existing/proposed innovation initiatives.	Stakeholders identified for innovation partnerships / GoI/States/Cities / Primary Service Delivery Partner / Programme Steering Board	GOI/State/City/ULB Buy in Continued demand from GOI for innovation interventions. / Innovations interventions can be identified that deliver desired outcomes.
	Outcome 4. Improved business environment in the urban sector in India for international (including UK) firms and investors.	1. By 2023, the percentage increase in the number of bids received from International (including UK) companies/consortia for high-value (c.£100m) urban interventions that champion good practice in gender equality, women’s economic empowerment and inclusive growth in India. To be baselined at programme start. / 2. By 2023, the percentage increase in the number of international (including UK) companies declaring their interest in and/or intention to invest in the Indian urban sector.	Survey of market / Survey of industry / Government of India data / DIT/UKIBC survey of UK business groups	Policy reforms, capacity development, exemplar projects and innovation/collaboration outputs will reduce barriers to international firms’ willingness to engage in the Indian urban sector. / International industry will have the capacity to engage in the urban sector.
	Outcome 5. Additional commercial opportunities for international, (including UK) companies in the Indian urban sector.	1. By 2023, the percentage increase in the number of high-value (c. £100m), high-quality (to international standards) opportunities released to the market, of which at least 7% is accessible to international and UK companies.	Government of India data / DIT/UKIBC survey of UK business groups / Industry Data	Demand for international investment in the Indian urban sector remains. / UK and international companies have capacity.
Indicative Outputs (exact outputs will be dependent on need of projects selected in design phase)	Output 1 Invitations to Tender are brought to the market for a minimum of five high-value (total min £500m) urban interventions that promote inclusive economic growth and poverty reduction, having overcome barriers to investment and having instituted transformational change in cities’ and states’ policies and processes relevant to urbanisation, acting as exemplars for others.	1. Number of Invitations to Tender (ITTs) that are issued to the market that are of such a quality that: / Their ultimate outcome/impact is calculated as improving the lives of minimum 500,000 urban citizens (total) within the first 2 years of project completion with a focus on driving inclusive economic growth and sustainability. / They present a total of min £500m commercial opportunities of which minimum £35m is accessible to international (including UK) companies. / 2. Number of ITTs that receive a minimum of 3 high-quality bids from high calibre bidders / 3. Number of ITTs that receive at least 2 bids from international or UK companies each of which have a minimum target of securing at least 7% of the total commercial opportunity.	Potential ITT bidders / Programme Steering Board / UK and international industry / GoI engagement and feedback	Sufficient suitable projects for development exist / Availability of finance / Industry will have capacity/volition to engage when barriers are removed / Buy-in from GoI, States and Cities
	Output 2 Relevant officials are upskilled to directly address capacity gaps that prevent the delivery of quality urban interventions and skills (e.g. financing, strategic leadership, contract management, procurement, evidence-based policy reform, securing environmental clearances, land acquisition issues, etc.) Skills are embedded in institutions (including through institutional reform and a train-the-trainer programme) beyond the footprint of this programme to ensure sustainability.	1. Number of officials directly upskilled before 2023 to address capacity gaps that prevent the delivery of high quality urban interventions. To include “train-the-trainer” component. / 2. Number of skilled roles that are identified within key urban institutions/bodies/GOI for which appropriate replicable solutions are found (e.g. skills stipend) and instituted to mitigate risk of skilled/trained individuals leaving. / 3. In support of Output 1, the number of policy reform initiatives that directly benefit from the skilled input of individuals who are newly trained under capacity development programme. / 4. The number of ITTs developed under Output 1 that directly benefit from the skilled input of individuals who are newly trained under the capacity development programme.	GoI/States/Cities / Primary Service Delivery Partner / Programme Steering Board / Upskilled officials	Suitable candidates can be identified for training. / Buy-in of their employers. / Methods can be found to mitigate risk of skilled individuals leaving.
	Output 3 Major innovation partnerships established in response to the prevailing requirements of the Government of India that foster improved collaboration between urban actors; disseminate lessons from both domestic and international experience in inclusive and sustainable urbanisation; and improve India’s access to the best solutions available to urban challenges.	1. Number of innovation partnerships (e.g. national innovation hubs/network, online platforms, large city partnerships etc.) established in response to the prevailing requirements of the Government of India that foster improved collaboration between urban actors; disseminate lessons from both domestic and international experience in inclusive and sustainable urbanisation; and improve India’s access to the best solutions available to urban challenges. / 2. Before 2023, the number of new urban interventions (outside the footprint of this programme) that directly benefit from information / knowledge / techniques / partnerships newly-acquired by GOI/States/Cities etc. / 3. The number of ITTs developed under Output 1 that directly benefit from GOI’s/states’/cities’ newly-acquired information / knowledge / techniques / partnerships.	GoI/ States/ Cities / Primary Service Delivery Partner / Programme Steering Board / Potential partnership stakeholders	Suitable collaboration/ innovation/ sharing of best practice interventions can be identified that meet the requirements and ambition of GOI. / Suitable partners can be found for institutional partnerships.
Activities	Project design and development, including securing access to finance and gaining relevant approvals (e.g. environmental, land acquisition etc.) prior to issuance of ITTs. / Policy engagement and reform / Capacity development / Improving collaboration and innovation through sharing of best practice	Number of policy consultations/workshops etc. held. / Number of capacity building workshops/train-the-trainer sessions etc. held. / Number of missions to the UK (or elsewhere) that showcase best practice and build institutional relationships.	GoI/ States/ Cities / Primary Service Delivery Partner / Programme Steering Board	Buy-in from GOI/states/cities / PSDP successfully plans, coordinates and delivers activities to time.
Input	£9.5-10.5m PF funding and HMG staff expertise (programme-funded and from core staff of relevant departments).

The document has been updated for external sharing and commercially sensitive information has been removed. Some sections of the document have been updated in line with the design recommendations and post commercial review.