## Cover
Building Safety Programme Data Release, England: 31 May 2023
Back to Contents
Background
This publication provides data on the remediation progress of high-rise (18 metres or more) residential buildings identified with unsafe Aluminium Composite Material (ACM) cladding systems and buildings with unsafe non-ACM cladding systems that are pursuing successful applications from their Building Safety Fund (BSF) Registration. This publication includes data on the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund. It also includes data on building safety enforcement action undertaken by Local Authorities in England. All data is as at 31 May 2023.
All BSF and ACM tables include buildings with both ACM cladding and non-ACM cladding and therefore combining these figures may result in double counting. Tab Combined_1 provides an overall summary of both remediation schemes without double counting.
Publication dates
The data tables in this spreadsheet were originally published at 9.30am 15 June 2023.
The next publication is scheduled for 20 July 2023.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
BuildingSafetyData2@levellingup.gov.uk
NewsDesk@levellingup.gov.uk
Date published: 15 June 2023

## Table_of_Contents
Building Safety Programme Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 May 2023
ACM_2	Remediation status of vacant buildings yet to complete ACM remediation by tenure, England, 31 May 2023
ACM_3	ACM remediation progress by local authority, England, 31 May 2023
ACM_4	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 May 2023
ACM_5	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 May 2023
ACM_6	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status
ACM_7	ACM remediation progress by sources of funding, England, 31 May 2023
ACM_8	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 May 2023
ACM_9	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 May 2023
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 May 2023
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 May 2023
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 May 2023
BSF_1	Remediation status of buildings within BSF by tenure, 31 May 2023
BSF_2	BSF remediation progress by region, England, 31 May 2023
BSF_3	BSF number of buildings by tenure and funding allocation type, England, 31 May 2023
BSF_4	BSF funding approved and expenditure by tenure, England, 31 May 2023
Combined_1	Remediation progress for buildings with unsafe ACM and non-ACM cladding, England, 31 May 2023
Enforcement_1	Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 31 May 2023
Enforcement_2	Building inspections conducted by local authorities, England, 31 May 2023
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 31 May 2023
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 31 May 2023

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1.	ACM_2
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_3, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to fully complete remediation works, including those that have completed works but are awaiting sign-off from building control where necessary.	ACM_6
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_7
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period.	ACM_7
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_9
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_9
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_9
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_9
[note 10]	Total figures may not sum due to rounding.	WWRF_1, WWRF_2, WWRF_3, BSF_3, BSF_4
[note 11]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2
[note 12]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_4
[note 13]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1
[note 14]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 15]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 16]	The Government-funded Joint inspection Team, hosted by the Local Government Association, provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4

## ACM_1
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	120	75%	160	69%	50	86%	23	74%	7	88%	360	73%
Works complete awaiting building control signoff	18	11%	28	12%	3	5%	3	10%	0	0%	52	11%
Remediation started - cladding removed	21	13%	15	6%	1	2%	1	3%	0	0%	38	8%
Remediation started	1	1%	12	5%	1	2%	3	10%	1	13%	18	4%
Remediation plans in place	0	0%	13	6%	1	2%	0	0%	0	0%	14	3%
Reported an intent to remediate	0	0%	4	2%	2	3%	1	3%	0	0%	7	1%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	160	100%	233	100%	58	100%	31	100%	8	100%	490	100%

## ACM_2
Remediation status of vacant buildings yet to complete ACM remediation by tenure, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	0	2	1	0	0
Remediation started - cladding removed	0	2	0	0	0
Remediation started	0	2	0	0	0
Remediation plans in place	0	1	0	0	0
Reported an intent to remediate	0	0	0	1	0
Remediation plan unclear	0	0	0	0	0
Total vacant buildings [note 1]	0	7	1	1	0

## ACM_3
ACM remediation progress by local authority, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	1 to 5	Between 50% and 99%	100%
Barnet	6 to 10	1 to 5	Less than 50%	Between 50% and 99%
Bedford	1 to 5	None	100%	100%
Birmingham	1 to 5	None	100%	100%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Less than 50%	100%
Bradford	1 to 5	1 to 5	Less than 50%	100%
Brent	11 to 20	11 to 20	Less than 50%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	1 to 5	Less than 50%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	100%
Hackney	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Hammersmith and Fulham	6 to 10	1 to 5	Between 50% and 99%	100%
Haringey	6 to 10	1 to 5	Between 50% and 99%	100%
Harrow	1 to 5	1 to 5	Between 50% and 99%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	None	100%	100%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	1 to 5	Less than 50%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	100%
Leeds	6 to 10	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	6 to 10	Between 50% and 99%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	1 to 5	Less than 50%	100%
Newcastle upon Tyne	6 to 10	None	100%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	100%
Norwich	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Nottingham	6 to 10	1 to 5	Between 50% and 99%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Reading	1 to 5	1 to 5	Between 50% and 99%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	11 to 20	Between 50% and 99%	100%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Slough	1 to 5	1 to 5	Between 50% and 99%	100%
Southwark	11 to 20	6 to 10	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	1 to 5	None	100%	100%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	11 to 20	Between 50% and 99%	Between 50% and 99%
Trafford	1 to 5	1 to 5	Less than 50%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_4
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 May 2023
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Greater Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	33	70%	7	39%	5	100%	1	50%	0	0%	46	64%
Works complete awaiting building control signoff	5	11%	6	33%	0	0%	0	0%	0	0%	11	15%
Remediation started - cladding removed	9	19%	3	17%	0	0%	1	50%	0	0%	13	18%
Remediation started	0	0%	2	11%	0	0%	0	0%	0	0%	2	3%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	18	100%	5	100%	2	100%	0	0%	72	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	55	68%	120	74%	9	69%	11	73%	0	0%	195	72%
Works complete awaiting building control signoff	13	16%	10	6%	2	15%	2	13%	0	0%	27	10%
Remediation started - cladding removed	12	15%	9	6%	0	0%	0	0%	0	0%	21	8%
Remediation started	1	1%	8	5%	1	8%	2	13%	1	100%	13	5%
Plans in place	0	0%	12	7%	1	8%	0	0%	0	0%	13	5%
Responded with intent	0	0%	2	1%	0	0%	0	0%	0	0%	2	1%
Remediation plan unclear	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Total buildings	81	100%	162	100%	13	100%	15	100%	1	100%	272	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	100%	33	62%	36	90%	11	79%	7	100%	119	82%
Works complete awaiting building control signoff	0	0%	12	23%	1	3%	1	7%	0	0%	14	10%
Remediation started - cladding removed	0	0%	3	6%	1	3%	0	0%	0	0%	4	3%
Remediation started	0	0%	2	4%	0	0%	1	7%	0	0%	3	2%
Plans in place	0	0%	1	2%	0	0%	0	0%	0	0%	1	1%
Responded with intent	0	0%	2	4%	2	5%	1	7%	0	0%	5	3%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	32	100%	53	100%	40	100%	14	100%	7	100%	146	100%

## ACM_5
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 May 2023
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	118	77%	143	76%	49	94%	22	81%	7	88%	339	79%
Works complete awaiting building control signoff	17	11%	21	11%	2	4%	2	7%	0	0%	42	10%
Remediation started - cladding removed	19	12%	12	6%	1	2%	1	4%	0	0%	33	8%
Remediation started	0	0%	7	4%	0	0%	1	4%	1	13%	9	2%
Plans in place	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Responded with intent	0	0%	0	0%	0	0%	1	4%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	187	100%	52	100%	27	100%	8	100%	428	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	119	76%	157	74%	50	93%	22	76%	7	88%	355	77%
Works complete awaiting building control signoff	18	12%	24	11%	3	6%	3	10%	0	0%	48	10%
Remediation started - cladding removed	19	12%	13	6%	1	2%	1	3%	0	0%	34	7%
Remediation started	0	0%	11	5%	0	0%	2	7%	1	13%	14	3%
Plans in place	0	0%	6	3%	0	0%	0	0%	0	0%	6	1%
Responded with intent	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	120	75%	159	70%	50	89%	23	74%	7	88%	359	75%
Works complete awaiting building control signoff	18	11%	26	12%	3	5%	3	10%	0	0%	50	10%
Remediation started - cladding removed	21	13%	15	7%	1	2%	1	3%	0	0%	38	8%
Remediation started	1	1%	11	5%	1	2%	3	10%	1	13%	17	4%
Plans in place	0	0%	11	5%	1	2%	0	0%	0	0%	12	2%
Responded with intent	0	0%	4	2%	0	0%	1	3%	0	0%	5	1%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	120	75%	160	69%	50	86%	23	74%	7	88%	360	73%
Works complete awaiting building control signoff	18	11%	28	12%	3	5%	3	10%	0	0%	52	11%
Remediation started - cladding removed	21	13%	15	6%	1	2%	1	3%	0	0%	38	8%
Remediation started	1	1%	12	5%	1	2%	3	10%	1	13%	18	4%
Plans in place	0	0%	13	6%	1	2%	0	0%	0	0%	14	3%
Responded with intent	0	0%	4	2%	2	3%	1	3%	0	0%	7	1%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	160	100%	233	100%	58	100%	31	100%	8	100%	490	100%

## ACM_6
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, 31 May 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	9,100	12,300	14,800	21,400	23,900
Yet to complete remediation [note_3]	2,700	6,700	7,600	9,400	10,300
Occupied and yet to complete remediation	2,700	6,100	7,100	8,800	9,800

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	2,500	12,300	14,800	14,800	17,300
Yet to complete remediation [note_3]	800	6,700	7,600	7,500	8,400
Occupied and yet to complete remediation	800	6,100	7,100	6,900	7,900

## ACM_7
ACM remediation progress by sources of funding, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note_4]	Not in social fund	Private: government funded / [note_5]	Private: not government funded
Remediation completed	113	7	61	99
Works complete awaiting building control signoff	18	0	20	8
Remediation started - cladding removed	11	10	12	3
Remediation started	1	0	8	4
Plans in place	0	0	11	2
Responded with intent	0	0	4	0
Remediation plan unclear	0	0	0	1
Total	143	17	116	117

## ACM_8
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	7	0
Applications approved: for pre-contract support	0	1
Full cost application submitted	0	0
Applications approved: for full costs	65	39
TOTAL	72	40

## ACM_9
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 May 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	292	228
Expenditure [note_8, note_9]	268	237

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 May 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	169	104	286
Waking Watch Replacement Fund	38	67	25	47	2,200	2.4	216	210	33
Total [note_10]	367	535	237	367	26,900	29.7	172	106	319

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 May 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Buildings	Approved Buildings	Approved Funding / (£ million)
Birmingham	9	8	1	0	0	9	8	1.6
Bristol	3	2	0	0	1	3	2	0.1
Greater London Authority	110	65	29	16	0	171	111	8.3
Greater Manchester Combined Authority	25	20	5	0	0	38	33	2.5
Leeds	10	9	0	1	0	12	11	1.8
Liverpool	18	17	1	0	0	19	18	1.7
Newcastle	3	3	0	0	0	3	3	0.4
Sheffield	6	5	0	1	0	7	6	0.5
DLUHC (1st tranche)	35	21	14	0	0	55	39	2.7
DLUHC (2nd tranche)	60	27	32	1	0	70	34	3.8
DLUHC (3rd tranche)	50	35	14	1	0	81	55	3.9
Total [note_10]	329	212	96	20	1	468	320	27.3

## WWRF_3
Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 May 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Buildings	Approved Buildings	Approved Funding (£m)
Birmingham	2	2	0	0	0	4	4	0.4
DLUHC	25	21	1	3	0	46	40	1.8
Greater Manchester Combined Authority	11	2	9	0	0	17	3	0.2
Leeds	0	0	0	0	0	0	0	0
Liverpool	0	0	0	0	0	0	0	0
Sheffield	0	0	0	0	0	0	0	0
Total [note_10]	38	25	10	3	0	67	47	2.4

## BSF_1
Remediation status of buildings within BSF by tenure, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	17	10%	20	2%
Remediation complete: awaiting building control sign-off	6	4%	101	10%
Remediation started	69	42%	194	18%
Remediation not yet started	73	44%	745	70%
Total buildings	165	100%	1060	100%

## BSF_2
BSF remediation progress by region, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region	Eligible Buildings in the BSF / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation [note_11] / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	170	109	35	26	15%	36%
London	726	501	157	68	9%	31%
East of England	45	31	7	7	16%	31%
East Midlands	26	17	7	2	8%	35%
North East	15	12	1	2	13%	20%
South East	91	46	25	20	22%	49%
South West	49	41	7	1	2%	16%
West Midlands	32	24	6	2	6%	25%
Yorkshire and The Humber	71	37	18	16	23%	48%
Total	1,225	818	263	144	12%	33%

## BSF_3
BSF number of buildings by tenure and funding allocation type, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells in this table are empty because data was not available for these variables.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Funding Allocation [note_10]	Private Sector Residential / Number	Social Sector Residential / Number	Total
Full Applications Approved	386		386
Pre-Tender Support Allocations	569		569
Total	955	100	1,055

## BSF_4
BSF funding approved and expenditure by tenure, England, 31 May 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data was not available for these variables.
Table BSF_4a: Amount of funding allocated by funding type and tenure for buildings eligible for the BSF.
Funding Allocations [note_10], [note_12]	Private Sector Residential / (£ millions)	Social Sector Residential / (£ millions)	Total / (£ millions)
Full Applications Approved	1,485
Pre-Tender Support Allocations	235
Total	1,720	195	1,915

Table BSF_4b: Amount of expenditure from the BSF by tenure.
Expenditure [note_10]	Private Sector Residential / (£ millions)	Social Sector Residential / (£ millions)	Total / (£ millions)
Expenditure	891	123	1,014

## Combined_1
Remediation progress for buildings with unsafe ACM and non-ACM cladding, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	312	78%	26	2%	9	10%	347	21%
Works complete awaiting building control signoff	43	11%	91	8%	18	20%	152	9%
Remediation started	32	8%	233	21%	54	59%	319	20%
Remediation not started	12	3%	784	69%	10	11%	805	50%
Total	399	100%	1,134	100%	91	100%	1,624	100%

## Enforcement_1
Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note_14].
Local Authority [note_2]	BSF only (non-ACM cladding only) / Number	ACM cladding only / Number	BSF (non-ACM) and ACM cladding / Number	Not in any remediation fund (non-ACM cladding only) / Number	Total / Number
Barking and Dagenham	0	0	0	0	0
Barnet	1	3	1	2	7
Birmingham	1	0	0	0	1
Bournemouth, Christchurch and Poole	2	2	0	1	5
Bradford	0	1	0	0	1
Brent	0	2	0	0	2
Brighton and Hove	0	0	0	0	0
Bristol, City of	0	1	0	0	1
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	15	1	0	18	34
City of London	0	0	0	0	0
Croydon	1	0	1	0	2
Dacorum	0	0	0	0	0
Ealing	2	1	1	0	4
Gateshead	0	0	0	0	0
Greenwich	3	0	0	0	3
Hackney	2	3	0	2	7
Hammersmith and Fulham	1	0	0	3	4
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	3	0	0	1	4
Hounslow	0	0	0	1	1
Ipswich	0	0	0	0	0
Islington	0	0	0	0	0
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	2	2	0	0	4
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	1	3	2	1	7
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	0	1	0	0	1
Merton	0	0	0	0	0
Milton Keynes	0	0	0	0	0
Newcastle upon Tyne	4	0	0	3	7
Newham	6	1	1	2	10
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	0	1	0	1	2
Plymouth	1	0	0	0	1
Portsmouth	0	1	0	1	2
Reading	0	0	0	0	0
Redbridge	1	0	0	0	1
Salford	1	0	0	0	1
Sheffield	0	0	0	0	0
Slough	0	0	0	0	0
Southampton	0	0	0	0	0
Southwark	13	4	2	7	26
Sunderland	0	0	0	0	0
Sutton	0	0	1	0	1
Thanet	0	0	0	0	0
Tower Hamlets	2	1	4	0	7
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	0	1
Wandsworth	1	2	1	0	4
Westminster	31	5	5	3	44
Windsor and Maidenhead	0	0	0	0	0
Others	13	0	2	10	25
Total	108	35	21	56	220

## Enforcement_2
Building inspections conducted by local authorities, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note_2]	Inspections with the building rated Category 1 [note_15] / Number	Inspections with the building rated Category 2 [note_15] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	0	0	0	0
Barnet	4	3	0	7
Birmingham	0	0	1	1
Bournemouth, Christchurch and Poole	5	0	0	5
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	1	0	1
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	0	33	1	34
City of London	0	0	0	0
Croydon	0	1	1	2
Dacorum	0	0	0	0
Ealing	1	3	0	4
Gateshead	0	0	0	0
Greenwich	2	0	1	3
Hackney	5	2	0	7
Hammersmith and Fulham	0	3	1	4
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	1	3	0	4
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	0	0
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	3	4	0	7
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	0	7	0	7
Newham	3	4	3	10
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	0	2	0	2
Plymouth	1	0	0	1
Portsmouth	1	0	1	2
Reading	0	0	0	0
Redbridge	0	1	0	1
Salford	0	1	0	1
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	0	0	0	0
Southwark	10	15	1	26
Sunderland	0	0	0	0
Sutton	1	1	0	2
Thanet	0	0	0	0
Tower Hamlets	0	5	1	6
Trafford	0	0	0	0
Waltham Forest	0	0	1	1
Wandsworth	1	2	1	4
Westminster	5	39	0	44
Windsor and Maidenhead	0	0	0	0
Others	11	12	2	25
Total	59	146	15	220

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note_2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number
Barking and Dagenham	0	0	0	0
Barnet	5	0	0	5
Birmingham	0	0	0	0
Bournemouth, Christchurch and Poole	3	0	0	3
Bradford	1	0	0	1
Brent	0	0	0	0
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	8	2	0	10
City of London	0	0	0	0
Croydon	0	0	0	0
Dacorum	0	0	0	0
Ealing	2	0	0	2
Gateshead	0	0	0	0
Greenwich	0	0	0	0
Hackney	5	0	0	5
Hammersmith and Fulham	0	1	0	1
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	0	1	0	1
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	0	0
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	0	0	2
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	5	0	0	5
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	2	0	4
Newham	3	0	0	3
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	1	0	0	1
Plymouth	1	0	0	1
Portsmouth	0	0	0	0
Reading	0	0	0	0
Redbridge	0	0	0	0
Salford	0	0	0	0
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	0	0	0	0
Southwark	8	0	0	8
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	4	0	0	4
Trafford	0	0	0	0
Waltham Forest	0	0	0	0
Wandsworth	0	0	0	0
Westminster	1	14	1	16
Windsor and Maidenhead	0	0	0	0
Others	14	0	0	14
Total	68	20	1	89

## Enforcement_4
Number of building inspections by local authorities supported by the Joint Inspection Team, England, 31 May 2023
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team.
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note_16] / Number
Barking and Dagenham	0
Barnet	4
Birmingham	1
Bournemouth, Christchurch and Poole	2
Bradford	0
Brent	2
Brighton and Hove	0
Bristol, City of	0
Bromley	0
Calderdale	0
Camden	4
City of London	0
Croydon	2
Dacorum	0
Ealing	4
Gateshead	0
Greenwich	3
Hackney	6
Hammersmith and Fulham	1
Haringey	0
Harrow	0
Hillingdon	2
Hounslow	1
Ipswich	0
Islington	0
Kensington and Chelsea	0
Kingston upon Thames	0
Kirklees	0
Lambeth	2
Leeds	0
Leicester	0
Lewisham	0
Liverpool	5
Maidstone	0
Manchester	0
Medway	0
Merton	0
Milton Keynes	0
Newcastle upon Tyne	1
Newham	10
North Somerset	0
Norwich	0
Nottingham	2
Plymouth	1
Portsmouth	2
Reading	0
Redbridge	1
Salford	1
Sheffield	0
Slough	0
Southampton	0
Southwark	4
Sunderland	0
Sutton	1
Thanet	0
Tower Hamlets	0
Trafford	0
Waltham Forest	1
Wandsworth	4
Westminster	2
Windsor and Maidenhead	0
Others	6
Total	75