## Annual Review Template

Title: India Economic Reform Programme
Programme Value £ (full life): £60 million		Review date: 23 November 2021
Programme Code: [AMP ID#] N/A	AMP start date: / 1 September 2017	AMP end date: / 31 March 2023

Summary of Programme Performance
Year	April 2017 – July 2019	July 2019 – July 2020
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

This is the third Annual Review for the India Economic Reform programme (Legacy Prosperity Fund Programme), which aims to deliver mutual prosperity for India and the UK, driving inclusive economic growth by opening up and developing new markets for domestic and international (including UK) business. The programme is delivering programmes in those themes (‘strands’) where UK strengths best match India’s priorities for reform: urban development, ease of doing business, financial services, skills and energy and low carbon.

The Technical Assistance Programme on Financial Services in India (FS) aims to materially progress the technical cooperation on financial services jointly agreed by the UK and India Prime Ministers. The programme aims to facilitate inclusive economic growth in the Indian financial sector by providing technical assistance in specific financial sector areas. Initiatives under the programme were structured around three pillars as per the initial design in Year 1 – Financial market development (FMD), Raising finance for Infrastructure (RFI) and Financial Technology development (FinTech) - which are to be delivered in partnership with relevant stakeholders (such as SEBI, IBBI, MCA, IRDAI, PFRDA etc.).

The seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK has now moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. Following a thorough review, the FCDO’s programme budget has been allocated in accordance with UK strategic priorities against a challenging financial climate of COVID.

Throughout the business planning process, the FCDO has strived to ensure that every penny of the ODA spend brings maximum strategic coherence, impact and value for taxpayers’ money. The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue.[1] This Annual Review reflects that the programme has had to refocus resources. As a result, the findings of this Annual Review reflect on a programme in transition.
[1] The programme was restructured to focus only on the high priority areas viz. FMD and the RFI through the T1 programme while bringing FinTech in-house.
The UK remains a world leader in international development, not only through the impact of these financial allocations but also through the creation of the FCDO, integrating diplomacy and development to deliver greater impact. We will return to our commitment to spend 0.7% of gross national income on ODA when the fiscal situation allows.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Strand Assessment: A+

Working with delivery partner Ernst & Young (EY), the Tranche 1 programme’s work on insolvency has been especially impactful, working in close partnership with Indian government agencies to deliver capacity building for officials, regulators and professionals and supporting policy development in a number of areas.
The programme has in place several achievements. With implementation focussed mainly in two quarters, the programme successfully achieved all 10 expected output indicators and 3 intermediate outcome indicators for the year. The programme was able to meet 100% of the forecasted spend for Year 2. Very positive feedback was received from senior officials of regulators such as IBBI, SEBI and IRDAI, post-delivery of the interventions which has strengthened the credibility and engagement of the programme within the government. The programme also significantly improved on the ways of working between EY, FCDO and external stakeholders, which led to faster decision making, reduced iterations and improved adaptability.
A joint DIT and legacy Prosperity Fund team led the FinTech in-house delivery of the programme from the 3rd quarter. The programmed achieved excellent results leveraging the existing relationships of the BHC network, thus providing optimal value for money. The FTA mentorship programme being the centrepiece of our plan, successfully identified 8 leading VC investors mentoring 22 cutting-edge FinTech firms from India, the UK and beyond who cover a range of sectors from SME finance and agricultural insurance to payments and lending.

Key achievements for Year 2 include:
- Pillar 1 – Insolvency: The track continued to show exceptional achievements including training of 3,689 Insolvency professionals/regulators/creditors thus, overachieving the target for Year 2. In addition, the track submitted two policy recommendation papers for the pre-pack regulation and drafted a new handbook of ethics for insolvency professionals, released publicly by IBBI in March 2021.
- Pillar 1 – Capital Markets: Conducted two trainings for 100 SEBI officials (target 30), 21% female participants (target 10%) with very positive post-training feedback from the regulator.
- Pillar 1 – Insurance: Conducted a training session for senior IRDAI officials on regulatory sandbox for insurance products. Post the session, IRDAI has launched their sandbox for India and is now said to be one of the most successful sandbox applications amongst regulators in India.
- Pillar 2 - RFI: Facilitated drafting financing plans for two organisations – Rail Infrastructure Development Company (Karnataka) Limited – "KRIDE” and The National Capital Region Transport Corporation (NCRTC). As per news reports, KRIDE received an allocation of ~£29million (INR 300Cr) from Government of India and ~£82million (INR 850[2] Cr from Government of Karnataka) for the FY 2021.
  [2] https://www.thehindu.com/news/cities/bangalore/850-crore-for-suburban-rail-project/article34021019.ece
- Pillar 3 – FinTech: Multiple activities such as hackathon, pitch event, mentorship programme and virtual knowledge sessions to support FinTech startups. These sessions helped identify 3 early stage and 4 growth start-ups and introduced FinTech Award startups to their mentors.
- FinTech In-House: Conducted 8 knowledge sessions with experts, a two day FinTech Boot Camp with women which had over 50 women entrepreneurs along with Senior Government officials and leading financial institutions and 1-2-1 mentorship sessions for the 22 companies.

Major lessons and recommendations for the year ahead [1/2 page]

Key lessons

- Aligning programme delivery to policy objectives, particularly ministerial commitments set out by the annual Economic and Financial Dialogue (EFD) between the Chancellor of the Exchequer and the Finance Minister of India: Helps to secure buy-in from GoI stakeholders and use programme funding to support our overarching economic and policy priorities. Examples are inclusion of priorities such as privatisation, GIFT City in our programme delivery plans.
- Support from UK institutions (government and private) are important to deliver programme objectives: Particularly on areas where the UK regulatory framework is perceived to be more advanced, direct involvement/contribution by UK institutions (such as the Insolvency Service, UK Government Institutions) is sought and welcomed by GoI stakeholders.
- Programme should adapt delivery to changing context and stakeholder priorities: In response to COVID 19 restrictions and changing stakeholder priorities, the programme adapted its delivery priorities and mechanisms.

Recommendations

Visibility on forward year programming is required to secure primary benefits:
In order to secure the intended primary benefits, outcome objectives and ensure programme sustainability, it is imperative to have clarity on the future years of programming.
Identify new outputs for Primary purpose and Secondary benefits realisation:
The de-scoping of some outputs and causal pathways in Year 2, following the ODA spend review, has affected the contribution towards primary purpose and secondary benefits (SBs) and the programme as envisaged in the design phase. Alternatively, new interventions/outputs could be planned based on the priorities of the Indian Government and the programme secondary benefit could be redefined to meet these priorities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The outcome and impact statements remains same for the programme as originally designed, however, outcome indicators 1a, 1c, 1e have been de-scoped. Post spending review, partial activities of RFI and FMD tracks have been de-scoped along with complete FinTech track from the T1 delivery. This has influenced a few intermediate outcome indicators.

EY conducted the initial preparatory work in quarter 1 of FY 20-21 on lines of identifying start-ups and mapping the mentors with the mentees (start-ups) of the Fintech accelerator hub. Post spending review, to continue this work, it was decided to implement it in-house. To effectively deliver the programme, the thematic of the delivery remained same and the programme continued to deliver on our commitments for the FTA (as originally been set up in partnership with EY). The programme delivery to the firms included mentorship, expert masterclasses, connections to businesses and investors and DIT support to go global.
We achieved a good value for money (VFM) in terms of economy perspective as the programme utilised the existing relationships of the BHC network with Fintech Ecosystem and stakeholders demonstrating a good utilisation of soft power without spending any extra budget on this component.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

In-spite of the budget cuts and delays due to the spending review, the programme has achieved excellent result by delivering all planned activities and milestones as per the revised scope in the agreed budget and timelines. The financial forecast has been achieved as planned for this year.

Apart from the planned activities, the programme delivered an additional 2 activities across the four selected tracks. The PMO team constantly monitored risks of underspend, especially those arising from the changing environment due to COVID-19, external stakeholders and third-party related risks. Risk mitigation steps were continuously discussed and key lessons learned were identified and shared regularly.

To address the uncertainty regarding the impact of COVID-19 pandemic in 2021 and beyond, the programme is identifying the high priority areas to be focused in coming years. In terms of implementation, the team is preparing in advance for multiple delivery mechanisms. Given the situation, delivery teams will have both a physical delivery plan as well as a virtual delivery plan ready to be proposed to stakeholders like SEBI, IBBI, IRDAI etc. and use the right medium as per the situation at the time of delivery.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

There has been significant positive momentum generated by the programme in Year 2, in terms of achieving all output indicator milestones, intermediate outcomes and a positive direction of travel towards the outcomes. This has been supported by strong engagement of key stakeholders, collaborative working between EY and FCDO, agile programme management and a strong implementation team.

We aim to continue building on the existing successful initiatives on supporting financial markets development, while closely linking programme delivery to policy objectives and EFD commitments.

The programme is exploring newer areas of collaboration basis emerging UK-India economic partnership priorities such GIFT City, Privatization etc. and exploring ways to streamline delivery within existing tracks to reduce the impact of de-scope and ensure the desired Impact and Outcome of the programme is achieved with the limited budget availability.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Target group participation in highly rated capability building and training for specific regulators of SEBI, IRDAI, PFRDA disaggregated by gender
Output number:		2	Output Score:	A+
Impact weighting (%):			Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
2a. Number of officials trained from SEBI (Capital Markets)	60 officials shall be trained on insider trading and forensics and, functioning of market and intermediaries / GESI: / At least 15% women officials trained in SEBI/IRDAI/PFRDA	Achieved : 100 / 43 SEBI officials in Quarter 3 on ‘Insider Trading and Market Abuse Surveillance’, / 57 SEBI officials were trained on ‘Electronic Trading and Corporate Governance’ / GESI: / More than 20% of the trained SEBI officials were women.
2b. Number of trainings held for training SEBI officials (Capital Markets)	Capital Markets - 2 trainings on 1) insider trading and forensics and 2) functioning of market and intermediaries	Achieved: 2 trainings / Trainings of mid-level SEBI officials on: / Insider trading and market abuse surveillance / Electronic/ algorithmic trading
2e. Number of trainings held for training IRDAI officials (Insurance)	1 training	Achieved: 1 / Training on ‘Regulatory Sandbox’ was conducted for IRDAI officials
2f. Number of officials trained from IRDAI (Insurance)	10-15 mid-level officials in relevant department are trained on topics related to Regulatory Sandbox / GESI: At least 15% women officials trained in SEBI/ IRDAI	Achieved: 11 IRDAI officials participated in the Regulatory Sandbox training conducted by the Insurance track. / 27% of the participants in the training were women
2g. Percentage of officials trained reporting the training as relevant and having improved their capability	70% / GESI: Yes, disaggregated by sex	Achieved: 78% / 78% positive feedback was received from both regulators - SEBI and IRDAI – as well as participants.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

On two indicators the output over achieved the targets. To reduce the risk of underspend, the Capital Markets team moved up the ‘Insider trading and market abuse surveillance’ training programme from Quarter 4 to Quarter 3. They were able to conduct this training programme within a short span of two weeks by leveraging their relationships with SEBI and their partnership network through EY UK. The capital markets track engaged with SEBI to identify priority topics for Year 2 capacity building activities. Considering the increasing number of violations by companies with respect to insider trading regulations, and the need to regulate such behaviour in the Indian markets it was felt that the issue of ‘Insider trading and market abuse surveillance’ was topical. The second training of SEBI officials was on the topic of ‘Electronic Trading and Corporate Governance’. Electronic Trading is a topic of interest, as it increases speed of transactions and reduces costs.

On IRDAI’s request the training topic ‘Building RBS/RBCF’ was changed to “Regulatory Sandbox”, as this is an area that the regulator is currently focusing on and is in nascent stages of development. The training session helped IRDAI to streamline their sandbox processes. Since the implementation of the training, IRDAI has now extended its sandbox regulations for 2 years and has received nearly 350+ applications across its two cohorts.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

EY achieved all outputs and outcomes for Y2 as per the logframe by delivering all planned activities within defined timelines as per the agreed budget. The delivery effectiveness was enhanced, by streamlining ways of working. Continuous reporting of data through prospero metadata sheets, logframe and ToC etc contributed to effectiveness in tracking and monitoring the programme

EY has provided partner level inputs pro-bono in Year 2 of implementation. Four EY UK partners have provided pro-bono time in preparation and sharing their insights as speakers at Insurance capacity building workshop for IRDAI.

The pillar has leveraged their strategic relationships with key stakeholders and FCDO’s and EY UK’s relationships to maximise delivery, outreach and efficiency.

To encourage SEBI officials to think holistically and promote equity, a GESI discussion on actions that small organisations with limited resources (to invest in data security and surveillance mechanisms) can take to prevent insider trading and safeguard their interests was conducted. Equity has been in-built into the programme design and approach from the beginning. A GESI strategy has been developed and GESI indicators have been incorporated into the logframe. Overall a very good representation of GESI has been demonstrated in this output.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Post spending review budget cuts, indicator 2c and 2d on Pensions were de-scoped. We will continue to keep outputs relevant to ministerial and governmental priorities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The forward plans for the programme is to continue building on the existing successful initiatives on supporting financial markets development, and look at providing enhanced regulatory and capacity building support for SEBI and IRDAI, which will be closely linked to our economic objectives.

Output Title	Insolvency: Capability building among practitioners, judiciary and regulators, creditors
Output number:		5	Output Score:	A++
Impact weighting (%):			Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
5a. Number of insolvency professionals (IPs), regulators and creditors trained under the programme	IPs: 1000 / Regulators: 60 officials / Financial creditors: 120 / GESI: / 10% of the seats through capability building being reserved for women / At least 15% female representation in the trainer/facilitator team	Achieved: Total number of trainings/workshops delivered: 19 / Insolvency professionals: 3021 / Regulators: 83 / Financial creditors: 585 / GESI / 11% of the participants across 19 trainings were women[3]. / 20% female representation in trainers/facilitators was seen across trainings
5b. Feedback from IBBI	Qualitative	Achieved / Overall feedback from IBBI and other stakeholders like IPA and SBI has been very positive. The regulator has been receptive of the trainings conducted by Insolvency track as part of the programme.
[3] ‘% female participation has only been reported for trainings where disaggregated data was available. For two trainings in Q1 (Avoidance transaction ~590 participants) and Q3 (Liquidation regime - 679 participants), disaggregated data isn’t available, therefore, they haven’t been added into the total base used for calculations.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

The programme provided training to 3500+ insolvency professionals, 500+ creditors from leading banks in India and 100+ regulators across 19 sessions on wide ranging topics such as research and presentation on liquidation regime in India ; training of insolvency professionals, regulators and creditors on Prepacks; creditors training etc.

The milestone achievement for Insolvency Professionals is thrice the target (3021 vs. 1000). The overall target for Insolvency professionals in Year 2 was increased from 600 to 1000 during the re-pivoting stage, post spend review. However, as the year progressed, EY got an overwhelming response to the virtual trainings from IPs due to increased buy-in and support from IBBI and MCA, which increased the overall participation and trebled the achievement against this milestone.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

This output has demonstrated excellent efficiency and equity in delivery.
The pillar has leveraged their strategic relationships with key stakeholders and EY UK’s relationships to maximise delivery, outreach and efficiency. EY also leveraged speakers from The Institute of Chartered Accountants in England and Wales (ICAEW) for a session on Ethical standards for Insolvency Professionals
Support from IBBI and other stakeholders, helped Insolvency track reach out to more participants per training session. The track was able to reach out to more than 3000 Insolvency professionals this year thus, overachieving their Year 2 target. This was feasible because of support from MCA, IBBI and EY UK.
The shift to virtual trainings using EY’s online collaboration tool enabled the tracks to engage a broad range of trainers from India, UK and US. It also ensured a wider outreach in terms of number of participants and their geographical representation from across India compared to physical trainings conducted where the trainers and participants engaged were geographically as well as numerically restricted owing to budget limitations on travel and food costs.
11% of the participants across 19 trainings and 20% of the trainers/speakers were women.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes to report.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The forward plans for the programme is to continue building on the existing successful delivery of the insolvency track, while closely aligning delivery plans to emerging objectives for MCA and IBBI, including on cross-border insolvency, group and personal insolvency, streamlining corporate insolvency process. This will work towards strengthening the implementation of the insolvency regime in India and improve the overall doing business environment for firms in the country. Going forwards, we also expect the track to look at providing lasting capacity building support for the regulator through bespoke ‘Train the Trainers’ initiatives, which will focus on intensive training exercises conducted for selected officials in addition to the wider training workshops organised for insolvency professions, creditors and regulators.

Output Title	Insolvency: Policy design & recommendations towards a more consistent insolvency framework which takes into consideration insolvency challenges that women and other socially excluded groups face in the Indian context
Output number:		6	Output Score:	A++
Impact weighting (%):			Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
6a. Number of policy recommendations provided to MCA/IBBI towards consistent and transparent framework	1	Achieved: 2 policy recommendations / Handbook on Ethics for Insolvency Professionals: Ethical and Regulatory Framework’ submitted to IBBI / The Draft research paper on DRO mechanism was delivered to IBBI.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

- The Handbook on Ethics for Insolvency Professionals was launched on 19 March 2021 at a webinar organized by IBBI in collaboration with British High Commission on “Pre-Pack Insolvency Resolution Process: Report of the Sub-Committee of the ILC”. The book includes a set of guidelines on ethical standards to be maintained by Insolvency Professionals (IPs) during resolution process. It incorporates leading practices from the UK and was developed in collaboration with IPs and IBBI. It is available on IBBI’s website at 0ab3ccba77975afcd9eb7ac679154de8.pdf (ibbi.gov.in).
- Developed a research paper on Debt Relief Orders (DRO) in support of IBBI’s work on development of Personal Insolvency regime. The report detailed the role of insolvency advisor/restructuring advisor and practices from UK including DRO and meditation clause.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Output 6 submitted 2 policy papers against the agreed milestone of 1 paper thus demonstrating efficiency and economy with maximum impact and value for money.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The programme team to work closely with IBBI and MCA to understand their emerging priorities for future programming, including on cross-border insolvency, group insolvency, personal insolvency, recommendations to strengthen the existing corporate insolvency process.

Output Title	RFI: Identified organisations supported to increase their attractiveness to domestic lenders / investors and international lenders / investors including from UK based on an inclusive investment strategy for economic, social and green infrastructure; progress on specific fund raising projects and increased access to infrastructure financing
Output number:		7	Output Score:	A
Impact weighting (%):			Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
7b. No. of organisations and/or projects supported in preparation of financial plan and guided in preparing for the process of fund raising through IUKIFH	2	Achieved : 2 organisation / Rail Infrastructure Development Company(Karnataka) Limited (KRIDE) / The National Capital Region Transport Corporation (NCRTC)

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Rail Infrastructure Development Company (Karnataka) Limited (KRIDE) which is undertaking the “Bengaluru Sub Urban Rail Project” and National Capital Region Transport Corporation (NCRTC) were supported through the programme. A presentation on various fundraising options, indicative processes, key benchmarking analysis, financial plan along with Teasers for multilateral financing institution lending and domestic banks & financial institutions lending were developed and submitted to KRIDE and NCRTC.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

RFI team used a locally based EY representative to meet concerned officials in a potential partner organisation based in Bengaluru thus optimising the delivery cost.

RFI track delivered all agreed milestones for KRIDE and NCRTC during the year, and in addition, they delivered a presentation on fund raising options free of cost. This additional activity led to a notional saving for FCDO of approximately GBP 11,000 in terms of unbilled work.
Senior officials at KRIDE in their discussions with potential investors are using the financial plan provided to KRIDE under the programme. These inputs will help KRIDE in the future to raise funds.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The output is further de-scoped for Year 3 and 4.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

No recommendations.

Output Title	FinTech: Innovation and Enablement - Support packages for 12 innovations and growth phase GESI compliant fintech projects aligned to financial inclusion and SME finance
Output number:		8	Output Score:	A
Impact weighting (%):			Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
8a. 'Number of FinTech projects provided support packages in the form of mentorship and industry connect sessions, tax, regulatory, market strategy and fund-raising support including pitching to investors	3 new projects and 4 existing projects identified in total to scale up / 3 existing projects taken to market (mentorship, strategy, industry connects, fundraising)	Achieved / 3 new and 4 existing projects were identified to scale up through the below activities. / At Hackathon-2 top 3 companies selected as winners for scale-up support. / Virtual pitch identified 4 growth phase startups to provide support. / The second milestone of taking 3 existing projects to market that was due in Quarter 4, could not be achieved as the FinTech programme has been de-scoped / GESI: At Hackathon-2, 20% of the finalist co-founders and 33% of the judging panel comprised of women.

Briefly describe the output’s activities, and provide supporting narrative for the score.

- At Hackathon-2, 10 FinTechs were shortlisted and the top 3 were selected for scale-up support. Hackathon themes were based on proposing solutions related to InsurTech, RegTech and financial inclusion in the COVID-19 Landscape.
- Virtual event conducted on 16 June to introduce the FinTech Awards 2020 global cohort of startups to the programme mentors.
- Virtual pitch sessions conducted on 24-25 June 2020 to identify 4 growth phase startups. Pitch event themes comprised of solutions to support financial inclusion, SME financing and improving insurance penetration through InsurTech and RegTech.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

- The delivery effectiveness was enhanced, by streamlining ways of working. Continuous reporting of data through prospero metadata sheets, logframe and ToC etc contributed to effectiveness in tracking and monitoring the programme.
- The pillar has leveraged their strategic relationships with key stakeholders and DIT’s and EY UK’s relationships to maximise delivery, outreach and efficiency.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

De-scoped from year 3 and 4.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The programme team will review the modalities of future delivery of the FinTech Pillar.

Output Title	Capability building and technical assistance. Workshops delivered to selected FinTech firms on emerging Fintech priorities
Output number:		9	Output Score:	A+
Impact weighting (%):			Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
10.a Number of Capacity Building/Knowledge sessions conducted for FinTech Startups	4	Achieved: 8 (4 direct under the programme and 4 leveraging DIT initiatives) / GESI: Out of 8mentors, 2 were women; 2 companies had women co-founders; 1 knowledge session was delivered by a women speaker
10.b. Number of women Boot camps and Mentorship workshops conducted to build the FinTech ecosystem by International (including UK) experts	1 Boot Camp; 1 Mentorship session	Achieved : 1 Boot Camp and 1 Mentorship session / GESI: Over 50 women participants in Boot Camp; Out of 8mentors, 2 were women

Briefly describe the output’s activities, and provide supporting narrative for the score.

- The programme delivered 8 knowledge sessions to Fintech firms on topics including India stack and digital on-boarding, payments landscape, account aggregator framework, post Covid-19 investor scenarios, regulatory environment and emerging trends in entrepreneurship.
- Rt Hon Lord Mayor of City of London Corporation, Alderman William Russell launched the FinTech Cohort in a virtual FinTech lauch event organised on 23 November 2020 . The event focused on introduction of UK-India FinTech Award (FTA) winners and mentors.
- A two day Fintech Bootcamp with Women entrepreneurs were organised in partnership with Rise created by Barclays and WE Hub. The event was attended by over 50 entrepreneurs along with Senior Government officials, leading financial institutions form the states of Ahmedabad, Hyderabad, Karnataka, Maharashtra and Tamil Nadu.
- Mentorship sessions for the 22 Indian and Global Cohort companies were organised with the 8 programme mentors identified for the programme. The sessions started from January up till March 2021.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

In Year 2, in order to optimise the resources post spending review, the FinTech pillar of the programme was moved in-house, delivered by leveraging wider BHC network resources. The programmed achieved excellent results leveraging the existing relationships of the BHC network, thus providing optimal value for money.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

FinTech log frame was redesigned to align to the deliverables of in-house delivery plan.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
The programme team will review the modalities of future delivery of the FinTech Pillar.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

Overall, we assess the risk of this programme as [X]. It is delivering strongly against outputs, and the FCDO working relationship with EY provides us with confidence that the programme’s strong position is maintainable. Key risks include:

- Continued risk of achieving the desired programme impact and outcomes towards the end of the programme due to programme re-planning with reduced scope and budget for Year 2 and 3.
- Reduced impact on cross cutting themes like VfM, GESI and secondary benefits. With the reduced scope for Year 2 and 3, there is a limited scope to showcase transformational impact on these themes. Specially on secondary benefits as the major contributors (FinTech, infrastructure finance) have reduced in scope.
- Potential short notice of next year’s funds may result in delayed start of the programme for year 3 and may have an impact in the delivery. Teams are in process of working out possible scenarios to mitigate this risk.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

The programme has delivered remarkably well in year 2 while successfully achieving all the agreed outputs and met the 100% forecast spend, in spite of a reduced delivery timeline of two quarters to deliver the year’s targets. The financial budget for year 2 was allocated at £898k. This was over achieved by the supplier with a reported spend of £904k.
Starting Year 2, the first two quarters were spent in re-pivoting the programme to address COVID 19 challenges and further realigning the programme to the outcome of the ODA spend review. Majority of the programme delivery work had completely stopped for over 3 months. The last 2 quarters were spent on implementation and the programme.

EY undertook a number of initiative to ensure quality delivery. The key steps takes were:

Financial Management:
To keep track of budget utilisation across the pillars, quarterly finance reports were submitted. Any deviations of 10% or more from the budget was discussed in monthly steering committee for ratification by FCDO and also detailed in the quarterly reports.

Programme Management:
- The pillars kept the programme team at FCDO updated on activity progress, challenges and programme adaptations on a weekly basis.
- PMO arranged session for the track teams with the MREL expert to simplify VFM and help explaining strategies of VFM and GESI interventions.
- Management billing reduced from 18% to 11% of PMO cost, while programme partner dedicated more time to the programme as opposed to what was budgeted for pro-bono (Partner attended all internal pillar calls, working groups etc.)
- To achieve maximum efficiency, resources on monitoring and evaluation, and gender and inclusion are shared across the programme.

Risk Management:
In Year 2, EY constantly monitored programme risks, especially those arising from the changing context due to COVID 19 and the programmatic pause due to ODA spend review, and identified risk mitigation steps. These risks were related to non-delivery or under-delivery of activities. RAG statuses were tracked regularly, and weekly updates were provided to FCDO at the working group meetings and also presented in the monthly steering committee meetings. The risks and mitigation steps were also quarterly and annually by PMO.

Date of last narrative financial report		Date of last audited annual statement