The latest version of this document will be issued by the IPA 8-10 weeks before a scheduled Expiry Health Check

Expiry Health Check Questionnaire

This questionnaire is a key element of the IPA’s Expiry Health Check (EHC) process. You are requested to complete this questionnaire and return as part of the Information Request prior to the EHC review session, typically three weeks before.

We use your responses to the questionnaire, alongside the document review, to build a good understanding of your contract, its performance, and your preparation for expiry. It also helps us prepare for, and focus the review session on the areas that merit further discussion. As such, we ask that you provide sufficient detail in your responses. Whilst some questions may require one line, others may need a short paragraph.

Questionnaire Information

HMT ID:
Project Name:
Date of Completion:
Completed by:

1. Contract Management and Expiry Planning

Purpose: To understand whether the authority understands the contractual terms for expiry and has assessed whether these are clear and comprehensive; and to review whether there is sufficient planning, resources and governance in place to enable a successful expiry.

#	Question	Expected standard at			Response
		7yr	5yr	3yr
1.1 Contractual Documents
1.1.1	Do you have the original contract documents? / Do you hold all variations to the contract? / Has the contract been updated as a result of changes?	The authority should hold all original contract documents including the PA, schedules, financing documents, leases and main subcontracts to which the authority is entitled. These should be fully executed and conformed, as necessary. / The authority should hold all variations to the contract, and the project documents updated as necessary.
1.1.2	Do you have the original financial model? / Do you have a current financial model?	The authority should hold the original financial model. This should be in excel or similar format. / If there have been any variations, refinancing and other key contractual events, the authority should hold an updated model as set out in the contract. This should be in excel or similar format. / Alternatively, a robust system should be in place to manage the cost impact of changes that have no material impact on the financial model, or where the financial impacts have been managed outside the financial model.
1.1.3	Has a contract document stocktake been undertaken and a document register produced? / What action has been taken where documents are missing?	The authority should have undertaken a document stocktake to identify whether it holds all the necessary documents and action should have been taken to address any gaps.	The authority should have undertaken a document stocktake to identify whether it holds all the necessary documents. Where there were gaps the documents have been obtained.
1.2 Expiry Planning
1.2.1	Has an expiry plan been developed?	A high-level milestone plan based on key contract and organisational dates should be in place covering BAU, exit and future services workstreams.	A detailed plan should be in place that integrates BAU, exit and FSP workstreams. The plan should include an appropriate level of work breakdown, identify interdependencies and a timeline (beyond high-level milestones).	As at 5 years, with more detail in the plan, plus an initial plan for handback and service transition covering, as relevant, final contractual survey, data quality and transfer, TUPE and people issues, service cut over etc.
1.2.2	Is there a risk register in place? / What are the arrangements for reviewing and updating the risk register?	Initial risks have been identified with some mitigation plans as part of initial planning. / Appropriate arrangements are in place for reviewing and updating the risk register.	A risk management plan and risk register is in place. Evidence of active risk management through the governance arrangements. / This should include effective internal risk management, and risk management with the private sector.
1.2.3	Does the timetable have sufficient time to successfully manage expiry and the transition to future service arrangements?	There is a high degree of confidence that the high-level schedule is achievable and is on track.	There is a high degree of confidence that the detailed schedule is achievable and is on track.	As at 5 years but also including the transition plan.
1.3 People and Resources
1.3.1	Have you determined the skills that will be needed to deliver expiry? / Have you identified how these skills, in terms of capability and capacity, can be provided in house and where they will need to be supplemented by external advisors?	A skills need analysis has been undertaken for the short-term tasks. / Gaps in in-house capability are identified. As necessary, short-term measures are in place to mitigate the skills gap.	A full analysis of the skills required for expiry has been completed. This analysis includes optimising the mix of in-house staff and external advisors. / Gaps in in-house capability are identified. As necessary, short-term measures are in place to mitigate the skills gap.
1.3.2	Do you have a people plan for expiry covering both staff and advisors?	An initial people plan has been developed based on short-terms skills requirement. / Current staffing levels are sufficient for the current tasks.	A detailed people plan is in place that is sufficient to deliver a successful expiry. The people plan identifies and meets the relevant skills requirements e.g. legal, technical, HR, and includes learning and development (as required). / Staff have been recruited as and when required by the plan. Current staffing levels are sufficient for current tasks. / Successions plans are in place, particularly for critical posts.
1.3.3	Do you have a budget allocation for expiry related costs including staff, advisors and other activities?	Initial budget requirements have been identified, and near term funding needs have been approved.	Budgets have been approved for the expiry period, or the budgeting period (ideally this would be for more than the current financial year). / The budgets are deemed sufficient to meet the project requirements, with risks clearly identified e.g. for unplanned disputes. / Resource requirements for post-expiry PFI close-down and transition support should be included.
1.4 Governance
1.4.1	Has a Senior Responsible Owner or a senior executive lead for expiry been appointed?	An SRO of sufficient seniority (director level) has been appointed with clear terms of reference and sufficient decision making authority to deliver expiry and transition to future services.
1.4.2	Has a project lead for expiry been appointed?	An expiry project lead has been appointed by the SRO with clear terms of reference and sufficient authority and capacity to manage expiry day to day. / The expiry project lead is sufficiently experienced and capable to undertake the role.
1.4.3	Do you have appropriate governance structures in place to support expiry and future service provision, in addition to BAU?	Governance structures have been adjusted to support the initial phase of expiry work. / The structures are clearly documented and understood and demonstrate integration with the wider corporate structures. / A meeting structure is in place with terms of reference. / Good project management principles are being adopted.	Governance structures have been adjusted to support expiry and integrated with wider organisation structures to ensure effective corporate oversight and decision making processes. / The structures are clearly documented and understood. A meeting structure is in place with terms of reference. / Good project management principles are being used.
1.5 Contract Expiry Terms
1.5.1	Do you have a good understanding of expiry terms? / Has a comprehensive review of the contract for expiry been undertaken?	The authority has undertaken a detailed contract review to identify all the clauses relevant to expiry. The review should have been undertaken by a competent person and documented appropriately. / Contractual gaps and ambiguities should be captured in a gaps list and risk register. / The authority should demonstrate a good understanding of the key expiry terms, particularly on processes, asset handback, any payments required, asset survey & condition, retentions, information sharing, and leases.
1.5.2	Are there expiry clauses in the contract, and are these clear, comprehensive and unambiguous?	There are explicit expiry clauses in the contract which are clear and comprehensive.
1.5.3	What have you done to address any ambiguities or gaps?	Ambiguities and gaps have been identified and documented in a gaps list and risk register.	As at Year 7 and ambiguities and gaps negotiated with the private sector to reach an agreement, or there is a clear plan to do so at an appropriate time.	As at 5 years and agreements on the ambiguities and gaps are being implemented without material issue.
1.5.4	Is there a contractual provision to extend the contract beyond the expiry date?	This question is for information only and is not assessed.
1.5.5	Are there any estates or assets which are integral to providing the service which remain with the private sector at the end of the contract?	This question is for information only and is not assessed.

2. Relationships

Purpose: To understand the current relationships between the public and private sector, and how these may change during expiry. This covers effective communication and transparency.

#	Question	Expected standard at					Response
		7yr	5yr		3yr
2.1 Current Relationship
2.1.1	How would you rate your relationship with the private sector parties, and why?	The authority has a constructive relationship with the private sector which is driving performance and enables effective resolution of issues without unnecessary (informal or formal) disputes. The relationship is based on mutual trust and respect.
2.1.2	How effective is communication and engagement with the private sector?	There are regular and effective communications between the public and private sector. This is supported by an appropriate meeting structure at various levels of seniority which enables performance review and issue escalation.
2.1.3	Is information provided in a timely manner routinely and when requested, and is it of a sufficient quality?	Information is routinely provided in accordance with the contract (or as otherwise agreed). When information is requested it is provided in a timely manner and is reasonably transparent.
2.1.4	What level of engagement do you have with directors of the SPV?	There is senior level engagement with the SPV directors. This is regular and focuses on strategic matters and relationships, and supports issue escalation as necessary. / The directors attend the project liaison committee (or equivalent) and are engaged in setting appropriate strategy, expectations and behaviours.
2.2 Cooperation on expiry
2.2.1	To what extent have there been expiry discussions with the private sector? / Have these discussions resulted in joint plans and agreements on managing expiry?	Discussions have been held with the private sector, with agreements on how the parties will approach expiry.	The authority and private sector have agreed detailed arrangements for managing expiry. This will likely include joint plans, governance, escalation/ dispute resolution, processes for resolving ambiguity and interpretations etc. / Expiry should be included in standing agendas, or specific meetings established.
2.2.2	Do you expect information to be provided in a timely manner and to sufficient quality during the expiry process?	The parties have discussed and agreed principles for information sharing.	Detailed agreements are in place that confirm timing of information sharing, process for data quality validation, and format. / As expiry approaches the assessment should include the effective and timely sharing of information.
2.2.3	Do you expect there to be disputes on expiry? If so, how do you believe these disputes will be conducted? / Disputes in this context should be considered to cover informal and formal disputes.	Disputes are considered unlikely and/or the authority is confident that disputes will be resolved effectively and efficiently.	Disputes are considered unlikely and/or the authority is confident that disputes will be resolved effectively and efficiently. / Parties will have considered and agreed how expiry disagreements and disputes will be managed effectively. / Where there have been disputes these have been effectively and efficiently resolved in accordance with the agreed processes, or as part of wider commercial agreements on expiry.

3. Assets

Purpose: To understand the current condition of assets, and sharing of asset information; and to determine the effectiveness of asset handback provisions

#	Question	Expected standard at			Response
		7yr	5yr	3yr
3.1 Current Asset Information
3.1.1	Do you have access to the PFI asset register and is it accurate?	There is an asset register in place, and the authority undertakes sufficient verification to be confident that the data is accurate. The register reflects changes arising from operations, maintenance, lifecycle and variations. / Ideally the asset register will be in electronic format.
3.1.2	Is there an IT based asset management system (e.g. CAFM) that is fit for purpose and contains accurate data? / Is the data in the system accurate?	There is a fit for purpose IT based asset management system to which the authority has access. The authority routinely verifies that the information is sufficient, accurate and complete in respect of asset information, maintenance records etc.
3.1.3	Is there a full record of statutory compliance documentation being maintained and available to the authority?	All statutory documentation is available and there is independent or authority assurance of the arrangement in place.
3.1.4	Is there a record of any unexpired warranties for the assets?	A log of warranties is available and aligned with the asset register.
3.2 Operational Asset Condition
3.2.1	What are the contractual requirements for condition of the assets during the contract term?	The contract has defined asset condition terms during the operation of the contract, and are these not ambiguous.
3.2.2	Have asset condition surveys been undertaken during the operational period? / Do you have access to the survey reports? / These surveys could be an obligation on the private sector, a right of the authority, or simply that a party has elected to do so.	Surveys have been undertaken (whether contractual or not) and available to the authority. The surveys undertaken are sufficiently comprehensive to assure asset condition and compliance with contractual asset condition terms. / Where the surveys are undertaken by the private sector the reports, of sufficient quality and detail, are shared with the authority.
3.2.3	Have remedial works identified in the surveys been completed to the required standard and in a timely manner?	Remedial works have been fully completed within reasonable timeframes and to the required standard. The authority can demonstrate that it has undertaken sufficient assurance of remedial works completion.
3.2.4	Are the assets currently compliant with the operational asset condition requirements? / How do you verify this?	The assets are in compliance with the contract terms, and the authority can demonstrate that their opinion is evidence based.
3.3 Maintenance and Lifecycle Planning and Delivery
3.3.1	Have maintenance and lifecycle plans been provided to the authority?	Maintenance and lifecycle plans have been provided, and these have sufficient detail, costing information (where there is an obligation to do so) and robustness to ensure ongoing compliance of the assets with the contractual requirements and with the plans set out and funded by the authority in the financial model. / Lifecycle plans are informed appropriately by asset surveys, asset performance and maintenance data.
3.3.2	Have maintenance plans been delivered in compliance with relevant standards? / How do you monitor this?	All works have been completed to the required standards. The SPV reports performance against maintenance plans as part of routine reporting. The authority can demonstrate appropriate assurance action to provide confidence in maintenance completion.
3.3.3	Have you reviewed periodic lifecycle plans to ensure that these are in accordance with industry standards and contractual terms?	Lifecycle plans are regularly reviewed by a competent person to ensure that they are sufficient to maintain the assets to the required standards. The authority may base their judgement on industry standards for expected life, contract assumptions on expected life (e.g. contractors proposals), or the original lifecycle / financial model.
3.3.4	Has the programme of asset replacement (lifecycle) in the plans been completed?	All works have been completed to the required standard. The authority can demonstrate that it is verifying this, or that there is independent certification of the works.
3.4 Assets at Expiry
3.4.1	Is the ownership of asset data at contract expiry understood? / Are the rights and obligations for transfer and data quality clear? / Is the timing of access to data appropriate to manage expiry and sourcing of future services?	The contract sets out asset data ownership and expiry, with obligations on transfer and data quality. / The authority has identified when the data is contractually available.	There is a shared understanding of data ownership and any ambiguity on data transfer and quality have been addressed. / The authority has identified when it will require data during expiry, and addressed any mismatch with contract timelines.	In addition to the 5 year process data handover processes have been developed (and potentially exercised to support procurement).
3.4.2	How clear and effective are the contractual asset handback conditions from a technical perspective? / If not, what action has been taken to address this?	Asset handback conditions are clearly drafted with no material ambiguity, and refer to documented standards.	Asset handback conditions are clearly drafted with no material ambiguity, and refer to documented standards. / Any ambiguity has been addressed between the parties and documented. The outcome is being used to support asset surveys and remedial work discussion.
3.4.3	Is there an obligation or right for a final asset condition survey? Is this sufficiently early for any major remedial works to be completed, and for commercial levers to be effective?	There is an obligation or right for a final condition survey with full transparency of survey outputs and remedial works. / If the survey is considered too late then this is captured as an issue by the authority, and has been raised with the SPV.	There is an obligation or right for a final condition survey with full transparency of survey outputs and remedial works. / If no obligation or right exists, suitable arrangements have been agreed to determine asset condition. / If the survey is considered too late then agreement has been reached on alternative plans to mitigate the risk (e.g. a survey at 5 years).	There is an obligation or right for a final condition survey with full transparency of survey outputs and remedial works. / If no obligation or right exists, suitable arrangements have been agreed to determine asset condition. / If the survey is considered too late then alternative plans to mitigate the risk have been implemented.
3.4.4	Is there a clear requirement for the development and agreement of a rectification plan to meet the handback conditions following the survey?	The contract is clear on the obligations of the SPV to develop a rectification plan, and provides the authority with sufficient rights to review and monitor the plan to assure handback conditions are met. / Any ambiguity has been identified.	The contract is clear on the obligations of the SPV to develop a rectification plan, and provides the authority with sufficient rights to review and monitor the plan to assure handback conditions are met. / Where surveys have been conducted, and remedial works identified, the obligations are being met i.e. a plan has been produced and works completed as agreed. / Where there is ambiguity this has been addressed by all parties and agreements documented.
3.4.5	Do you expect the assets to meet the handback criteria at the end of the contract? Why?	Assets are expected to be handed back in line with the contract terms. / This assessment may be based on a good understanding of current condition, asset management arrangements, and knowledge of handback processes.	Assets are expected to be handed back in line with the contract terms. / This assessment may be based on a good understanding of current conditions, early asset surveys, and agreement on standards and processes.

4. Commercial Position

Purpose: To understand the current commercial position on the contract, and the commercial position for expiry, and how this is informing the authority’s commercial approach to expiry.

#	Question	Expected standard at			Response
		7yr	5yr	3yr
4.1 Current commercial position
4.1.1	Is the private sector operating in line with the contractual expectations?	The SPV and Services Provider is performing to the required standard, or better, with good information sharing including compliant reporting and use of the payment mechanism. This should include deductions being levied as appropriate. / Where there is underperformance more weight should be given to areas which have a direct impact on effective expiry management.
4.1.2	What commercial and financial levers are available to the authority to ensure asset condition during the operational phase? / Are these considered effective?	The authority has a good understanding of the commercial and financial levers available to them and it knows which are likely to be effective. The authority demonstrates a clear approach to using its contractual, non-contractual, and relationship levers in working with the private sector. / Where applicable, the authority has used these rights effectively.
4.1.3	Are there, or have there been, any disputes (informal and formal), or notices served on the contract? / How have these been resolved?	Where disputes have arisen, or notices have been served, they have been resolved effectively and efficiently. The expectation would be that these have been resolved in a constructive and business like manner. / There is no presumption that disputes that have progressed through the full extent of the DRP process should result in a lower score. It is reasonable to allocate more weighting to more recent disputes.
4.1.4	Do you understand how the investors make their return on the contract?	The authority has a basic understanding of how the investors make their returns (e.g. dividends, sub-debt, MSA payments), when the majority of the returns are forecast to be extracted / paid and how this may affect behaviours.
4.1.5	Do you have an understanding of the financial performance of the contract from the point of view of the private sector parties (service provider and SPV)? Is this reflected in your identification of commercial levers (Q4.1.2 above)?	The authority has a good understanding of the level of the investors’ returns by reviewing company accounts and other available material, and how these compare to original expectations in the financial model. This is reflected in the authority’s commercial approach to expiry.
4.2 Funding for Asset Condition during contract term
4.2.1	Is the funding obligation between the parties for asset maintenance and lifecycle clear in the contract and financial model?	Asset maintenance and lifecycle funding is clearly defined between the parties and/or shown in the financial model. / If the authority has either retained some funding risk for assets, or taken back risk via a variation, the assessment could be reduced based on how clearly the risk is allocated and how effectively it is being managed.
4.2.2	Does the authority have access to sufficient and quality information to understand how lifecycle funding has been used, and to compare it to contractual and/or financial model assumptions?	The authority has access to sufficient information to review lifecycle investment and compare this to the contractual assumptions. This may include access to information on lifecycle works, cost data, balance of reserve accounts and lifecycle models.
4.2.3	Have you reviewed whether the lifecycle and other funding retained by the SPV is likely to be sufficient to meet current and future expenditure commitments?	The authority has reviewed the lifecycle and other funding retained within the SPV to determine whether it is broadly sufficient to meet future lifecycle commitments of the SPV. This judgement has been made using relevant information e.g. surveys and lifecycle plans, by an appropriately qualified person.
4.2.4	Do you know what reserves (e.g. sinking fund or reserve accounts) exist within the PFI? / Are you clear what happens to unspent reserves on expiry?	The authority is fully aware of the reserves that exist and how any residual balances are distributed at expiry. Where there is a right to the information, they are monitoring current value and use of the reserve as part of their expiry activity.
4.3 Contractual position on expiry
4.3.1	Does the authority need to make any payments to the private sector on expiry? For example to buy the asset or spares. / If no payments are required is question is N/A	The authority understands that it has to make a payment, and has an understanding of the value and terms of the payment.	The authority has a good understanding of the terms, has estimated the value of the payment, and made budget provision. The authority has engaged with the private sector to ensure clarity on the process.	As 5-years, ensuring that valuation is reviewed routinely. / Where any payment is optional, or has options, appropriate approval has been sought via a business case. / The BC may be part of future service approvals
4.3.2	Do you know when the debt is paid back, and how this impacts on your commercial levers and the incentives for the private sector?	The authority is aware of when the debt is repaid, how this aligns with other expiry activities, and how this may change the incentives of the private sector, and control of free cash in the SPV.	The authority knows when the debt is repaid, and how this relates to other expiry activities (e.g. asset condition surveys). They understand how this will change incentives for the SPV and controls on free cash in the SPV. This is reflected in their commercial approach and relations management plan.
4.3.3	Does the contract allow the authority to retain or withhold unitary charge in case of a failure to complete lifecycle or remedial works in line with the contract or agreed remediation plans? / Are these provisions sufficient to incentivise the private sector to meet handback conditions?	The contract has clear and enforceable rights to withhold payments where works have been identified to comply with the contractual condition standards, or these works have not been completed in a timely manner. The amounts that can be withheld are sufficient to incentivise the private sector and, if required, for the authority to undertake these works. / The provisions are sufficiently detailed in terms of the process of retention and release of funds etc. / Where applicable, the authority has used these rights effectively. This includes using the paymech, where appropriate to do so, to incentivise remedial works.
4.3.4	What is your commercial approach to ensuring assets are compliant at handback, and gaining timely access to quality asset data, if you anticipate issues?	The authority understands contractual and non-contractual levers and has initial ideas on how these may be used.	The authority has developed a reasonable commercial approach through to expiry, built on its contractual and non-contractual levers. It reflects wider insights from its understanding of the contract, asset condition and information, commercial incentives of the private sector and their approach to relationship management.

5. Future Services

Purpose: To understand the future strategy of the authority, whether it understands the current contractual services. To understand if the authority understands what information it requires when to support future service sourcing and transition, and whether it is likely to get/ is getting the necessary information.

#	Question	Expected standard at			Response
		7yr	5yr	3yr
5.1 Future strategy and plans development
5.1.1	Do you have a strategy for assets and services following expiry? / Note that the exact timing of strategy development, and associated business case approvals will be dependent on the decisions required and authority processes. Where existing assets are unlikely to be needed, or require significant moderation then earlier decisions will be required.	Early work has commenced. / This is likely to consider asset and service utilisation, future need, estate strategy, and carbon net zero targets. / A long list of options are likely to have been identified, with analysis started and soft market testing planned as required. / Work is coherent with cross-cutting wider authority strategies.	The strategy is in development and progressing as planned. There has been engagement with approving bodies, ideally through an outline business case.	A strategy has been developed and approved via a business case, or a clear plan is in place for timely approvals.
5.1.2	Is there a plan in place for the sourcing of future arrangements to deliver the future strategy (see Q5.1.1)? / Is this plan aligned and integrated with the wider expiry plans?	A high-level milestone plan for sourcing of future arrangement based on the emerging strategy and organisational dates should be in place. / There should be alignment with the BAU and exit workstreams with key interdependencies identified.	A detailed plan should be in place which should be integrated with BAU and exit workstreams. The plan should include a detailed work breakdown (including sourcing and approval), identify interdependencies and a timeline and risk register.	As 5 years plus initial plan for handback and service transition covering data quality and transfer, TUPE and people issues, communications, mobilisation and service cut over etc.
5.2 Experience and capability for future services sourcing If sourcing options have not been determined, then 5.2.1 - 5.2.4 should all be answered.
5.2.1	If applicable, have you, in the last 3 years, undertaken a re-procurement or outsourcing of comparable scale, including TUPE transfer?	The authority has undertaken a comparable activity in the last 3 years, and that the experience is available to the team that will be undertaking the re-procurement of services.
5.2.2	If applicable, have you, in the last 3 years, undertaken an insourcing of comparable scale, including TUPE transfer?	The authority has undertaken a comparable activity in the last 3 years, and that the experience is available to the team that will be undertaking the insourcing of services.
5.2.3	If insourcing any part of the service, what experience and capability do you have of delivering similar services to those being insourced from the PFI?	The authority has extensive experience and capability in delivering similar services on its non-PFI estate.
5.2.4	If there is a need to undertake built new assets, or redevelop existing PFI assets (post-expiry) as part of the future strategy have you delivered similar capital works projects in the last 5 years?	The authority has undertaken a comparable activity in the last 5 years, and that the experience is available to the team that will be procuring the capital works.
5.2.5	What is your understanding of the market for the services you are planning on sourcing?	The authority has a broad understanding of the market, which is informing its strategy development.	The authority has engaged with the market to inform its future sourcing strategy and business case development.	The authority continues to monitor the market to check that there are no major changes which would impact on its sourcing plans for future services.
5.3 Knowledge of current services to support future services sourcing
5.3.1	Do you understand how the SPV and key services providers deliver the service you receive? / This should include direct service provision, management and back office functions.	The authority has details of all of the service providers (including subcontractors to the main service provider). They have a basic understanding of the scope of services, management and back office, and the key contract terms. / This is enabling them to develop high-level future service options.	The authority has details of all of the service providers (including subcontractors to the main service provider). They have a good understanding of the scope of services, management and back office, and the key contract terms. / This is enabling them to develop detailed future options.	The authority has details of all of the service providers (including subcontractors to the main service provider). They have a good understanding of the scope of services, management and back office, and the key contract terms. / This is enabling them to develop detailed future options.
5.3.2	Do you know what systems, equipment and spares are used by the contractor and which you or a future service provider will need to take over or reprovide? / What are the obligations for the transfer of these systems (including data), equipment and spares? / Are you confident in the quantum and quality of the systems, data, equipment and spares that will be transferred? / Systems could include asset management systems, helpdesk, visitor booking systems.	The authority is aware of systems et al that are used by the private sector; whether these are transferred.	The authority has a detailed list of systems, equipment and spares held, sufficient to start to plan its service delivery or to provide in due course to bidders. / Obligations for transfer are understood and clarified with the private sector. Ambiguities and gaps have been clarified and agreed with the private sector, or there is a plan to do so. / For the items transferring to the authority, there is a plan to audit and verify the quality and quantum of the systems et al.	The authority has audited and verified the system et al which are due to return to it. It has plans in place with the private sector to continue to monitor and verify through to expiry. / There is agreement between the authority and private sector on transfer and condition at expiry. / Where systems et al are to be available to future contract bidders, there is sufficient information, and agreed support, from the outgoing contractor to enable bidding and eventual transfer to the new contractor.
5.3.3	Have you been able to access the data and information necessary for sourcing future services? Are you able to use your full contractual rights to access information?	The authority has assessed whether the information rights in the PFI are sufficient to support future sourcing activity. / It makes good operational use of these provisions, with the private sector providing the information in the required format, accurately and timely.	The authority has agreed a sharing protocol and timetable with the private sector to support future services sourcing needs. This includes addressing any shortfalls in information rights. / Where information has been requested it has been accurate, timely and relevant i.e. it is sufficient to meet the needs of the authority at that time.	As 5 years plus a data room is established and populated. / Or if too early, a defined requirement for the data room has been defined, and a plan to establish and populate.
5.4 Transfer of Staff
5.4.1	Do you understand the number of staff that may be subject to TUPE? / Do you understand your rights to staff data, and the timing of this? / Do you believe there will be challenges in getting access to this data?	The authority is aware that some staff may be covered by TUPE regulations. / The authority is aware of the general rights to data. The authority believes that the private sector will meet its legal and contractual obligations on data sharing.	The authority is aware that some staff may be covered by TUPE regulations, with a broad understanding of numbers. / The authority is aware of the rights and time access to the data. The authority believes that the private sector will meet its legal and contractual obligations on data sharing.	The authority has a good understanding of the numbers, and current terms and conditions. / The authority and private sector have agreement on what information will be shared and when. / The authority is confident, based on these agreements, that data will be shared as agreed.
5.4.2	Do you understand the pension arrangements of those staff potentially subject to TUPE?	The authority is broadly aware of the pension arrangements of the staff potential covered by TUPE.	The authority is aware of the pension arrangements of the staff potential covered by TUPE.	The authority is aware of the pension arrangements, and has identified any material issues.