# FCDO Strategic Impact Evaluation and Learning (SIEL) Programme: Call for Proposals
## Introduction
1. The Strategic Impact Evaluation and Learning (SIEL) programme will deliver impact evaluations of FCDO programmes. It will maximise the return on FCDO’s investment in knowledge by evaluating in areas where evaluation budgets currently do not reach adequately, and employing a centralised process to identify and address gaps in the global evidence base which are relevant to FCDO’s priorities.
2. The programme is comprised of three components:
  1. Robust impact evaluations of FCDO Programmes selected through a centralised process led by the SIEL implementing partner in partnership with FCDO’s Evaluation Unit (60% of budget);
  2. Follow-up studies to assess long-run impact where previous studies have assessed outcomes at project close (15%).
  3. Capacity building in FCDO around commissioning, managing, interpreting and identifying opportunities for future impact evaluation (15%).[1]
    [1] The remainder of the budget comprises administration and overhead costs, plus monitoring and evaluation.
3. This is a Call for Proposals to deliver all three components. The intention is these are delivered together by the same organisation or consortium of partners (the Implementation Partner), although it is also possible for the implementation partner to contract-out some of the work.
4. This Call for Proposals sets the scope of work, requirements and reporting procedures for the Implementing Partner.
## Objectives
1. The intended outcomes of this programme are:
  1. A strengthened evidence base of ‘what works’ including in the long run;
  2. Improved efficiency and effectiveness of programmes and policies at the global level in strategic priority areas for FCDO;
  3. FCDO staff are equipped to deploy and exploit impact evaluation to maximize Value for Money.
## Scope
1. The full design of SIEL is not yet pre-determined, and it is intended that this Call for Proposals will identify the core offer of a potential collaborator with FCDO, to be developed into a full Memorandum of Understanding or Accountable Grant Agreement with the chosen partner.
2. SIEL could seek to evaluate FCDO programmes and foreign policy activities in any thematic area in development and diplomacy, in any part of the world;
3. FCDO’s current key priority areas set out in the International Development Strategy are: investment, women and girls, humanitarian, climate change, nature and global health. There is also potential for the programme to address topics highlighted in the Integrated Review Refresh (2023) and International Technology Strategy (2023).
4. SIEL priority areas could expand further and/or change over time in response to Ministerial preferences.
5. Further details about FCDO’s thinking about the SIEL Programme are included in the Annex to this document.
## Capability
1. The implementation partner will need to demonstrate proven expertise to:
  1. Deliver impact evaluations employing randomized controlled trials and quasi-experimental methods. The supplier should either offer the full spectrum of activities from design, working with in-country partners and FCDO central office, data collection, analysis and evaluation writing or have strong abilities in one or more parts of this chain and the ability to contract out the remainder to offer FCDO an end-to-end service.
  2. Enable course correction and adaptive learning in programmes.
  3. Be agile and able to harness cutting edge expertise to support the application of innovative technologies and approaches at pace in response to FCDO’s requirements.
  4. Drive uptake of impact evaluation evidence including through expertise in effective communication to non-technical audiences.
  5. Manage/build effective networks to support delivery of the work.
  6. Carry out follow up studies, potentially including where possible working with the organisation that originally conducted the impact evaluation.
  7. Build capacity in government agencies related to impact evaluation.
  8. Carry out effective project/ programme and financial management and reporting in accordance with FCDO’s requirements.
2. A partner or consortium will need to be able to demonstrate that they can develop and implement multiple impact evaluations across a broad thematic spectrum, working closely with FCDO policy teams and advisors. Other core capacities will include:
  1. Ability to adapt to new priorities/areas and evidence, including scale down or up depending on demand, need and available budget.
  2. Ability to maintain a) core technical team/consortium to deliver the objectives; provide credible, world-leading expertise; and collaborate with FCDO technical leads and PRO/SROs; b) flexible pool on demand: to respond to FCDO’s rapid needs and changing priorities; and c) specialist functions: for strategic uptake and lessons sharing; and capacity building of FCDO staff.
## Performance management
1. FCDO together with the implementing partner will establish a set of indicators for monitoring progress in the delivery of outputs, dissemination of these outputs and their use, with annual targets. FCDO will monitor progress against these targets continuously and formally assess this on a quarterly basis.
2. SIEL’s payment structure will support performance management. FCDO will pay in arrears, or at least not in advance of need, and the approval process will involve checks on quality and timeliness of outputs. FCDO has mechanisms to manage underperformance, including reducing payments.
3. Payments could include a mixture of output-based payments and payments for time and expenses, depending on the agreement with the implementing partner.
4. Further details of the Financial and management arrangements for SIEL are contained in the Annex, Part 2.
## Call for proposals process, budget and funding arrangement
1. Organisations should complete the Call for Proposals Response Form published alongside this document and send to Jonathan Stern and David Currie (email addresses at end of this document). Depending on responses received, FCDO may select a partner/consortium after this stage or request more detailed information from shortlisted partners.
2. Organisations can submit solo or as a consortium. If submitting as a consortium the proposal must come from the lead partner and list all implementing organisations, including details on what each organisation will deliver.
3. The total budget for the chosen partner to deliver these components is £13m over 7 years, with the possibility of extension for a further three years subject to approvals. Further details on the envisaged allocation of this funding between components and funding types can be found in the Financial and Management arrangements section in the Annex. Proposals should include an indicative cost breakdown, and may wish to draw on the template and guidance on the Accountable Grant Arrangement: budget template and guidance website at gov.uk.
4. Proposals will be assessed against the following criteria:
  1. Potential to work with FCDO programme and policy teams and deliver impact evaluations to the standard of the international frontier (25%).
  2. Potential to deliver follow-up studies of already completed evaluations (20%).
  3. Ability to develop FCDO capabilities for designing, procuring, and managing and being intelligent customers of IE studies (20%).
  4. Potential to deliver an adaptive, programme responsive learning agenda and to effectively disseminate and use this evidence to influence FCDO and partners’ interventions (20%).
  5. Ability to deliver on time and to budget, managing cost drivers and responding at pace to deliver Value for Money (15%).
5. All proposals should set out the core staff they will provide, including cost in addition to the range of expertise (technical, thematic, geographic etc) which they are able to draw on. This information will be used as part of the assessment against the above criteria. For further details of FCDO’s expectations for SIEL see the Annex to this Call for Proposals.
6. Although the Annex to this document should be seen by potential bidders as a guide, we welcome innovative proposals and where justified FCDO will be flexible in how we achieve the objectives of SIEL through a partnership with the chosen implementer.
7. FCDO may invite bidders to clarify aspects of their Proposal prior to making a final selection. We also reserve the right to invite bidders to an evaluation meeting in which we may ask for further presentations.
8. Following the selection of a winning proposal from this Call for Proposals exercise, FCDO will work with the chosen bidder to draw up an Accountable Grant or Memorandum of Understanding to deliver the programme over the period 2023-2030.
9. FCDO does not guarantee that any of the Proposals received will be taken forward, and if none meet our requirements, we reserve the right to revise the programme and/or the procurement process to meet the aims set out in this Call for Proposals.
10. The envisaged timeline for 2023/4 is as follows:

## Timeline (Indicative)
4 July 2023	Call for Proposals Window Opens
20 July 2023	Window for clarification questions Opens
11 August 2023	Window for clarification questions Closes.
25 Aug 2023	Call for Proposals Window Closes
8 September 2023	Winning Proposal chosen.
29 October 2023	Accountable Grant or Memorandum of Understanding in place with chosen Partner
November- December 2023	Inception period in which programme of work will be agreed
January- March 2024	Initial phase of work with workshops to determine evidence gaps for SIEL to address and identify evaluation questions.

Please contact Jonathan Stern (Jonathan.Stern@fcdo.gov.uk) or David Currie (David.Currie@fcdo.gov.uk) should you have any questions or concerns. Any response will be anonymised and shared with all potential bidding parties. To facilitate this, requests for clarifications may only be accepted until 11 August 2023.
# Annex: Programme Details
Programme Specification

# WHAT WILL SIEL DO?
SIEL aims to achieve an Impact Evaluation portfolio which provides greater value for money for FCDO through three key outputs:

Strategic and rigorous Impact Evaluations (IEs)
1. SIEL will contribute to the evidence base in under-evaluated areas through impact evaluation studies. It will answer critical evaluation questions which speak to FCDO objectives, filling internationally recognized gaps in the evidence base.
2. SIEL will de-link FCDO’s evaluation budgets from programme budgets which will enable impact evaluations for smaller programmes without compromising the resources available to those programmes. Furthermore, through SIEL, FCDO will be able to spend evaluation resources outside the lifecycle of the programme: before a programme starts (for example to test alternative delivery strategies before scaling-up) and after a programme is finished (for example to assess-long term impact of an intervention).
3. SIEL will trial innovative methods where appropriate. For example, the experience of the Centre of Excellence for Development Impact and Learning (CEDIL) programme suggests that structural models and machine learning, as well as qualitative methods, can combine well with experimental methodologies to build understanding of how and why an intervention works or does not work.[2]
  [2] Masset E, Rathinam F, Nath M, Vigneri M, Wood B 2019 Successful Impact Evaluations: Lessons from DFID and 3ie. CEDIL Inception Paper No 6: London
4. SIEL will support rigorous and evidence-based adaptive programme support. This could include ex-ante data collection for diagnostic purposes, lab-in-the-field experiments for proof of concept ahead of programme initiation, and nimble adaptive trials testing the best delivery options before scaling-up. This will improve the effectiveness and efficiency of programmes collaborating with SIEL.

Follow-up evaluative activities to assess programmes’ impact and sustainability in the long-run.
1. SIEL will make it possible to carry out follow-up studies in areas of strategic priority for the organisation. These may be desirable where:
  1. Programmes have been impact-evaluated at closure, but there is lack of evidence around the persistence of the effect; or,
  2. Programmes are expected to produce long-run impacts which are not fully realised at closure (for example, education programmes targeting primary school children and aiming to improve their future labour-market outcome(s)).
  3. Follow up evaluations have the potential to fill evidence gaps in FCDO priority areas.
2. It is customary for IEs to measure impact on short-term outcomes as a proxy for longer-term changes based on a theory of change. SIEL will generate robust evidence of the long run impact of programmes by using data from already closed programmes, applying impact evaluation techniques.
3. We anticipate criteria for selection of these studies to include quality of the original IE design, likelihood of success in recontacting intervention beneficiaries and respondents, alignment with FCDO strategic priorities, ability to address evidence gaps as well as to influence future programmes and policies.
4. Where possible we will seek interested partners to co-finance these follow up studies to leverage FCDO’s funding and increase the potential take-up of their findings.

Capacity Building, Engagement and Dissemination
1. SIEL will build capacity in FCDO through a dedicated technical support component for FCDO staff. This could include:
  1. Engagement with FCDO’s advisory cadres (with a focus on evaluation) to build the technical skills to advise on, commission, interrogate and manage future impact evaluation studies.
  2. Workshops and engagement with policy advisors and other cadres designing programmes to build their understanding of what impact evaluation can offer, how and when to consider it and seek support to design it into a programme. This should include Senior Civil Servants to strengthen cultural commitment to IE within FCDO.
2. SIEL’s ultimate aim is to influence programme and policy design both within and outside FCDO, including at the global level. Following the model of the Centre of Excellence for Development Impact and Learning (CEDIL),[3] SIEL will have a research uptake and communication workstream, and the SIEL partner will be required to allocate staff resources to this, including a research uptake lead.
  [3] Centre of Excellence for Development Impact and Learning CEDIL (cedilprogramme.org)
3. Like CEDIL, SIEL will require the Implementing partner to produce a stakeholder engagement and evidence use plan (or to include this within a broader Evidence and Learning plan), including communication products and activities as key deliverables (see Annex 2- indicative logframe). CEDIL’s 2022 Annual Review indicates the programme achieved a high degree of engagement through attendance at online seminars and through social media using such an approach.
4. SIEL will involve ongoing engagement with decision makers including Senior Civil Servants to build strong ownership and understanding of its findings.
#### How will this be achieved?
1. The inputs required to achieve these outputs are funding, technical and policy skills and a governance structure in FCDO centred on the Evaluation Unit.
2. The funding to deliver the SIEL programme is £13m over seven years. Since impact evaluations are an R&D activity, this will principally be capital budget, from Official Development Assistance, but non-ODA budget will be included for evaluation of influencing or other activities that do not classify as ODA eligible spend. For further details see the Financial and Management Arrangements section below.
3. SIEL will provide access to evaluation specialists with deep expertise not only in IE methodologies but also in the thematic areas where SIEL will operate. Deployed to support programme teams that are considered an appropriate match, the IE experts will work on developing evidence for an intervention from design to closure. Their role will be to:
  1. Support FCDO in identifying evidence gaps and questions for SIEL to target.
  2. Engage with FCDO programme teams, policy makers and advisors to build understanding of and demand for impact evaluation, leading to a pipeline of expressions of interest to be developed into full impact evaluations.
  3. Develop an Evidence and Learning plan for interventions and wider uptake of that evidence- this sets out what evidence will be developed to improve VFM as the programme is rolled out and also to assess the final impact of the intervention;
  4. Co-design impact evaluation studies and related data collection and management together with FCDO teams and implementing partners. This could include supporting theory of change development;
  5. Draw from a network of thematic and evaluation experts (academics, data scientists, etc) including those from the relevant country(ies).
  6. Ensure ethical approval is obtained and that inclusive data protocols and strategies that ensure safety and security of respondents and enumerators are developed;
  7. Procure data collection services where needed;
  8. Conduct data analysis and write evaluation reports and briefs;
  9. Engage with FCDO programme teams and programme implementing partners to ensure IE findings are understood and implemented where appropriate;
  10. Contribute to wider dissemination of IE findings and policy implication beyond FCDO.
  11. Build capacity in FCDO to understand, commission and deploy impact evaluation studies.
4. Evaluation Unit (EVU), a team of evaluation specialists located in the Economics and Evaluation Directorate, will manage the SIEL programme. In collaboration with partners in Research and Evidence Directorate (RED) and relevant experts, they will decide what to evaluate and how.
5. Evaluations will be chosen following a three-step process:
  1. Firstly, the Evaluation Unit together with the Implementing Partner will identify evidence gaps and high-level evaluation questions related to strategic priorities for the department through expert consultations and workshops.
  2. Secondly, outreach and awareness raising with programme and policy teams will follow, which may inform changes to the questions and evidence gaps.
  3. Thirdly, expressions of interest will be invited from policy and programme teams at Concept Note stage (or equivalent) in multiple rounds. The SIEL Steering Committee will then choose which evaluations to finance based on their strategic relevance, potential to fill an evidence gap, relevance to upcoming policy decision-making, feasibility, and additionality. The goal of the SIEL Steering Committee and this process is to maximise the Value for Money of knowledge generated through the programme. For further details see below, and a worked example in Box 1.

# HOW WILL SIEL SELECT AND DELIVER IMPACT EVALUATIONS OF FCDO INTERVENTIONS?
Figure 1: SIEL operational model
Engagement and influencing

1. FCDO identifies strategic priority areas evidence gaps and questions, through thematic workshops
2. Outreach to policy/ programme teams
3. Bidding windows open and evaluations selected
4. Research teams formed and evidence, learning and data plan developed
5. Data collection procured (if needed) and evaluation conducted
Figure 1 summarises the process envisaged for SIEL by FCDO. The process is envisaged in three stages:
  1. Identifying Evidence Gaps relevant to Strategic Priority Areas
1. As a first step, Evaluation Unit, facilitated by the Implementing Partner and in consultation with relevant stakeholders, identifies a set of thematic areas from FCDO’s strategic priorities where evidence gaps could be filled through investment in impact evaluation. Strategic priorities are identified in FCDO’s International Development Strategy (2022),[4] Integrated Review Refresh (2023),[5] and Country Diagnostics exercises. Evidence Gap Maps and systematic reviews from 3IE and others could also inform this process, in addition to FCDO’s Best Buys.
  [4] UK government's strategy for international development - GOV.UK (www.gov.uk)
  [5] Integrated Review Refresh 2023: Responding to a more contested and volatile world - GOV.UK (www.gov.uk)
2. The implementing partner will then facilitate workshops on a discrete number of thematic areas to produce a refined set of evidence gaps and evaluation questions. These workshops will draw on academic knowledge, the Best Buys and other Evidence Gap Maps in conjunction with a practical perspective from policy makers about what is needed to improve the quality of programming and activities in FCDO. The Implementing partner may also contribute evidence synthesis and expertise to the evidence gap identification process.

  1. Outreach to policy/programme teams.
1. Once evidence gaps and high-level questions have been identified, the Implementing partner together with FCDO’s Evaluation Unit (EVU) will carry out outreach to programme teams to engage them in SIEL, using the network of Heads of Profession (HOPs) in FCDO to identify possible programmes to target, as well as engagement with Heads of Mission and Development Directors.
2. The Implementing partner will conduct seminars with programmes at design (Concept Note approval) stage. These seminars will raise awareness of the evidence gaps and questions identified in stage i) and potentially garner feedback for some further refinement of the questions. Principally, they will build demand from policy/programme teams, highlighting the opportunity to learn ‘what works’ and to make a programme distinctive and lead to better future programming. They will also ensure teams are aware of the timing and requirements of impact evaluation, including building in the study at the outset and carrying out randomisation of the intervention and/or data collection. This involves the programme team ceding some control of the intervention to the research team, and spending considerable time engaging with them in return for robust evidence which will inform better VFM.

  1. Call for Expressions of Interest
1. After seminars and outreach, EVU together with the Implementing partner will launch a call for Expressions of Interest (EOIs) for each thematic area inviting FCDO programme teams to submit a short 5-6 page proposal for their programme. The high-level evidence gaps and questions identified in i) will be clearly set out in the Call for EOIs. Bids should indicate the proposed evaluation topic and question(s) including a high-level indication of methodology, how the IE will fill an identified evidence gap and/or question; and how results will be used by the programme team (and more broadly) to inform programme and policy decisions, including key deadlines or policy decision points.
2. Projects will then be selected by a team of reviewers from Economics and Evaluation Directorate, Research and Evidence Directorate and the Implementing partner, potentially with an expert from the Evaluation Quality Assurance Service (EQUALS) service[6]. Criteria are likely to include (but not be limited to) strategic relevance, meaningful contribution to the evidence base, relevance to upcoming policy decision making, feasibility and an assessment of additionality, meaning the evaluation would be unlikely to go ahead in the absence of SIEL due to the size, novelty, topic, or other unique feature(s) of the programme. Box 1 gives a hypothetical example of how a programme and question might be chosen.
  [6] The EQUALS service provides independent QA and advice to FCDO evaluations on an ongoing basis.

Box 1: Illustrative example of evaluation question development / FCDO’s International Development Strategy (2022) and Integrated Review Refresh (2023) identifiy climate change as a major priority. FCDO’s internal synthesis product, the Best Buy for Climate Change (2019) identifies a number of areas with mixed or low evidence in the area of Climate change adaptation, including climate smart agriculture, irrigation and community based adaptation. / Firstly EVU in collaboration with RED and other stakeholders, supported by the Implementing partner would hold a workshop to consider areas of focus for the SIEL programme. It is possible climate change could emerge as one of a number of thematic priorities for SIEL. A second workshop could then focus on climate change mitigation and adaptation. In this workshop FCDO experts, policy makers and relevant external actors could consider the Climate Best Buy and complementary products including evidence gap maps and synthesis products and select where they think the greatest evidence gaps lie. Hypothetically, they could decide that these are in climate smart agriculture and community based adaptation but that recent/ other studies have filled the gap on irrigation. They would produce a set of high level evaluation questions, e.g: / Which climate smart agriculture interventions are effective and why? / What approaches to promoting them are most cost effective? / Are there combinations of climate-smart practices which are more cost effective than the sum of their parts when combined? / In stage ii) policy/ programme teams designing climate adaptation interventions would be called to a seminar, using the HoP networks, SCS and EVU’s networks across the department. Those with climate smart agriculture and community based adaptaiton interventions would be particularly targeted (amongst other identified gaps from stage i). The meeting would then involve a conversation between practitioners and impact evaluation/ evidence experts which would build understanding of impact evaluation and demand from programme teams to participate in SIEL. / Following this seminar, EVU could put out a call for Expressions of Interest, inviting those teams that attended to submit a bid. The programme teams would then propose their own evaluation questions, which would need to have some alignment with stage i) identified questions to be selected but might also further develop the questions, considering the particularities of their programme and the evidence needs of their area. The list could include (hypothetically): / Is no-till agriculture cost effective in the Horn of Africa? / Which is more effective for reaching farmers with information about improved practices- SMS, radio or field schools? / Is it more cost effective to combine promotion of no-till farming with intercropping and mulching or are the approaches as cost effective on their own? / The selection panel for SIEL would then meet, and select EOIs and evaluation questions to take forward in that round. These would be further developed when research teams are formed around each selected impact evaluation, resulting in a final set of evaluation questions.

Should an intervention be selected for a SIEL impact evaluation, EVU will agree clear roles and responsibilities with the FCDO programme team setting out expectations for the duration of the programme and the evaluation, which would be signed off by a Senior Civil Servant. In the case of programmes, EVU will require the team to include a summary of the evaluation plan(s) worked out at design stage in the final Business case for the programme. Depending on the response to the first bidding round, additional bidding rounds could respond to priorities as they arise. However due to the need for impact evaluations to run over the lifetime of a programme to evaluate its full impact, evaluations starting after year 3 of the programme would likely need to focus on short-term/ nimble RCT studies and/or follow up studies. The diagram in Figure 2 illustrates the SIEL operational model.

  1. Delivery of Impact Evaluation Studies

1. The implementing Partner is expected to possess substantial in-house impact evaluation expertise that covers FCDO’s priorities, in addition to capacity building and research dissemination, such that they could conduct the major elements of the programme themselves. However external collaboration is expected and required as detailed below, and the implementing Partner could also form a consortium with other organisations to achieve the required coverage to deliver on FCDO’s priorities.
2. Once programmes that constitute a suitable match for SIEL are identified by steps i-iii) above, research teams to conduct each study are formed by the implementing Partner. These teams will each have a lead researcher from the implementing partner’s pool of experts which could include academics, researchers, and experts in the field. The implementing partner will be expected to leverage their network to bring on board relevant complementary expertise to conduct the study. Qualitative work and other methods e.g. structural models, machine learning could have an important role in shedding light on how and why the intervention worked. It is important that the relevant expertise is brought on board at design stage to shape the IE.
3. Following a co-production model, the implementing partner’s research team will work together with FCDO programme teams to develop their theory of change and an Evidence and Learning Plan which will include at its core the IE design and data strategy. This document will also set out the way ahead for the study implementation and for stakeholder engagement.
4. When suitable, use of innovative sources of data that do not require face-to-face data collection will be explored and tested (for example geo-satellite, web-scraped or social media data). If data collection is needed, the implementing partner will procure and manage this. The partner(s) will be responsible for data protocols, safety and security and to make sure they conform with FCDO guidance and policies. They will also be responsible for ensuring each IE study receives ethical approval and that research protocols and design are adhered to.
5. We envisage an active collaboration between the research team, the programme team and implementing partner(s) during intervention delivery.
6. We want to promote an Impact Evaluation model that goes beyond measuring impact at the end of an intervention, by providing an embedded learning function, generating the right evidence at the right time to inform delivery. Therefore, the Evidence and Learning Plan will also allow for generation of evidence to inform programme adaptation and decision making. This approach is informed by DIME’s ‘Trial and Adopt’ agenda, which Legovini et al (2015) show contributes to improved delivery efficiency. We expect the SIEL implementing partner to be adaptive themselves, seizing opportunities for evidence generating activities (e.g., nimble RCTs, experimental games) that could help optimise the delivery of the programme as they arise.
7. Engagement and policy and programme influencing activities need to happen on an ongoing basis. This is to make sure that SIEL evidence feeds into decision making through the lifecycle of programmes and to ensure that IE studies are seen by programme teams and implementing partners as an integral part of delivery.
8. The implementing partner must provide dedicated resources for ensuring engagement with key stakeholders around each IE, liaising between FCDO Evaluation Unit, Programme teams and implementing partners, SIEL research teams and any other stakeholders we would like to influence through IE studies. A robust stakeholder engagement and communication plan should be developed as part of the Evidence and Learning Plan.

Figure 2: SIEL operating model for delivering Impact Evaluations under Options 2 & 3

Evaluation design
Baseline data collection (if needed)
Evidence shared and discussed

Delivery adaptation decision made

Delivery adaptation implemented

Data collected and analysed

Endline data collection
Analysis reporting dissemination
Before intervention delivery:
- Engagement with policy/ programme teams to build interest, Expressions of Interest and Selection of studies to take forward by Steering Committee.
- Collaboration with programme in developing Theory of Change
- Evidence and Learning Plan to include:
- Research questions and methodology
- Data strategy, tools and protocols.
- Pre-analysis plan, to be registered in advance.
- Ethical approvals
- Stakeholder engagement and Evidence Use plan.

During intervention delivery:
- Real-time monitoring, when suitable using innovative sources of data (geo-spatial, social media, etc.);
- Nimble & adaptive RCTs to test delivery options;
- Policy and wider stakeholder engagement and feedback;
- Mid-line data collection and evaluation (if appropriate).

After intervention delivery:
- Data analysis;
- Evaluation report, Working Paper and policy briefs produced and QA’d;
- Publication in peer-reviewed journal where appropriate
- Results discussion and dissemination;
- Data anonymised and made public.

Evidence-based policy engagement and influencing activities through the lifetime of an IE study.
#### Follow Up Studies
Figure 3 shows the envisaged operating model for SIEL to identify and conduct follow-up evaluations for already concluded programmes. Suitable IE studies could be identified through a mixture of a bidding window made available to advisors in FCDO and/or the use of Management Information (MI) data to identify IE studies that have recently concluded or about to be concluded (at the earliest, endline data collection should be happening), leading to a direct approach from EVU to the relevant advisor(s).

Figure 3: SIEL operational model for follow-up evaluations.

1. Concluded IE studies using RCT or quasi-experimental methods identified
Original evaluator offered follow up opportunity
3. Follow-up studies selected and design finalised
4. Data collection procured and study conducted
2. Call for proposals for follow-up studies open
Workable
Not workable
1. For follow-up studies the design, data strategy and identification of respondents (which cannot be shared with other organisations for security reasons) is usually held by the institution that conducted the original IE. Therefore, the best VfM option is to invite the research teams who conducted the IE in the first place to also conduct the follow-up study.
2. EVU together with the implementing partner will engage Programme and country teams to build policy demand for follow-up studies.
3. Proposals will be reviewed by a panel composed by Economics and Evaluation Directorate, Research and Evidence Directorate and SIEL implementing partner and selected based on pre-agreed criteria that will be defined in collaboration with the implementing partner. We anticipate criteria to include quality of the original IE design, likelihood of success in recontacting intervention beneficiaries and respondents, alignment with FCDO strategic priorities, ability to address evidence gaps as well as to influence future programmes and policies.
4. Once follow-up evaluations are identified, research teams leading the studies are responsible for making sure that ethical approvals are updated, data protocols and strategies are revived and data collection services are procured to conduct the follow-up studies. Research teams will also be responsible for making sure the follow-up evaluation reports are drafted and finalised incorporating FCDO comments, policy briefs are produced and results are disseminated. Since the programmes that delivered the intervention are likely closed, Evaluation Unit will make sure evaluation reports are Quality Assured, internally communicated, and made public.

# THEORY OF CHANGE (ToC)
1. The programme’s ToC aims to address the following key issues:
  1. IEs are not systematically happening in areas of strategic priority for the organisation and/or where the evidence gap is larger;
  2. To conduct an impact evaluation, dedicated technical expertise is needed from pre-pipeline stage; not all teams have this expertise available, and
  3. Evaluation budget is linked to programme budget, meaning that rigorous impact evaluations are only happening in programmes with a more generous budget. But this is not necessarily where interesting evaluation questions are.
2. To overcome these issues, the SIEL programme will provide dedicated expertise and funds.
3. Once strategically relevant programmes for collaboration with SIEL have been identified, technical support will be flexibly deployed to help develop the Theory of Change (ToC) for the programme or activity and identify key assumptions and supporting evidence. This will create a better, shared understanding of what the programme aims to achieve and identify key gaps where there is little and/or anecdotal evidence supporting assumptions.
4. An impact evaluation provides evidence of whether the theory underlying the intervention(s) was right and holds true in the operating context of the intervention. I.e., an IE will tell if the programme worked and “how much” it worked. It can also enable estimation of cost-effectiveness of activities.
5. To maximise VfM of programmes and to ensure validity of IE results, SIEL will promote an adaptive approach to programme management and IEs: the programme will evaluate the overall impact of the intervention but before that it will also make sure the intervention is made as effective as possible through adaptive learning.
6. To achieve this, technical experts will support programme teams to develop not only the overall IE design for the programme (or one or more of its components) but also an evidence and learning plan to generate evidence needed at the beginning and along the lifetime of the programme to enable evidence-based, adaptive decision making able to maximise VfM of the intervention along its life-cycle.
7. Publishing IE results and pro-active communication and dissemination of findings will give the opportunity to influence programmes and policies operating in strategic areas of FCDO interest on a global scale. This will not only magnify the impact of IE investments, but it will also develop UK’s reputation as a science power and an evidence-committed force for good in the world.
8. The Theory of Change described here is summarised by Figure 4 below:
Figure 5: Theory of Change for SIEL

Financial and Management Arrangements
#### Source and Type of Funding
FCDO will assign up to £13m of CDEL research funds, over seven years from April 2023 to March 2030, including up to £2.5m of non-ODA. The programme will also have the option to apply for a costed or no-cost extension for a further three years, to March 2033, subject to the appropriate approvals.

#### Cost Profile and Disbursement of Funds
An indicative cost profile for SIEL is as follows:
Table 5: SIEL indicative spend profile. Figures in Pounds Sterling (£)
Year	2023/4	2024/5	2025/6	2026/7	2027/8	2028/9	2029/30	%
Overheads/ administration	35,000	140,000	140,000	140,000	140,000	140,000	175,000	7%
Impact Evaluations	300,000	1,200,000	1,200,000	1,200,000	1,200,000	1,200,000	1,500,000	60%
Follow up studies	75,000	300,000	300,000	300,000	300,000	300,000	375,000	15%
Capacity building and dissemination	75,000	300,000	300,000	300,000	300,000	300,000	375,000	15%
M&E	15,000	60,000	60,000	60,000	60,000	60,000	75,000	3%
Total	500,000	2,000,000	2,000,000	2,000,000	2,000,000	2,000,000	2,500,000	13,000,000
Of Which non-ODA	400,000	400,000	400,000	300,000	300,000	300,000	400,000	2,500,000

1. The first year will mainly comprise procuring the programme and setting up the new evaluation function, including carrying out workshops to identify priority evidence gaps, build interest and identify an initial portfolio of projects to evaluate. From year two, there will be heavy impact evaluation activity as the bulk of the work on study design and engagement will be carried out in Years two and three. Year two may also feature more capacity building work. From years three and four there will be more of a focus on nimble evaluations and follow up studies that can be delivered within year, and years five to seven will feature analysis and reporting on the evaluations.
2. The choice of funding model will depend on the chosen supplier(s) and any constraints on their way of working but will be consistent with FCDO policies. Funds could be disbursed through a hybrid of output/ deliverable based payments and costs for time and expenses, for example to cover travel and/or staff overheads. FCDO will agree with the implementing partner during the inception phase whether monthly invoicing is required; FCDO’s preference here is quarterly. The approval process will include checks on quality and timeliness of outputs.
#### Currency and taxes
All financial commitments will be made by FCDO in sterling. Downstream partners will be expected to monitor and make provisions for potential exchange rate movements over the life of their projects.
#### Break points
FCDO will include a break clause in the agreement/s at the end of the 2024/5 financial year to reserve the right to revise or discontinue the programme funding beyond this point in line with Spending Review limits, FCDO needs and priorities. This approach is in line with current FCDO PrOF guidelines (for approval processes) and has been used for a range of FCDO research funding mechanisms.

#### Monitoring and financial risks
1. The FCDO programme team will undertake a due diligence assessment before disbursing any funds to obtain the necessary assurances.
2. FCDO will analyse financial reports and review invoices to ensure consistency with agreed budget, progress and VfM.

#### Exit Strategy
1. Major delivery, operational, external context, safeguarding, financial, fiduciary or reputational issues may trigger consideration of early closure of the programme. In these cases, FCDO will review the range of available options, which include continuing, pausing, scaling back, adapting, or closing the programme, the likely impacts of these options, including on value for money, and the potential risks and their mitigation.
2. Elements of an exit plan should be included in proposals at the bid stage , focussing on maximising the learning from the impact evaluations for the long run, after the programme has closed. This will be developed further at inception of the programme.