Annual Review - Summary Sheet (Programmes Under £1 million)

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Energy and Low Carbon
Programme Value: £20m / Status (delete as applicable) Transition Funding		Review Date: 15 May 2019
Programme Code: PF IND 924001	Start Date: April 2017	End Date: March 2020

Summary of Programme Performance
Year		2017-18	2018-19
Programme Score		A	A
Risk Rating		Minor	Minor

Programme Outcome (use the exact wording from the approved Outline Business Case or Concept Note as appropriate)
Contribution to the portfolio level Primary benefit outcome Improved conditions for sustainable and inclusive growth in India through / Improved policy and business ecosystem and stronger and more efficient energy markets in India / Additional investments in cleaner energy delivers for women and men (target of £2.5bn by 2025) / Contribution to portfolio level Secondary Benefits outcome Mutually beneficial economic relationships are developed in sectors where the UK has a comparative advantage. International, including UK, and Indian companies find it easier to trade and invest. through / Enhanced engagement by international and UK firms in India’s energy market (reflected in £150m additional business for UK firms; £1bn investment opportunities unlocked for UK capital; and additional UK and international firms enter the Indian energy market)
Progress towards Programme Outcome. Do the Outcome Statement and associated indicators remain appropriate? Are any significant changes to programme design proposed (eg: outputs, budget, and timelines)?
Progress: / The early phase of this programme has yielded some strong and promising progress. There has been no significant change in the external environment that has undermined the essential theory of change. / Progress has already been made towards the Programme Outcome during the Annual Review period, with concrete results achieved using very small amounts of funding. Strategic programme delivery mechanisms have evolved in ways that have exceeded expectations, including agreement of £14m additional co-funding by GoI on Power and Renewables elements to make the initiative a genuine collaboration. / Securing co-funding in this way is a substantive indicator of early progress on partnership (output 2) and co-ownership that provides a new model of Prosperity Fund working and significantly increases prospects for relevance and sustainability. The collaboration is robust, backed up by formal G2G processes (Joint Working Groups etc) and accompanied by a ministerial Energy Dialogue. / Changing the funding model to a joint India-UK funded approach has necessarily involved extending the timeframe for finalising approvals, with implementation of Tranche 1 initiatives now expected by end 2019, but this is judged to be well worth the expected added value, and complementary delivery channels have been actioned to provide early mechanisms for implementation (e.g. IEA collaboration). : / Measurable results contributing to primary and secondary benefit outcomes have been delivered, largely through targeted Tranche 2 projects. These include: / One specific policy reform (Revised National Mission on Enhanced Energy Efficiency) and one operational GoI process has been improved (contract management for gas). / 2MW equivalent of new energy capacity has been delivered through early pilot activity (Knowledge Exchange Platform KEP) in seven energy-intensive industrial sites. This translates into financial savings of £1m during just three months of the associated £47,965 value project and an additional £3m worth savings in the subsequent 1.5 years post project conclusion. Spill over and demonstration effects are expected from this early pilot, with plans in place to provide substantial scale-up support to KEP. / £1.5bn worth green finance investment opportunities for UK capital providers were unlocked through just £50,922 value project support for issuance of Green Bonds by Indian companies at London Stock Exchange. / Targeted delivery mechanisms have been developed to support strategic delivery of programme outcome. These include the following: / Four T1 programmes with Government of India: / Programmes on Renewable Energy (with MNRE) and on Power (with MOP) with UK contribution of £7m each) are in advanced stages of approvals, and will each be match-funded by £7m each from UK and India. Programme design has been informed by a structured G2G process under the India-UK MOU on Energy Collaboration, involving two Joint Working Groups and three thematic Task Forces, to ensure these programmes match GoI priorities with UK capabilities. / A third bilateral Joint Working Group - on oil and gas - was instituted during the reporting period, which has set an agenda for collaboration that is currently being refined through a Tranche 2 project, supported by senior HMG visits. This is expected to result in identification of potential areas to be taken up under Tranche 1 programme of up to £5m PF contribution. / Working with the Urban PF Strand, approvals have been secured under a Joint Action Plan on Urban Development for collaboration on electric mobility. Our live T2 scoping project on electric mobility will inform design of a collaboration programme of up to £1m. This will be complemented by activity above with MOP and MNRE who are also important GoI actors on electric mobility. / Five T2 initiatives, two of which leverage existing UK-supported programmes cies: / Building on DFID India’s successful Power Sector Reform programme and working through existing delivery partners, a programme (with up to £1m PF contribution) to catalyse additional investments in clean energy by Indian Railways - India’s largest energy consumer and the world’s eighth largest employer. / Resources (up to £2m) to scale up the UK-supported Clean Energy Transitions Programme of the International Energy Agency (IEA) and to enhance IEA technical assistance to India on energy security. / One new Chevening Fellowship on Energy to build the capabilities of a targeted cadre of next generation decision makers in India. / Support to realise India’s demand for World Bank technical assistance on priority areas like designing investment opportunities for battery development. / Support to operationalise the newly instituted India-UK Green Finance Forum Secretariat to develop the green finance market. / Establishment/strengthening of three private sector networks to support delivery over next 4 years: These include establishment of a new Corporate Green Leadership Alliance to catalyse investments by large corporates into cleaner energy; strengthening of the existing UK-supported Knowledge Exchange Platform to drive industrial energy efficiency through policy advocacy and best practice sharing including with UK businesses; and establishment of the UK-India Green Finance Forum to unlock opportunities for UK-based green finance providers. / Changes to Programme Design: No significant changes to the programme design in terms of outputs and budgets are proposed.
Were all the Outputs delivered as planned, with the planned results? If yes, please note the result. If not, please explain. Include gender and inclusion dimensions.
Output Number[1]	Progress			Output Score
Evidence against policy papers, research, recommendations and roadmaps developed and socialized, that align with national/ state priorities and include gender and inclusion considerations (15%)	Policy outputs have been produced on 4 broad themes, with results in line or marginally exceeding expectations, including active influence on policy as well as production of a series of guidelines and recommendations. These include the following / Report on Industrial Energy Efficiency Market Potential that estimated energy savings potential and associated investments. Result achieved so far: Findings from this report informed the Government of India’s revised draft National Mission on Enhanced Energy Efficiency.) / Report on strengthening corporate green leadership in India by TERI which proposed solutions for scale up of corporate climate action. Result achieved so far: recommendations on creating a rating system for renewable energy developers is currently being operationalised by India’s Energy Transition Commission. / Draft Roadmaps for 4 states for Electric Mobility deployment, including gender and inclusion considerations. Result achieved so far: Strong state government demand to use Road maps to translate new policy into action through substantive technical assistance planned under the PF programme in years 3-5. / Status papers on Demand Side Management and Smart Grids for pan-India and 7 states have been developed and shared with policy and regulatory bodies at national and state level. These papers include recommendations for policy and market interventions needed to accelerate implementation. Result achieved so far: Strong state government demand to use recommendations to drive action through substantive technical assistance planned under the PF programme in years 3-5.			A
Strengthened partnerships through dialogue, delegations and active collaboration between diverse govt., private sector and civil society stakeholders at different levels which have shaped innovative programming (10%)	Results have exceeded expectations with a highly structured process of G2G engagement in place across all themes, and considerable depth of engagement across multiple stakeholders. / UK-India bilateral Energy for Growth partnership has been strengthened, through contributions to: / two ministerial Energy Dialogues / one Steering Committee on Renewables and Power (at PUS levels) / three Joint Working Groups / three technical Task Forces / multiple engagements in 6 states / ten delegations between the UK and India supported by or associated with the Energy PF programme, incorporating policy, innovation and commercial experts) / Results include: / Structured areas of collaboration agreed under formal G2G processes. / Active bilateral collaboration between policy, innovation, civil society and commercial actors on electricity markets, energy storage, energy efficiency, gas markets, electric mobility deployment of solar and wind, green finance. / Stronger relationships for collaboration at policy, technical and commercial level / Enhanced awareness both ways of opportunities in India’s energy markets and the nature of UK capability, and enhanced mutual interest in collaboration, including strong expressions of interest from senior State and central government officials. / Enhanced awareness amongst targeted Indian stakeholders of the potential opportunities of Prosperity-funded activity. / Development of concrete collaboration proposals / New knowledge/products matching India’s needs and UK capability created and communicated to relevant stakeholders at national and state levels in India, through Tranche 2 projects on oil and gas, electric mobility, Demand Side Management and smart grids. / Significant opportunities created for enhanced engagement by international/UK firms in India’s energy market. This included: / Support to India’s six large energy sector companies to prepare for Green Bond issuances, resulting in £1.5bn investment opportunities for UK based investors through bonds issued on London Stock Exchange. / 6 delegations of businesses and policy makers covering Power and Renewables sector (1), Electric Mobility (1), Industrial Energy Efficiency (1), Oil and Gas (2) and Green Finance (1) were facilitated through PF support, enabling showcasing of UK commercial solutions and networking with Indian players for partnership opportunities. Delegations included senior women representatives who participated in consultations at the state workshops. / Participatory energy audits and targeted workshops have been conducted to support six UK companies (Fairport, Grundon and Mechatherm, Power star, Bristol Blue Green and SEaB Energy) to test feasibility of their products/services at sites of Indian companies (e.g., Raymond, Arvind Textilies, Vedanta), leading to £4m savings.			A+
Increased capacity through tailored training and knowledge programmes in priority sectors for more inclusive and sustainable growth (10%)	Despite the early phase of programme delivery, three Platforms for increased private sector partnerships have been established/strengthened through PF support. These will be significant for catalysing private sector action necessary to deliver primary and secondary benefit outcomes. / A new Alliance on Corporate Green Leadership has been established that adds value by joining up existing industry-led coalitions. The Alliance will catalyse uptake of cleaner and more efficient energy solutions by the private sector. / The Knowledge Exchange Platform on industrial energy efficiency (established through PF support 2015-17) was further strengthened by support on widening membership, building advocacy capability and developing business plan for enhanced effectiveness. / A new UK-India Forum on Green Finance was launched with strong participation from influential UK and Indian member organisations and a well-developed scale-up plan. Through experience sharing, policy advocacy and investor-investee match-making services, the Forum will help unlock commercial opportunities for UK based players on green finance. / In addition: / Training in March 2018 in Delhi outlined a new streamlined IT tool for contract management for oil and gas operators (15) and government staff (10). Result achieved so far: The tool is being used and adapted by officials for monitoring Discovered Small Fields – India’s gas licensing initiative. / Seven field visits to industrial sites organised to enable technical personnel (cement, textiles and aluminium) learn and adopt best practices on energy efficiency practices and technologies. Result achieved so far: Capacity building initiatives by Knowledge Exchange Platform (KEP) amongst seven energy intensive units led to energy savings of £1m during the life of the projects and an estimated £3m worth savings after the life of the project (within 1.5 years of project implementation)			A
Best practice on inclusive and sustainable growth identified and shared, through testing/evaluation, dissemination, advocacy and knowledge exchange (10%)	14+ events on the policy, regulatory, technology and market development aspects of priority programme themes. / Renewable Energy – Representatives of electricity distribution companies across 5 states supported to share best practices in a Roundtable as part of ELECRAMA 2018, a major event in the energy sector. / Electric Mobility - 400 participants reached across government, private and academia out in 3 state level workshops. This has helped build better understanding among the relevant stakeholders on policy, technical and infrastructural requirements for deployment of electric mobility solutions, including from UK. Senior women officials from states actively engaged in the knowledge exchange workshops. / Industrial Energy Efficiency: 4 events organised (3 state level and 1 national) through KEP to facilitate best practice sharing on international energy efficiency technologies and services, including from the UK. / Corporate Green Leadership: 70 representatives from corporate sector and associated service providers supported with best practice sharing through 4 events. / Oil and Gas: 3 workshops held (in Sept 2017, March 2018 and July 2019) to share UK and international best practices with Indian regulatory and policy making bodies. / Access to best practice tech and expertise on energy efficiency in the cement sector enabled through new Mobile Application tool (‘DaKShaTA’) launched in 2018. Uptake: The mobile app has been installed by at least 500 industries. Scale out: GoI has requested the tool to be replicated for other industrial sectors.			A
Inclusive market development via demonstrating and testing new and innovative technologies/commercial models and development of projects/project pipeline (5%)	No substantive results expected in this early phase, but some promising early concrete results nevertheless delivered. / An information technology based tool has been developed to support better contract management by the regulatory bodies for monitoring gas contracts under discovered small fields. The tool enables more transparent and time-bound approval process for businesses. Result achieved so far: The tool has been adopted by the oil and gas sector regulator (Directorate General of Hydrocarbons) for two rounds of oil and gas block auctions (Discovered Small Fields Rounds 1 and 2). / Report produced on proposals on specific regulatory and market building initiatives to support green finance development in India. Result achieved so far: The recommendations of the report have been endorsed the India UK Forum on Green Finance and incorporated in the new stream of longer term work being finalised for PF support on green finance. / Supported technical and commercial feasibility assessment for 1 energy efficient smelter technology at the site of Vedanta Ltd, Jhasuguda. The technology is supplied by UK based Mechatherm Ltd. The potential investment in this technology is worth INR 84 crores (£9.3m). Result achieved so far: Commercial discussions ongoing between the two companies for deployment.			A
Effective programme development and approval, management, governance, procurement, contract management, coordination and learning systems in place (50%)	Approval of T1 projects is still pending due to changes in the external environment, but otherwise strategic programme delivery mechanisms have evolved in ways that have exceeded expectations, including agreement of £14m additional co-funding by GoI on Power and Renewables elements to make the initiative a genuine collaboration. / Securing co-funding in this way is a substantive indicator of early progress on partnership (output 2 above) and co-ownership that provides a new model of Prosperity Fund working that significantly increases prospects for relevance and sustainability. The collaboration is robust, backed up by formal G2G processes to ensure these programmes match GoI priorities with UK capabilities. These include 2 Ministerial Energy Dialogues, 1 Steering Committee meeting on Renewables and Power (at PUS levels), 4 Joint Working Group meetings (at UK DG equivalent levels in India) and 5 meetings of 3 focussed Task Forces. / Changing the funding model to a joint India-UK funded approach has necessarily involved extending the timeframe for finalising T1 approvals. Implementation of T1 initiatives is now expected by end 2019, but this is judged to be well worth the expected added value. / To front-load delivery through complementary channels, partnerships are being actioned that offer early mechanisms for implementation, including by building on existing UK-supported initiatives (see below). / Design of T1 programmes and delivery of early results above has also been enabled through strategic use of smaller T2 projects. Many of these have been scoping instruments for developing stakeholder buy-in at central and state level, informing T1 programme design and filling knowledge gaps that would otherwise have been expected to take place during T1 inception phase (hence streamlining implementation). / Summary of programme development: / T1 programmes with Government of India: / Renewable Energy and Storage (with MNRE) is in advanced stages of approval, and will be match-funded by £7m each from UK and India. / Smart Power (with MOP) is in advanced stages of approval, and will be match-funded by £7m each from UK and India. / Oil and Gas (with MoPNG). Up to £5m PF funding expected; design being refined through a live Tranche 2 project. / Electric mobility (with MoHUA under Joint Action Plan on Urban Development). Live T2 scoping project will inform design of a collaboration programme of up to £1m. This will be complemented by activity above with MOP and MNRE who are also important GoI actors on electric mobility. / T2 delivery initiatives: / Building on DFID India’s successful Power Sector Reform programme and working through existing delivery partners, a programme (with up to £1m PF contribution) to catalyse additional investments in clean energy by Indian Railways - India’s largest energy consumer and the world’s eighth largest employer. Implementation expected to start by August 2019 following conclusion of FCO and DFID approvals and Change Control process. / Resources (up to £2m) to scale up the UK-supported Clean Energy Transitions Programme of the International Energy Agency (IEA) and to enhance IEA technical assistance to India on energy security. Implementation expected to start immediately after IEA Governing Board approvals in June 2019. / Support to realise India’s demand for World Bank technical assistance on GoI priorities like designing investment opportunities for battery development. Implementation expected to start in October 2019 / T2 Capacity building initiatives: / One new Chevening Fellowship on Energy to build the capabilities of a targeted cadre of next generation decision makers in India. First Fellowships to start in 2020. / Three private sector networks to support delivery over next 4 years. These include establishment of a new Corporate Green Leadership Alliance (by August 2019) to catalyse investments by large corporates into cleaner energy; strengthening of the existing UK-supported Knowledge Exchange Platform to drive industrial energy efficiency through policy advocacy and best practice sharing including with UK businesses (implementation to start October 2019); and establishment of the UK-India Green Finance Forum to unlock opportunities for UK-based green finance providers (implementation to start October 2019). / Governance: / The SRO for the Energy and Low Carbon Strand is responsible for governance of the overall programme. / A Project Steering Committee for the two Tranche I programmes with MoP and MNRE respectively has been suggested. This Committee, comprising nominated GoI and FCO officials will oversee progress on activities and outcomes. Governance has yet to be decided for Oil and Gas programme. / For larger Tranche 2 sub-programmes with other delivery partners, Project Advisory Committees, with representation from FCO and respective delivery partners are being considered. / Smaller sized Tranche 2 programmes are governed on a proportionate basis with FCO Policy Lead and Programme Manager keeping an oversight on the progress through periodic review meetings and standard PF reporting procedures. / Procurement and Contract Management: 10 T2 projects have been procured to date in line with HMG mandatory procedures. Formal training and informal capacity strengthening has taken place across the FCO Energy Team to enhance skills on theory of change, logframe, commercial/procurement procedures, evaluation methods and MREL. Feedback mechanisms have been built in to address unsatisfactory delivery by suppliers.			B
How have you driven value for money?
The programme has achieved significant value for money results by securing a co-funding approach with GOI for 70% of the programme to date (power and renewables themes). Other elements of VFM include: / Economy / All live projects were procured through FCO commercial team according to open tendering. Procurement systems ensured selection based on both technically sound and financially competitive bids. Regular financial and performance controls in place to ensure robust programme and financial management. State-based Prosperity Advisers have been proactively involved to add value to programme management, strengthen local stakeholder engagement and minimize travel costs. / Most projects have achieved cost savings through contributions from businesses and industry associations/chambers of commerce, including to cover cost of travel and accommodation. / High level visits have been used strategically to advance programme design and delivery, and to secure additional resources for delegations and visits. / Spill over effects beyond the PF focal states have been achieved by spreading knowledge and best practice to other states, and encouraging non-PF states to self-fund their participation in project activities (e.g. involvement of Kerala state in electric mobility scoping project) / Efficiency / Joint programming through other PF strands – e.g. with Urban strand on electric mobility – has made an active contribution to overall delivery and pioneered new models of delivery for Prosperity. / Project teams have built on their previous project experience to identify barriers and engage stakeholders in programme activities. / Outputs and recommendations from Transition projects in 17-18 were used to inform new programmes (e.g. desk research with TERI was used to inform design of a more transformational Green Leadership Alliance) / Engaging wider HMG and other bilateral/multilateral actors in project activities has helped to reach more and better targeted stakeholders, reduced risks of duplication and exploited synergies. / Reporting mechanisms and regular update meetings with delivery partners built in to track risks, address delays and capture lessons. Learning sessions on process improvements have been instituted to drive performance. / Effectiveness / Scaling up platforms such as KEP has already resulted in £1 million efficiency savings for companies that participated. / Relationships and activities/outputs achieved through other UK-supported activity (e.g. DFID, BEIS) have been used to shore up Prosperity engagement, provide entry points, secure buy-in and take a strategic One-HMG approach to programming. / Adaptive programming (e.g. in Green Leadership, Electric Mobility projects) has responded to changing stakeholder priorities and needs and seized emerging opportunities in priority States at no additional cost. This has also boosted credibility and deepened relationships with States. / Gender and Inclusion: / Projects delivered to date have related to the overall aim of contributing to inclusive growth and followed compliance with the UK Gender Equality Act. Many projects are scoping/knowledge pieces that were found to be largely gender neutral in nature. Illustrative actions have been to: / proactively consult women-led enterprises and women respondents in project design, implementation and for framing recommendations; / integrate opportunities for women’s empowerment into knowledge and scoping pieces, e.g. case studies in Electric Mobility State Approach Papers. These will be reviewed by the state governments as they design and implement new policies and programmes; / disaggregate data by gender where possible; / proactively engage with MSMEs and their industry networks to identify the needs of smaller enterprises and how cleaner energy solutions can be driven through supply chains (e.g. Green Leadership Alliance project). / The focus going forward will be to develop metrics and hold suppliers for T1 and larger T2 projects accountable (using gender scorecard and other tools) for delivering against gender and inclusion criteria.
Financial Management
Annual Budget Allocation		Spending Outturn ( till 31 March 2019)	Variance (difference between planned and actual costs)
£446,454 / of which staff £		£431,692 / of which staff £	£14,672
Please explain any variance in planned and actual expenditure, where the difference is greater than 5%, including within themes or country allocations. Cover any changes in Prosperity Fund financed staffing.
The variance is less than 5% (3%) primarily to address delays in project completion and also due to projects still being in the implementation stage. T2 projects of 18-19 are still underway. Some activities were delayed due to state and national elections and longer negotiations to secure government approval, especially on joint funding arrangements.
What lessons have been learnt? Has any evidence emerged that might affect the theory of change or programme design/implementation?
The following key lessons learned will be used to shape ongoing design and implementation: / Importance of T2 projects to drive design of T1, maintain profile and momentum with stakeholders and fill knowledge gaps. / Energy Minister’s preference for a joint funded approach to build in genuine mutual collaboration. / Importance of closing knowledge gaps on India’s priorities and UK capabilities to inform programme design. Scoping work through smaller projects is important both for design/knowledge strengthening, but also for developing relationships with key stakeholders and building a constituency of like-minded partners. / Engaging senior officials in states is essential to secure buy-in and identify strategic priorities. / Do not underestimate the time and manpower needed to secure buy–in and consensus on collaboration themes and approaches. / Continued engagement and follow-up after the end of funding to small projects is essential to assess ongoing results and impacts. / An adaptive approach to programme design and implementation is needed to be able to respond to evolving and spin off opportunities. / Prosperity programming that contains both primary (ODA) and secondary (UK opportunity) objectives is more complex to design, and has to navigate grey areas regarding ODAbility and compliance with the UK’s IDA. Senior support is needed to provide space for experimentation and learning, and to defend approaches robustly. / Industry associations have strong convening power for engaging public and private sector stakeholders in India. / Structured involvement of FCO and other HMG (DIT) during implementation important to drive results and maximise positioning of the UK.
Risks and Issues: Any changes in programme risk or risk trends? Where risks have become issues what mitigating actions have been taken and how effective have these been?
Sensitivity to ‘aid to India’ by Energy Ministers has delayed approvals of programmes and led to a preferred path of joint funding. Mitigation has included embracing the joint funding approach as a opportunity and clearly communicating our new modern collaboration narrative. / Emerging political and public scrutiny in the UK of oil and gas collaboration threatens to undermine productive work in this sector that is vital for India’s energy security, economic development and ability to power an effective clean energy transition. Mitigation has included developing a stronger narrative on the compatibility of oil and gas partnerships with UK policy on climate change and decarbonisation. / Regulatory bodies and policy makers have been unwilling to share data with delivery partners. Regular focussed engagements with these organisations with FCO staff has helped get some leverage to seek data. / Changes in key interlocutors delay programme approvals. Early engagement with key stakeholders and development of complementary delivery channels has helped mitigate risks of delayed implementation. / The new Indian government that will be established after elections in May 2019 may have new or changing priorities, and buy-in to the programme will need to be re-affirmed. Mitigation has included close scrutiny of both main parties’ manifestos – both of which are supportive of the Energy programme themes – and early and regular engagement with new decision makers. / To avoid overlap or duplication of efforts, joint initiatives have been explored and regular coordination takes place with government departments and agencies, regulators, industry coalitions, think-tanks, funding agencies and other key stakeholders. / Limited commitment from UK stakeholders and regulatory bodies remains a risk to project delivery, including on Oil and Gas, requiring additional effort and staff. / Weak capacity of delivery partners in getting stakeholder buy-in, data access etc was mitigated through hand-holding partners, continuous engagement and oversight to drive results with value for money.
[1] List all the Outputs as stated on the approved Project Proposal Form