Programme Completion Review

Title: Better Health Programme
Final Programme Spend £ (full life): £36.5m	Review Date:	December 2022
Programme Code: Not on AMP	Start Date: / Aug 2018 / (OBC approval)	End Date: / December 2022 (Business Case end date)

Summary of Programme Performance

Year	19/20	20/21	21/22	22/23
Programme Score	A	A	B	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://www.gov.uk/government/publications/better-health-programme
DevTracker Links to all logframes used during programme lifetime:	Not published

A. Summary and Overview

Description of the programme and what it has achieved
The Better Health Programme (BHP) was a three-year programme, which aimed to improve health outcomes, and provides technical collaboration for eight partner countries (Brazil, Mexico, South Africa, Malaysia, Myanmar, Philippines, Thailand and Vietnam) to strengthen their health systems, specifically by addressing the burden of non-communicable diseases (NCDs) and increasing access to safer, quality health care. It also sought to capture secondary benefits working with Department for International Trade (DIT) to create and capitalise on opportunities for mutually beneficial economic relationships between host countries and UK business and the NHS. These were capitalised using a complementary non-Official Development Assistance (ODA) budget and are reported here but, as not formally part of the ODA programme funding not included in the overall performance rating.
There were substantial changes in the context within which the programme operated over the three-year period of operation. The emergence of the COVID-19 pandemic and the reduction of ODA spending from 0.7 to 0.5% of Gross National Income (GNI) in 2021 resulted in many planned activities being reprogrammed towards COVID-19 or cut[1] with early programme closures in Mexico (Nov 2021), Brazil (July 2022) and following the February 2021 coup in Myanmar. At the same time as budget cuts, as part of the wider merger of the FCO and DFID, the overall management of the BHP moved from the FCO Prosperity Fund to the new FCDO Global Health and C19 Directorate, with management of the South Africa portfolio moving across to the British High Commission in Pretoria. For this reason, South Africa is only included briefly within the scope of this review.
[1] See 2021 Annual Review for more detailed breakdowns of activity scale-backs.
The BHP delivery model was complex, in that it consisted of commercial contracts with four regional Delivery Partners (who worked with FCDO to manage a series of national-level sub-contracts and implement a programme of health system strengthening interventions) and an MoU with the NHS Consortium for Global Health (representing a wide range of NHS technical arms lengths bodies) as Strategic Partner to provide peer-to-peer health systems technical collaboration with partner governments. It also financed Programme-funded Health Advisers in each of the BHP countries supporting programme implementation, government relationships and dialogue and collaborated with DIT to maximise secondary benefits through the creation of opportunities through the ODA programme and additional non-ODA funding.

Despite the challenges encountered, the BHP scored an A at the PCR and successfully demonstrates how health systems strengthening programmes can bring benefits to both the recipient country and the UK by bringing together ODA and non-ODA financing. The programme made good progress toward the two primary outcomes and overall the outputs were met but the scale and sustainability of impact is considered more limited, except in the case of Brazil where programme impact is seen to be particularly strong with clear evidence of impact on national policy and planned nationwide scale-up of BHP interventions. This can be seen as a result of overly ambitious impact statement, significant “leaps of faith” between outputs, outcomes and impact and the scale of ODA budget reductions and cuts to planned programme activities, many of which were envisaged to drive activity scale-up and handover as part of wider sustainability plans (see below).

Major lessons learned, evidence generated and recommendations

While no end-line evaluation was conducted for BHP (a result of the budget cuts), significant lessons were generated throughout the programme including through the conduct of a mid-term evaluation, a series of country case studies and programme closure workshops. These learnings will all be used by the FCDO to inform future programming.

The impact of the Covid-19 pandemic and the scale of the ODA budget reductions has meant that opportunities for scaling-up and sustainability across the programme have not been fully realised. The importance of considering value for money and sustainability principles, both strategic and operational, in the decision-making on budget reductions and a need for early and regular discussion on sustainability in programme design and implementation has been highlighted. For example, in Malaysia wider impact and sustainability was impacted through a) the reduction in ODA funding which meant plans to scale-up a pilot digital health programme beyond the three pilot communities within the project period were discontinued and b) unforeseen legal risk that meant that the NCD digital app developed cannot be transferred to a local partner to use and roll-out further.

Similarly, in the Philippines initiatives were implemented at the City level with an ambitious plan to transfer lessons and scale-up interventions to other local authorities in the later stages of programme delivery. While there are clear ongoing intentions to transfer findings to other areas, significant budget reductions in the second half of the programme period meant this was not possible within the timeframe anticipated with some doubt as to whether it will still be possible. Early signs are at least good, with the City Administration showing strong commitment to transferring the health management information system developed under BHP to other Administrations across the Philippines and some financing already secured to support this.

In line with the FCDO Health System Strengthening (HSS) Position Paper principle of respecting country leadership and working together, the programme evidenced the importance of working in partnership to support context-appropriate and user-driven approaches. In Vietnam, the programme utilised a needs-based approach in supporting three major medical universities to reform their specialty education and in developing competency-based training programmes. Co-design was strong in some countries of the programme but there were opportunities for improvement in others, with differing levels of buy-in noted across some programme stakeholders. The role of the Health Adviser at Post is particularly important here, Health Advisers often acting as the bridges between implementation partners and Government counterparts and playing a key health diplomacy role, using the BHP to sustain and strengthen UK-host country health relationships. However even the Health Advisers found it challenging to engage with the full range of relevant government partners needed to take the needed multi-sectoral approach.

A weakness of BHP identified by a wide range of programme stakeholders was the failure to build-in strong enough cross-country learning exchanges and networks to allow countries to share experiences, tackle mutually-felt challenges (particularly in the face of the COVID-19 pandemic) and build longer-term partnerships and alliances that would outlive the life of the programme.

A global programme, BHP was originally designed with a view to both responding to country-led demands for technical assistance and ensuring lessons were shared between participant countries. However a combination of factors meant inter-country learning exchanges and networking opportunities were largely missed. For example, it appears that the complexity of the programme design led to unclear roles and responsibilities between different delivery partners early on allowing cross-country learning activities to largely fall-between the gaps (and pointing to the importance of avoiding overly complex delivery models in future). Then, with the budget cuts activity plans were stripped back heavily, with any work seen to be non-essential to delivering programme impact (e.g. evaluation, regional workshops) de-funded.

Noting the huge express demand for cross-country learning exchange across a number of the BHP partner countries and the demonstrated impact of the limited number of NHS Consortium (NHSC) led global and regional learning exchanges held, this was a significant opportunity lost to strengthen regional relationships and drive longer-term impact through BHP.

How this report was conducted

This PCR was conducted through a desk review of BHP Annual Reviews and deliverables, country case studies, which included consultation and direct interviews with a broad range of health stakeholders, Delivery Partner led project closure reports, consultation with programme implementation partners, government counterparts and FCDO country-based Health Advisers.

Noting the complex design and nested approach to monitoring and evaluation (whereby each country programme had its own logframe indicators and targets that did not aggregate neatly in to the master programme logframe) this review does not attempt to cover all results from all countries in detail, instead drawing out a range of examples from different countries to illustrate results across different outcome and output areas.

Actions following approval of this report

All programmes actions, in relation to asset transfer, outstanding payments and receipt of audited statements have been completed.

Programme design and implementation lessons are directly contributing to the ongoing design of a new investment that both has more realistic impact ambitions and a significantly simpler delivery design.
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£79.3m	£36.5m
Timeframe	August 2018 (OBC approval)	December 2022 (Business Case end date)
Outcomes	Outcome 1: Increased coverage and utilisation of effective support and services for NCD prevention, treatment and management / Outcome 2: Improved equitable access to safe and quality healthcare, especially for women and marginalised groups	There were no changes made to the two primary outcome statements. / All indicator targets were achieved across both outcome areas.

Overall assessment of programme outcomes, sustainability and VfM

Overall BHP achieved the full suite of outcome level targets set out, but as noted above, it is important to note that the proxy indicators selected (e.g. # of policies or strategies implemented with and for marginalised groups) do not allow us to assess the direct impact of interventions on (equitable) service coverage. Further while all countries included indicators to track progress towards outcome one, only three countries (Brazil, Thailand and Malaysia) tracked progress towards outcome two. This said, there are some strong examples of impact – particularly from Brazil and the Philippines – which point to a positive impact of BHP-funded interventions on non-communicable diseases. In the case of Brazil for example, it is estimated that the suite of interventions delivered will ultimately result in over 7.5 million more Brazilians living in remote areas accessing digital primary health care given the translation of pilots in to a national digital health programme and associated regulatory changes and partnership formation to support scaling-up across the country.

All countries tracked progress to outcome 1 with more limited coverage tracked on outcome 2. This mixed picture likely reflects a number of factors, including a lack of clear linear pathway between outputs and outcomes, an over-ambitious theory of change and original level of ambition and the impacts of the activity reprogramming and budget cuts described above. That less progress is seen towards improving equity of access (outcome 2) also points to the wider challenges and costs associated with reaching the marginalised groups.

Outcome 1: Increased coverage and utilisation of effective support and services for NCD prevention, treatment and management (especially women and marginalised groups).

All outcome indicator targets were achieved across all countries, with overall achievement greatest in Brazil where direct impact can be seen between intervention delivery and health service coverage, and evidence of significant planned scale-up beyond the intervention area is clear. In other countries, assessing scale of impact on intervention coverage is more difficult given a tendency to focus on such indicators as the number of healthcare workers trained and/or policy or strategy documents influenced and the lag-time between these and impact on service coverage.

In Brazil, in partnership with BHP the Ministry of Health (MoH) and the Hospital das Clínicas da Faculdade de Medicina da Universidade de São Paulo (HCFMUSP) delivered digital primary care solutions to remote communities in the Amazon region (up to 12 hours from the nearest doctor), connecting patients and local nurses with dedicated doctors in São Paulo. The results have proved the effectiveness of this model, with over 300,000 patients (against a target of 274,000) using telemedicine in an 18-month period and 94% of the consultations requiring no need for further in-person treatment, demonstrating strong virtual diagnosis and high patient satisfaction.

Following the success of digital interventions supported by BHP, the HCFMUSP has created dedicated governance with senior leaders in the hospital to sponsor initiatives, make decisions and address barriers as they emerge. As a result, the digital health area in HCFMUSP now has 31 dedicated staff and has secured £17 million in new revenue to support the scaling-up of six projects nationally through to the end of 2024.

Outcome 2: Improved equitable access to safe and quality healthcare, especially for women and marginalised groups.

While Gender, Equity and Social Inclusion (GESI) studies were conducted and plans developed for all countries, and country case studies point to some strong examples of progress against this outcome (e.g. Brazil Digital Health Programme noted under outcome 1, Philippines programme to increase access to diabetes services amongst poor and marginalised urban populations described in more detail below) overall assessment is, once again, difficult. This reflects the use of activity-level proxy indicators (# policies or strategies designed with and for marginalised groups, # community-led initiatives or pilots implemented to improve access of marginalised groups to health services) given the limited ability to directly impact equitable access within the short programme delivery period, with targets set for only three countries (Brazil, Thailand and Malaysia).

While not captured by the logframe targets, in the Philippines, BHP worked extensively to design and deliver e-training courses to build the capacity of healthcare providers to increase accessibility of diabetes services by marginalised and poor urban pregnant women. To date, over 250 healthcare workers in Pasig City have completed the training and all show enhanced test scores following the completion of the training and reported rates of diabetes have increased significantly, pointing to increased numbers of people utilising services and being correctly diagnosed.

BHP Brazil (as referenced above) has demonstrated significant progress towards equity where using remote / virtual medical appointments meant those in remote areas have been able to access doctors easily. The Brazil programme in partnership with HCFMUSP also championed the creation of the first patient advisory group in a public hospital as part of wider efforts to improve quality of care for all patients. The patient group has a diverse composition of gender, age, race, income and disability.

In Malaysia, programme design was underpinned by a commitment to responding to community-based priorities to tackle NCDs. This resulted in a focus on strengthening the capacity of community health volunteers (CHVs) to tackle obesity – with a particularly strong focus on prevention through healthy lifestyles - through the community health volunteers and community out-reach. However, while the intent had been to tailor the interventions and messaging to different minority ethnic groups and communities, this did not happen as a result of the ODA budget cuts limiting ability to drive a more inclusive approach and improve equity of intervention coverage and impact. Further, evidence suggests that the digital app developed as a key tool for increasing community obesity awareness and improving diet and lifestyle reached only a limited number of users (see output 1). Overall, while the output indicator targets were met for Malaysia, direct impact on equitable access appears more limited with significant learnings for future programming (see lessons learned above).

Outcome 3: New opportunities and mutually beneficial economic relationships identified as part of the BHP are established.

BHP has shown that post Prosperity Fund, the BHP model can deliver new opportunities, both commercial and non-commercial, through mutual benefit and learning. A key role for BHP has been to build trusted and mutually beneficial economic relationships.

Over the programme life this outcome has seen over 125 non-commercial[2] and 15 commercial wins at a value of £403 million tracked across the eight BHP core countries[3], achieved with supplementary activity supported by non-ODA financing. Early engagement with DIT in the design stage of the programme was critical to identify opportunities for the UK healthcare system, with a One HMG approach across FCDO and DIT networks in UK and overseas, a coherent secondary benefits strategy, tracking of opportunities and internal interfaces and communication key to success.
[2] non-commercial opportunities include new or strengthened collaborations with UK institutions, such as network affects, mutually beneficial bilateral dialogues in health
[3] Source: DIT tracking data.

Examples of opportunities and mutually beneficial economic relationships identified as part of the BHP delivery include:
- A UK-Malaysian workforce partnership initiated by BHP, FCDO, DHSC and DIT to support the sustainable and ethical recruitment of Malaysian healthcare workers in to the UK NHS;
- UK-Brazil life science exchanges including a dialogue series on digital health application to C19 with UK and Brazil experts and a UK-Brazil Genomics “virtual trade mission” which included 300 participants from public and private sectors on both sides generating a range of outcomes including a UK-Brazil partnership in Genomics, precision medicine and advanced therapies medicinal products;
- A series of UK Government webinars with Asian Development Bank sharing UK expertise in primary care, net-zero healthcare and paediatric vaccine delivery with over a 2000+ overseas audience;
- Establishing a Health Education England – Thailand Managed Education Partnership covering international recruitment, educational placements, and technical collaboration between heath systems;
- UK- South African Health Products Regulatory Authority (SAPHRA) MoU to demonstrate the countries’ intentions to collaborate to support innovative medicines approvals to benefit patients (supported by NHSC activity financed under BHP);
- Digital health in Vietnam, Malaysia and Philippines including in telemedicine and education & training;
- Life sciences in Brazil, South Africa and Mexico including in Biopharma and Medical devices;
- Health systems strengthening in Thailand including in consultancy and workforce expertise;
- Covid-19 vaccines and diagnostic deals in a range of BHP countries.

The pivot towards COVID-19 pandemic, although creating operational barriers, provided increased opportunities for mutual beneficial economic relationships. This is highlighted through examples in South Africa with support to the National Department of Health on surge hospitals, through vaccine roll-out seminars in the Philippines and UK-Brazil partnerships, specifically in Genomics and Precision Medicine.

The programme has shown that NHSC and delivery partners can offer substantial input in this area and it is important to maximise the mutual benefits from the insight, networks and support of these delivery partners to enhance opportunities and build sustainability through partnerships. The importance of linking events was highlighted ‘to bridge’ from the primary programme activities to secondary benefit opportunities. For example, this was seen in Brazil through the digital health workshops on the digital health tools in the Covid-19 pandemic, promoting the exchange of experiences between British and Brazilian experts. The NHS experience and expertise in the wider health system produced the majority of non-commercial wins and a recommendation for future programming is to harness a wider group of organisations’ experiences in the UK sector, especially in science & technology and Universal Health Coverage applications.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The envisioned impact of the programme was reduced premature mortality from NCDs through prevention and treatment. The global theory of change (shown below) illustrates the pathways through which activities delivered were expected to lead to the delivery of three outputs which, in turn, were expected to contribute to the two outcomes of 1) increased coverage and utilisation of effective support and services for NCD prevention, treatment, management and 2) improved equitable access to safe and quality healthcare. As a legacy Prosperity Fund Programme, BHP sought to garner secondary commercial and non-commercial benefits for the UK through the relationships forged through the programme.

No major changes were made to the theory of change throughout the lifetime of the programme. However, significant changes were made to the results framework to reflect changes in the type and scope of activities that were being undertaken, with resultant impact on the level of overall expected scale of impact at the outcome and impact level.

The Annual Review 20/21 noted that the programme was moderately off-track to deliver the expected results, in part due to overly ambitious outcome and impact statements, and as a result of cuts to planned programme activities due to budget reductions. It was also noted that many of the country programme indicators had changed and were no longer aligned with the global results framework indicators and a recommendation was made to conduct a review of the global logframe. Changes to the global logframe indicators following review are set out in Annex A below. These reflect an effort to both better bring together results from across multiple BHP projects and countries and re-align delivery ambitions with the significantly smaller budget available.

## C: Detailed Output Assessment

Output 1	Increased use of digital technology and improved integration and utilisation of health information and data to inform practice and tackle the burden of NCDs and improve quality of care
Output Score	A
Impact weighting (%)	33% (all outputs were weighted equally)		Impact weighting revised since last AR?	No

Output Indicator		Baseline (2019)	Final Logframe Target (December 2022)	Final Result Achieved
# tools, strategies or frameworks developed to strengthen digital health information systems and architecture to enable monitoring and surveillance of disease, patient registry systems or telehealth consultations		0	25	Met expectation: 27 / Brazil =12 / Malaysia = 2 / Mexico = 1 / Myanmar = 1 / Philippines = 8 / Thailand = 1 / Vietnam = 2
# studies developed to strengthen digital health information systems and architecture to enable monitoring and surveillance of disease, patient registry systems or telehealth consultations		0	6	Met expectation: 6 / Brazil = 3 / Philippines = 1 / Vietnam = 2

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Overall the BHP achieved its targets for Output 1, scoring an A, with some examples discussed further below.

Digital health was an area of particular strength and value-add within BHP with demand for support strong, with the NHSC facilitating technical collaboration between country partners and NHS Digital on a number of workstreams. The programme supported a wide range of different activities in seven BHP countries (Brazil, Malaysia, Mexico, Myanmar, Philippines, Thailand and Vietnam) to support the use of digital technology and improved integration and utilisation of health information and data. Interventions included, for example the development of a downloadable app (called ‘MicroGuide’) and associated training materials in Mexico. The programme trained primary health care providers in 100 clinics to enable them to access diagnosis and treatment guidelines for diabetes and hypertension to improve diagnosis and treatment.

In the Philippines in response to the pressure the COVID-19 pandemic placed on NCD care and specific demand from the Local Government Unit (LGU) in Pasig City, the programme worked with the LGU to conduct a study on ‘Improving NCD Programme Management in an Environment with a Communicable Disease Pandemic’ to generate lessons on the impacts of COVID-19 on NCD services and find ways to improve NCD strategies that could be implemented in a decentralised setting. This study helped inform the design of Philippine’s first digital patient registry for NCDs - a Multi-Programme Local Mapping Tool (MuPLoMT), developed under BHP, to support NCD risk assessment through digitised patient data, with expected reach across a population of over 1 million in Pasig City and Iloilo City.

The Brazil programme for example aimed to tackle pressing structural challenges in the Brazilian Public Healthcare System in collaboration with the Brazilian MoH and the leading research and teaching hospital in the country (HCFMUSP). BHP Brazil supported HCFMUSP in implementing over 20 digital health initiatives whilst establishing the governance and management infrastructure to continue implementing and expanding this strategy, which included new ways of delivering digital training for healthcare professionals. Key to this was the collaboration with the NHSC and NHS ALBs, specifically seen through facilitated knowledge exchange with NHS Digital, Genomic England and National Institute of Health and Care Excellence (NICE). Further detail on one of the Brazil programme's most impactful digital interventions is described under outcome 1.

For progress and achievements captured across previous output indicators, please refer to the Better Health Programme Annual Review 2021. For details of changes made to output indicators please see Annex A below.

Lessons learned through this output, and recommendations for future programming

Learning from country examples shows the need to build in expectations around sustainability from the outset and seek broad-based commitment to sustainability from the partner government throughout the programme. The vital role of community participation in the feasibility and sustainability of digital health policies and guidelines development is also noted here.

The development and build of new digital products, in some country examples, represented limited value for money. As discussed above in section A, sustainability was impacted in Malaysia, not only through the limited uptake of the digital tool developed but also through an unforeseen issue encountered in the transfer of a digital asset at the end of the programme. It is a recommendation for future programming to do early market and legal context analysis and early engagement to build on country partnerships and to capitalise on existing digital products on the market, where feasible.

Output 2	Capability building through education and training, knowledge exchange, strategy and policy development/implementation to tackle the burden of NCDs and Covid-19, and improve quality of care
Output Score	A
Impact weighting (%)	33% (all outputs were weighted equally)		Impact weighting revised since last AR?	No

Output Indicator		Baseline (2019)	Final Logframe Target (December 2022)	Final Result Achieved
2.1. # of health stakeholders accessing training (including CPD) interventions relating to NCD prevention, treatment and management; quality of care; genomics; or digital health provision.		0	7380	Significantly underachieved: 6418 / Brazil = 3315 / Malaysia = 107 / Mexico = 119 / Philippines = 523 / Thailand = 2113 / Vietnam = 241
2.2. # operational documents (action plans, protocols and guidelines) to tackle NCDs or improve quality of care at national, regional, local levels.		0	19	Met expectation:19 / Brazil = 5 / Malaysia = 1 / Mexico = 2 / Thailand = 5 / Vietnam = 6
2.3. # of feedback mechanisms in place to enable service users to provide inputs to inform policy strategy, clinical and quality standards		0	6	Met expectation: 6 / Brazil = 4 / Malaysia = 2
2.4. # of academic curricula or training modules developed that can develop workforce capacity to prevent, manage and treat NCDs		0	19	Met expectation: 22 / Brazil = 2 / Malaysia = 1 / Mexico = 5 / Myanmar = 6 / Philippines = 7 / Vietnam = 1
2.5. # of knowledge exchanges facilitated by the NHS Consortium for Global Health		0	138	Marginally underachieved: 130

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Performance against this output area was mixed, with three of the five indicators achieving or marginally exceeding their targets but significantly underachieving against indicator 2.1 (largely a result of the early closure of the Brazil Programme which resulted in the significant scaling back of healthcare worker training activities) and marginally underachieving against another (2.5), a reflection of reduced country-level demand for NHSC-led knowledge exchanges in the face of a reduced overall programme portfolio of activity.

The programme supported a range of different activities under this output in six of the BHP countries (Malaysia, Mexico, Myanmar, Philippines, Thailand and Vietnam). Interventions were highly varied and tailored to the country contexts. Health workforce education and training included, for example, the development and delivery of a nursing diploma in Mexico, the training of community health volunteers in Malaysia, and support to continued professional development on NCDs to healthcare workers in Thailand, with 94 hospitals joining the Healthcare Accreditation Programme focused on improving quality of care. The Philippines established local learning networks to improve access to training of health workers in NCDs, risk-assessment, and patient care, with five accredited courses developed and over 15,000 unique attendees engaged by the University of the Philippines College of Public Health in COVID-19 shared learning.

There was significant underachievement in the number of health stakeholders accessing training (indicator 2.1 – the indicator was expanded to incorporate a broader range of subject matter in training activities), which can be attributed to the early closure of the BHP Brazil programme. In Thailand, where there was a focus on capacity building of health professionals by promoting lifelong learning culture through CPD, on the otherhand, the programme evidenced a significant over-achievement driven by a shift from in-person to virtual training which allowed for a substantial increase in the numbers participating. While the shift from in-person to virtual training allowed a significantly higher number of health professionals to attend, the impact of the shift on the quality of the training and/or on learning and behavioural outcomes is less clear.

Achievements under this output can also be seen in the number of academic curricula or training modules developed that can develop workforce capacity to prevent, manage and treat NCDs (indicator 2.4 – showing slight overachievement). In Mexico particularly this can be seen through the development of a curriculum for Advanced Practice Nursing (APN), which promoted the role of nurse leadership in health system development. The programme recruited leading nurses to work as champions and identify challenges for the advancement of the APN role. The advancement of the APN role provides nurses (a large proportion of whom are female and have had limited opportunities for advancement into more senior or specialised roles to date) with a clear route to more specialist training and enhanced career progression. Before the BHP Mexico intervention, there was little support and opportunity for training around APN roles.

In Vietnam, BHP Strategic Partner, NHSC brought together experts from Public Health England and NHS Digital to provide recommendations on building an integrated and resilient NCD surveillance system under Vietnam’s National Action Plan on NCDs 2021-2025, including at a workshop convened by the Ministry of Health (MoH) and WHO. MoH colleagues stated that they valued the NHS partners’ technical input on crosscutting issues, such as data quality, interoperability and workforce development.

Lessons learned through this output, and recommendations for future programming

Whilst this output noted increases in some countries in the numbers being trained following the pivot to virtual online training and learning, more could have been done to explore the impact on the quality of training and delivery and guide the development of more effective virtual learning interventions beyond the life of the programme. A more qualitative M&E focus on the implementation of learnings from training could have supported improved delivery. This could have been enhanced further if the programme had embedded mechanisms for shared learning between participating countries and programme partners.

Output 3	Life sciences and health research and development to tackle the burden of NCDs and improve quality of care
Output Score	A
Impact weighting (%)	33% (all outputs were weighted equally)		Impact weighting revised since last AR?	No

Output Indicator		Baseline (2019)	Final Logframe Target / (December 2022)	Final Result Achieved
3.1. # countries with new networks for commissioning, conducting or disseminating life sciences research		0	4	Met expectation: 4 / Brazil = 2 / Malaysia = 1 / Mexico = 1
3.2. # countries demonstrating evidence of national or subnational government structures prioritising life sciences research or incorporating research into policymaking processes		0	3	Met expectation: 3 / Thailand = 1 / Philippines = 1 / Mexico = 1
3.3. # of new structures or policies in place that provide a basis for research development and cooperation		0	6	Met expectation: 6 / Brazil = 6
3.4. # of number of new BHP-supported publications around life sciences, NCDs or quality of care		0	9	Exceeded:15 / Brazil = 1 / Malaysia = 14

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Overall the BHP achieved its targets for Output 3, scoring an A. Five countries (Brazil, Malaysia, Mexico, Philippines and Thailand) implemented projects contributing to this output area.

Examples across this output include, the generation and publication of research findings from the piloting of community approaches to reducing obesity and NCD prevention in Malaysia (to note targets were exceeded under indicator 3.4 and the formal publication of evidence generated by BHP Malaysia leaves a sustainable legacy). In Thailand the programme supported the development of the country’s capacity in genomics and in Brazil the programme worked with a wide range of stakeholders to create new research ecosystems and a more conducive environment for medical R&D. In Brazil this was seen through the collaboration with the MoH and the restructure of the National Clinical Research Network, which provided critical technical input and benchmarks on digital health initiatives to support the publication of the digital health regulatory framework and help launch the Brazil Genomes Programme, both of which will serve as catalysts for the medical R&D environment in Brazil.

While not captured within the output targets, it is worth noting the significant impact of efforts to enhance evidence-based decision making in health in the Philippines under the BHP, a wider example of strong contribution against this output area. In 2019 the Philippines enacted Universal Health Care Law mandating health technology assessments (HTA) as a fair and transparent priority-setting mechanism for the national health insurance scheme. BHP Strategic Partner, NHSC, brought together experts and convened a series of peer-to-peer virtual knowledge exchanges between NICE and the Philippines’ Department of Health (DoH) designed to strengthen DoH capacity to use HTA. This collaboration resulted in significantly increased HTA capability within the Philippines’ DoH, as demonstrated by their subsequent commissioning and conduct of over 20 HTAs in 2021 alone. The collaboration continues with NICE and DoH co-developing policies for embedding HTA into clinical guidelines, gearing towards the establishment of the Philippine Center for Disease Control and Prevention.

Lessons learned through this output, and recommendations for future programming

Whilst indicators were consistently met under this output, there were notable challenges on sustainability. There was a commitment to the effectiveness of the programme in decision-making on budget reductions as part of ODA cuts, through the prioritisation of key initiatives with greater potential to generate impact, but this inevitably led to impacts on sustainability of outcomes, as evidenced in Brazil where this led to milestones for the Health Technology Appraisal and National Clinical Research Network being discontinued.

A recommendation for future programming would be to engage all programme partners in consistent and formal discussions about sustainability from the inception phase until the end of the programme.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

The Business Case set out that ‘overall efficiency, effectiveness, economy and equity, the delivery model and approach to commissioning the work is expected to achieve high value for money’.

The programme’s external evaluation completed in April 2021 concluded that ‘the programme continues to score ‘good’ on value for money with a strong approach to procurement and cost controls, governance and programme and risk management’. However, a lack of strong VfM metrics and the cutting of the envisaged endline programme evaluation (as part of wider cost-saving mechanisms) mean that it is difficult to robustly compare overall programme VfM to the original business case proposition. This said, given significant cuts to the programme over-time with clear impacts on activity scale-up and transition to national partners, cost-effectiveness and overall VfM is likely to be lower than originally envisaged.

It is noted however, that relationships built through BHP have led to significant UK influence within and beyond the health sector and are valued by partner governments and health institutions, leading to sustained UK-host country relationships and strong programme effectiveness as measured by the strength of partnerships and UK influencing capabilities. The BHP model, through collaboration with DIT, aimed to maximise opportunities for mutually beneficial economic relationships in the health sector for the UK and international businesses and demonstrates an impact value of £403 million (as attributed by DIT) pointing to extremely strong cost-benefit returns.

At the delivery level, economy and efficiency are arguably stronger than envisaged in the original BHP, a result of a rapid and effective shift from in-person to virtual technical exchange necessitated by the Covid-19 pandemic. The impact of this shift on intervention effectiveness is however unclear.

VfM might have been improved through earlier and clearer laying out of individual partner value-add and implementation role with discussions conducted as part of this PCR clearly highlighting missed opportunities for stronger cross-country learning and network building that resulted from a lack of clarity around each partner’s role at the regional and global level.

The programme supported the FCDO Health Systems Strengthening Position Paper ‘leave no one behind’ principle by ensuring Gender, Equity and Social Inclusion (GESI) was integral to the programme design. However and as set out under outcome 2, whilst programmes had a broad range of equity and inclusion focus, such as gender, age, socioeconomic status and ethnicity (in Thailand for example, 77% of workshop participants were female and in year 3 all workshops provided interpreter services), more consideration could have been given to the intersection between these vulnerability characteristics and the barriers associated with these intersectional identities, demonstrating the importance of clear and accountable mechanisms for monitoring and reporting to ensure impact can be best measured and evidenced.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The risk rating of the programme was Moderate, fitting with FCDO and Departmental risk appetite, and this remained at programme closure.

FCDO Programme Management and Delivery Partners regularly reviewed and monitored risks through the lifecycle of the programme, with country-level risk registers and a central risk register maintained. Delivery Partners and Health Advisers reported back on in-country risk intelligence; they were particularly agile at identifying, analysing, and proposing mitigations to in-country risks. Risks were tracked across the programme and all risks allocated risk owners to ensure that the risk is continually assessed and mitigation strategies and actions are implemented. Risks were regularly reported on through established governance and reporting processes.

The programme reflected delivery risks as a result of ODA reductions, with a reduction in programme activity required to fall within reduced allocation and realignment of activity, which placed continued uncertainty on delivery with resulting impacts on sustainability as covered extensively in this PCR. Operational risks in relation to resourcing were identified through concerns in implementation over the delivery partner’s ability to mobilise technical resources and also through country and central resource seeking alternative employment opportunities towards the end of the programme.

The main risk to the programme in terms of achieving its intended outcome and impact was the COVID-19 pandemic. In the early stages of the pandemic the programme had to rapidly pivot. The COVID-19 pandemic led to restrictions across BHP countries and on BHP staff in carrying out business as usual activities. This also impacted engagement with programme stakeholders and country governments and availability of technical assistance draw-down capacity from NHS ALBs, some of whom were diverted to pandemic response.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The programme’s contractual set-up was challenging with four Implementation Partners, with performance varying across them and different milestone arrangements and payment schedules. Despite this complexity, the direct relationships between Implementation Partners, Health Advisers, FCDO Programme Team and Strategic Partner remained effective with all highlighting the value of their respective expertise.

Quarterly reports (with the exception of South East Asia which operated a monthly reporting cycle due to a large portfolio delivering across five BHP countries) on progress against Milestones were shared and reviewed by Health Advisers at Post, and the PRO and SRO in the central Programme Management team, with input from the Strategic Partner, where required.

BHP contracts were managed by Key Performance Indicators (KPIs) Framework and Payment by Results (PbR) mechanisms to maintain quality delivery. In Q3 21/22, following an initiative led by the Cabinet Office, FCDO undertook efforts to enhance the management of contracts by publishing the top three KPIs of our most critical contracts, in order to meet transparency requirements and improve delivery. The remaining BHP contracts (South East Asia and Brazil) were required to report quarterly on their top three KPIs, which evidenced delivery against milestones, budget variance and reporting. All KPIs, for the remainder of the programme, were met as part of the quarterly transparency reporting initiative.

Where issues in performance were identified, they were dealt with well and consistently using contract management systems to manage improvements i.e. against KPI Framework. This was put into practice in 2021 when one Implementation Partner’s financial performance, reporting and monitoring was found to be inconsistent with contractual agreements. A cross-team approach was employed to work through issues, which included engagement from the Strategic Partner, Implementation Partner, FCDO teams (at Post and in UK and Commercial) and a lessons learned exercise was held, moderated by the former PF Evaluation Partner (Integrity Global), to acknowledge the difficulties and learn from them to move forward and agree new parameters for performance. Whilst the programme in Mexico was subsequently unable to secure sufficient ODA funding to complete the programme, a small allocation was made to allow the programme to close responsibly in November 2021, as a result of the progress made in agreeing new reporting parameters with the Implementation Partner, a collaborative approach was taken to programme closure with the final audit approved.

In Brazil the implementation partner performed consistently on commercial and financial management. A standard-quarterly financial cycle was used to forecast and invoice completed work, with the invoices (based on deliverables) always matching the forecast budget closely. As a result, achieved all KPI payment targets.

In South East Asia the implementation partner performed consistently against a monthly reporting and financial cycle, meeting KPI and PbR performance indicators, with only one KPI failure (budget variance) identified during the programme delivery in South East Asia. Additional layers of complexity were identified in the delivery model in South East Asia, with a regional delivery partner and sub-contractor in country, which led to some early issues experienced in regards to working remits and ownership of relationships.

The management of the South Africa portfolio moved across to the British High Commission early in implementation.

Throughout the Covid-19 pandemic the programme maintained a flexible and adaptive delivery approach, demonstrating an ability to pivot and shift to virtual and remote working. Conversely, through these changes the pandemic boosted the economy and efficiency of the programme as many countries accelerated digital transformations and transitions in health care and health systems.

It was noted that accountability and reporting requirements involved in the delivery model sometimes placed an administrative burden on multiple partners, which impacted the efficiency of the programme.

Programme-level approach to monitoring and evaluation

The programmes’ M&E structures followed the standard Prosperity Fund approach of quarterly reporting against country-level logframe progress. The delivery partners produced monthly narrative reports that outlined progress towards objectives, risk monitoring, political economy analyses, and contributions to GESI and lessons learned. They also completed annual reports to synthesise the monitoring data collected each year.

A recommendation at the Annual Review in 2021 was that there needed to be a greater focus on using both the country and the global logframes to monitor and manage the programmes performance, and a substantial review of the global logframe was carried out in consultation with delivery partners and health advisers. Detail of changes to the global logframe are set out in Annex A.

A mid-term evaluation was carried out early in 2021 to evaluate delivery plans and early results. The final evaluation planned for the programme was cut following reductions in ODA funding.

Date of last narrative financial report	South East Asia (PwC): Nov 2022 / Brazil (McKinsey): Oct 2022 / Mexico (DAI): Sept 2022 / NHSC (HEE): Jan 2023	Date of last audited annual statement	South East Asia: Dec 2022 / Brazil: Aug 2022 / Mexico: July 2022 / NHSC: HEE Aug 2022, UKHSA March 2021

## Annex A – Table of changes to the logframe
	Previous Indicator	New Indicator
Output 1	Evidence of NCD data available via digital health information systems, used to improve practice in NCDs / Discontinued because focus of digital work went beyond NCDs to quality care or other areas that incorporated, but were not limited to, NCDs.	# tools, strategies or frameworks developed to strengthen digital health information systems and architecture to enable monitoring and surveillance of disease, patient registry systems or telehealth consultations / New indicator enables a broader range of digital activities to be incorporated
	Evidence of health workers accessing digital learning mechanisms, used to improve QoC practice in NCDs / All training was delivered through a digital or hybrid model during Covid-19, so this indicator became duplicative of Output 2.1	# studies developed to strengthen digital health information systems and architecture to enable monitoring and surveillance of disease, patient registry systems or telehealth consultations / New indicator highlights research related to digital health
Output 2	# of health workers accessing training (including cpd) interventions on national NCD standards for prevention, treatment and management / Previous indicator did not acknowledge training beyond NCDs	# of health stakeholders accessing training (including CPD) interventions relating to NCD prevention, treatment and management; quality of care; genomics; or digital health provision. / New indicator incorporates a broader range of subject matter incorporated in training activities
	# of countries with operational guidance (action plans, protocols and guidelines) to tackle NCDs, working to improve quality of implementation at national, regional, local levels. / Previous indicator referred to # of countries, with a higher target than the number of countries in the BHP programme	# operational documents (action plans, protocols and guidelines) to tackle NCDs or improve quality of care at national, regional, local levels. / New indicator refers to # of documents instead of # of countries and incorporates quality of care activities
		# of academic curricula or training modules developed that can develop workforce capacity to prevent, manage and treat NCDs / New indicator included to acknowledge development of academic curricula and other training modules.
		# of knowledge exchanges facilitated by the NHS Consortium for Global Health / New indicator to acknowledge NHSC deliverables towards this output
Output 3	# of new NCD findings and articles published (linked to BHP) in quality peer reviewed journals / Previous indicator was limited to NCD research	# of number of new BHP-supported publications around life sciences, NCDs or quality of care / New indicator incorporates other areas of health research
	# of new NCD related Health Technology Assessments initiated and/or completed to inform policy, standards, guidelines and priority setting / Some HTA activities were discontinued due to ODA reductions or the scope changed, so the indicator was removed. HTA activities continued in South Africa, but the BHP programme there became bilateral	# countries with new networks for commissioning, conducting or disseminating life sciences research / New indicator to incorporate a broader range of research activities
		# countries demonstrating evidence of national or subnational government structures prioritising life sciences research or incorporating research into policymaking processes / New indicator to incorporate a broader range of research activities