Programme Completion Review

Title: Global Future Cities Programme
Final Programme Spend £ (full life): £52.8m (BC value: £80m)	Review Date: April 2023
Programme Code: GB-GOV-3-PF-FUT-921	Start Date: 01.09.2019	End Date: 18.11.2022

Summary of Programme Performance

Year	2019 (Lite)	2020	2021	2022 / (PCR)
Programme Score	A	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	N/A

DevTracker Link to Business Case (and any addendum):
DevTracker Links to all logframes used during programme lifetime:

A. Summary and Overview

The Global Future Cities Programme (GFCP) supported a select number of cities in middle-income countries to generate greater and more inclusive local economic growth by improving the way their cities are planned and managed. This included developing more sustainable and environmentally resilient cities, supporting a reduction in poverty and social inequality faced by many urban populations and the creation of mutually beneficial two-way trade and investment opportunities for the UK and other international actors. These interventions worked across three inter-linked objectives and pillars of programme activity:

Increased access to safe, affordable, sustainable transport: Through support to the development of integrated multi-modal public transport systems.

Well governed, technologically innovative, inclusive, and integrated urban planning and management: Through support to the development and adoption of city master plans, inclusive spatial strategies, transparent planning instruments, improved processes and regulations.

Increased resilience and reduced socio-economic and environmental damage caused by natural disasters: Through the adoption and implementation of inclusive evidence-based resilience and risk mitigation strategies and plans.

The programme was led by the Foreign, Commonwealth and Development Office (FCDO), with an oversight structure that drew on resource from the Department for International Trade (DIT). It delivered a set of targeted technical assistance interventions in 19 selected cities across ten countries: Brazil, Indonesia, Malaysia, Myanmar (closed 2021), Nigeria, Philippines, South Africa, Thailand, Turkey and Vietnam.

The programme operated through the delivery of technical assistance to city authorities in processes of regulatory change, institutional design and evidence based policy making, as well as providing capacity development support to those authorities and the implementation of select pilot projects. Interventions in these pillars were delivered by a set of private sector delivery partners who were contracted on geographic lines (including Adam Smith International in Nigeria, Arup in Turkey, EY in Brazil, PwC in South Africa and Mott MacDonald in South East Asia) and were overseen on a day-to-day basis by the FCDO teams at Post. Further oversight of work taking place in cities was undertaken by a programme management team housed centrally in the FCDO and through UN-Habitat, who had a ‘Strategic Partner’ role on this programme via a Memorandum of Understanding (MoU) held with the FCDO.

The programme originally had a total programming budget of £80m, which included platform, and staff costs. Following Covid-19 and ODA reprioritisation, the central GFCP budget was reduced to £52m. Additionally for 2021/22 there was £4.65m bilateral funding from outside of the central GFC programme for South Africa and Turkey for Future Cities programme delivery. The business case anticipated that the programme would end in December 2022. However, due to a number of factors the programme was concluded on 31 March 2022. Some activity continued in SE Asia until 18 November 2022 through alternative bilateral funding sources.

The seismic impact of the Covid pandemic on the UK economy forced the UK government to take tough but necessary funding decisions, and as announced in 2020, the UK moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. Following a thorough review, the FCDO’s programme budget was allocated in accordance with UK strategic priorities against a challenging financial climate of COVID. Throughout the business planning process, the FCDO strived to ensure that every penny of the ODA spend brought maximum strategic coherence, impact and value for taxpayers’ money. The move to 0.5% resulted in changes to this programme, which was adapted, and this Programme Closure Review reflects that the programme had to refocus resources accordingly.

The Comprehensive Spending Review (CSR) process in Spring 2021 raised questions about the size and scale of the programme. An overall 40% budget reduction was agreed. In addition, the projects in South Africa and Turkey gained Post funding and became ‘bilateralised’ i.e. budgeted and run from Post. In response to the Covid-19 emergency, £1.9m of the programme’s reduced budget was reallocated to South Africa for urgent Covid mitigation work. The CSR process also resulted in SE Asia region successfully bidding for an extra £2.6m budget to support the programme’s continuation in 2022/23 (until November 2022) and the projects in Brazil and Nigeria closed in March 2022 – see Finance section for more detail.

Terms of reference for the Programme Completion Review

The purpose of this review is to provide an independent assessment of successful delivery over the lifetime of the Prosperity Fund’s Global Future Cities Programme against its stated objectives, following the conclusion of the Programme in November 2022. The review assesses:

- delivery of outputs as set out in the logframe, the quality of programme governance and partnership arrangements against approaches set out in the business case;
- the extent to which the anticipated outputs have been delivered, and the extent to which it can reasonably be expected outcomes and benefits will be delivered, and the timeframe for this;
- the extent to which key cross-cutting issues including gender and inclusion were sufficiently considered in delivery plans and activities undertaken;
- the extent to which the programme adapted successfully to the ongoing restrictions caused by the Covid-19 pandemic;
- whether the programme delivered good value for money (VfM);
- the extent to which the programme adapted successfully to the significant budget reductions following cuts in ODA spending for 2021/22;
- whether the closure of the programme was effectively managed, and whether lessons for future programmes can be learned from this process; and
- arrangements in place to ensure learning from the programme can contribute to the development of future programmes, and supporting international dialogue and sharing of experiences on the development of future cities.

Major lessons learned, evidence generated and recommendations
- Programmes focused on future cities need to be of large scale and long duration, and continue to adopt a holistic approach (e.g. covering financial elements, technology, and social and equalities outcomes). Large scale programmes: 1) took account of the timeframe for implementing major urban development of infrastructure programmes; 2) provided resources for a range of capability building, stakeholder engagement and technical support, all of which are essential for infrastructure delivery; 3) encouraged the participation of other organisations e.g. UN Habitat in the case of the GFCP; and 4) were of interest to large firms with depth and breadth of capability who can provide expert support across the programme.
- The timeline for the development and delivery of the Programme was structured around in-country projects having a four-month inception phase, and a 26-month implementation phase. This imposed an inflexible structure on projects, that was not always optimal, especially as the transition from the inception phase to the implementation phase is critical, and requires the full support and engagement of all project participants. Future programmes should consider allowing greater flexibility to develop the timeline for specific projects.
- Agreeing MoUs between municipal authorities, delivery partners, FCDO and other stakeholders in place at the outset of the projects, to provide clarity about roles, responsibilities and desired outcomes would help ensure better co-ordination and a higher level of commitment from municipal partners. Future programmes should also consider whether data protocols/annexes should be part of this suite of documentation, so there is clarity about the availability, format and accessibility of data at the outset, as well as any key gaps.
- Projects in municipal areas changed and evolved during the design phase (e.g. in Bursa from a focus on transport to the Internet of Things). This created challenges where terms of reference were tightly defined, and funding and Delivery Partner support linked to these. Additional challenges were created by shifts in local politics and political priorities; which could be disruptive as political support for the projects was essential to successful delivery. Greater flexibility and a clearer process for changing these would make it easier to manage projects and reduce friction.
- Greater provision should have been made within the Programme to provide support for: 1) technical elements of the project, including data gathering and systems testing; 2) work to de-risk projects (in relation to financial and technical risk), to help advance these to the point that they were investment ready; and 3) demonstration projects, to prove that these approaches were practical and would deliver positive impacts. Demonstration projects are particularly important when proposals require expensive or large scale alterations to urban environments, to provide assurance to decision makers.
- Municipal authorities/UN Habitat would welcome future programmes either having the resources to provide investment support for implementing infrastructure projects within the programme, or clearer links with organisations and/or programmes that could provide this support, rather than the majority of funding being allocated to technical assistance.
- Whilst Covid19 created challenges for the delivery of projects in all the participating cities, FCDO, the Delivery Partners and local stakeholders all proved flexible and adaptable, and able to switch to making greater use of digital technologies for stakeholder engagement and to support delivery. This has provided useful lessons for the design of these elements of future programmes, which would have the additional benefit of increasing resilience.
- There are opportunities that have yet to be realised, to learn from and embed the knowledge and expertise gained in the delivery of GFCP and other infrastructure programmes focused on development, into the delivery and operation of major projects in the UK. This is particularly in relation to social inclusion outcomes, stakeholder engagement and the realisation of GESI objectives, which are generally not as integrated into major projects and programmes delivered by organisations within the UK.
- An independent evaluation was conducted Tetra Tech/Integrity in Spring 2021 covering Feb 20 to Jan 21.

How this report was conducted

The purpose of this review is to provide an independent assessment of successful delivery over the lifetime of the Prosperity Fund’s Global Future Cities Programme against its stated objectives, following the conclusion of the Programme in November 2022.

The review was written by an independent reviewer, working with the Programme Team (PT) with support from the ECD Economist, BIPD GESI advisor, Strategic Partner and DP input. It was informed by a review of programme documentation, as well as remote and face to face interviews with FCDO staff working on the programme in overseas posts, selected Delivery Partners (Arup, Mott Macdonald, the Adam Smith Institute) and the Strategic Partner (UN Habitat). A field visit was also undertaken to Turkey, including meetings with partner organisations (municipal authorities in Istanbul and Bursa).

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£80m	£52.8m
Timeframe	BC sign-off: 2018 / Programme end: December 2022	BC sign-off: 2018 / Programme end: / Rest of the World: March 2022 / SE Asia: November 2022
Outcomes	Initial outcome-level targets: / More affordable and accessible transport systems / Better integrated urban planning and management / Increased resilience to environmental disasters	Outcome-level achievement: / These indicators remained unchanged from the BC / Each of the targets was achieved; see output measures for more detail

Overall assessment of programme outcomes, sustainability and VfM

Due to Covid-19 and ODA reprioritisation the GFC budget was reduced over a three year period from £80 million to £52 million. Despite this challenge, the efforts of the FCDO Programme Team, staff in posts and the Delivery Partners enabled the redesign of the scope of the Programme and activities outputs surpassed their targets (see Section C) placing the Programme in a good position to deliver the outcomes over the long term.

Most of the projected outcomes and impacts are unlikely to be realised within a 10-year period (as anticipated in the business case), partly due to the early closure of the Programme, but also because of the long timeframes for significant policy changes or investment in and implementation of projects in complex urban environments. However, there is already some evidence to show good progress towards them. This is particularly the case in relation to the Primary Benefits of inclusive growth and supporting sustainable urban environments. There is evidence from a number of cities that the Programme will deliver long-term impacts, including:

- Istanbul: the Sustainable Urban Management Plan (SUMP), published on 28 March 2022, is the first in Turkey, and the first in a megacity of 16m people. The SUMP has 9 key objectives, which aim to deliver 3 key themes: 1) the transition to low carbon; 2) seamless integration of modes; and 3) reducing congestion. There are also 4 cross-cutting sub themes: 1) safety; 2) GESI; 3) resilience; and 4) innovation. These are aligned with the UN Sustainable Development Goals. The SUMP is being used to guide investment in projects, and there is a monitoring and evaluation framework in place tby which the city will assess whether it is delivering its objectives;
- Bursa: the first municipality in Turkey to develop a Smart City Strategy, which has identified 141 individual projects, including an open data platform, tourism app (available now), on electric vehicle adoption and energy management. The Smart City Strategy was launched in the latter half of 2022. Bursa is also now part of an international peer group of smart cities taking forward work in this area;
- Ho Chi Minh City: piloting a proof of concept for a smart city project, and the project delivered the Technical Standard Framework that could support an integrated ticketing system. The UK Government has also worked with Arup and the Vietnamese Government on a Smart City Handbook, profiling smart city opportunities in Vietnam, and there are developing links between BSI, the Connected Places Catapult and UK firms on standards relevant to smart cities and digital technical standards;
- Cebu: a comprehensive, evidence-based land use plan to provide a strategic framework for future development was made ready for Presidential approval;
- New Clark City: to build a new sustainable urban environment that enhance inclusive economic growth, reduce poverty and gender inequality, and is safer and more resilient. The New Clark City Central Park was awarded the SEMEC Gold Award (Analysis and Planning Category) in the Singapore Landscape Architecture Awards 2022.
- Bandung: a 12 month pilot project for sustainable and integrated transport will start in 2023.
- Surabaya: In 2022 the Surabaya Urban Transformation Project won the Best International Future Place Award at the Golden Pineapple Awards as an example of excellence in partnership and collaboration to create a new set of urban design guidelines to transform one of Asia’s red light districts, which was developed with the local community.
- Bangkok: delivered masterplan for future transit development, supporting future development of the city for a range of uses, developed with local community engagement and support;
- Melaka: a Green Transport Masterplan for Melaka State has been developed through the GFCP. This included two successful pilot projects, in relation to the digitisation of bus information for passengers, and the use of e-bicycles in the heritage area of the city. The Melaka pilots have attracted interest from other cities, and are likely to inspire similar projects elsewhere in the State. The city also presented on its projects at the ASEAN Infrastructure Forum; and
- Iskandar: The programme supported the delivery of the Smart Integrated Mobility Management System (SIMMS) Implementation Strategy, which collects data to inform policy and improve network management. This project has won an innovation award: The Pilot Citizen Feedback Portal developed as part of Future Cities Malaysia, in partnership with Iskandar Puteri City Council (MBIP) has won the Esri Malaysia Geo Innovation Award (EMGI). The Programme also led to the embedding of a new approach to GESI in projects and programmes in Iskandar, and the signing of an MoU between Iskandar Transport Authority and Transport for West Midlands.

Equity

The most recent G&I scorecard also rated GFC as RAG-rating green across all dimensions with good evidence of the programme delivering equitable outputs. The Review Team was also presented with clear evidence of how the emphasis on G&I across all aspects of the Programme has influenced partners in countries and cities to change their approach to stakeholder engagement, and increase the participation of disadvantaged groups (e.g. women and girls, the disabled, older people) – see also Section C below – Gender, Equality and Social Inclusion.

VfM

The Programme has achieved its intended primary outcomes, with a number of important policies or other initiatives launched in the partner cities, a number of which have won awards. Whilst the Programme has not yet delivered the anticipated secondary benefits, there have been some limited commercial successes for UK firms, including one that developed an App for the Bursa municipality. Transport planning software, developed by Podaris in the UK to support collaborative planning, was also used to support delivery of projects in Malaysia. However, there is evidence that the secondary benefits are likely to materialise over a longer timeframe, given the influence of the Programme on the future policies and strategies of partner cities, and the potential for these to be replicated elsewhere in these countries. Arup have reported that the relationship with the city of Ankara that was developed through the Programme has enabled them to win further projects from the municipality. It is also possible that the secondary benefits could exceed projections, if the challenges of sustainable urban management and climate change have a significant impact on future investment plans by national governments, urban authorities and Multilateral Institutions.

Therefore, the Review concluded that on the balance of evidence, the Programme has delivered value for money.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The programme’s theory of change was designed to contribute to a Primary Purpose of inclusive economic growth and the reduction of poverty and social inequality, gender equality and women’s economic empowerment, through supporting sustainable urban environments. It aimed to do this through contributing to three inter-connected outcomes: more affordable and accessible transport systems; better integrated urban planning and management; and increased resilience to environmental disasters. The programme also aimed to achieve secondary benefits to the UK and other international actors, in the form of growth in exports, investment returns and enhanced soft power.

Evidence from the the implementation phase up to closure in 2022 indicates that the Theory of Change (ToC) remained valid and relevant in the partner cities, and there was a coherent internal logic across the ToC, activities, outputs and existing and projected outcomes and impacts. The level of city partner and stakeholder commitment to the projects, including in relation to urban policies, strategies and planned investments, as well as follow-on funding leveraged from other funding agencies indicates the focus of the Programme was aligned with stakeholder priorities, and that no changes to the ToC, outcomes or indicators were required in the final stages of the Programme.

The overall output scores were good across the Programme, and accurately reflect the successes recorded in the ground. Typically with infrastructure projects even successful delivery of outputs can result in outputs being achieved a number of years after programme closure. The evidence on this Programme is that sustainability of outcomes was good, with local stakeholders taking forward project initiatives started by the projects; as such the expectation is that achievement of outputs is likely in the coming years.

Over the course of the Programme the logframe had a number of evolutions. Specifically, the main challenge was bringing together the individual country logframes that reflect the respective project results with the overall programme logframe, in order to give a programme-level result. The last annual review in 2021 effectively pulled together a representative programme logframe and this methodology has been repeated for this PCR. Both programme and country-level logframes are attached in the annexes.

## C: Detailed Output Assessment

The results have been mapped against the global programme LogFrame (LF) which covers all ten country programmes.

The mapping exercise involved aligning country level indicators to programme ToC statements at output and Intermediate Outcome (IO) level by Monitoring/Reporting (MR) and Evaluation/Learning (EL). The Programme Team (PT) and Monitoring, Reporting, Evaluation and Learning (MREL) adviser matched country-level mapping to programme Theory of Change (TOC) statements, consulting with country leads and DPs to populate data to inform the aggregate view of programme level indicators contained in the global LF.

Note: outputs are an illustration of programme achievements, but do not include ALL country indicators.

Output Number and Title		1 - GFC supported strategic and planning systems and instruments, including supporting systems, data and learning in place
Output Score		A+
Impact weighting (%)		20	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1 Number of Inclusive & evidence based frameworks, policies, strategies, pilots, plans, systems/datasets supported	Turkey = 17 / Nigeria= 71 / SA=22 / Philippines=12 / Indonesia =15 / Vietnam =3 / Thailand= 18 / Malaysia =20 / Myanmar=2 / Planned = 180		Turkey = 18 / Nigeria= 71 / SA=22 / Philippines=24 / Indonesia =21 / Vietnam =5 / Thailand= 30 / Malaysia =30 / Myanmar=2 / Brazil = 4 / Planned = 227	Turkey = 17 / Nigeria= 90 / SA=27[1] / Philippines=38 / Indonesia =50 / Vietnam =1 / Thailand= 24 / Malaysia =21 / Myanmar=11 / Brazil = 13 / Achieved = 282 Note this is the only indicator that all 10 countries are reporting against for the global level logframe.
1.2 Number of inclusive pilot projects/research products/strategies	SA= 9 / Indonesia =9 / Malaysia = 4 / Planned = 22		SA= 9 / Indonesia = 12 Malaysia = 8 / Brazil= 6 / Planned = 35	SA= 9 / Indonesia = 12 / Malaysia = 8 / Brazil= 6 / Achieved = 35
1.3 Number of plans/systems/datasets for developing and utilising open data management	Nigeria= 49 / SA = 8 / Philippines = 1 / Planned = 58		Nigeria= 49 / SA = 8 / Philippines = 1 / Planned = 58	Nigeria= 58 / SA = 15 / Philippines = 2 / Achieved = 75
1.4 No. of showcased best practices based on international and national standards in the field of public transportation, urban social and built environment management, and resilience	NA		Philippines = 13 / Indonesia = 53 / Vietnam = 45 / Myanmar = 5 / Planned = 116	Philippines = 44 / Indonesia = 95 / Vietnam = 61 / Myanmar = 11 / Achieved = 211
[1] Note that for South Africa and Myanmar due to the decentralisation of the programme (as in the case of SA) and the termination of the programme in Myanmar, the milestones and data actuals are reported up to April 2021.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The programme has performed well in the area of TA support to planning, data, systems and facilitating the documentation and learning from best practice, with some examples of adaptation in response to Covid-19. Examples of inclusive approaches include assessing data availability in informal settlements, linking marginalised neighbourhoods, and road accessibility audits conducted by and for people with disabilities. All ten countries reported deliverables for technical products measured by indicator 1.1 and the target has been exceeded. For these reasons the output scored A+.

A few highlights:
The GFCP has also enabled UN Habitat to develop and test the UN Sustainable Development Goal Assessment Tool, to support the integration of the UN SDGs into strategies and plans for future urban development. This was first trialled on projects in Turkey. The GFCP has also led to the development of two UN Habitat programme-level publications which capture key learning points for the benefit of other partners and programmes, one focused on processes, and the second identifying best practice.

- In South East Asia, the programme delivered by Mott MacDonald an estimated £1.5 billion of future investments that were catalysed across 12 interventions.
- South Africa, in Cape Town Urban, delivered 10 (T3) datasets and, in its Covid-19 work, cites learning about data availability in informal settlements, where “we learnt a lot about data availability in that sector, to feed back into the overall data strategy. The city appreciated that a lot”; and in Thekwini Urban, delivered a Data Management Principles framework.
- Bangkok Decision Support System (DSS) Resilience introduced ‘Moata’ as a digital platform developed by Mott McDonald, with the city “very impressed with quality, function and usefulness of the platform.”
- Turkey – The project supported the development of the Istanbul Sustainable Urban Mobility Plan, the first SUMP in Turkey, and also the first in global megacity of c16m, as well as the identification of 26 specific projects, methodologies and approaches to support its implementation. The targets incorporated include: to achieve more equal access to transport; and to achieve net zero carbon by 2050. Other cities in Turkey began developing SUMPs inspired by the success in Istanbul. And after successful pilots for both interventions, Ankara Transport has delivered the bicycle masterplan linking marginalised neighbourhoods with the industrial parks cycling road.
- Nigeria, Lagos Transport - delivered 43 (T42) datasets and established two cloud storage platforms for data sharing across MDAs[2], Lagos Water and Abeokuta Transport interventions and Ogun State.
  [2] MDAs - Ministries, Departments and Agencies is a term referencing Nigerian government structures.
- Nigeria, Lagos – an outline Business Case was designed for the development of water transport, which was heralded by the state as providing “the structure of what is required to make water transport successful”. (City Official)
- Philippines, New Clark City - delivered a Draft Institutional Development Framework for the sustainability unit which it leveraged to sign an MoU with the city in October 2020.
- Myanmar (before February 2021), Yangon delivered a concept design for street upgrades, providing good pilots of accessibility audits conducted by and for persons with disabilities.

Output Number and Title		2 - High quality capacity building is facilitated/delivered through GFC to City authority staff (officials and technical) in transport, urban planning and resilience
Output Score		A
Impact weighting (%)		20	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1 Number of city authority capacity building sessions in transport, urban planning or resilience	Turkey= 2 / Nigeria = 56 / SA = 9 / Planned= 67		Turkey= 13 / Nigeria = 56 / SA = 9 / Planned = 78	Turkey= 15 / Nigeria = 55 / SA = 16 / Achieved = 86
2.2 Number of people (men and women) from city authorities trained and their capacity built in transport, urban planning or resilience	Nigeria = 55 / Turkey = 54 / Indonesia = 54 / Vietnam = 54 / Thailand = 54 / Malaysia = 54 / Planned = 325		Turkey = 139 / Indonesia = 600 / Vietnam = 105 / Thailand = 355 / Malaysia = 72 / Disaggregation for Men/Women (excl Turkey): / Planned = 1,132 / = 777/355 / 31% Women	Turkey = 339 / Indonesia Men/Women = 710 (448/262) / Vietnam Men/Women = 261 (183/78) / Thailand Men/Women = 990 (656/334) / Malaysia Men/Women =252 (148/104) / Disaggregation for Men/Women (excl Turkey): / Achieved = 2,213 / Men/Women = 1435/778 / 35% Women

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Capacity building in the programme was focused on institutional capacity and processes, such as improved GESI considerations, strategic urban sector planning and project management, and was a mixture of formal training and learning by doing. City authority stakeholder engagements were prone to delays due to Covid-19, yet reported results in terms of the numbers trained and capacity built exceeded logframe targets. This was because delivery teams were quick to pivot to online adapted training, which worked well to reach city authority staff, in spite of pressure of Covid-19 on municipality focus and time.

Remote working produced some positive unexpected effects. In some instances, engagement with city authorities was strengthened using remote communications, as the normal barriers to communication were broken down, facilitating more frequent contact with a wider network of (high-level) stakeholders and greater speed in setting up meetings. For example, in Bangkok, a digital workshop with city stakeholders was planned for senior staff and 30 people, yet it was opened up to 100 participants, which was very positive. It is likely this accounts in some cases for the overachievement of the actual number of people reached compared to the target.

All ten-country programmes demonstrated rapid adaptation to Covid-19, and by mid-March 2020, had all taken up remote working. Where necessary (e.g. Abeokuta in Nigeria, and in Turkey Municipalities), additional support and capacity building was provided to city authorities to get them functioning on a virtual platform. However, city authorities were also immediately under pressure to respond to the pandemic, with less ability to support the projects.

Capacity building sessions also included (Thailand) direct training by international experts, including UK experts on cross-cutting issues (such as Gender and Inclusion; sustainability; SDGs). In Vietnam senior officials attended training, reporting early positive results (78% of officials reported the training programme to have a positive impact on their work against a target of 70%).

Output scored an A even though targets exceeded because these two indicators are not sufficiently different to present a more convincing picture of success, and there is no specific measure of quality of training (although no negative feedback on the sessions apparent). Also although some disaggregated data was available it was incomplete; this is a lesson learned – requirements for disaggregation should not be left to operational agreement but should be put into contractual KPIs with DPs.

Output Number and Title		3 - Participatory design workshops held with city level officials and external stakeholders (local community groups, local entrepreneurs, private sector and/or NGOs) including for GESI groups
Output Score		A
Impact weighting (%)		15	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
3.1 Number of participatory design and stakeholder workshop sessions	SA = 11 / Myanmar = 12 / Planned= 23		SA =11 Myanmar = 12 Planned =23	SA= 9 / Myanmar = 16 / Achieved = 25
3.2 Number of stakeholder groups consulted / or who attend workshops	Nigeria = 47 / Philippines = 8 / Indonesia = 3 / Vietnam = 4 / Thailand = 20 / Malaysia = 11 / Planned = 93		Nigeria = 47 / Philippines = 12 / Indonesia = 5 / Vietnam = 4 / Thailand = 43 / Malaysia = 22 / Planned = 133	Nigeria = 58 / Philippines = 30 / Indonesia = 66 / Vietnam = 8 / Thailand = 1 / Malaysia = 53 / Achieved = 216

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Covid-19 was particularly disruptive to interventions which sought community and beneficiary engagement and consultation to inform their design. End-beneficiary engagements, including household and passenger surveys, were either postponed or proceeded at a slower pace. Examples include: NCC, where community surveys meant to inform design will only happen after the design to validate it; South Africa Soweto Strategic Area Framework, which was postponed and then reduced intended community engagement; Abeokuta Urban, where engagement was postponed and then reduced and merged with the Abeokuta Transport engagement; and Brazil, Belo Horizonte which revised the methodology for its transport survey from in-person to virtual.

In spite of the challenges to reach vulnerable groups and community groups, Countries still managed to exceed their target in indicator 3.2 by almost double. In addition, concerning broader consultation and inclusion, the programme gained significant traction in GESI. For example, leads in Vietnam worked with six different vulnerable groups for STS and two for Resilience Intervention, leading to improvements in understanding:
- the accessibility of marginalised groups toward current public transportation;
- their knowledge, attitude and perception of the pilot project;
- the flooding impacts to their daily life; and
- what they suggested/ expected from local government to mitigate the flood chances and flooding negative impacts in their neighbourhood and citywide.
The New Clark City project in the Philippines, that provides TA to the Bases Conversion and Development Authority (BCDA) to develop a Comprehensive Sustainability Plan, was affected by an ongoing land claims dispute between the BCDA and an indigenous community. The delivery team successfully held consultation meetings with several stakeholders, including the National Commission on Indigenous Peoples and UN-Habitat, to inform the development of a Social Situation and Impact Analysis report. Throughout the negotiations the delivery team maintained a close working relationship with the BCDA and the situation has now been successfully resolved.

Nigeria made strides in engagement of different types of stakeholders and social groups, particularly in transport interventions, where 37 (T29) planning and policy stakeholder workshops were held. In Lagos Waterways, Future Cities Nigeria (FCN) successfully engaged informal boat operators to identify ways to formalise water transport:
- in Abeokuta Transport, it reached a limited number of women and people with disabilities through WhatsApp to provide GESI input into transport plans; and
- in Abeokuta Urban, it engaged traditional rulers and their constituent communities to map communities to inform planning work.
The output scored A, because of the success in significantly exceeding targets in a broad representation of countries and range of stakeholder groups, despite Covid-19 difficulties meaning reaching end beneficiaries became more difficult. The limited country scope meant an A+ was not justified.

Indicator 3.1 is in all likelihood under-reported across the 10 countries. From monitoring data submitted and relevant indicators mapped from country logframes, only two countries had data against this indicator – which given 3.2 (referring to workshop attendance) is reported by six countries is an underestimate. Nevertheless, the final assessment is based on actual figures reported.

Output Number and Title		4 - Inclusive communication strategies and stakeholder engagement activities that seek to lead to increased awareness and active participation of stakeholders including citizens
Output Score		A
Impact weighting (%)		15	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
4.1 Number of communication strategies/activities delivered that support citizen participation	Turkey = 21 / Nigeria = 2 / Indonesia = 6 / Thailand = 6 / Planned= 35		Turkey = 48 / Nigeria = 2 / Indonesia = 12 / Thailand = 24 / Planned = 86	Turkey = 82 / Nigeria = 2 / Indonesia = 43 / Thailand = 22 / Achieved = 149
4.2 Number of partnerships established with city level officials, community groups, private sector or NGO representatives	Turkey=2 / Nigeria= 21 / Planned = 23		Turkey=3 / Nigeria= 26 / Planned = 29	Turkey = 4 / Nigeria = 19 / Achieved = 23

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

New partnerships were established in two partner countries. Turkey reported the establishment of four partnerships (or coordination structures), with separate teams of cross-departmental stakeholders established in each engaged municipality. This was achieved in the context of city partners who had previously not worked in multi-disciplinary teams. Bursa and Istanbul Municipalities’ use of cross-departmental engagement has reportedly expanded beyond the interventions. Ankara municipality set up a new unit to promote the use of participatory processes across the authority. The unit, called SUMO, includes consultants and NGOs working across the government department with a particular focus on GESI.

Nigeria established two partnerships with MDAs to promote data sharing and open governance. Partnerships were established for Lagos Urban and Transport (a partnership of nine relevant departments) and Abeokuta Transport.

Whilst there is evidence of a good standard of communication and stakeholder engagement activities, a score of A was considered more appropriate than A+ due to the more limited geographical scope i.e. not including all countries in the programme. Communication and public engagement strategies were intended to increase awareness and active participation of stakeholders, including citizens. The programme disseminated information about country GFC activities/reforms and their benefits, especially for vulnerable and excluded groups. Typical methods used were knowledge sharing platforms, newsletters, and participatory stakeholder workshops. Thailand held a knowledge sharing roadshow and community GESI capacity building workshops to raise awareness.

Output Number and Title		5 - Strengthened stakeholder (including citizens) engagement and participation in strategy building and implementation of sustainable transport management, urban resilience and urban planning
Output Score		A
Impact weighting (%)		15	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
5.1 Number of end beneficiaries reached / consulted on issues around strategy, sustainable transport, urban planning and resilience	Planned = 111,392		Turkey = 8,382 / Indonesia = 1,500 / Vietnam = 1,510 / Thailand = 825 / Malaysia = 100 / Myanmar = 100,000 / Planned = 112,317	Turkey = 8,795 / Indonesia = 3,592 / Vietnam = 0[3] / Thailand = 550 / Malaysia = 183 / Myanmar = 106,521 / Achieved = 119,641
[3] Vietnam used the following indicator: No. of individuals participating in surveys assessing public perceptions/experience of flooding and payment for public transport in HCMC. Covid prohibited the undertaking of the planned survey (May 21) hence they have a nil return

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Turkey recorded 8,795 citizens reached through online end-beneficiary surveys and virtual engagements. This was recognised as a significant achievement given the low levels of stakeholder engagement and absence of feedback mechanisms at baseline.

South Africa made notable progress in wider stakeholder engagement through the official launch of the programme in Cape Town, Durban and Johannesburg; and end-beneficiary engagement including a series of workshops as part of the Soweto Strategic Area Framework, which gathered information on community needs and provided feedback to the community. The 4IR intervention held a semi-virtual workshop with representatives of the minibus taxi industry.

Nigeria progressed in engagement of wider stakeholders, particularly in transport interventions, where planning and policy stakeholder workshops were held. In Lagos Waterways, Future Cities Nigeria (FCN) successfully engaged informal boat operators to identify ways to formalise water transport; in Abeokuta transport, it reached a limited number of women and disabled beneficiaries through WhatsApp to provide GESI input into transport plans; and in Abeokuta Urban, it engaged traditional rulers and their constituent communities to map out the communities.

The output scored A by managing to exceed its targeted reach of end beneficiaries through the use of innovative online methods (although the single indicator meant a higher score was not justified). This achievement is noted for South East Asia countries and interventions targeting resilience measures, where online consultations and communication drives enabled significant reach, in Indonesia (3,592), Myanmar (106,521), and Thailand (550). However, the limitations of social media in targeting and reaching vulnerable groups are noted—for example, in an absence of GESI disaggregation in the Myanmar results.

Output Number and Title		6 - New and strengthened relationships and opportunities created with the business sector and other stakeholders key to the creation of mutual prosperity. (Secondary Benefit)
Output Score		A
Impact weighting (%)		15	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
6.1 Number of opportunities shared/businesses consulted/trade missions/key relationships established	Planned = 40		Turkey = 19 / Indonesia = 10 / SA = 5 / Philippines = 3 / Vietnam = tbc / Thailand = 4 / Brazil = 2 / Total = 43	Turkey = 24 / Indonesia = 53 / SA = 4 / Philippines = 18 / Vietnam = tbc / Thailand = 4 / Brazil = 2 / Achieved = 105

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
There was demonstrable progress towards delivery of secondary benefits within the Programme overall, although by programme close the projects supported reached different stages in relation to realising these.

Recorded trade benefits included contracts for Podaris (transport software) for use in the delivery of projects in Malaysia, and in Bursa (Turkey) a UK firm was successful in winning the contract to develop the App for tourists to use in the Old Town. Arup also reported that as a result of working on the Programme in Ankara, they were able to build a relationship with the municipal authority that enabled them to win two contracts from a client they had not previously worked for.

In relation to the delivery of other secondary benefits, in Vietnam, specific initiatives included the signature of an MoU between DCMS and MIC in relation to digital standards and B2B co-operation, the signature of an MoU between the Connected Places Catapult (CPC) and Becamex IDC (an SOE), in relation to a smart city development. An additional MoU was also signed between Transport for the West Midlands and Iskandar Transport Authority in Malaysia, and there was also collaboration between Transport for Greater Manchester and Ogun State in Nigeria.

The Programme also led to the participation of city authorities in trade missions that may lead to further secondary benefits being generated following programme closure. A Vietnamese delegation attended London Technology Week (meeting BSI and CPC), anda Vietnam Smart Cities Mission was organised in Oct 2022. In the Philippines, a trade and investment roadshow for New Clark City to the UK took place.

The original approach to SBs was based on sound analysis of the comparative advantage of the UK in smart cities, but the design of interventions was not focused on the SB potential.
While GFCP had not yet achieved commercial SB wins by programme close, there is evidence of progress made to generate network effects, soft power and a pipeline of SB opportunities across all partner countries.

- The transport and urban planning pillars were made more conducive than the resilience pillar to generate SBs for the UK. This was attributed to the lack of specific UK comparative advantages in some of the areas supported by resilience interventions, such as earthquake preparedness.[4]
  [4] The Business Case had correctly anticipated that the contribution of the resilience pillar to UK SBs would be minor and estimated only about GBP 300,000 in SBs for this pillar.
- Technology and data solutions opportunities might take about 18 months to realise, from initial lead to contract, according to stakeholders. In contrast, timescales are much longer when it comes to infrastructure investments. The programme has pathways to both short- and long-term opportunities, but it has recorded more traction with the shorter-term technology and data solution opportunities, particularly exports of software and hardware.[5]
  [5] This was evidenced by the relative frequency of sector mentions across SB trackers as well as by interviews with stakeholders.
- There were differences in SBs performance across countries. Turkey, Nigeria, the Philippines and Malaysia were the countries with the most relationships established, businesses consulted, activities delivered and opportunities shared, according to the logframe SB indicator. DIT also expanded its support to Vietnam and Thailand as well, which generated new activity there.

The output scored A because of good evidence of business contact and engagement; the output was judged to not merit A+ due to the unknown quality of the opportunities/contacts enumerated. To ensure SB opportunities generated by the programme were being realised for UK business, a non-ODA-funded component complemented the programme in 2020 and 2021. A DIT sector specialist on smart cities, specifically on tech and data solutions, was hired to manage the funding, while DIT trade missions in country were tasked to work closely with FCDO staff.

Summary of the short-term investment cases GFCP SE Asia at programme exit

No.	Intervention	Investment project	Estimated investment / (GBP, million)	Reference / Document
1	Bandung	Green ancillary bus operations for the downtown area	4	TRANSMIT-0004: / Estimasi biaya operasional - Pilot project Transformasi angkutan
2	Surabaya Urban	Regeneration of Dolly Kampung neighbourhood	51	High level estimates only - not included in intervention scope
3	Surabaya Resilience	Earthquake mitigation and preparedness plan	3.5	RPT-00025: Strategies to Unlock Financing
4	Iskandar	Intelligent Transport System (ITS) masterplan	16.5	RPT-501: Cost / Estimate for SIMMS / Implementation
5	Melaka	Green bus network masterplan	73	RPT-313 & 414: GBN and HAIMP / Procurement Strategy / Operational and Business Plan
6	Bangkok DSS	Flood management and rain forecast system	16	High level estimates only - not included in intervention scope
7	Bangkok TODP	Transit Oriented Development for Ratch Gateway	592	RPT-0014: / Ratchaphruek Gateway / Investment Case
8	Cebu	Climate resilient urban development masterplan	168	RPT-0012: Executive / Summary
9	New Clark City	Central Park development master plan	481	RPT-0012: Housing / Final FS GFCP NCC / Central Park Final FS
10	HCMC GIS	Digitalisation of city drainage network for flood management	6.5	RPT-5004: Long term implementation operation plan
11	HCMC STS	Phase 2 of smart ticketing system implementation	131	RPT-Task 4-3: Report on Financial model
Total			1,533

   Gender, Equality and Social Inclusion

The impacts of COVID-19 were felt throughout the Programme, with intervention teams having to review and adapt planned GESI activities due to the unforeseen disruption. Of importance to highlight here is the agility, resilience and ingenuity demonstrated by intervention teams to ensure business continuity, value for money, and to maintain engagement with GESI priority community groups to inform intervention design and delivery within this context.

GFCP met the PF’s minimum standards on G&I across all six scorecard dimensions assessed by independent evaluators and made significant efforts to promote G&I-related outcomes. The Programme’s GESI ambition, objectives and activities all become clearer as it progressed during the first year of implementation (2020/21) and this progress was built upon during 2021/22 and up until programme closure.

The PT and DPs demonstrated a strong commitment to GESI throughout the delivery phase of the Programme, and identified the relevant expertise necessary to design and deliver on GESI results. All countries conducted G&I impact assessments and developed action plans which informed delivery. Each DP had a comprehensive GESI plan and proactively checked that project activities built in GESI consideration from the outset and during delivery. Action plans for interventions focused on the urban planning and transport pillar, which affordede the most opportunity for delivery of G&I results. Monthly supplier reports included a specific GESI sector reporting on progress, and understood the need to ensure greater attention on data disaggregation to track progress for different social groups. Some community and end-beneficiary engagement suffered delays due to Covid-19-related restrictions. Where possible, delivery teams appropriately adapted to conduct reduced community engagement through virtual consultations.

Over the delivery timeline of the Global Future Cities South East Asia (GFCP SEA) programme, the GESI team generated learning and behaviour change in GESI at both the project and programme levels. Evidence from the interventions showed good achievements of empowerment-level GESI outcomes in line with ambitions set by the Programme. Similar efforts were made in Nigeria, Brazil and Turkey – see table below for examples of some of this work.

GESI activity overall could have been designed better if the level of ambition were more clearly established in partnership with city authorities, and GESI action plans fully co-created with cities to ensure buy-in. Greater attention to co-creation and joint review would have helped to increase the likelihood of uptake of GESI expertise, capacity building opportunities and sustainability. Nevertheless, although some activity was delayed due to Covid-19 and budget constraints, the Programme’s final evaluation identified that it had achieved some good output-level G&I results. Latterly, a consensus and clear direction for G&I across country programmes was achieved.

GFCP met the PF’s minimum standards on G&I across all six scorecard dimensions, as assessed by independent evaluators, and made significant progress promoting G&I-related outcomes. The programme’s GESI ambition, objectives and activities became clearer as it progressed during the first year of implementation (2020/21) and this progress was built upon during 2021/22 and into closure in November 2022.

The PT and DPs demonstrated a strong commitment to GESI throughout the delivery phase of the Programme, and identified the relevant expertise necessary to design and deliver on GESI results.
For example, throughout March 2022, and as part of the GFCP’s commitment towards improving the lives of women around Southeast Asia, the delivery team launched a campaign to highlight women's achievements, discuss continuing and emerging women’s empowerment and gender equality issues, and to celebradte the progress made by furthering the rights of women around South East Asia.

The network of seven G&I champions at country and PT level was maintained throughout the life of the Programme, ensuring a focus on GESI outcomes was maintained throughout, and that the experience of this can be captured for the benefit of future programmes. Specific outputs that will be of use included a thematic keysheet on Women’s Economic Empowerment and Disability Inclusion in Future Cities programmes, developed in co-ordination with FCDO SDAs and the Work Opportunities for Women (WoW) Helpdesk, which should be further disseminated. Lessons learnt from SE Asia have been published on the UN-Habitat Knowledge Platform.

If the country partners continue to implement the approach embedded in the Programme in relation to GESI, it is likely to generate positive results that promote gender equality, social inclusion and women’s economic empowerment. By influencing government decision making, around the transport and urban planning pillars in particular, it is likely that G&I considerations will continue to be integrated into the planning and design of urban development infrastructure which will address the needs of excluded groups. However, the Programme’s experience indicated that the success or sustainability of these results appears dependent on the capacity and commitment of city authorities to creating more participatory and inclusive planning processes, emphasising the importance of building further buy-in and capacity building into delivery phases of future programmes.

Examples of GESI work in GFCP projects
Country	Capacity Building & Engagement	Influencing policy, standards and frameworks; adaptation
Indonesia	The Surabaya Urban Transformation project, which developed and delivered a number of physical, social and economic interventions to regenerate the suburb of Dolly, won the Best International Future Place award at the Pineapples (an international award for placemaking). The project delivered new design standards and a set of urban design guidelines, and implemented other programmes, including an entrepreneur strategy and new place branding, all developed in partnership with the local community.	Suraya was a blueprint for other areas of poverty and social exclusion, by showing that proper engagement with the beneficiaries will bring about success, for the benefit of all.
Malaysia	The Programme piloted a new approach to GESI, and broader social engagement with groups across society in Iskandar.	GFCP led to the implementation of a new approach to embedding GESI within the delivery of a wide range of transport and urban development projects and programmes within Iskandar State. In Melacca, the State established a consultative group to advise of GESI considerations in future projects and programmes.
Myanmar	Yangon project was stopped in February 2021 due to the military coup.	The project established a framework on how to renew two streets within a major city, ensuring all vulnerable groups were included in the final design.
Philippines	The Singapore Landscape Architecture Awards (SILA) is a biennial event that honours industry’s benchmark and innovative practices of landscape architecture. It celebrates the outstanding local and international projects of architectural firms recognised in Singapore. The SILA Gold Award 2022 was presented to the BE Manila team for the New Clark City Central Park project in recognition of the quality of design based on sensitivity to the local context, environmental sustainability, social value, inclusivity, and attention to detail. The consideration of the inclusive spatial experience for the various specific user groups, especially for the local community, were evaluated and part of the criteria of judging.	The New Clark City project was a landmark project. The NCC Central Park is the centrepiece green public space at the heart of New Clark City, a planned city in the Philippines which has been designed to be the country's first smart, resilient and green metropolis. Covering 45 hectares, it will become the largest public park to be built in the Philippines in more than 50 years. Its innovative nature-based design supports climate resiliency (park’s retention pond doubles as a flood mitigation infrastructure) and promotes biodiversity in NCC, thus ensuring economic growth is sustainable and inclusive. The programme conducted a series of participatory workshops, consultations and on-the-ground interviews with over 200 stakeholders in government, business, academia, civic organisations, communities including from the indigenous groups, women, youth and persons with disabilities. The outcome of such dialogues have resulted in the production of a Social Situational and Impact Assessment report – which had then become the main source of social data that complemented the technical and geophysical information that influenced the vision and design of the park. The programme also supported the development of the masterplan of a climate-resilient and inclusive housing community; and a framework for establishing the first ever Philippine government sustainability unit.
Thailand	The Transit-Oriented Development (TOD) Project in Bangkok attempted to solve its major traffic problem by expanding its mass transit systems city-wide. A side effect of the expansion was that new mass transit systems and stations have promoted urban growth and regeneration in those areas and caused surrounding land values to spike. Often this was to the detriment of local communities and businesses. The TOD programme worked with the local authority, BMA, to create a masterplan for urban development of surrounding areas with the aim to increase the use of public transportation and decrease traffic congestion in the new residential and commercial areas. The work on the TOD introduced two core principles, which were not previously been part of Bangkok’s planning process: ensuring social inclusion and promoting citizen-centric development. The TOD aimed to show how a comprehensive, consultative, citizen-centric approach could work in Bangkok – drawing city planners and local stakeholders into the planning process.	The Transit-Oriented Development project was developed under an ‘Equitable TOD’ concept, which aimed to elevate and prioritise investments and policies that benefits citizen from all socio-economic groups. This equitable TOD will ensure that local communities and businesses will benefit from the new developments. The TOD provided a master plan for development to the local authority BMA, which will aid the creation of an inclusive, mixed-use community with diverse cultural, green and artistic activities. Low-energy infrastructure and a climate resilient design was taken into account since the area is flood prone. Lastly, connectivity and sustainable transportation was also be a focus. The approach established in TOD will provide best practice to drive changes for new development projects in Bangkok.
Vietnam		In the Ticketing Intervention, the GESI benefits included gender-sensitive recruitment within city governance structures, GESI sensitisation, capacity building of city officials and innovations in utilising gender and disability disaggregated data. The expected mandated adoption of the Technical Standard Framework / (TSF) and substantive adoption of recommendations for a city-wide fare policy will generate new GESI benefits beyond the end of the intervention.
Brazil	In Belo Horizonte the number of people from vulnerable groups who participated in meetings were 38%. This brought a rich vein of knowledge and experience to the project and was able to develop the project for the benefit of all. / In Recife, the working groups were organized taking into account that at least 20% of the workshop participants were women and/or representatives of disadvantaged groups (requirement of the gender and social inclusion action plan, located in the Inception Report). In addition to the participation of professionals with expertise and experience in common with a specific theme, related to a specific block of initiatives. Of the 31 professionals involved in the working groups, 48% were women.	In Belo Horizonte three technical specifications were made focusing on gender and inclusion, explaining the impacts in gender and social inclusion of the technologies that make up the Global Solution. The Image recognition and georeferencing system allows identifying the needs of people with disabilities or difficulty in locomotion, increasing the comfort of these passengers through information such as seat availability and itinerary. The app, through the panic button and complaint reports, provides increased security specially for women. In addition, Wi-Fi on buses is essential for low-income people to access the Internet during the travel and in obtaining passenger data, which contribute to the improvement in planning and allow the user to plan their trip in order to meet their needs. The successful adaption to reflect the needs of the most vulnerable has been a success of the project. / In Recife, in the strategic planning the parameter of gender, age, social class, disability and race used in the Aptitude and Digital Inclusion Survey of the Civil Society of the Metropolitan Region of Recife, carried out during a feasibility phase, are being considered. Due to budget cuts this programme closed early although there were promising indicators that standards and adaption were being taken into account.
Nigeria	Lagos Urban Renewal Guidelines / • An introductory section provided background information on the importance of integrating gender equality and social inclusion considerations into urban renewal initiatives in Lagos. / • An entire set of guidelines - ‘GL13’ - is devoted to principles for ensuring accessibility for people with disabilities. The guideline outlines universal design considerations as well as links to external resources intended to help planners integrate disability concerns into slum upgrading programmes. / • A whole section – Annex 4 – outlines concrete ways in which GESI considerations can be mainstreamed into specific interventions to benefit women and marginalized groups. / Lagos Transport Full Business Case / Key GESI recommendations included: / • Prioritising safety on both landside and waterside infrastructure, for example, by providing adequate lighting and camera surveillance and ensuring that channels exist for reporting cases of violence and harassment at terminals and on-board ferries. / • Making fare concessions for especially vulnerable passengers, for example, by putting daily or weekly caps on travel expenditure and allowing children and PWDs to travel free of charge or at reduced fares. / Abeokuta Urban Situation Report / Key GESI recommendations included: / • Improving the linkages between the formal and informal economies, as women are overwhelmingly represented in the latter. Conversely, as the report shows, women are underrepresented in sectors of the formal economy (such as information technology) where economic gains are highest. / • Providing up-to-date data disaggregated by sex, age, disability and income level to facilitate the delivery of public and private services and help the state government to realise inclusive development more broadly. / • Establishing partnerships between the state government and local NGOs to reduce the significant disparities in access to healthcare, education and employment faced by women, youths and people with disabilities. / Abeokuta Transport Policy / The policy advocated meeting the needs of women and vulnerable groups in the following ways: / • Ensure respect for the dignity and independence of women, youth, children, senior citizens and people with disabilities. / • Ensure reasonable efforts are made to provide women and vulnerable groups opportunities equal to that given to others. / • Allow people with disabilities to benefit from the same services, in the same place and in a similar way to others, to the greatest extent possible. / • Ensure that all citizens have adequate means of securing safe access to essential services including, among others, their place of work, business or education, markets and shops, health services. / • Give priority to non-motorised means of travel (e.g., walking, cycling) and public transport rather than private transport. / • Ensure that new development applications include adequate provision for the above in order to be approved by the state government.	The project succeeded in mainstreaming GESI considerations into key deliverables on the transport and urban planning interventions, as well as on the Ogun State extension project. Those considerations have the potential to result in improved accessibility, safety, and affordability for women and vulnerable groups across all the interventions. Many of the considerations, if implemented, have the potential to go beyond the minimum compliance threshold specified by the Prosperity Fund’s Gender and Inclusion Framework, and lead to empowering/transformative outcomes for the target groups. While significant progress was made on the GESI workstream, funding cuts introduced partway into the project diminished its impact on the overall programme.
Turkey	The programme developed a Gender Inclusion Action Plan (GIAP), which prioritised engagement with a range of excluded groups, including women and girls, young people and elderly, the disabled, those on low incomes, LBTG, ethnic minorities, immigrants. This engagement was integrated throughout the design and delivery of the programme (the Sustainable Urban Mobility Plan in Istanbul and Smart City Strategy in Bursa), with specific logframe targets and KPIs, which were effective in driving engagement activity in municipalities. / The evaluation of the GIAP showed it exceeded its target of 85% for engagement, achieving 92% by the end of the programme. It also targeted a 25% participation rate amongst under-represented groups in engagement activities, but achieved a level of engagement of 52-75%.	The work undertaken by Arup (the Delivery Partner) and municipalities informed the production of a GESI Manual, which is available for local authorities in Turkey to use. The programme also led to local authorities experimenting with different strategies for engagement, including exhibitions in public areas such as parks and metro stations, and online engagement activities. / The municipal authority in Istanbul also created a team to implement the sustainable mobility strategy which has a specific remit to continue engagement with under-represented groups as the SUMP is developed and implemented.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

The outputs above have similar VfM findings, so the review team have provided an overall summary below.

Based on the evidence provided to the review team and analysis of outputs, the programme has demonstrated “Effectiveness”. While Covid-19 restrictions required the Programme to adapt its approach to delivery, this often had a positive effect on the numbers of beneficiaries reached, and this is likely to deliver the intended outcomes over the long term following programme closure. The Programme had robust methods of financial reporting, however a lesson learned is to bring these results together with the logframes to better track VfM along the four E dimensions (economy, efficiency, effectiveness and equity).

Global Future Cities in South East Asia showed an estimated investment catalysing factor across 12 interventions. Under the three thematic catagories of Resilience, Urban and Transport GFC showed the following additional investment. These investments below can also be broken down per country:

Theme	GFCP Spend	Catalysed Investment
Resilience	6	£195m
Urban	11	£1,115m
Transport	9	£224m
Total	£26m	£1.5b

As expected, by moving to remote delivery, spending on some costs fell, such as travel spend which was 64% lower than budgeted. The initial challenge was for DPs to use those savings to adapt to online delivery. Some delivery partners had already developed financial management tools, which enhanced economy and efficiency; when this adaptation was required (and in the context of reduced budgets) these systems supported the introduction of alternative activities which delivered quality outputs efficiently, but at a lower cost. For example, the Turkey DP identified cost savings with several sub-contractors and were able to re-negotiate contracts to allow for efficient re-allocations to other programme activities

As delivery partners moved to deliver capacity building sessions remotely, this reduced the economic and physical barriers to attending, allowing the number of people trained to surpass the target by 103%. Participatory design workshops saw the number of stakeholders consulted almost double and the overall number of beneficiaries consulted surpassed the target by 6.5%. This clearly demonstrated the value of technology in facilitating and improving efficiency, albeit if in-person training achieved better quality outcomes (which is difficult to assess) then that efficiency gain would be negated to some extent.

The GFCP showed significant potential to promote G&I-related outcomes and ensure that the design and implementation of transport, urban planning and resilience pillars promoted equity. Improved G&I focus during 2021 resulted in improved outcomes; this effort continued to the end of the programme and beyond, driven by the increased engagement and knowledge of city stakeholders. One output (2.2 – see above) disaggregated indicator data that demonstrated a good G&I result.

The Evaluation also noted that there were G&I experts and G&I champions appointed and action plans in place in all countries. In addition, the VfM tracker introduced by the South East Asia DP offers some insight into how DPs improve and protect VfM throughout implementation following the four Es.

DPs strengthened their G&I expertise and capacity in urban planning (e.g. in South Africa) to achieve the outcomes outlined in the business case for different social groups, facilitating equitable outcomes. While the switch to remote delivery did allow the engagement of some previously hard to reach groups, some cities faced difficulties engaging high numbers of women and excluded groups, such as people with disabilities. In some cases, this was due to a reluctance to engage unless compensated for their data usage or due to general disinterest in municipal outreach. Additionally, while capacity-building workshops did reach high numbers of beneficiaries, the “Effectiveness” of these outputs were not assessed in every country due to the challenge of collecting comprehensive feedback virtually and the time required for stakeholders to deploy this knowledge. However, evidence overall was positive, with Turkey reporting 30% of officials using knowledge within 12 months since the output was delivered.

The Programme has ensured economy through its contractual cost control measures. The last year of operation saw cost containment measures work effectively to ensure payments were made only upon delivery of milestones. This was particularly beneficial when Covid-19 began to delay implementation allowing for payments to be reduced where milestones were not delivered. It is recommended in future to consider output unit cost analysis which would further improve cost control and monitoring.

As stated in the business case, the full realisation of outcomes is unlikely within a 10 year timeframe, so it is too early to assess whether these outputs have fully delivered the intended outcomes outlined in the business case. However, given the success in the number of beneficiaries reached and some evidence to show capacity building has been effective (78% of officials reporting training enhanced their work, 11% above target); this indicates the programme is on track to deliver the outcomes following closure. DP exit plans included sustainability plans to maintain momentum towards the delivery of outcomes. FCDO intends to carry out monitoring of outcomes, impact and benefits through follow up programmes.

Note on VfM metrics

Although the Programme had a system of contractual KPIs to ensure milestones were delivered before payments, these indicators were not aligned to the Programme Logframe, moreover specific VfM metrics were not developed. To assess VfM, this review judges “Effectiveness” by whether the delivery of outputs met expectations and so placed the Programme on track to deliver outcomes according to the Theory of Change.

Benchmarking of costs was not carried out primarily due to the bespoke nature of the interventions making direct comparators very difficult to find and measure. The contract tendering process did provide a cost comparison from the detail in the bids received. Some ad hoc benchmarking was also undertaken by Mott MacDonald in SE Asia when assessing sub-contractors, that helped drive selection of the winning sub-contractor.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

Over the life of the Programme the main risks have been around managing the delivery impact and reputational impact of successive reductions to the planned budget in both 2020/21 and 2021/22. Careful adjustment to suppliers’ scope of work and by the Stragegic Partner (UN Habitat) meant that delivery impacts were effectively managed and most projects drew to a successful conclusion. Likewise, the continuation of most project streams (albeit with reduced ambition in some cases) meant that the reputational impact on FCDO was limited; GFC continued to have a strong brand presence and in some countries the brand was used beyond the end of the Programme e.g. South Africa, Indonesia.

The Programme continued to review and monitor programme risks throughout the final reporting period (April 2022 – November 2022). No risks were escalated to the Strategic Programme Board.

Main residual risk exposure (post mitigation) have been around:

- level of city stakeholder engagement impacting delivery;
- mobilisation challenges slowing delivery (during 2020 in particular);
- mobilising and maintaining GESI aspect of programme;
- impact of Covid-19 on delivery (2020/21), impact of budget cuts (both 2020/21 and 2021/22) on delivery scope; and
- longer term impact on the reputation of FCDO of reduced scope following budget cuts.
Careful management and mitigations put in place controlled these risks adequately and no risks remained above the risk appetite level for any length of time. A full and detailed risk register was maintained; final (September 2022) top risks are outlined in the table below.

Risk summary table (September 2022)

Top and new Programme Risks – Overall Programme Risk Appetite: Cautious
Risk Description	Severity at last review	Mitigation Actions to reduce risk to target level; target date; and progress.	Post mitigation RAYG Rating	Requires escalation to SRO?
FC10 Policy & Programme Delivery: Secondary benefits - UK companies do not take advantage of the investment/ export opportunities.	Amber	Extensive consultation with UK future cities industries (including professional institutes) demonstrates a capability and desire to enter these markets. DBT expertise and professional institutes will be used to identify firms interested in working internationally. / DBT Sector specialist left in April 2021 when budget not available to continue	Yellow	No
FC35 Policy & Programme Delivery: Covid-19 has impacted the delivery of the programme but could impact in the future through further waves of infection. It could also impact the Cities ability to fund the implementation of the TA projects as they prioritise health and social care.	Green	Covid-19 risk receded during final year of programme operation	Green	No
FC38 Reputation: Risk to reputation of FCDO if project delivery outcomes are significantly impacted following CSR outcomes affecting UK reputation as an ODA project partner.	Yellow	Budget continued to be restricted in 2022/23 in SEA. GFCP Programme Managers worked closely with DPs and city stakeholders to manage impact of scope reductions	Yellow	No
FC39 Financial & Fiduciary: An ongoing risk for this year is that there is an overspend caused by over-programming that is designed to maintain overall delivery objectives despite the impact of the reduced CSR settlement.	Yellow	Final year SE Asia budget was carefully managed to avoid overspend	Green	No
FC41 Policy & Programme Delivery: The sustainability of programme interventions may be limited by the early closure of the main programme in March 2022	Amber	The programme worked with SE Asia team to work up local funding to continue Future Cities interventions for 2022/23 in the SE Asia region following main programme closure. / For 2023/24 and beyond the GCI CofE will provide continuity of TA on city and urban projects with the aim of maintaining progress on GFCP projects where relevant	Yellow	No

After review, there were no risks to report under Safeguarding, Gender Equality or Climate & Environment.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Commercial issues
The programme contract manager closely monitored commercial developments with the five commercial Delivery Partners and the Strategic Partner, UN-Habitat. The Programme held monthly contract management meetings with DPs at which delivery, financial and contractual issues were reviewed. Detailed monthly reports were provided in advance of the meetings and used as the basis for review and discussion. Weekly meetings were held with UN-Habitat covering similar ground. In addition, strategic direction was regularly discussed and reviewed with DPs and UNH.

Weekly meetings were held with the FCDO’s commercial team and all key commercial processes and decisions were socialised with them.

DP performance in areas of financial management, monitoring and reporting was satisfactory with no major issues or risks to report during the AR period. Delivery against contract KPIs and Terms & Conditions did not raised any concerns and contract obligations were being met. No SRM scorecard assessment was undertaken by the programme.

Changes in a delay to a milestone or activity, or an amendment to the budget, were actioned in line with the requirements for a contract variation in line with the original signed Call-Off Contract. The boxes below show the number of contract variations that were issued over the life of the programme. The two most complex variations were linked to the overall budget cuts, which started in July 2020 and November 2020 covering reduced budgets for the year due to Covid-19 and the ODA cut respectively. The reduced budgets for 2021/22 also required further significant variations. In all cases the programme had close support from the Commercial Directorate, as well as ongoing commercial support including regular catch-up meetings.

The original contracts with each of the five delivery partners (not including UN-Habitat) of the Global Future Cities Programme were scheduled to end in December 2022. In the event, the strategic decision was to end all but the Mott MacDonald contract in March 2022. The MMD contract finished in November 2022 following the end of the SE Asia element of the programme.

The original MOU with UN-Habitat was due to end 31 March 2022, but was extended until 30 September 2022. The first table below shows the differences in contract end terms between all delivery partners. The following three tables shows the number of contract amendments per financial year.

Country	Strategic Partner / Delivery partner	Original Start Date	Original End Date	Revised End Date	Comment
Regional	UN-Habitat (MOU)	12.9.19	31.3.22	30.9.22	The MOU was managed by the RCIT programme Team London until 1.4.2022 when responsibility for the MOU was transferred to the PMO in BHC Singapore. An MOU extension was signed on 28.3.2022 to extend the MOU until 30.9.2022.
SE Asia	Mott MacDonald	18.10.19	31.12.22	18.11.2022	Initial period of contract was with Prosperity Fund, FCO. Contract then moved to ECGD, FCDO in 2020 before transferring to SEAD when it became bilateral programme in April 2022.
Nigeria	Adam Smith Institute	23.9.19	31.12.22	31.3.2022	The RCIT Programme in London issued a change request to end the GFC programme on 31 March 2022.
Brazil	Ernst & Young	12.9.19	31.12.22	31.3.2022	The RCIT Programme in London issued a change request to end the GFC programme on 31 March 2022.
South Africa	PwC	9.9.19	31.12.22	31.12.2022	From 1.4.2021 BHC Pretoria took over the management of the contract and all future funding. Contract end date confirmed for 31.12.2022 in CRSA16 dated 15.5.2022.
Turkey	Ove & Arup	9.9.19	31.12.22	31.3.2022	From 1.4.2021 funding for GFC Turkey was bilaterialised although RCIT London continued to manage the contract on behalf of BE Istanbul. Change request was issued on 1.3.2022 to confirm completion of programme on 31.3.2022.

Contract Variations FY20/21
Country	Strategic Partner / Delivery partner	Number of MOU / Contract Variations	Comment
Regional	UN-Habitat (MOU)	Nil	Some changes agreed in principle but were rolled up into 2021/22 MOU update
SE Asia	Mott MacDonald	10	Covid-19 & ODA cut variations, plus routine scope changes
Nigeria	Adam Smith Institute	12	Covid-19 & ODA cut variations, plus routine scope changes
Brazil	Ernst & Young	10	Covid-19 & ODA cut variations, plus routine scope changes
South Africa	PwC	9	Covid-19 & ODA cut variations, plus routine scope changes
Turkey	Ove Arup	7	Covid-19 & ODA cut variations, plus routine scope changes

Contract Variations FY21/22
Country	Strategic Partner / Delivery partner	Number of MOU / Contract Variations	Comment
Regional	UN-Habitat (MOU)	1	Budget & scope variations
SE Asia	Mott MacDonald	2	Budget & scope variations
Nigeria	Adam Smith Institute	2	Budget & scope variations
Brazil	Ernst & Young	1	Budget & scope variations
South Africa	PwC	n/a	April 2021: moved to Pretoria to manage
Turkey	Ove Arup	1	Budget & scope variations

Contract Variations FY22/23
Country	Strategic Partner / Delivery partner	Number of MOU / Contract Variations	Comment
Regional	UN-Habitat (MOU)	1	Budget & scope variations
SE Asia	Mott MacDonald	1	Budget & scope variations
Nigeria	Adam Smith Institute	0	Budget & scope variations
Brazil	Ernst & Young	0	Budget & scope variations
South Africa	PwC	n/a	April 2021: moved to Pretoria to manage
Turkey	Ove Arup	0	Budget & scope variations

Financial performance

Programme budget performance was proactively managed throughout the life of the programe with regular reviews and monthly meetings with Finance colleagues at which forecasts were challenged.

Budget Overview FY20/21
Category	Original allocation	Revised allocation	Spend	Variation v. revised
UN-Habitat	£1,615,230	£2,279,308	£1,854,174	-18.7
SE Asia - Mott MacDonald	£12,000,000	£17,953,218	£12,635,665	-29.6
Brazil – Ernst & Young	£1,170,372	£1,170,372	£1,402,854	19.9
Nigeria – Adam Smith Intl	£1,500,000	£3,680,477	£3,902,487	6.0
South Africa - PWC	£3,554,447	£5,396,618	£4,854,599	-10.0
Turkey – Ove Arup	£2,000,000	£4,019,268	£3,506,290	-12.8
Admin/Staff Costs	£1,159,951	£1,518,977	£1,403,825*	-7.6
Total	£23,000,000	£36,018,237	£29,561,941	-17.9

* Admin and staff costs represented 4.7% of the total spend.

The £23m budget allocation shown above did not reflect the projected programme spending plans for the FY which were circa £36m. An administrative oversight meant that when the Programme’s budget allocation was finalised at £36m the finance system was not updated to reflect the revised allocation. Finance were aware of the discrepancy and recognised that the Programme’s actual spend forecast (following Covid-19 adjustment – see below) did in fact represent an underspend against the correct allocation rather than an apparent overspend.

Following the Covid-19 impact savings exercise in summer 2020 the Programme made downward budget revisions of £6.2m; £1.9m of this was reallocated to South Africa for urgent Covid mitigation work. This left a net reduction of £4.3m against the agreed allocation of £36m and a final spend of circa £29m (see table above). These were achieved through adjusting milestones in the context of Covid-19 and moving to largely online delivery. Importantly, the final spend did allow the GFCP to fulfil its commitments to work with city authorities on the full range of planned GFCP projects.

Budget Overview FY21/22
Category	Allocation	Forecast	Variation	Comments
UN-Habitat	£1,426,013	£1,426,013	0%	On target
SE Asia - Mott MacDonald	£9,403,566”	£10,097,774	7.1%	Over programming ~ £700k
Brazil – Ernst & Young	£355,018	£355,018	0%	On target
Nigeria – ASI	£1,419,770	£1,419,770	0%	On target
South Africa – PWC*	0	0	-	Bilateralised budget
Turkey – Ove Arup*	0	0	-	Bilateralised budget
Admin/Travel Costs	£20,000	£15,000	-28.5%	Planned travel reduced due to persistent Covid-19
Total	£12,624,367	£13,313,577	5.2%

* budgets bilateralised and therefore held by Post for 2021/22
“ includes £3.7m SE Asia bilateral funding

Following the 2021/22 CSR budget cuts, GFC Programme had to make 40% budget reductions in FY21/22. After extensive discussions with Posts, the strategic partner and the delivery partners were able to achieve the reduction without cancellation of any programme interventions, although some limited changes in scope were required. However, significant DP expenses were removed e.g. the SE Asia DP Mott MacDonald reduced expenses across all the region’s countries by a total of £936k through a combination of efficiencies and reduced travel.

For 2021/22 the Programme’s central budget for SE Asia was supplemented by bilateral funding of £2.6m from FCDO’s SE Asia region. In addition, although the programme continued into FY21/22 in Turkey (£1.9m) and South Africa (£2.75m), the funding for these projects came from the bilateral budget and not GFCP. All contract variations required were completed the Programme final actual spend did increase beyond the planned overprogarmming of 5% more than budget.

Considering the disruption of Covid-19 and ODA reprioritisation, the Programme performed well in adapting inputs to achieve delivery of its outputs beyond the anticipated targets. Delivery partners showed good applications of technology to support delivery. For example, SE Asia’s digital solutions platform designed and run by Mott MacDonald - ‘Moata’ - allowed the streamlining of key data across stakeholders which enhanced VfM by reducing staff time on report generation by 30%. Additionally, the system strongly enhanced analysis of the equity of outputs with metrics aligned to the LogFrame which also ensured efficiency.

Budget Overview FY22/23
Category	Allocation	Forecast	Variation	Comments
UN-Habitat	$904,642	$904,642	0%	Agreed budget between Post and UNH. Roe .701
SE Asia - Mott MacDonald	£1,994,014	£1,980,014	-0.7%	Agreed budget between Post and Mott.
Brazil – Ernst & Young	0	0	-	Closed
Nigeria – ASI	0	0	-	Closed
South Africa – PWC*	0	0	-	Bilateralised budget
Turkey – Ove Arup*	0	0	-	Closed
Admin/Travel Costs	0	0	-	Closed
Total	£2,628,168	£2,614,168	-0.5%

The management of the contracts for both Mott MacDonald and UN-Habitat were transferred via a contract change request to the British High Commission in Singapore. The last activities in SE Asia took place in September 2022, which were led by Mott MacDonald and UN-Habitat. The Mott MacDonald Programme Management Officer remained open until November 2022, when all final transactions were completed. The revised MOU with UN-Habitat dated 28 September 2022 reflected that UN-Habitat's activities ended on 30 September 2022.

Programme-level approach to monitoring and evaluation [1/2 page]

Throughout the programme activities were closely monitored by the CBS team in partner countries and the central programme team based in the UK. Regular monthly performance reports were generated by suppliers and UN-H and monthly meetings reviewed and discussed the reports and considered appropriate remedial action where necessary. Logframes were maintained at country level and pulled together into a programme logframe for annual review and PCR purposes. A quarterly programme board was held, chaired by the SRO, and attended by the Deputy Director Head of Department, when progress was reviewed, risks considered and actions escalated as appropriate.

Various in-country surveys and meetings took place over the life of the programme led by the supplier and monitored by the local CBS programme team. In addition, UN-H held regular meetings at which progress and performance were reviewed. Supplementing the annual reviews, a comprehensive, fully independent evaluation of the programme was carried out in 2021 and recommendations carried forward.

Overall, the monitoring and evaluation was assessed as effective and proportionate.

Date of last narrative financial report	September 2021	Date of last audited annual statement	NA